## Plan
| Minimum | Most Likely | Maximum | Duration | Risk Note
Analyze | 3 | 4 | 5 | 4
Design | 2 | 3 | 4 | 3
Build | 4 | 5 | 8 | 5.6667 | NF Requirements (IM, IS, HR, …)
Test | 3 | 3.5 | 6 | 4.1667 | UAT iteration risk
Deploy | 1 | 1.5 | 2 | 1.5
Go Live Date |  |  |  | 18.3333

## XLRisk
Simulation Settings |  | Simulation Inputs |  | Simulation Outputs
Seed | 0
Update Screen | FALSE | Range | Formula | Range | Name
Iterations | 1000 | Plan!$G$4 | RiskTriang(D4,E4,F4) | Plan!$G$9 | LiveDate
Latin Hypercube | TRUE | Plan!$G$5 | RiskTriang(D5,E5,F5)
Calculate data dables during simulation | TRUE | Plan!$G$6 | RiskTriang(D6,E6,F6)
|  | Plan!$G$7 | RiskTriang(D7,E7,F7)
|  | Plan!$G$8 | RiskTriang(D8,E8,F8)
Macro to run before each iteration
Macro to run after each iteration

## Risk Results 2
Navigation |  | Inputs |  |  |  |  | Outputs | Simulation Statistics |  | Output Cumulative Distributions | Output Distributions | Risk Tornado Diagram
Risk Outputs |  | Plan!$G$4 | Plan!$G$5 | Plan!$G$6 | Plan!$G$7 | Plan!$G$8 | Plan!$G$9 |  | Plan!$G$9 |  |  |  |  | Correlations - Column 1 sorted
Simulation Statistics | Iterations | RiskTriang(D4,E4,F4) | RiskTriang(D5,E5,F5) | RiskTriang(D6,E6,F6) | RiskTriang(D7,E7,F7) | RiskTriang(D8,E8,F8) | LiveDate |  | LiveDate |  |  | Select Output: | Plan!$G$9 |  | Plan!$G$9
Risk Output Percentiles | 1 | 4.558 | 2.8321 | 4.9165 | 5.1253 | 1.3789 | 18.8108 | Mean | 18.3333 |  |  | Name: | LiveDate | Risk Inputs | LiveDate
Calculate Percent Rank | 2 | 3.7525 | 3.2598 | 4.7934 | 3.7557 | 1.522 | 17.0833 | Median | 18.3535 |  |  | 1 |  | Plan!$G$8 | 0.10941
Correlations | 3 | 4.1368 | 2.4304 | 6.7515 | 4.0681 | 1.4501 | 18.8367 | Mode | #N/A |  |  | Tornado Diagram for LiveDate (Plan!$G$9) |  | Plan!$G$5 | 0.32483
Output Cumulative Distributions | 4 | 3.4958 | 3.7 | 6.8543 | 3.3844 | 1.8229 | 19.2573 | Std. Deviation | 1.235 |  |  |  |  | Plan!$G$4 | 0.3415
Output Distributions | 5 | 3.6351 | 2.5385 | 4.932 | 4.2778 | 1.7708 | 17.1541 | Variance | 1.5251 |  |  |  |  | Plan!$G$7 | 0.5494
Risk Tornado Diagram | 6 | 4.2043 | 2.5554 | 6.2655 | 4.5836 | 1.3656 | 18.9744 | Kurtosis | -0.35712 |  |  |  |  | Plan!$G$6 | 0.68191
| 7 | 4.2189 | 3.4362 | 5.5786 | 4.4068 | 1.3162 | 18.9566 | Skewness | 0.16347
| 8 | 3.5005 | 3.0325 | 5.0558 | 3.7226 | 1.8913 | 17.2026 | Minimum | 15.3148
| 9 | 3.4718 | 2.8129 | 5.4961 | 5.5604 | 1.4426 | 18.7837 | Maximum | 22.8389
| 10 | 3.6476 | 2.7203 | 4.2656 | 5.1538 | 1.6365 | 17.4237 | Range | 7.5242
| 11 | 3.8133 | 2.2262 | 5.4291 | 3.5809 | 1.4402 | 16.4897 | Count | 1000
| 12 | 4.4403 | 2.9842 | 4.834 | 4.8093 | 1.2629 | 18.3308 | Error Count | 0
| 13 | 3.6676 | 2.2776 | 4.8934 | 3.4686 | 1.9314 | 16.2386 | Std. Error | 0.039053
| 14 | 3.5188 | 2.3817 | 6.0417 | 3.3359 | 1.5105 | 16.7885 | Confidence Level (95%) | 0.076636
| 15 | 3.7632 | 2.5616 | 4.7665 | 4.6313 | 1.1302 | 16.8528
| 16 | 3.7082 | 3.3429 | 5.4193 | 3.2888 | 1.4487 | 17.2078 | Percentiles
| 17 | 3.7809 | 2.9268 | 6.3016 | 4.0985 | 1.4538 | 18.5616 |  | Plan!$G$9
| 18 | 3.4555 | 3.0357 | 6.5347 | 5.0657 | 1.0171 | 19.1086 |  | LiveDate
| 19 | 4.0905 | 3.1439 | 5.5132 | 4.5786 | 1.2946 | 18.6208 | 0% | 15.3148
| 20 | 3.4983 | 3.442 | 5.3614 | 3.4482 | 1.7226 | 17.4725 | 2.5% | 16.0611
| 21 | 4.4675 | 3.3138 | 7.1311 | 3.7383 | 1.3431 | 19.9939 | 5% | 16.3324
| 22 | 3.9092 | 2.7148 | 5.2612 | 3.7468 | 1.5277 | 17.1596 | 7.5% | 16.5847
| 23 | 4.0054 | 3.4399 | 4.7304 | 3.9844 | 1.6353 | 17.7954 | 10% | 16.7585
| 24 | 4.1299 | 2.844 | 5.8585 | 4.8939 | 1.5327 | 19.259 | 12.5% | 16.913
| 25 | 4.0718 | 2.4497 | 5.3481 | 5.6145 | 1.2441 | 18.7282 | 15% | 17.0109
| 26 | 3.7586 | 2.2134 | 5.5823 | 5.0817 | 1.6322 | 18.2683 | 17.5% | 17.1123
| 27 | 3.3188 | 3.3302 | 4.24 | 3.1444 | 1.6887 | 15.7221 | 20% | 17.2026
| 28 | 4.1799 | 2.7791 | 6.047 | 4.5019 | 1.5496 | 19.0575 | 22.5% | 17.3101
| 29 | 3.8404 | 3.1223 | 5.8919 | 5.3963 | 1.2365 | 19.4874 | 25% | 17.4373
| 30 | 4.3595 | 2.4421 | 4.7806 | 3.9094 | 1.621 | 17.1126 | 27.5% | 17.5277
| 31 | 3.7129 | 3.7072 | 7.176 | 4.3654 | 1.5147 | 20.4762 | 30% | 17.637
| 32 | 3.3516 | 2.6908 | 4.5333 | 5.0322 | 1.8041 | 17.4119 | 32.5% | 17.7291
| 33 | 4.4084 | 3.0397 | 7.1041 | 4.9314 | 1.6661 | 21.1497 | 35% | 17.7981
| 34 | 3.5915 | 2.914 | 5.0899 | 3.6767 | 1.6567 | 16.9287 | 37.5% | 17.8526
| 35 | 3.502 | 2.5649 | 5.9687 | 3.6734 | 1.4918 | 17.2009 | 40% | 17.9348
| 36 | 3.6295 | 3.4919 | 5.9888 | 4.9524 | 1.4723 | 19.535 | 42.5% | 18.0219
| 37 | 4.134 | 2.9082 | 4.4802 | 5.2501 | 1.8388 | 18.6113 | 45% | 18.1106
| 38 | 3.2029 | 2.9463 | 5.417 | 5.7218 | 1.4297 | 18.7176 | 47.5% | 18.2241
| 39 | 3.4233 | 2.1832 | 5.3078 | 3.1621 | 1.9079 | 15.9844 | 50% | 18.3535
| 40 | 4.0659 | 3.5045 | 5.2287 | 4.279 | 1.6752 | 18.7533 | 52.5% | 18.4231
| 41 | 3.4697 | 2.6539 | 4.5271 | 3.7195 | 1.5832 | 15.9534 | 55% | 18.4725
| 42 | 3.7612 | 3.2324 | 5.5193 | 5.46 | 1.5776 | 19.5504 | 57.5% | 18.5641
| 43 | 4.0605 | 3.2237 | 5.2765 | 3.9514 | 1.0761 | 17.5882 | 60% | 18.6252
| 44 | 4.0181 | 2.4168 | 6.0028 | 4.635 | 1.375 | 18.4478 | 62.5% | 18.7145
| 45 | 4.4874 | 2.4227 | 4.3603 | 4.9883 | 1.7034 | 17.9621 | 65% | 18.8019
| 46 | 3.9568 | 2.7898 | 5.5401 | 4.14 | 1.6 | 18.0268 | 67.5% | 18.8959
| 47 | 4.0968 | 3.5855 | 6.9816 | 3.3427 | 1.4743 | 19.4808 | 70% | 18.9963
| 48 | 3.6138 | 3.4383 | 5.3106 | 4.3759 | 1.3486 | 18.0872 | 72.5% | 19.0953
| 49 | 4.7163 | 2.8332 | 5.9297 | 4.5912 | 1.565 | 19.6354 | 75% | 19.1749
| 50 | 3.8034 | 3.002 | 6.0969 | 3.1803 | 1.6955 | 17.7781 | 77.5% | 19.2799
| 51 | 4.1091 | 2.8182 | 5.3296 | 3.1134 | 1.9661 | 17.3364 | 80% | 19.4415
| 52 | 4.1193 | 3.3334 | 5.3556 | 4.1708 | 1.5928 | 18.572 | 82.5% | 19.541
| 53 | 4.2839 | 3.448 | 6.1214 | 3.9582 | 1.3679 | 19.1793 | 85% | 19.6352
| 54 | 4.2562 | 3.2872 | 6.5054 | 4.6384 | 1.2464 | 19.9336 | 87.5% | 19.7795
| 55 | 4.4044 | 3.9222 | 6.533 | 3.2832 | 1.5138 | 19.6565 | 90% | 19.9983
| 56 | 4.5032 | 3.0134 | 5.5586 | 5.5933 | 1.3856 | 20.0542 | 92.5% | 20.2028
| 57 | 3.9753 | 2.6819 | 4.6594 | 4.5131 | 1.4942 | 17.3239 | 95% | 20.4739
| 58 | 4.2536 | 2.3208 | 7.4354 | 5.7027 | 1.1151 | 20.8276 | 97.5% | 20.772
| 59 | 3.6155 | 3.0288 | 6.8965 | 3.5712 | 1.5629 | 18.6749 | 100% | 22.8389
| 60 | 3.5709 | 2.9289 | 5.4467 | 3.7585 | 1.4327 | 17.1376
| 61 | 4.3275 | 2.1338 | 6.0886 | 3.638 | 1.5352 | 17.7232 | Percent Rank
| 62 | 3.5825 | 2.5349 | 4.2187 | 3.7602 | 1.7055 | 15.8017 |  | Plan!$G$9
| 63 | 4.5112 | 3.247 | 6.0057 | 4.8384 | 1.5032 | 20.1055 |  | LiveDate
| 64 | 3.554 | 3.1106 | 6.3746 | 3.5818 | 1.2772 | 17.8983 | Enter Value: | 16.3324
| 65 | 4.476 | 3.273 | 4.7001 | 3.6642 | 1.2318 | 17.3451 | % rank: | 5%
| 66 | 3.7699 | 2.6089 | 5.5497 | 4.8107 | 1.6992 | 18.4385
| 67 | 4.2783 | 3.7853 | 6.3698 | 3.66 | 1.5417 | 19.6352 | Correlations
| 68 | 4.0785 | 2.2309 | 5.6402 | 4.1044 | 1.6447 | 17.6987 |  | Plan!$G$9
| 69 | 4.0895 | 2.399 | 6.8015 | 3.9752 | 1.4203 | 18.6855 | Risk Inputs | LiveDate
| 70 | 3.8086 | 2.7872 | 7.4913 | 4.6148 | 1.1171 | 19.819 | Plan!$G$4 | 0.3415
| 71 | 4.369 | 2.8842 | 4.2195 | 3.9343 | 1.4367 | 16.8436 | Plan!$G$5 | 0.32483
| 72 | 3.9394 | 3.6068 | 5.4647 | 3.8351 | 1.5393 | 18.3853 | Plan!$G$6 | 0.68191
| 73 | 4.028 | 2.7372 | 6.8573 | 3.3979 | 1.6063 | 18.6267 | Plan!$G$7 | 0.5494
| 74 | 3.5068 | 3.1953 | 5.6314 | 4.9476 | 1.6912 | 18.9724 | Plan!$G$8 | 0.10941
| 75 | 4.539 | 3.3315 | 6.5001 | 3.5584 | 1.6795 | 19.6085
| 76 | 4.2509 | 3.5428 | 5.3809 | 3.4149 | 1.3945 | 17.9839
| 77 | 4.1569 | 2.8778 | 6.0865 | 4.1063 | 1.3592 | 18.5866
| 78 | 3.9071 | 3.6628 | 4.8877 | 4.6463 | 1.2777 | 18.3817
| 79 | 4.5803 | 3.0044 | 6.5853 | 4.3956 | 1.4924 | 20.058
| 80 | 4.1335 | 2.8436 | 5.1012 | 4.8813 | 1.7996 | 18.7592
| 81 | 4.0337 | 2.2485 | 4.5557 | 4.0103 | 1.3436 | 16.1919
| 82 | 3.5605 | 3.129 | 6.6229 | 4.3865 | 1.1677 | 18.8666
| 83 | 4.464 | 3.354 | 5.5912 | 4.6846 | 1.6504 | 19.7441
| 84 | 4.3083 | 2.3018 | 5.1666 | 3.3622 | 1.5967 | 16.7356
| 85 | 4.3022 | 2.4475 | 4.6885 | 4.9662 | 1.2385 | 17.6429
| 86 | 4.2145 | 2.9034 | 6.5776 | 4.8474 | 1.4682 | 20.011
| 87 | 4.0736 | 3.089 | 5.8966 | 4.067 | 1.3324 | 18.4585
| 88 | 3.2407 | 2.6552 | 5.3434 | 3.4524 | 1.2407 | 15.9324
| 89 | 3.8163 | 2.7824 | 5.0468 | 3.488 | 1.4098 | 16.5432
| 90 | 3.8328 | 3.0493 | 6.495 | 4.9094 | 1.173 | 19.4595
| 91 | 4.001 | 3.4111 | 6.7353 | 3.7282 | 1.5707 | 19.4463
| 92 | 3.6741 | 2.4932 | 6.8365 | 3.7111 | 1.6491 | 18.3641
| 93 | 4.0526 | 2.1961 | 5.7601 | 3.6536 | 1.2709 | 16.9333
| 94 | 4.2629 | 2.7856 | 4.8651 | 3.694 | 1.4956 | 17.1032
| 95 | 3.6072 | 3.2953 | 4.9544 | 3.9717 | 1.5414 | 17.37
| 96 | 3.6097 | 3.4834 | 5.0381 | 4.2177 | 1.6924 | 18.0413
| 97 | 4.4371 | 2.2722 | 7.0138 | 3.9159 | 1.5027 | 19.1416
| 98 | 4.2118 | 2.3637 | 6.8895 | 3.6812 | 1.6464 | 18.7927
| 99 | 4.3872 | 2.8608 | 4.3321 | 3.2402 | 1.183 | 16.0033
| 100 | 3.8947 | 2.6633 | 6.0925 | 4.4157 | 1.5339 | 18.6001
| 101 | 4.3899 | 3.6416 | 4.7923 | 4.1841 | 1.8557 | 18.8636
| 102 | 4.6545 | 3.1628 | 6.9153 | 4.8879 | 1.1514 | 20.7719
| 103 | 4.2212 | 3.6566 | 5.3071 | 3.6837 | 1.4319 | 18.3006
| 104 | 4.1137 | 2.9407 | 4.9486 | 3.995 | 1.5301 | 17.5281
| 105 | 4.172 | 3.2463 | 5.8404 | 4.4288 | 1.4142 | 19.1017
| 106 | 4.0845 | 3.6879 | 5.2627 | 4.1328 | 1.6559 | 18.8238
| 107 | 4.3851 | 3.305 | 5.0845 | 5.7703 | 1.2524 | 19.7973
| 108 | 3.1254 | 2.7822 | 5.4318 | 3.3108 | 1.7285 | 16.3787
| 109 | 3.5501 | 3.1366 | 5.2192 | 3.4828 | 1.2853 | 16.674
| 110 | 3.7913 | 3.0993 | 5.468 | 3.8316 | 1.4558 | 17.646
| 111 | 4.0846 | 3.361 | 6.8059 | 4.0942 | 1.6022 | 19.948
| 112 | 3.5527 | 2.8283 | 5.0498 | 3.5685 | 1.3834 | 16.3827
| 113 | 4.57 | 2.6264 | 6.1004 | 5.0585 | 1.1714 | 19.5268
| 114 | 3.9655 | 2.5164 | 5.2893 | 3.8546 | 1.5805 | 17.2064
| 115 | 3.9774 | 2.7292 | 5.8069 | 4.0049 | 1.3406 | 17.859
| 116 | 4.6066 | 3.1641 | 4.9629 | 5 | 1.7091 | 19.4427
| 117 | 4.0567 | 2.828 | 7.4437 | 3.9457 | 1.3457 | 19.6197
| 118 | 3.6408 | 3.1884 | 6.7612 | 3.6444 | 1.7478 | 18.9825
| 119 | 3.9683 | 3.0715 | 4.5213 | 3.2585 | 1.7562 | 16.5758
| 120 | 4.8218 | 2.8369 | 5.2004 | 4.4233 | 1.8105 | 19.0929
| 121 | 4.3388 | 2.7808 | 5.7411 | 4.0814 | 1.4778 | 18.42
| 122 | 3.5101 | 2.8059 | 6.5818 | 3.6996 | 1.4081 | 18.0055
| 123 | 4.0158 | 2.7067 | 7.2884 | 4.8855 | 1.5825 | 20.4788
| 124 | 4.1494 | 2.4555 | 4.5253 | 3.7031 | 1.1278 | 15.961
| 125 | 4.0202 | 3.3868 | 4.9672 | 4.2493 | 1.5863 | 18.2099
| 126 | 4.184 | 2.5012 | 5.3316 | 4.9606 | 1.2339 | 18.2112
| 127 | 4.3631 | 2.6357 | 5.0699 | 4.8177 | 1.6301 | 18.5165
| 128 | 3.4114 | 2.6014 | 6.1071 | 4.9161 | 1.694 | 18.73
| 129 | 3.2288 | 2.4964 | 6.6004 | 3.4345 | 1.2121 | 16.9721
| 130 | 3.9641 | 2.9189 | 5.0105 | 4.3037 | 1.874 | 18.0712
| 131 | 3.9233 | 2.9688 | 7.3494 | 4.8725 | 1.5984 | 20.7124
| 132 | 4.2283 | 3.1151 | 6.4438 | 3.8085 | 1.7123 | 19.308
| 133 | 4.2495 | 3.5068 | 4.9567 | 4.7866 | 1.4089 | 18.9085
| 134 | 4.1804 | 3.1576 | 6.5406 | 4.8793 | 1.2064 | 19.9643
| 135 | 3.5042 | 2.6501 | 4.3155 | 4.192 | 1.4002 | 16.062
| 136 | 4.3172 | 2.742 | 5.0204 | 3.7651 | 1.8379 | 17.6826
| 137 | 4.7009 | 2.4696 | 5.1609 | 4.6514 | 1.5591 | 18.542
| 138 | 4.4824 | 2.5723 | 5.6022 | 4.7293 | 1.1893 | 18.5755
| 139 | 4.4556 | 2.6638 | 5.9666 | 3.4949 | 1.3484 | 17.9294
| 140 | 4.4202 | 2.4608 | 4.6318 | 3.5369 | 1.9047 | 16.9544
| 141 | 3.6696 | 3.6623 | 4.6514 | 4.0392 | 1.3074 | 17.3299
| 142 | 3.85 | 3.6125 | 6.6806 | 3.5631 | 1.6055 | 19.3118
| 143 | 4.3457 | 3.6026 | 6.1574 | 5.1635 | 1.4226 | 20.6918
| 144 | 4.7354 | 3.4935 | 6.2307 | 3.6067 | 1.5169 | 19.5832
| 145 | 3.9184 | 3.0619 | 5.7343 | 4.2691 | 1.3999 | 18.3836
| 146 | 3.9365 | 3.5683 | 6.7848 | 4.0097 | 1.4732 | 19.7726
| 147 | 4.8191 | 2.6301 | 5.2938 | 3.7307 | 1.5124 | 17.9862
| 148 | 3.6038 | 3.0221 | 7.7431 | 4.414 | 1.3977 | 20.1805
| 149 | 3.4411 | 2.5336 | 5.9341 | 4.0038 | 1.4511 | 17.3638
| 150 | 3.2544 | 2.7506 | 4.014 | 4.5888 | 1.4077 | 16.0155
| 151 | 4.7768 | 2.5094 | 5.6763 | 5.4203 | 1.3298 | 19.7127
| 152 | 4.4274 | 3.5189 | 6.851 | 4.2042 | 1.7004 | 20.702
| 153 | 4.5502 | 2.216 | 6.1853 | 4.6235 | 1.1443 | 18.7194
| 154 | 4.5243 | 3.3206 | 6.1057 | 3.6354 | 1.5869 | 19.1729
| 155 | 4.243 | 2.5784 | 5.0673 | 4.5054 | 1.708 | 18.102
| 156 | 3.1653 | 3.0629 | 7.8872 | 4.1242 | 1.4247 | 19.6644
| 157 | 4.4256 | 3.8949 | 4.6075 | 3.3763 | 1.5083 | 17.8125
| 158 | 3.8992 | 2.4063 | 7.0513 | 5.1687 | 1.0883 | 19.6137
| 159 | 4.5294 | 3.5545 | 7.5115 | 3.3948 | 1.2181 | 20.2083
| 160 | 3.7764 | 2.1103 | 5.2721 | 4.292 | 1.4371 | 16.888
| 161 | 4.5897 | 2.5193 | 7.2637 | 3.3639 | 1.4022 | 19.1389
| 162 | 3.9596 | 2.2387 | 5.6488 | 3.3695 | 1.1586 | 16.3751
| 163 | 3.4305 | 2.8953 | 7.2737 | 3.9116 | 1.3761 | 18.8873
| 164 | 3.4977 | 3.3569 | 5.8745 | 3.6055 | 1.407 | 17.7417
| 165 | 3.8689 | 3.4237 | 5.172 | 4.4534 | 1.4849 | 18.4031
| 166 | 3.9318 | 2.9387 | 7.2116 | 5.3428 | 1.1264 | 20.5512
| 167 | 3.4079 | 3.8049 | 5.3832 | 3.2607 | 1.4127 | 17.2694
| 168 | 3.5658 | 2.2923 | 4.8907 | 3.5866 | 1.515 | 15.8504
| 169 | 4.4506 | 2.9315 | 4.5765 | 5.2706 | 1.4765 | 18.7058
| 170 | 3.2093 | 3.0635 | 6.8785 | 5.249 | 1.7173 | 20.1178
| 171 | 3.8296 | 2.9094 | 5.0334 | 4.3005 | 1.4111 | 17.484
| 172 | 4.2273 | 3.3115 | 6.4345 | 4.8009 | 1.8799 | 20.6541
| 173 | 3.5413 | 3.5484 | 4.68 | 5.3876 | 1.5944 | 18.7517
| 174 | 4.4942 | 2.3318 | 6.0657 | 5.8558 | 1.7196 | 20.4671
| 175 | 3.5152 | 3.2618 | 4.5944 | 3.8004 | 1.5721 | 16.744
| 176 | 4.2972 | 2.6738 | 5.4696 | 4.5531 | 1.4697 | 18.4633
| 177 | 3.7477 | 2.4895 | 5.2489 | 5.1795 | 1.6216 | 18.2871
| 178 | 4.3345 | 2.86 | 4.871 | 3.9178 | 1.7129 | 17.6962
| 179 | 3.7929 | 3.1066 | 5.0875 | 4.1288 | 1.7913 | 17.9071
| 180 | 4.7945 | 3.3005 | 6.3507 | 3.4218 | 1.6635 | 19.531
| 181 | 4.1028 | 3.8837 | 4.5725 | 4.0832 | 1.5334 | 18.1757
| 182 | 3.6768 | 2.5323 | 5.2816 | 5.101 | 1.4579 | 18.0495
| 183 | 4.2233 | 3.2335 | 6.6241 | 3.4036 | 1.6378 | 19.1223
| 184 | 4.1891 | 2.7846 | 4.8176 | 3.6107 | 1.4618 | 16.8639
| 185 | 3.9901 | 3.1551 | 6.3676 | 5.1382 | 1.4446 | 20.0956
| 186 | 4.0994 | 3.207 | 5.3759 | 4.4028 | 1.4898 | 18.575
| 187 | 4.5684 | 2.771 | 5.963 | 4.4313 | 1.6047 | 19.3384
| 188 | 4.7463 | 3.2152 | 5.8848 | 4.3627 | 1.3202 | 19.5293
| 189 | 4.167 | 2.491 | 5.1102 | 5.7716 | 1.3243 | 18.8641
| 190 | 3.5332 | 3.1785 | 5.4636 | 3.1749 | 1.3251 | 16.6753
| 191 | 4.586 | 2.6042 | 4.9178 | 4.3077 | 1.3353 | 17.751
| 192 | 4.1122 | 3.117 | 7.6243 | 4.7209 | 1.4592 | 21.0336
| 193 | 4.4444 | 2.9814 | 4.5846 | 3.9891 | 1.5016 | 17.5011
| 194 | 4.007 | 2.4358 | 4.9506 | 4.3668 | 1.4603 | 17.2205
| 195 | 3.8376 | 2.8297 | 4.9129 | 4.0632 | 1.4969 | 17.1402
| 196 | 3.6848 | 3.5291 | 5.2536 | 3.4796 | 1.789 | 17.7361
| 197 | 3.6647 | 3.1337 | 5.7287 | 3.2758 | 1.4866 | 17.2895
| 198 | 4.2441 | 2.5829 | 5.0597 | 3.7445 | 1.1748 | 16.806
| 199 | 3.7211 | 3.1354 | 6.1564 | 4.4985 | 1.7137 | 19.225
| 200 | 4.1637 | 3.572 | 4.5101 | 3.5695 | 1.2719 | 17.0873
| 201 | 4.3233 | 2.5686 | 4.2716 | 3.2728 | 1.841 | 16.2773
| 202 | 3.4865 | 2.7925 | 5.0233 | 3.5514 | 1.3967 | 16.2504
| 203 | 3.8263 | 3.2911 | 4.9085 | 3.8432 | 1.6944 | 17.5635
| 204 | 4.2769 | 2.3535 | 6.0952 | 4.1379 | 1.6119 | 18.4754
| 205 | 3.6278 | 3.0513 | 5.3885 | 5.6825 | 1.6152 | 19.3653
| 206 | 3.3244 | 3.0025 | 4.8087 | 3.786 | 1.2745 | 16.1962
| 207 | 3.8509 | 3.0946 | 6.0122 | 3.5364 | 1.2346 | 17.7287
| 208 | 3.2806 | 2.9662 | 5.7557 | 4.2371 | 1.4996 | 17.7392
| 209 | 4.6849 | 2.9644 | 5.4567 | 4.2258 | 1.6787 | 19.0105
| 210 | 3.8977 | 3.4542 | 4.6648 | 3.8238 | 1.3952 | 17.2357
| 211 | 3.6727 | 3.0469 | 5.0657 | 4.6475 | 1.7338 | 18.1666
| 212 | 3.8425 | 3.257 | 6.6311 | 4.5321 | 1.7424 | 20.0051
| 213 | 4.1756 | 3.1681 | 5.1381 | 3.9799 | 1.6771 | 18.1387
| 214 | 3.3591 | 2.8389 | 5.4739 | 3.0308 | 1.8325 | 16.5352
| 215 | 3.8663 | 3.5172 | 5.4715 | 5.4907 | 1.5376 | 19.8833
| 216 | 4.0694 | 3.053 | 4.3759 | 5.1994 | 1.806 | 18.5037
| 217 | 3.798 | 2.263 | 5.8888 | 3.619 | 1.1523 | 16.721
| 218 | 4.7205 | 3.5268 | 6.9479 | 3.9204 | 1.7677 | 20.8834
| 219 | 3.9938 | 2.8492 | 4.9943 | 3.819 | 1.1655 | 16.8219
| 220 | 4.3747 | 3.078 | 4.6834 | 5.117 | 1.4584 | 18.7114
| 221 | 4.6311 | 2.7348 | 6.5582 | 4.4575 | 1.339 | 19.7206
| 222 | 3.9981 | 3.5151 | 4.9972 | 3.3216 | 1.7901 | 17.6222
| 223 | 3.9585 | 2.9582 | 6.6172 | 5.3321 | 1.4433 | 20.3093
| 224 | 3.8156 | 2.5306 | 6.1458 | 4.2223 | 1.9587 | 18.6731
| 225 | 4.3189 | 3.3662 | 6.5182 | 3.8593 | 1.5179 | 19.5804
| 226 | 3.986 | 2.659 | 7.0435 | 4.6224 | 1.5007 | 19.8116
| 227 | 4.2927 | 2.463 | 5.3974 | 4.1173 | 1.6172 | 17.8875
| 228 | 3.6795 | 2.7768 | 5.0781 | 3.5669 | 1.7595 | 16.8607
| 229 | 4.0978 | 3.726 | 5.596 | 3.3459 | 1.6541 | 18.4198
| 230 | 4.4485 | 2.8926 | 5.5231 | 4.4415 | 1.58 | 18.8857
| 231 | 3.7373 | 3.0943 | 6.5094 | 4.2098 | 1.3717 | 18.9226
| 232 | 4.6205 | 2.9059 | 4.2837 | 5.4527 | 1.6016 | 18.8644
| 233 | 4.1205 | 2.393 | 5.8231 | 3.95 | 1.5199 | 17.8066
| 234 | 4.3951 | 2.8508 | 5.9247 | 4.6695 | 1.0505 | 18.8906
| 235 | 3.3896 | 3.3176 | 5.9331 | 3.0594 | 1.3447 | 17.0444
| 236 | 3.9955 | 2.9443 | 4.8964 | 3.5608 | 1.5743 | 16.9712
| 237 | 3.5425 | 2.3826 | 5.2113 | 4.2195 | 1.5991 | 16.9549
| 238 | 4.0076 | 3.131 | 6.3248 | 3.7711 | 1.3736 | 18.608
| 239 | 4.6125 | 2.9825 | 5.2478 | 3.9621 | 1.4278 | 18.2327
| 240 | 4.8946 | 2.814 | 5.8649 | 4.2967 | 1.4274 | 19.2976
| 241 | 4.0138 | 3.0875 | 5.7816 | 3.9398 | 1.7628 | 18.5855
| 242 | 3.6862 | 2.9554 | 6.8755 | 4.1144 | 1.6614 | 19.2929
| 243 | 3.9604 | 3.7048 | 5.0606 | 3.2148 | 1.5696 | 17.5102
| 244 | 4.6046 | 2.762 | 4.7872 | 3.5097 | 1.4459 | 17.1095
| 245 | 4.3577 | 3.3908 | 5.6096 | 5.223 | 1.39 | 19.9711
| 246 | 3.1443 | 2.7431 | 4.2463 | 3.8506 | 1.3305 | 15.3148
| 247 | 4.4853 | 2.6391 | 6.3606 | 4.5244 | 1.254 | 19.2633
| 248 | 3.9335 | 2.8479 | 5.2338 | 3.6923 | 1.7774 | 17.4848
| 249 | 3.557 | 2.4181 | 5.6035 | 5.0768 | 1.4263 | 18.0816
| 250 | 4.7311 | 3.4946 | 6.0368 | 4.4403 | 1.6328 | 20.3357
| 251 | 3.2098 | 3.2113 | 4.8373 | 4.0883 | 1.1956 | 16.5423
| 252 | 3.3542 | 3.1794 | 4.7633 | 4.9622 | 1.5214 | 17.7805
| 253 | 3.9061 | 2.3675 | 4.3734 | 3.4973 | 1.3689 | 15.5131
| 254 | 3.9009 | 2.741 | 5.164 | 4.1422 | 1.9882 | 17.9363
| 255 | 4.1597 | 2.811 | 5.6821 | 3.6551 | 1.824 | 18.132
| 256 | 4.2656 | 2.6354 | 4.7369 | 3.5267 | 1.5062 | 16.6708
| 257 | 4.0125 | 2.5071 | 4.2561 | 3.671 | 1.3851 | 15.8318
| 258 | 4.1409 | 3.2308 | 6.36 | 4.3103 | 1.6173 | 19.6594
| 259 | 3.4326 | 3.5749 | 4.3246 | 4.3606 | 1.4753 | 17.1679
| 260 | 4.2489 | 2.7249 | 6.4404 | 4.3354 | 1.3145 | 19.0642
| 261 | 4.1057 | 2.8654 | 5.4934 | 4.7401 | 1.3603 | 18.565
| 262 | 4.7276 | 3.8242 | 5.6053 | 5.194 | 1.5729 | 20.9238
| 263 | 4.2407 | 2.6419 | 5.2315 | 3.5347 | 1.4452 | 17.0939
| 264 | 4.3226 | 2.7315 | 5.7435 | 3.6781 | 1.5562 | 18.032
| 265 | 4.5618 | 2.5151 | 5.6178 | 3.3692 | 1.4771 | 17.541
| 266 | 3.8828 | 2.7467 | 5.9441 | 4.1563 | 1.7365 | 18.4664
| 267 | 4.2702 | 2.8467 | 4.7464 | 3.8272 | 1.751 | 17.4415
| 268 | 4.2106 | 3.4149 | 6.9606 | 3.9076 | 1.8785 | 20.3721
| 269 | 4.0595 | 3.1856 | 4.6745 | 3.5209 | 1.8138 | 17.2543
| 270 | 3.7183 | 3.6306 | 5.8393 | 4.2071 | 1.3723 | 18.7676
| 271 | 3.6927 | 3.4693 | 4.4263 | 4.3461 | 1.2103 | 17.1447
| 272 | 3.9289 | 2.5894 | 5.818 | 3.4737 | 1.6426 | 17.4526
| 273 | 3.8607 | 2.3352 | 4.5994 | 3.9255 | 1.2792 | 16
| 274 | 4.0861 | 2.7754 | 4.5683 | 3.7852 | 1.2515 | 16.4665
| 275 | 3.2342 | 3.2817 | 6.9848 | 4.0019 | 1.3609 | 18.8635
| 276 | 3.3117 | 3.1594 | 5.1564 | 4.0782 | 1.5908 | 17.2965
| 277 | 4.2613 | 3.2676 | 5.0733 | 5.8374 | 1.8065 | 20.2461
| 278 | 3.6972 | 3.0918 | 6.2923 | 4.0535 | 1.411 | 18.5459
| 279 | 3.9978 | 2.9677 | 5.57 | 3.9056 | 1.8929 | 18.334
| 280 | 4.3858 | 2.1087 | 6.2156 | 4.0385 | 1.673 | 18.4216
| 281 | 3.6398 | 2.4122 | 7.0202 | 4.3429 | 1.1393 | 18.5544
| 282 | 4.5191 | 2.6278 | 5.8606 | 5.2177 | 1.0697 | 19.2949
| 283 | 3.3466 | 3.0387 | 5.1427 | 3.7072 | 1.4744 | 16.7097
| 284 | 3.0236 | 3.4016 | 4.6352 | 4.369 | 1.7157 | 17.1451
| 285 | 4.1561 | 3.2479 | 5.1194 | 3.6409 | 1.4012 | 17.5654
| 286 | 4.021 | 3.6272 | 7.2505 | 3.9944 | 1.6498 | 20.543
| 287 | 3.1977 | 3.3714 | 5.2442 | 3.9553 | 1.4608 | 17.2293
| 288 | 4.1322 | 3.5951 | 4.9867 | 4.1992 | 1.797 | 18.7103
| 289 | 3.8566 | 3.0904 | 4.9064 | 3.8438 | 1.7695 | 17.4667
| 290 | 4.0647 | 3.1346 | 5.1277 | 3.5291 | 1.5821 | 17.4382
| 291 | 4.4914 | 3.7024 | 5.9129 | 3.1597 | 1.3005 | 18.567
| 292 | 4.6016 | 3.4445 | 5.1056 | 4.229 | 1.7494 | 19.1302
| 293 | 3.5675 | 2.5278 | 4.9986 | 4.2595 | 1.702 | 17.0554
| 294 | 3.8335 | 3.1699 | 6.9429 | 3.5926 | 1.4661 | 19.005
| 295 | 3.5327 | 3.2501 | 5.1027 | 4.5168 | 1.6037 | 18.006
| 296 | 3.7468 | 2.9542 | 4.6675 | 5.6369 | 1.3592 | 18.3646
| 297 | 3.3257 | 3.1088 | 6.6736 | 5.2637 | 1.8305 | 20.2024
| 298 | 3.8534 | 3.2837 | 6.0088 | 3.9598 | 1.3269 | 18.4326
| 299 | 3.9785 | 2.545 | 6.074 | 4.5269 | 1.2835 | 18.408
| 300 | 3.9055 | 3.7341 | 5.4534 | 3.7576 | 1.6247 | 18.4752
| 301 | 4.2196 | 2.9785 | 5.0977 | 3.5745 | 1.6316 | 17.5019
| 302 | 3.5258 | 2.996 | 6.1492 | 3.9444 | 1.3625 | 17.9779
| 303 | 3.9192 | 2.4688 | 7.2281 | 3.2365 | 1.6839 | 18.5365
| 304 | 4.5273 | 3.0229 | 5.7697 | 3.8101 | 1.4822 | 18.6123
| 305 | 3.7354 | 3.2043 | 4.9811 | 3.6658 | 1.4717 | 17.0583
| 306 | 3.446 | 3.6367 | 6.6908 | 4.4623 | 1.4214 | 19.6572
| 307 | 3.6013 | 3.1386 | 4.6359 | 5.232 | 1.4334 | 18.0413
| 308 | 3.5281 | 3.3962 | 5.5044 | 3.7131 | 1.8536 | 17.9954
| 309 | 4.3762 | 2.4951 | 5.3343 | 4.4255 | 1.1789 | 17.8099
| 310 | 4.0609 | 2.9244 | 7.7724 | 3.931 | 1.7256 | 20.4144
| 311 | 4.4458 | 3.3467 | 7.2926 | 4.4788 | 1.4065 | 20.9704
| 312 | 4.6209 | 2.5259 | 4.5442 | 4.7343 | 1.5668 | 17.9922
| 313 | 4.5724 | 3.8491 | 5.3517 | 3.5165 | 1.6261 | 18.9158
| 314 | 4.7902 | 2.5524 | 4.7886 | 3.7894 | 1.6775 | 17.5982
| 315 | 3.6598 | 2.877 | 5.6435 | 5.484 | 1.2658 | 18.9301
| 316 | 4.551 | 3.081 | 4.8518 | 3.55 | 1.7312 | 17.7651
| 317 | 4.0287 | 3.0514 | 5.6528 | 3.9193 | 1.4497 | 18.1018
| 318 | 4.3493 | 3.3283 | 5.3442 | 4.6904 | 1.7466 | 19.4588
| 319 | 4.2262 | 2.4378 | 5.8333 | 3.5249 | 1.4058 | 17.4278
| 320 | 4.2008 | 2.8259 | 7.2427 | 3.7504 | 1.4511 | 19.471
| 321 | 3.2605 | 2.9356 | 6.774 | 3.3074 | 1.6411 | 17.9186
| 322 | 4.5075 | 3.8423 | 4.2007 | 4.0654 | 1.4981 | 18.1139
| 323 | 3.8911 | 2.7965 | 5.425 | 4.3221 | 1.3212 | 17.7559
| 324 | 4.1698 | 2.9624 | 4.6218 | 5.2958 | 1.8496 | 18.8995
| 325 | 4.0008 | 3.1511 | 5.4012 | 3.8062 | 1.4474 | 17.8067
| 326 | 4.5319 | 3.6918 | 5.5728 | 4.8479 | 1.9347 | 20.5791
| 327 | 3.7627 | 2.7535 | 6.5684 | 4.3401 | 1.7218 | 19.1466
| 328 | 3.81 | 2.8676 | 5.3954 | 4.8773 | 1.6306 | 18.5808
| 329 | 3.6234 | 3.1404 | 6.487 | 4.1959 | 1.5271 | 18.9737
| 330 | 3.9806 | 2.9532 | 5.1822 | 5.0985 | 1.2958 | 18.5102
| 331 | 4.0102 | 2.8872 | 6.597 | 3.6094 | 1.4121 | 18.5159
| 332 | 3.9927 | 2.6956 | 5.4033 | 4.7081 | 1.5781 | 18.3778
| 333 | 3.8708 | 2.3588 | 6.3369 | 4.2016 | 1.4709 | 18.239
| 334 | 4.4299 | 3.1421 | 4.5655 | 3.2978 | 1.5048 | 16.9401
| 335 | 3.383 | 3.0344 | 6.482 | 4.9683 | 1.3095 | 19.1772
| 336 | 3.7813 | 2.7268 | 6.1693 | 4.1125 | 1.5467 | 18.3366
| 337 | 4.7569 | 3.0819 | 5.488 | 5.3655 | 1.5219 | 20.2141
| 338 | 4.0553 | 2.7704 | 7.0228 | 3.8673 | 1.5621 | 19.278
| 339 | 4.2068 | 2.7254 | 5.2055 | 4.9346 | 1.2955 | 18.3678
| 340 | 3.0718 | 2.6705 | 6.2777 | 4.2727 | 1.4691 | 17.7617
| 341 | 3.5798 | 2.4834 | 5.8292 | 3.9038 | 1.2842 | 17.0804
| 342 | 3.6933 | 2.8918 | 6.3327 | 3.6172 | 1.2671 | 17.802
| 343 | 3.8723 | 3.5257 | 6.4677 | 3.9734 | 1.3816 | 19.2207
| 344 | 4.1002 | 2.9964 | 6.8677 | 3.6558 | 1.5091 | 19.1292
| 345 | 4.7399 | 3.2131 | 7.0331 | 4.4856 | 1.3674 | 20.8391
| 346 | 4.8564 | 3.0984 | 7.0904 | 5.4789 | 1.4991 | 22.0234
| 347 | 4.5539 | 3.5978 | 4.7521 | 4.3236 | 1.4189 | 18.6463
| 348 | 4.6137 | 3.3695 | 5.1703 | 3.5952 | 1.6981 | 18.447
| 349 | 4.6233 | 3.4262 | 6.9912 | 3.2174 | 1.7395 | 19.9975
| 350 | 4.4431 | 2.2596 | 6.0776 | 4.4353 | 1.3228 | 18.5384
| 351 | 3.6912 | 3.0171 | 5.7223 | 3.8741 | 1.289 | 17.5938
| 352 | 3.9892 | 2.9849 | 6.4493 | 3.0968 | 1.3557 | 17.8759
| 353 | 3.4361 | 3.8526 | 4.9696 | 4.1092 | 1.4407 | 17.8082
| 354 | 3.3721 | 2.5545 | 6.0688 | 4.8305 | 1.7451 | 18.5712
| 355 | 3.8275 | 2.0519 | 5.7447 | 4.8418 | 1.2647 | 17.7307
| 356 | 3.5602 | 3.0184 | 6.7426 | 3.5177 | 1.4827 | 18.3216
| 357 | 3.5208 | 3.044 | 5.693 | 5.1864 | 1.7918 | 19.236
| 358 | 4.4801 | 2.7012 | 4.6866 | 3.5773 | 1.1802 | 16.6254
| 359 | 3.734 | 3.6463 | 4.7615 | 4.6129 | 1.3811 | 18.1357
| 360 | 3.8769 | 3.4564 | 4.4645 | 5.1051 | 1.5459 | 18.4487
| 361 | 3.3982 | 3.3899 | 6.7264 | 3.6513 | 1.4493 | 18.6151
| 362 | 4.2579 | 3.0689 | 7.0049 | 4.9717 | 1.4131 | 20.7165
| 363 | 3.8575 | 2.9906 | 4.9917 | 3.4486 | 1.7318 | 17.0202
| 364 | 4.4657 | 3.3059 | 4.8781 | 4.4638 | 1.0305 | 18.144
| 365 | 3.6318 | 3.187 | 4.5007 | 4.9462 | 1.6335 | 17.8991
| 366 | 4.3327 | 2.5413 | 5.8826 | 3.4635 | 1.8266 | 18.0467
| 367 | 3.7382 | 3.2856 | 5.1549 | 5.3787 | 1.3314 | 18.8888
| 368 | 4.2986 | 3.0251 | 5.6953 | 4.8142 | 1.2454 | 19.0786
| 369 | 4.7543 | 3.3741 | 5.6352 | 5.3207 | 1.3338 | 20.4181
| 370 | 4.0354 | 3.4123 | 4.8002 | 3.2278 | 1.9376 | 17.4133
| 371 | 3.573 | 3.479 | 4.9196 | 3.5528 | 1.4819 | 17.0063
| 372 | 3.8636 | 3.2173 | 6.1642 | 3.3549 | 1.2855 | 17.8854
| 373 | 4.2665 | 2.5803 | 5.6607 | 3.1363 | 1.1745 | 16.8185
| 374 | 4.0506 | 3.4503 | 7.5849 | 3.7483 | 1.4939 | 20.3281
| 375 | 4.5615 | 2.8092 | 5.5652 | 3.6485 | 1.48 | 18.0644
| 376 | 4.197 | 3.1996 | 4.7797 | 5.6636 | 1.4811 | 19.321
| 377 | 3.6884 | 3.3553 | 6.3838 | 5.0281 | 1.4316 | 19.8872
| 378 | 3.6335 | 3.6335 | 5.7985 | 3.5784 | 1.3933 | 18.0371
| 379 | 3.2646 | 2.971 | 4.7704 | 4.8213 | 1.4225 | 17.2498
| 380 | 3.8802 | 2.2496 | 5.9749 | 3.489 | 1.3762 | 16.9699
| 381 | 4.3126 | 3.1427 | 5.7372 | 4.0989 | 1.1332 | 18.4247
| 382 | 4.1447 | 3.2627 | 4.9676 | 4.0195 | 1.4187 | 17.8133
| 383 | 3.5639 | 3.1813 | 5.8642 | 4.5405 | 1.3104 | 18.4603
| 384 | 4.9151 | 2.8191 | 6.9072 | 4.203 | 1.3865 | 20.2309
| 385 | 3.7778 | 3.0096 | 4.4963 | 3.507 | 1.3533 | 16.144
| 386 | 4.7112 | 2.7137 | 6.7798 | 3.8374 | 1.5194 | 19.5615
| 387 | 3.0906 | 2.748 | 4.4915 | 4.153 | 1.4346 | 15.9176
| 388 | 3.8394 | 2.9116 | 5.1785 | 3.2634 | 1.7392 | 16.9321
| 389 | 3.6261 | 2.0984 | 5.3153 | 4.4054 | 1.6012 | 17.0464
| 390 | 4.3516 | 3.1917 | 4.9743 | 3.4936 | 1.9495 | 17.9607
| 391 | 3.3574 | 2.7645 | 6.4532 | 3.6574 | 1.336 | 17.5685
| 392 | 4.4624 | 2.4984 | 7.3409 | 4.4925 | 1.642 | 20.4361
| 393 | 3.9666 | 3.6506 | 6.2286 | 4.3726 | 1.3014 | 19.5198
| 394 | 3.8346 | 3.1502 | 6.5745 | 4.1829 | 1.8669 | 19.6092
| 395 | 3.5853 | 2.073 | 5.0174 | 4.2542 | 1.2036 | 16.1336
| 396 | 4.2 | 2.2974 | 6.5644 | 3.4408 | 1.5536 | 18.0561
| 397 | 4.1661 | 3.097 | 6.3081 | 4.4182 | 1.5532 | 19.5427
| 398 | 4.453 | 2.5959 | 5.5766 | 3.1228 | 1.3628 | 17.1111
| 399 | 4.7065 | 3.4323 | 5.0942 | 5.0088 | 1.6673 | 19.9092
| 400 | 3.9415 | 2.3769 | 4.3016 | 4.4461 | 1.7151 | 16.7813
| 401 | 4.042 | 2.1438 | 5.3242 | 3.752 | 1.5372 | 16.7992
| 402 | 3.7398 | 2.6211 | 5.6631 | 3.6262 | 1.2889 | 16.9391
| 403 | 3.8937 | 3.0683 | 7.3233 | 4.0407 | 1.2019 | 19.528
| 404 | 4.4008 | 2.7322 | 5.7726 | 4.2417 | 1.2622 | 18.4095
| 405 | 3.9311 | 3.2741 | 5.7659 | 4.1728 | 1.7807 | 18.9247
| 406 | 3.9462 | 3.9352 | 4.7456 | 3.5009 | 1.6076 | 17.7355
| 407 | 3.7511 | 3.1614 | 4.9527 | 3.279 | 1.6126 | 16.7569
| 408 | 3.3032 | 2.3631 | 6.2931 | 3.891 | 1.7642 | 17.6146
| 409 | 3.7011 | 2.0433 | 6.4229 | 4.3276 | 1.4302 | 17.9251
| 410 | 3.1808 | 3.0368 | 5.412 | 3.7739 | 1.3132 | 16.7168
| 411 | 3.9254 | 3.2749 | 5.1806 | 3.8922 | 1.543 | 17.8162
| 412 | 3.7549 | 3.2784 | 5.8158 | 4.9419 | 1.4179 | 19.2089
| 413 | 4.0477 | 2.7125 | 5.9927 | 5.5028 | 1.3702 | 19.6259
| 414 | 3.784 | 3.0842 | 4.2763 | 3.8226 | 1.6835 | 16.6506
| 415 | 3.8595 | 3.7703 | 7.8209 | 3.3171 | 1.214 | 19.9819
| 416 | 3.865 | 2.9974 | 4.6008 | 3.3525 | 1.3785 | 16.1941
| 417 | 3.953 | 2.391 | 4.8674 | 3.8343 | 1.3614 | 16.407
| 418 | 4.4241 | 3.1239 | 5.9722 | 4.5346 | 1.5857 | 19.6404
| 419 | 3.8988 | 3.1445 | 4.8145 | 4.4486 | 1.3186 | 17.625
| 420 | 4.2343 | 2.6246 | 4.8223 | 3.7068 | 1.766 | 17.1541
| 421 | 4.1391 | 3.4615 | 4.6246 | 5.2391 | 1.7956 | 19.2599
| 422 | 4.4325 | 2.8991 | 5.6812 | 3.419 | 1.3555 | 17.7873
| 423 | 3.4243 | 2.5915 | 6.4602 | 4.9933 | 1.5692 | 19.0385
| 424 | 3.0784 | 2.9447 | 5.8126 | 4.5968 | 1.5749 | 18.0075
| 425 | 3.9727 | 2.749 | 5.4427 | 3.4349 | 1.6436 | 17.2429
| 426 | 3.8739 | 3.8184 | 5.5325 | 4.6626 | 1.5875 | 19.4748
| 427 | 3.2717 | 2.2025 | 6.9499 | 3.6461 | 1.6589 | 17.7291
| 428 | 3.6202 | 2.6831 | 5.3197 | 4.2122 | 1.5022 | 17.3375
| 429 | 4.6407 | 2.6888 | 5.096 | 3.251 | 1.1044 | 16.7808
| 430 | 4.6649 | 3.219 | 7.2349 | 4.0338 | 1.2095 | 20.3621
| 431 | 3.9129 | 3.2977 | 5.3668 | 4.4825 | 1.6687 | 18.7286
| 432 | 4.2606 | 3.0851 | 6.189 | 4.9034 | 1.7815 | 20.2195
| 433 | 4.3402 | 2.8568 | 5.7189 | 3.4995 | 1.243 | 17.6584
| 434 | 4.1243 | 2.4862 | 4.7499 | 4.9558 | 1.4834 | 17.7995
| 435 | 3.8074 | 3.3264 | 4.6709 | 3.3059 | 1.2114 | 16.3221
| 436 | 3.0511 | 3.5399 | 7.3744 | 3.3503 | 1.1914 | 18.5071
| 437 | 4.0457 | 3.2881 | 4.7201 | 3.9379 | 1.4877 | 17.4795
| 438 | 3.7296 | 2.9378 | 4.7747 | 5.2682 | 1.5444 | 18.2547
| 439 | 4.074 | 3.0057 | 5.7893 | 4.2165 | 1.1481 | 18.2336
| 440 | 3.7953 | 3.1912 | 7.1663 | 3.4785 | 1.5452 | 19.1765
| 441 | 3.7562 | 2.9362 | 7.5038 | 3.2915 | 1.2913 | 18.7792
| 442 | 4.3293 | 2.8166 | 4.3962 | 4.272 | 1.5511 | 17.3652
| 443 | 4.4962 | 3.7544 | 5.5706 | 3.8609 | 1.3422 | 19.0242
| 444 | 4.814 | 2.768 | 6.0245 | 5.063 | 1.4703 | 20.1398
| 445 | 3.684 | 3.1139 | 5.626 | 4.7887 | 1.5608 | 18.7734
| 446 | 4.3152 | 3.0158 | 5.688 | 3.5311 | 1.6622 | 18.2122
| 447 | 3.4286 | 3.4729 | 6.6666 | 4.8619 | 1.2227 | 19.6527
| 448 | 4.3731 | 2.6718 | 5.1067 | 3.2078 | 1.4549 | 16.8142
| 449 | 4.5456 | 2.7777 | 6.6373 | 5.1318 | 1.2367 | 20.3291
| 450 | 3.6807 | 2.8988 | 7.2199 | 4.7703 | 1.5345 | 20.1041
| 451 | 4.4113 | 2.3716 | 7.1941 | 5.2894 | 1.0375 | 20.3039
| 452 | 3.7691 | 2.7554 | 5.4505 | 4.6796 | 1.1767 | 17.8313
| 453 | 4.1087 | 2.8896 | 5.2116 | 3.3479 | 1.512 | 17.0697
| 454 | 4.3312 | 2.926 | 6.2339 | 3.6177 | 1.2046 | 18.3135
| 455 | 4.1877 | 2.4076 | 6.474 | 3.73 | 1.6083 | 18.4077
| 456 | 4.0442 | 2.8534 | 6.1398 | 3.5916 | 1.8525 | 18.4815
| 457 | 3.8758 | 3.0239 | 6.9372 | 3.576 | 1.6719 | 19.0847
| 458 | 3.7246 | 2.8204 | 7.3059 | 3.3559 | 1.4718 | 18.6786
| 459 | 4.8703 | 2.6584 | 4.3366 | 3.697 | 1.5155 | 17.0778
| 460 | 4.6477 | 3.0484 | 6.43 | 3.8814 | 1.233 | 19.2405
| 461 | 4.1981 | 3.3042 | 5.6123 | 4.7437 | 1.4428 | 19.3011
| 462 | 4.0307 | 2.8741 | 5.8769 | 5.3277 | 1.2389 | 19.3484
| 463 | 4.1274 | 2.7725 | 5.3995 | 3.3312 | 1.3127 | 16.9434
| 464 | 4.5251 | 2.964 | 6.412 | 4.5936 | 1.5836 | 20.0783
| 465 | 4.3277 | 2.7222 | 5.9377 | 3.6226 | 1.3526 | 17.9629
| 466 | 4.3999 | 3.1849 | 5.2686 | 4.3877 | 1.1315 | 18.3725
| 467 | 3.5364 | 3.4509 | 5.5505 | 3.9361 | 1.5361 | 18.01
| 468 | 3.5645 | 3.0352 | 6.7074 | 3.8296 | 1.5352 | 18.6719
| 469 | 3.416 | 2.9415 | 6.0593 | 4.6284 | 1.9436 | 18.9889
| 470 | 4.1363 | 2.6659 | 5.2516 | 4.0435 | 1.5643 | 17.6615
| 471 | 4.0368 | 2.5986 | 5.6468 | 3.7701 | 1.2505 | 17.3028
| 472 | 3.9993 | 3.2522 | 7.5267 | 4.1864 | 1.6814 | 20.6459
| 473 | 3.3368 | 2.2333 | 4.7737 | 4.1626 | 1.7241 | 16.2306
| 474 | 3.6525 | 2.7385 | 5.4055 | 3.6608 | 1.5382 | 16.9954
| 475 | 4.4725 | 2.6025 | 4.8746 | 3.9907 | 1.8648 | 17.805
| 476 | 3.4339 | 2.5768 | 4.9724 | 3.1952 | 1.6404 | 15.8188
| 477 | 4.1547 | 2.8515 | 5.9982 | 3.4379 | 1.2917 | 17.7341
| 478 | 3.2436 | 2.6487 | 6.2057 | 4.4712 | 1.4392 | 18.0084
| 479 | 3.654 | 2.592 | 4.7234 | 4.52 | 1.7274 | 17.2168
| 480 | 3.3969 | 2.8707 | 5.7834 | 4.7573 | 1.4761 | 18.2843
| 481 | 3.9151 | 2.7982 | 5.2971 | 3.8612 | 1.8154 | 17.687
| 482 | 3.4856 | 2.3043 | 6.2411 | 3.9681 | 1.5724 | 17.5715
| 483 | 4.0391 | 2.879 | 6.0526 | 3.693 | 1.6895 | 18.3532
| 484 | 4.489 | 3.7196 | 5.0446 | 4.1274 | 1.1066 | 18.4872
| 485 | 4.1628 | 3.6838 | 5.2839 | 3.5225 | 1.4594 | 18.1125
| 486 | 3.4932 | 2.9621 | 6.218 | 4.7768 | 1.2749 | 18.7249
| 487 | 4.3602 | 3.6539 | 5.4397 | 5.3369 | 1.3634 | 20.154
| 488 | 3.4394 | 3.6691 | 4.5175 | 3.715 | 1.7859 | 17.1269
| 489 | 3.87 | 2.2944 | 6.3233 | 3.3923 | 1.6156 | 17.4955
| 490 | 3.368 | 2.5854 | 4.5502 | 3.1084 | 1.8035 | 15.4154
| 491 | 4.2374 | 2.858 | 4.5929 | 4.4836 | 1.3547 | 17.5267
| 492 | 3.4616 | 3.4218 | 4.3642 | 4.2842 | 1.0622 | 16.5939
| 493 | 3.7865 | 2.8635 | 7.161 | 5.285 | 1.4267 | 20.5227
| 494 | 3.927 | 3.1121 | 5.9404 | 4.6955 | 1.0587 | 18.7336
| 495 | 4.6383 | 2.8645 | 5.5047 | 3.2546 | 1.3827 | 17.6448
| 496 | 4.4055 | 2.9884 | 4.8622 | 4.1188 | 1.4801 | 17.855
| 497 | 3.8059 | 2.6121 | 6.7926 | 3.8115 | 1.8968 | 18.9189
| 498 | 4.4226 | 3.6802 | 6.0642 | 5.5243 | 1.3392 | 21.0306
| 499 | 4.6316 | 3.1712 | 6.1173 | 3.4985 | 1.4963 | 18.9148
| 500 | 4.6878 | 3.1972 | 5.2733 | 5.8174 | 1.6511 | 20.6268
| 501 | 3.6625 | 3.2995 | 4.8395 | 3.313 | 1.5972 | 16.7117
| 502 | 4.2346 | 2.8085 | 6.1132 | 3.848 | 1.4308 | 18.4351
| 503 | 3.5978 | 2.616 | 5.8483 | 4.0864 | 1.1842 | 17.3326
| 504 | 4.3097 | 3.1226 | 4.9922 | 4.5222 | 1.5735 | 18.5201
| 505 | 4.3254 | 3.536 | 7.205 | 4.0357 | 1.5557 | 20.6578
| 506 | 4.2243 | 3.4049 | 5.9004 | 4.6641 | 1.5509 | 19.7445
| 507 | 3.5382 | 3.0702 | 4.6978 | 5.0225 | 1.493 | 17.8217
| 508 | 4.3472 | 3.4773 | 4.9847 | 4.7308 | 1.2761 | 18.816
| 509 | 3.465 | 2.8665 | 4.9828 | 3.9281 | 1.205 | 16.4474
| 510 | 4.1944 | 3.1573 | 5.2917 | 3.7769 | 1.1906 | 17.6109
| 511 | 3.8523 | 3.395 | 6.5457 | 3.7963 | 1.8083 | 19.3976
| 512 | 4.3782 | 3.0196 | 5.1898 | 3.4908 | 1.7844 | 17.8628
| 513 | 3.479 | 2.6102 | 4.3908 | 3.4012 | 1.72 | 15.6012
| 514 | 4.6362 | 3.153 | 4.6495 | 3.873 | 1.1926 | 17.5044
| 515 | 3.4818 | 3.8378 | 5.6377 | 3.5062 | 1.3473 | 17.8108
| 516 | 3.9829 | 2.9896 | 7.0283 | 4.1902 | 1.5174 | 19.7083
| 517 | 4.4693 | 2.6857 | 6.2462 | 4.8513 | 1.7794 | 20.032
| 518 | 4.1169 | 3.7315 | 7.4527 | 4.3305 | 1.548 | 21.1796
| 519 | 3.3943 | 2.9765 | 5.3893 | 3.8132 | 1.6691 | 17.2425
| 520 | 4.0036 | 3.3514 | 4.9298 | 4.0263 | 1.6466 | 17.9577
| 521 | 4.5097 | 3.2058 | 6.2822 | 4.0708 | 1.6703 | 19.7388
| 522 | 4.1929 | 3.3738 | 6.1798 | 4.7063 | 1.6455 | 20.0983
| 523 | 3.7746 | 3.0965 | 6.592 | 3.2702 | 1.6556 | 18.3889
| 524 | 3.3756 | 3.1164 | 5.2382 | 3.7976 | 1.4462 | 16.9741
| 525 | 3.3641 | 2.9159 | 4.904 | 5.2119 | 1.9688 | 18.3646
| 526 | 3.7592 | 2.9742 | 4.8589 | 4.8593 | 1.4353 | 17.8868
| 527 | 3.8364 | 2.539 | 7.3988 | 5.5944 | 1.3733 | 20.7419
| 528 | 4.2463 | 2.8524 | 6.0289 | 3.4183 | 1.4855 | 18.0313
| 529 | 3.7265 | 2.7393 | 6.5141 | 3.601 | 1.1809 | 17.7618
| 530 | 3.8212 | 2.8972 | 6.0186 | 3.4841 | 1.4756 | 17.6968
| 531 | 3.4633 | 3.2084 | 4.9105 | 3.2354 | 1.5044 | 16.322
| 532 | 4.7626 | 3.3479 | 5.7758 | 4.3579 | 1.4887 | 19.7329
| 533 | 4.1902 | 2.8026 | 5.6708 | 5.0381 | 1.4989 | 19.2006
| 534 | 3.4204 | 3.0308 | 5.4827 | 4.7534 | 1.4733 | 18.1606
| 535 | 4.1869 | 2.6563 | 5.2804 | 4.9823 | 1.6729 | 18.7787
| 536 | 4.3703 | 3.4306 | 4.8292 | 4.353 | 1.6596 | 18.6426
| 537 | 3.8623 | 3.3835 | 6.7274 | 4.3835 | 1.8345 | 20.1913
| 538 | 3.9499 | 3.2691 | 4.1802 | 3.4576 | 1.2799 | 16.1367
| 539 | 4.6444 | 2.696 | 5.5104 | 3.7809 | 1.5579 | 18.1895
| 540 | 4.271 | 3.6728 | 5.5618 | 5.4417 | 1.776 | 20.7232
| 541 | 4.0248 | 2.5507 | 6.9239 | 4.2434 | 1.143 | 18.8859
| 542 | 4.8069 | 2.2438 | 5.8114 | 3.2435 | 1.8211 | 17.9267
| 543 | 3.3216 | 3.2207 | 6.921 | 3.6022 | 1.9229 | 18.9884
| 544 | 3.8878 | 3.7223 | 5.1968 | 4.4743 | 1.5949 | 18.8761
| 545 | 3.8384 | 3.0435 | 5.0525 | 3.9978 | 1.3343 | 17.2664
| 546 | 3.6953 | 2.8253 | 4.7426 | 3.4768 | 1.7549 | 16.495
| 547 | 3.9111 | 3.3583 | 6.1116 | 3.4591 | 1.4047 | 18.2447
| 548 | 3.5995 | 2.9281 | 7.072 | 4.1666 | 1.8358 | 19.6019
| 549 | 3.1883 | 3.1931 | 6.5264 | 5.0542 | 1.5477 | 19.5096
| 550 | 4.3798 | 2.6742 | 6.789 | 4.5457 | 1.1373 | 19.526
| 551 | 3.8792 | 2.9514 | 5.9916 | 3.0793 | 1.0663 | 16.9677
| 552 | 3.4138 | 3.2654 | 6.0821 | 4.2618 | 1.4026 | 18.4257
| 553 | 3.9356 | 3.5808 | 5.1159 | 3.4256 | 1.4624 | 17.5203
| 554 | 4.9701 | 3.5619 | 4.5611 | 3.9018 | 1.2828 | 18.2777
| 555 | 4.5758 | 3.0867 | 6.3178 | 4.313 | 1.298 | 19.5911
| 556 | 4.7971 | 2.5588 | 5.981 | 3.358 | 1.3514 | 18.0464
| 557 | 3.8193 | 2.9237 | 5.7951 | 3.5122 | 1.2 | 17.2503
| 558 | 4.0492 | 3.2395 | 6.6053 | 3.6987 | 1.4042 | 18.9969
| 559 | 3.9244 | 3.1015 | 7.3586 | 3.7884 | 1.4812 | 19.6541
| 560 | 4.4807 | 2.1345 | 5.1946 | 3.47 | 1.4788 | 16.7586
| 561 | 3.306 | 2.4741 | 6.3533 | 4.7652 | 1.5427 | 18.4413
| 562 | 3.3131 | 2.8224 | 4.4439 | 3.9916 | 1.5209 | 16.0918
| 563 | 3.9043 | 2.2799 | 5.6657 | 5.5141 | 1.7436 | 19.1075
| 564 | 4.033 | 2.5568 | 6.1949 | 4.2677 | 1.5503 | 18.6027
| 565 | 4.1017 | 3.558 | 5.4993 | 4.4761 | 1.8826 | 19.5177
| 566 | 4.7734 | 2.8216 | 5.0314 | 4.0486 | 1.5641 | 18.2391
| 567 | 4.6669 | 2.6939 | 5.1439 | 3.4515 | 1.6163 | 17.5725
| 568 | 3.9142 | 2.3753 | 5.5943 | 4.4599 | 1.4649 | 17.8087
| 569 | 3.7429 | 3.1278 | 4.8106 | 4.2857 | 1.7747 | 17.7418
| 570 | 3.9688 | 2.6234 | 4.6756 | 4.1361 | 1.4234 | 16.8273
| 571 | 4.0884 | 2.9472 | 4.7177 | 3.8246 | 1.5324 | 17.1102
| 572 | 3.7272 | 3.4179 | 5.1756 | 3.8522 | 1.7935 | 17.9665
| 573 | 4.0948 | 3.3167 | 5.0914 | 4.8046 | 1.3493 | 18.6568
| 574 | 3.4497 | 3.2943 | 5.6571 | 3.9694 | 1.7608 | 18.1313
| 575 | 3.8891 | 3.5317 | 5.0185 | 4.7168 | 1.5265 | 18.6826
| 576 | 3.7902 | 2.8824 | 5.1317 | 5.9198 | 1.3581 | 19.0823
| 577 | 3.7437 | 2.9492 | 5.872 | 3.4389 | 1.1104 | 17.1142
| 578 | 4.2914 | 3.9088 | 5.4495 | 3.503 | 1.2904 | 18.4431
| 579 | 3.4479 | 3.5802 | 5.221 | 4.5685 | 1.1878 | 18.0054
| 580 | 3.7664 | 3.0031 | 6.7155 | 3.8019 | 1.5921 | 18.8791
| 581 | 3.7 | 3.1479 | 5.2025 | 4.0216 | 1.8696 | 17.9417
| 582 | 3.1915 | 2.2552 | 6.7606 | 3.612 | 1.5587 | 17.3781
| 583 | 3.6506 | 2.9075 | 4.9244 | 5.1393 | 1.6277 | 18.2495
| 584 | 3.9175 | 2.5049 | 5.9462 | 3.6288 | 1.8513 | 17.8486
| 585 | 4.522 | 3.3799 | 5.0633 | 4.2656 | 1.9276 | 19.1583
| 586 | 3.6219 | 3.2405 | 5.5826 | 3.542 | 1.0966 | 17.0837
| 587 | 3.379 | 3.3971 | 5.8365 | 3.7415 | 1.541 | 17.895
| 588 | 4.2299 | 3.0478 | 5.3125 | 3.6759 | 1.8223 | 18.0884
| 589 | 4.3187 | 3.5759 | 5.1592 | 3.8986 | 1.6256 | 18.578
| 590 | 4.0263 | 2.699 | 7.3293 | 4.3073 | 1.4947 | 19.8565
| 591 | 3.3858 | 2.7101 | 5.6535 | 3.8657 | 1.1638 | 16.779
| 592 | 3.9278 | 3.2711 | 4.6948 | 3.4154 | 1.2271 | 16.5362
| 593 | 4.2156 | 2.8731 | 5.0275 | 4.8987 | 1.6029 | 18.6178
| 594 | 3.5567 | 3.0606 | 5.3187 | 4.2592 | 1.3885 | 17.5837
| 595 | 3.7113 | 2.9719 | 5.3856 | 3.6322 | 1.396 | 17.097
| 596 | 3.8238 | 3.1766 | 4.935 | 4.7918 | 1.185 | 17.9121
| 597 | 4.2417 | 2.4459 | 5.7914 | 3.3279 | 1.4288 | 17.2357
| 598 | 4.8607 | 2.8112 | 6.2255 | 4.1608 | 1.0947 | 19.1529
| 599 | 4.1223 | 2.7043 | 5.3935 | 4.2567 | 1.511 | 17.9877
| 600 | 4.286 | 2.1758 | 5.0799 | 3.4752 | 1.6806 | 16.6975
| 601 | 3.2939 | 3.4465 | 4.8968 | 4.0592 | 1.4419 | 17.1383
| 602 | 4.0813 | 3.2971 | 4.5084 | 3.8564 | 1.3712 | 17.1144
| 603 | 4.0923 | 3.1251 | 7.5667 | 4.78 | 1.316 | 20.8801
| 604 | 4.4579 | 2.9423 | 4.606 | 5.2272 | 1.3034 | 18.5368
| 605 | 3.8019 | 3.5233 | 4.617 | 3.7395 | 1.7738 | 17.4554
| 606 | 4.4345 | 2.5945 | 6.2024 | 5.1594 | 1.5571 | 19.9479
| 607 | 3.8447 | 3.3369 | 6.6132 | 3.2505 | 1.7878 | 18.8331
| 608 | 3.6444 | 2.7454 | 6.7131 | 4.1523 | 1.3113 | 18.5666
| 609 | 3.2925 | 3.073 | 4.825 | 4.3333 | 1.7377 | 17.2615
| 610 | 3.3334 | 3.0832 | 4.8496 | 3.883 | 1.248 | 16.3972
| 611 | 4.1412 | 3.0301 | 5.4838 | 4.6534 | 1.1983 | 18.5068
| 612 | 4.5178 | 3.1817 | 6.6623 | 4.4109 | 1.5129 | 20.2856
| 613 | 3.4185 | 2.9568 | 5.025 | 4.0715 | 1.54 | 17.0118
| 614 | 4.1816 | 2.3441 | 5.1505 | 4.0562 | 1.6485 | 17.3808
| 615 | 3.5295 | 2.8154 | 5.9534 | 3.5467 | 1.6868 | 17.5318
| 616 | 4.4566 | 2.5129 | 4.3464 | 5.5426 | 1.2926 | 18.1511
| 617 | 4.3107 | 3.534 | 6.9002 | 3.2682 | 1.1462 | 19.1593
| 618 | 3.8779 | 2.8623 | 7.1379 | 4.1221 | 1.1964 | 19.1965
| 619 | 4.1305 | 2.975 | 4.4729 | 3.7923 | 1.2973 | 16.6679
| 620 | 3.8905 | 2.9666 | 5.0823 | 3.9808 | 1.3876 | 17.3078
| 621 | 4.0399 | 2.6464 | 5.589 | 4.1264 | 1.048 | 17.4497
| 622 | 4.1269 | 2.8413 | 4.4517 | 3.3025 | 1.4571 | 16.1796
| 623 | 4.0222 | 3.1271 | 6.273 | 4.608 | 1.7654 | 19.7958
| 624 | 3.4037 | 3.0722 | 7.1111 | 4.7566 | 1.3663 | 19.7099
| 625 | 4.0302 | 2.2882 | 6.8135 | 3.5967 | 1.5113 | 18.2399
| 626 | 3.6813 | 2.6798 | 6.407 | 4.7475 | 1.2554 | 18.771
| 627 | 4.1607 | 3.2772 | 7.0972 | 4.7129 | 1.609 | 20.857
| 628 | 4.3565 | 2.3117 | 7.1546 | 4.1754 | 1.516 | 19.5142
| 629 | 4.7228 | 2.7581 | 5.9171 | 4.2386 | 1.1127 | 18.7493
| 630 | 3.9883 | 3.1039 | 5.2172 | 4.0128 | 1.4176 | 17.7397
| 631 | 4.4326 | 2.6519 | 5.1846 | 5.2025 | 1.387 | 18.8585
| 632 | 4.6959 | 2.9398 | 6.1908 | 3.4551 | 1.8733 | 19.1549
| 633 | 4.3834 | 2.0873 | 6.8831 | 3.725 | 1.2421 | 18.3209
| 634 | 4.355 | 2.6924 | 4.7136 | 3.4427 | 1.3972 | 16.6009
| 635 | 3.9217 | 3.393 | 6.2131 | 3.8689 | 1.3368 | 18.7336
| 636 | 4.393 | 3.3817 | 4.9406 | 3.4549 | 1.6359 | 17.8061
| 637 | 3.1722 | 2.7632 | 4.9291 | 3.5447 | 1.5163 | 15.9255
| 638 | 4.5014 | 3.5655 | 5.6848 | 3.7629 | 1.23 | 18.7447
| 639 | 4.0682 | 3.4342 | 5.173 | 3.642 | 1.3905 | 17.7079
| 640 | 3.3411 | 3.4635 | 6.2788 | 3.7649 | 1.322 | 18.1703
| 641 | 3.9855 | 3.264 | 5.5867 | 4.3433 | 1.4842 | 18.6636
| 642 | 4.0664 | 2.91 | 4.7689 | 3.4678 | 1.8331 | 17.0461
| 643 | 3.1172 | 2.3555 | 5.697 | 3.6245 | 1.4784 | 16.2726
| 644 | 4.3474 | 2.4287 | 6.2508 | 5.5713 | 1.2535 | 19.8517
| 645 | 3.2182 | 3.869 | 4.712 | 5.6531 | 1.2578 | 18.7101
| 646 | 4.3003 | 2.9009 | 6.2588 | 4.9247 | 1.9548 | 20.3395
| 647 | 4.2019 | 2.6189 | 5.6428 | 4.0502 | 1.8422 | 18.3559
| 648 | 4.4385 | 3.3766 | 4.8034 | 4.055 | 1.161 | 17.8345
| 649 | 4.4167 | 2.6977 | 5.2779 | 3.8856 | 1.5286 | 17.8065
| 650 | 4.2951 | 3.7795 | 6.3994 | 4.5587 | 1.5961 | 20.6288
| 651 | 3.9228 | 3.2358 | 5.364 | 4.0316 | 1.3176 | 17.8718
| 652 | 3.9028 | 3.5217 | 5.5251 | 5.3561 | 1.5054 | 19.8111
| 653 | 3.6715 | 2.7019 | 5.434 | 5.1918 | 1.393 | 18.3922
| 654 | 3.1352 | 2.3859 | 6.3043 | 3.7176 | 1.5886 | 17.1317
| 655 | 4.1648 | 3.486 | 4.7058 | 3.6362 | 1.6291 | 17.622
| 656 | 3.7833 | 3.6151 | 5.0293 | 3.3 | 1.8285 | 17.5563
| 657 | 3.9702 | 2.9504 | 5.0156 | 4.1582 | 1.6233 | 17.7177
| 658 | 4.2874 | 3.8797 | 5.8039 | 3.6275 | 1.5072 | 19.1057
| 659 | 3.9797 | 3.0788 | 4.5829 | 4.0462 | 1.2699 | 16.9574
| 660 | 4.3663 | 2.3382 | 4.8804 | 3.4108 | 1.3089 | 16.3045
| 661 | 3.7327 | 2.7097 | 5.2438 | 5.0508 | 1.6386 | 18.3757
| 662 | 4.0224 | 3.0923 | 7.5933 | 4.0165 | 1.3275 | 20.0521
| 663 | 4.7642 | 2.4655 | 4.965 | 4.6585 | 1.6847 | 18.5379
| 664 | 4.2551 | 2.8047 | 5.0869 | 5.0735 | 1.7061 | 18.9263
| 665 | 4.593 | 2.2701 | 4.4373 | 5.5266 | 1.628 | 18.4549
| 666 | 3.8672 | 3.2926 | 5.9071 | 4.8321 | 1.6271 | 19.5261
| 667 | 3.5749 | 2.9174 | 5.3708 | 3.1449 | 1.5976 | 16.6056
| 668 | 3.7094 | 3.2804 | 5.8034 | 4.1432 | 1.688 | 18.6243
| 669 | 3.7712 | 2.7615 | 4.6403 | 5.6261 | 1.6647 | 18.4637
| 670 | 3.6423 | 3.3499 | 4.6439 | 3.4822 | 1.5684 | 16.6867
| 671 | 3.9528 | 3.6165 | 5.2869 | 3.6313 | 1.1858 | 17.6734
| 672 | 4.0091 | 3.045 | 4.5381 | 3.1291 | 1.5676 | 16.2889
| 673 | 4.105 | 2.5634 | 5.7851 | 3.5848 | 1.5998 | 17.6381
| 674 | 4.1428 | 3.0556 | 6.5632 | 4.1876 | 1.3068 | 19.256
| 675 | 3.9164 | 3.3521 | 5.5662 | 4.5125 | 1.6829 | 19.0301
| 676 | 3.8002 | 2.1653 | 5.2225 | 5.9111 | 1.8187 | 18.9178
| 677 | 4.1529 | 3.5035 | 6.0203 | 3.6692 | 1.2285 | 18.5744
| 678 | 3.8817 | 3.4031 | 5.8545 | 3.5838 | 1.4913 | 18.2145
| 679 | 4.4999 | 3.1458 | 6.6675 | 5.3039 | 1.6475 | 21.2645
| 680 | 4.3617 | 3.1008 | 5.1525 | 4.2239 | 1.7829 | 18.6218
| 681 | 4.91 | 3.0589 | 6.1617 | 5.4161 | 1.6395 | 21.1862
| 682 | 3.7121 | 3.0568 | 6.3454 | 3.3306 | 1.2877 | 17.7327
| 683 | 3.4526 | 2.8907 | 5.7061 | 4.1475 | 1.2307 | 17.4277
| 684 | 4.2753 | 2.6406 | 6.3924 | 4.5654 | 1.5577 | 19.4314
| 685 | 3.4885 | 2.5423 | 4.7985 | 3.6212 | 1.81 | 16.2604
| 686 | 3.9546 | 3.4541 | 5.0406 | 3.6135 | 1.6661 | 17.729
| 687 | 3.9743 | 3.1718 | 5.7632 | 3.7946 | 1.4338 | 18.1377
| 688 | 3.9875 | 2.7686 | 5.1261 | 5.3466 | 1.4211 | 18.6499
| 689 | 3.9823 | 3.3082 | 7.3889 | 3.4098 | 1.1203 | 19.2096
| 690 | 4.7078 | 3.1069 | 5.1873 | 4.0273 | 1.7163 | 18.7456
| 691 | 3.8456 | 2.4781 | 5.1479 | 4.3794 | 1.3467 | 17.1976
| 692 | 3.6259 | 3.5691 | 5.4609 | 3.4855 | 1.3745 | 17.5159
| 693 | 3.9439 | 2.9521 | 7.6421 | 3.322 | 1.6142 | 19.4744
| 694 | 3.5781 | 2.8008 | 5.4765 | 5.1753 | 1.4397 | 18.4704
| 695 | 4.1071 | 3.1051 | 5.2091 | 5.1453 | 1.3117 | 18.8785
| 696 | 3.9018 | 3.0111 | 6.8191 | 4.4929 | 1.2164 | 19.4412
| 697 | 3.2453 | 2.9877 | 5.9841 | 4.7939 | 1.414 | 18.425
| 698 | 4.4491 | 3.6435 | 7.1241 | 3.5559 | 1.1696 | 19.9423
| 699 | 3.656 | 3.0267 | 6.5494 | 3.9824 | 1.5386 | 18.753
| 700 | 3.8928 | 2.9028 | 5.2265 | 3.2793 | 1.0838 | 16.3853
| 701 | 3.9494 | 3.3399 | 5.5168 | 3.8053 | 1.226 | 17.8375
| 702 | 3.2523 | 2.5473 | 4.8856 | 3.9475 | 1.5521 | 16.1848
| 703 | 3.2735 | 2.6668 | 6.6991 | 3.4606 | 1.5183 | 17.6184
| 704 | 3.6655 | 2.3185 | 6.0402 | 5.4367 | 1.4638 | 18.9246
| 705 | 4.0758 | 3.3242 | 4.5328 | 3.5296 | 1.467 | 16.9294
| 706 | 4.5137 | 3.7462 | 7.069 | 3.5997 | 1.5676 | 20.4963
| 707 | 3.8309 | 3.0661 | 4.8533 | 4.4368 | 1.6138 | 17.8009
| 708 | 3.8431 | 2.8548 | 4.4015 | 3.7754 | 1.3892 | 16.2639
| 709 | 4.0113 | 3.2289 | 5.958 | 5.2978 | 1.8004 | 20.2965
| 710 | 3.7408 | 2.8803 | 5.5092 | 3.3786 | 1.52 | 17.0289
| 711 | 4.2217 | 2.7886 | 6.0775 | 4.6756 | 1.4411 | 19.2045
| 712 | 4.4604 | 3.5091 | 6.0282 | 4.0296 | 1.5897 | 19.617
| 713 | 4.5149 | 3.2143 | 6.1344 | 3.5545 | 1.9207 | 19.3388
| 714 | 3.6126 | 3.7361 | 6.7978 | 4.7839 | 1.5001 | 20.4305
| 715 | 4.1732 | 3.2019 | 5.1663 | 3.7328 | 1.5845 | 17.8587
| 716 | 3.9483 | 3.6101 | 5.4915 | 3.2961 | 1.5292 | 17.8752
| 717 | 3.5386 | 2.9022 | 6.9969 | 3.9872 | 1.2581 | 18.683
| 718 | 3.9765 | 3.0406 | 5.7494 | 3.3148 | 1.6074 | 17.6886
| 719 | 3.1764 | 3.3635 | 7.4183 | 3.3251 | 1.4542 | 18.7376
| 720 | 4.6792 | 2.2081 | 5.1165 | 4.0186 | 1.3188 | 17.3413
| 721 | 4.3972 | 3.4285 | 5.6154 | 4.8973 | 1.2644 | 19.6027
| 722 | 3.8851 | 2.4396 | 6.6811 | 3.6038 | 1.3937 | 18.0032
| 723 | 4.129 | 2.9181 | 5.0137 | 5.0451 | 1.5365 | 18.6423
| 724 | 4.0025 | 2.8856 | 4.899 | 3.4056 | 1.7529 | 16.9457
| 725 | 3.9812 | 3.3228 | 5.1245 | 3.6803 | 1.5309 | 17.6397
| 726 | 4.6826 | 3.0535 | 5.296 | 3.7161 | 1.4153 | 18.1635
| 727 | 3.9942 | 3.7119 | 5.0013 | 4.838 | 1.4929 | 19.0384
| 728 | 4.2363 | 3.0749 | 6.845 | 4.6437 | 1.6739 | 20.4738
| 729 | 3.6029 | 2.4847 | 4.9261 | 3.4069 | 1.6067 | 16.0273
| 730 | 3.7644 | 3.3107 | 4.9429 | 3.8205 | 1.1537 | 16.9923
| 731 | 4.5343 | 2.5978 | 5.0509 | 3.5127 | 1.7045 | 17.4002
| 732 | 3.4773 | 2.983 | 6.0141 | 3.339 | 1.2414 | 17.0547
| 733 | 3.8205 | 2.913 | 4.4091 | 4.3503 | 1.816 | 17.309
| 734 | 4.2586 | 3.6247 | 4.7974 | 3.2312 | 1.22 | 17.1318
| 735 | 4.6488 | 3.653 | 7.608 | 3.3353 | 1.887 | 21.1322
| 736 | 4.7701 | 3.1295 | 6.8344 | 4.5859 | 1.5599 | 20.8798
| 737 | 4.147 | 2.97 | 6.5157 | 3.5413 | 1.634 | 18.808
| 738 | 4.6567 | 3.3874 | 4.9457 | 3.887 | 1.2494 | 18.1262
| 739 | 3.549 | 2.5478 | 4.8364 | 3.3957 | 1.5795 | 15.9085
| 740 | 4.5434 | 2.8398 | 6.6418 | 4.6002 | 1.3063 | 19.9315
| 741 | 3.5462 | 2.9727 | 6.7497 | 5.3604 | 1.4243 | 20.0533
| 742 | 4.0316 | 3.5444 | 4.6111 | 5.1105 | 1.7513 | 19.049
| 743 | 4.5965 | 3.0664 | 6.4364 | 4.3551 | 1.5658 | 20.0202
| 744 | 3.4816 | 3.6363 | 5.9796 | 4.317 | 1.604 | 19.0186
| 745 | 4.9495 | 2.2681 | 4.9378 | 4.9767 | 1.5955 | 18.7277
| 746 | 4.0918 | 2.7923 | 5.7083 | 3.5151 | 1.3796 | 17.4871
| 747 | 4.4131 | 3.2187 | 5.1126 | 5.5411 | 1.5056 | 19.7911
| 748 | 4.8864 | 2.9982 | 5.6731 | 5.6094 | 1.6766 | 20.8436
| 749 | 3.6357 | 2.4816 | 6.9766 | 4.6871 | 1.2149 | 18.996
| 750 | 4.7481 | 2.2202 | 6.3286 | 4.9047 | 1.8612 | 20.0627
| 751 | 3.3437 | 3.3771 | 6.6569 | 4.8551 | 1.4442 | 19.6771
| 752 | 4.0878 | 2.6882 | 5.3392 | 4.5035 | 1.735 | 18.3537
| 753 | 3.7677 | 3.2246 | 5.5359 | 3.5618 | 1.4355 | 17.5256
| 754 | 3.956 | 3.1601 | 6.1269 | 5.0848 | 1.6185 | 19.9463
| 755 | 4.5756 | 2.9486 | 5.5 | 5.1274 | 1.8274 | 19.979
| 756 | 3.8463 | 3.0105 | 5.9081 | 3.202 | 1.4551 | 17.4221
| 757 | 4.3806 | 2.4446 | 6.6331 | 3.7668 | 1.8846 | 19.1098
| 758 | 3.7066 | 3.1833 | 5.3739 | 4.3495 | 1.3327 | 17.946
| 759 | 3.9712 | 3.0738 | 7.4267 | 3.7822 | 1.7835 | 20.0374
| 760 | 4.4151 | 3.2898 | 5.613 | 4.9277 | 1.2985 | 19.5442
| 761 | 4.2727 | 3.7395 | 5.6228 | 3.4286 | 1.3894 | 18.4528
| 762 | 3.9379 | 3.4155 | 5.9243 | 4.5568 | 1.2242 | 19.0587
| 763 | 4.8431 | 2.9342 | 5.1395 | 3.8413 | 1.2258 | 17.9839
| 764 | 3.9576 | 3.4059 | 5.9018 | 4.6569 | 1.108 | 19.0303
| 765 | 4.0686 | 2.5027 | 5.0069 | 3.6681 | 1.2002 | 16.4465
| 766 | 4.1775 | 3.4247 | 6.1422 | 4.3731 | 1.6515 | 19.7691
| 767 | 4.2525 | 3.1747 | 6.1348 | 3.589 | 1.4653 | 18.6163
| 768 | 4.5852 | 2.8564 | 4.1712 | 5.0065 | 1.155 | 17.7743
| 769 | 3.7753 | 3.2416 | 5.0389 | 5.0432 | 1.4168 | 18.5157
| 770 | 4.2319 | 2.5222 | 5.5469 | 5.4264 | 1.6928 | 19.4202
| 771 | 4.4777 | 3.2565 | 5.3366 | 3.9249 | 1.5241 | 18.5199
| 772 | 3.8138 | 3.7506 | 5.4786 | 5.3128 | 1.2614 | 19.6171
| 773 | 3.5962 | 3.2553 | 5.3231 | 3.5723 | 1.4628 | 17.2096
| 774 | 3.6578 | 2.9305 | 4.8212 | 3.9423 | 1.6372 | 16.9891
| 775 | 4.2081 | 3.5514 | 5.3723 | 5.115 | 1.3805 | 19.6273
| 776 | 4.4082 | 3.0546 | 5.3028 | 4.5358 | 1.6195 | 18.9209
| 777 | 3.9102 | 3.4989 | 7.7828 | 5.8017 | 1.8453 | 22.8389
| 778 | 4.6099 | 3.4874 | 4.8831 | 3.3718 | 1.0824 | 17.4346
| 779 | 4.0269 | 3.3096 | 5.3055 | 3.7038 | 1.4647 | 17.8106
| 780 | 3.4589 | 3.7565 | 4.7287 | 3.7095 | 1.5491 | 17.2027
| 781 | 3.5924 | 3.0409 | 6.0444 | 3.3595 | 1.3047 | 17.342
| 782 | 3.9626 | 3.623 | 6.3102 | 3.8935 | 1.4364 | 19.2257
| 783 | 4.2897 | 2.8882 | 4.4335 | 3.914 | 1.668 | 17.1933
| 784 | 3.9203 | 2.9924 | 4.2952 | 4.0889 | 1.6857 | 16.9826
| 785 | 4.1232 | 2.9153 | 6.6868 | 4.7224 | 1.5763 | 20.0241
| 786 | 4.0536 | 3.0062 | 5.7543 | 4.4666 | 1.2805 | 18.5612
| 787 | 3.9475 | 3.0278 | 4.6928 | 3.5906 | 1.6643 | 16.923
| 788 | 3.3816 | 2.9203 | 6.4626 | 4.6816 | 1.4481 | 18.8942
| 789 | 3.8253 | 3.4726 | 5.075 | 3.5197 | 1.5462 | 17.4387
| 790 | 3.7992 | 3.2535 | 7.6919 | 4.2816 | 1.7559 | 20.7821
| 791 | 4.1257 | 3.2226 | 5.2299 | 5.3089 | 1.3922 | 19.2793
| 792 | 4.1861 | 3.0334 | 5.7604 | 4.9975 | 1.7102 | 19.6876
| 793 | 3.9296 | 2.8013 | 5.7973 | 5.4996 | 1.5234 | 19.5512
| 794 | 3.5869 | 2.4256 | 7.0636 | 3.8399 | 1.0428 | 17.9588
| 795 | 4.4176 | 2.5735 | 4.3173 | 3.4133 | 1.6574 | 16.3791
| 796 | 3.7722 | 2.3429 | 6.3391 | 4.4217 | 1.4894 | 18.3653
| 797 | 3.7232 | 3.9559 | 7.407 | 4.6408 | 1.2733 | 21.0002
| 798 | 3.7861 | 2.6469 | 7.3117 | 3.6886 | 1.5086 | 18.9419
| 799 | 4.6278 | 2.4316 | 4.9012 | 4.7611 | 1.6223 | 18.3441
| 800 | 4.3655 | 2.7048 | 5.5575 | 4.0063 | 1.5613 | 18.1954
| 801 | 4.0939 | 3.2512 | 5.4412 | 3.6433 | 1.5915 | 18.0211
| 802 | 3.6187 | 2.5873 | 5.8517 | 3.9568 | 1.818 | 17.8326
| 803 | 4.835 | 3.4757 | 6.4018 | 4.5749 | 1.4882 | 20.7756
| 804 | 4.4746 | 2.5104 | 4.4864 | 3.4296 | 1.2604 | 16.1614
| 805 | 4.6727 | 2.98 | 5.1214 | 3.2255 | 1.8482 | 17.8478
| 806 | 4.1507 | 3.325 | 6.2491 | 4.5076 | 1.4635 | 19.6959
| 807 | 4.3048 | 3.1195 | 6.4184 | 4.0153 | 1.5554 | 19.4134
| 808 | 4.0636 | 2.9227 | 6.9635 | 3.9216 | 1.3918 | 19.2632
| 809 | 3.6896 | 3.2089 | 4.4152 | 3.5482 | 1.8977 | 16.7595
| 810 | 4.0047 | 3.5895 | 4.1958 | 3.0407 | 1.3541 | 16.1848
| 811 | 4.2057 | 3.8606 | 5.5145 | 3.3811 | 1.5012 | 18.4632
| 812 | 4.1158 | 2.9918 | 5.7024 | 3.5433 | 1.5792 | 17.9324
| 813 | 4.2735 | 3.2701 | 4.4844 | 5.7288 | 1.6188 | 19.3755
| 814 | 4.3365 | 3.3684 | 5.6756 | 4.5797 | 1.4528 | 19.413
| 815 | 4.1154 | 2.7232 | 5.6912 | 4.4337 | 1.4869 | 18.4504
| 816 | 3.3702 | 3.7992 | 4.5433 | 3.7787 | 1.2076 | 16.699
| 817 | 4.0467 | 2.8364 | 6.4822 | 3.8313 | 1.6815 | 18.8781
| 818 | 3.2978 | 2.3714 | 5.4229 | 3.8702 | 1.6987 | 16.6611
| 819 | 3.4562 | 3.468 | 5.8469 | 3.734 | 1.6523 | 18.1574
| 820 | 3.16 | 3.3617 | 5.7337 | 5.2088 | 1.0993 | 18.5635
| 821 | 4.2385 | 3.0208 | 4.8431 | 4.2347 | 1.4103 | 17.7475
| 822 | 4.1613 | 3.3452 | 6.4275 | 3.967 | 1.4575 | 19.3586
| 823 | 3.6459 | 3.1323 | 7.0823 | 5.2784 | 1.6442 | 20.7832
| 824 | 4.556 | 2.5667 | 4.9766 | 4.0763 | 1.3383 | 17.514
| 825 | 3.7318 | 3.0181 | 4.4223 | 4.1784 | 1.5229 | 16.8735
| 826 | 3.9452 | 2.8756 | 6.4939 | 4.6718 | 1.405 | 19.3916
| 827 | 3.6176 | 3.7157 | 4.4573 | 5.3744 | 1.1225 | 18.2875
| 828 | 4.3425 | 2.3964 | 4.4124 | 4.2756 | 1.6104 | 17.0373
| 829 | 4.8314 | 3.4361 | 7.1488 | 4.0606 | 1.4384 | 20.9153
| 830 | 4.5465 | 3.026 | 7.1171 | 5.4003 | 1.9124 | 22.0023
| 831 | 3.7024 | 3.3994 | 5.8957 | 5.1495 | 1.5133 | 19.6603
| 832 | 4.4932 | 3.0765 | 6.3786 | 3.6894 | 1.4197 | 19.0574
| 833 | 3.6387 | 3.1549 | 6.9677 | 4.914 | 1.6968 | 20.3721
| 834 | 4.3213 | 3.0881 | 4.6614 | 3.1717 | 1.3054 | 16.5479
| 835 | 3.7885 | 3.5837 | 5.2357 | 4.6992 | 1.7945 | 19.1017
| 836 | 4.0386 | 2.9792 | 4.9791 | 4.8246 | 1.2868 | 18.1083
| 837 | 3.7184 | 3.6682 | 5.879 | 3.8964 | 1.3018 | 18.4637
| 838 | 4.4031 | 2.8351 | 4.8484 | 4.2468 | 1.1619 | 17.4954
| 839 | 4.2471 | 2.7904 | 5.0084 | 3.5086 | 1.4843 | 17.0389
| 840 | 3.5447 | 3.2375 | 5.7104 | 3.5571 | 1.5847 | 17.6345
| 841 | 3.8481 | 2.1609 | 5.7792 | 3.1993 | 1.5446 | 16.5321
| 842 | 4.691 | 2.9862 | 5.3795 | 4.3029 | 1.7068 | 19.0664
| 843 | 4.0629 | 2.5248 | 5.4193 | 5.2599 | 1.9073 | 19.1743
| 844 | 4.3038 | 2.6787 | 4.2324 | 5.0197 | 1.4518 | 17.6864
| 845 | 4.9353 | 2.9209 | 5.2138 | 4.6949 | 1.3986 | 19.1634
| 846 | 3.9654 | 3.2434 | 4.5029 | 3.9341 | 1.5248 | 17.1705
| 847 | 4.7815 | 3.538 | 4.7245 | 3.8531 | 1.639 | 18.5362
| 848 | 3.7974 | 3.118 | 6.4763 | 4.4894 | 1.7484 | 19.6295
| 849 | 4.6996 | 3.5923 | 5.5408 | 3.3878 | 1.6129 | 18.8336
| 850 | 4.2856 | 3.166 | 6.1224 | 4.3989 | 1.623 | 19.5958
| 851 | 4.0184 | 3.5005 | 7.0878 | 3.0945 | 1.4863 | 19.1873
| 852 | 4.1134 | 3.791 | 5.2413 | 3.7726 | 1.1576 | 18.0759
| 853 | 3.884 | 2.8704 | 4.6287 | 4.603 | 1.528 | 17.5141
| 854 | 3.594 | 2.4134 | 4.9892 | 3.9528 | 1.3836 | 16.333
| 855 | 3.4752 | 2.7742 | 5.2556 | 4.8258 | 1.5319 | 17.8627
| 856 | 3.7162 | 3.3154 | 5.5298 | 4.9192 | 1.4951 | 18.9757
| 857 | 4.0565 | 2.9612 | 4.8155 | 3.3909 | 1.2597 | 16.4838
| 858 | 4.1711 | 2.7564 | 5.4263 | 3.4316 | 1.1205 | 16.9059
| 859 | 4.0145 | 2.6781 | 5.1098 | 3.9033 | 1.4379 | 17.1435
| 860 | 4.1957 | 2.4536 | 6.0584 | 4.3899 | 1.5633 | 18.6608
| 861 | 4.2099 | 3.1132 | 7.6751 | 3.6339 | 1.3454 | 19.9775
| 862 | 3.6553 | 2.9325 | 5.2581 | 4.7379 | 1.3237 | 17.9076
| 863 | 3.1281 | 2.8721 | 6.0318 | 4.4975 | 1.7406 | 18.2701
| 864 | 3.7454 | 3.409 | 6.8218 | 3.9991 | 1.4612 | 19.4365
| 865 | 3.6691 | 3.1775 | 4.7338 | 3.5982 | 1.5759 | 16.7545
| 866 | 3.571 | 2.6335 | 4.8459 | 4.0955 | 1.4035 | 16.5495
| 867 | 3.8488 | 3.2271 | 5.9112 | 3.6874 | 1.7776 | 18.4521
| 868 | 3.2273 | 3.2449 | 6.6082 | 3.3408 | 1.3149 | 17.736
| 869 | 3.2857 | 3.3342 | 5.8438 | 4.092 | 1.4669 | 18.0225
| 870 | 3.9845 | 2.1866 | 4.44 | 3.7907 | 1.5879 | 15.9898
| 871 | 4.1382 | 3.1028 | 6.256 | 4.8649 | 1.4159 | 19.7778
| 872 | 4.1748 | 2.1534 | 6.8271 | 4.2311 | 1.7588 | 19.1451
| 873 | 3.6971 | 3.5105 | 6.6993 | 5.014 | 1.4165 | 20.3374
| 874 | 4.0496 | 3.2298 | 4.8571 | 3.4436 | 1.5905 | 17.1706
| 875 | 4.1518 | 2.645 | 7.4759 | 4.3203 | 1.5661 | 20.1591
| 876 | 3.2884 | 3.3023 | 6.2884 | 4.5621 | 1.6095 | 19.0507
| 877 | 4.264 | 2.607 | 4.1575 | 3.387 | 1.1945 | 15.6099
| 878 | 3.3915 | 3.173 | 4.7093 | 4.2887 | 1.8599 | 17.4224
| 879 | 3.8872 | 2.6214 | 6.1729 | 5.3937 | 1.4531 | 19.5281
| 880 | 3.8182 | 2.5761 | 6.2076 | 3.8767 | 1.2222 | 17.7008
| 881 | 4.874 | 3.4593 | 5.598 | 3.8786 | 1.767 | 19.5769
| 882 | 4.6697 | 3.7726 | 4.4738 | 4.1083 | 1.5437 | 18.5682
| 883 | 4.8502 | 3.4617 | 5.5354 | 4.6747 | 1.7293 | 20.2513
| 884 | 4.0811 | 3.7868 | 6.7663 | 3.2949 | 1.5068 | 19.436
| 885 | 3.3072 | 3.3848 | 4.7399 | 4.2317 | 1.6239 | 17.2876
| 886 | 4.536 | 2.8812 | 5.7249 | 3.1858 | 1.725 | 18.0529
| 887 | 4.5925 | 3.8096 | 6.3139 | 4.9855 | 1.7979 | 21.4995
| 888 | 4.3909 | 2.4566 | 6.1523 | 3.7459 | 1.0724 | 17.8182
| 889 | 4.3137 | 3.9456 | 6.0553 | 5.09 | 1.1018 | 20.5063
| 890 | 3.4441 | 2.7521 | 4.0919 | 5.0036 | 1.5311 | 16.8227
| 891 | 3.1493 | 3.065 | 5.9957 | 4.1504 | 1.3575 | 17.7179
| 892 | 3.8038 | 3.514 | 6.5543 | 3.191 | 1.3031 | 18.3662
| 893 | 3.8113 | 3.3192 | 5.3258 | 5.0678 | 1.7417 | 19.2658
| 894 | 3.2233 | 3.4823 | 6.6505 | 5.2416 | 1.5256 | 20.1232
| 895 | 4.3367 | 2.8939 | 5.8259 | 3.7424 | 1.5769 | 18.3759
| 896 | 3.9914 | 2.9049 | 6.9296 | 4.453 | 1.4467 | 19.7257
| 897 | 3.4675 | 2.4215 | 5.9204 | 4.1635 | 1.7333 | 17.7062
| 898 | 3.6763 | 2.846 | 5.3499 | 3.4001 | 1.6205 | 16.8928
| 899 | 3.7053 | 3.6198 | 5.9551 | 4.6279 | 1.4562 | 19.3644
| 900 | 4.3708 | 3.2001 | 6.2707 | 4.1149 | 1.3257 | 19.2821
| 901 | 4.5812 | 3.8281 | 5.1337 | 3.6857 | 1.6745 | 18.9032
| 902 | 3.6606 | 3.3392 | 5.2641 | 3.6717 | 1.653 | 17.5886
| 903 | 4.0769 | 3.7596 | 6.864 | 3.2463 | 1.663 | 19.6098
| 904 | 3.8555 | 2.8234 | 4.8316 | 3.8035 | 1.9024 | 17.2165
| 905 | 3.5843 | 3.4899 | 5.4373 | 4.1748 | 1.6876 | 18.3739
| 906 | 4.0578 | 2.896 | 5.6207 | 3.374 | 1.4017 | 17.3502
| 907 | 4.0825 | 2.6852 | 5.0045 | 3.1207 | 1.7181 | 16.6109
| 908 | 4.1104 | 2.6377 | 6.7193 | 4.4452 | 1.5716 | 19.4843
| 909 | 4.2176 | 3.1984 | 6.6484 | 4.5707 | 1.9168 | 20.5518
| 910 | 3.7219 | 3.2593 | 7.1992 | 4.5724 | 1.8128 | 20.5656
| 911 | 3.9962 | 2.6616 | 4.3049 | 4.1673 | 1.7444 | 16.8745
| 912 | 3.3615 | 2.3228 | 6.7411 | 4.8697 | 1.5036 | 18.7987
| 913 | 4.1483 | 2.3158 | 5.6679 | 4.9389 | 1.7573 | 18.8283
| 914 | 4.281 | 2.6764 | 5.949 | 4.5295 | 1.221 | 18.6569
| 915 | 4.1832 | 3.5608 | 5.3658 | 5.4498 | 1.3401 | 19.8997
| 916 | 3.7489 | 2.5209 | 4.5884 | 3.4722 | 1.5079 | 15.8383
| 917 | 3.9515 | 3.2357 | 5.2995 | 3.2872 | 1.3292 | 17.1032
| 918 | 3.1037 | 2.35 | 7.7168 | 3.8454 | 1.5096 | 18.5255
| 919 | 3.9432 | 3.013 | 4.356 | 3.8967 | 1.3202 | 16.529
| 920 | 3.402 | 2.6136 | 4.8729 | 3.7252 | 1.167 | 15.7808
| 921 | 4.8025 | 2.7543 | 7.366 | 4.4083 | 1.2178 | 20.5489
| 922 | 4.2679 | 2.1244 | 6.5233 | 3.6142 | 1.7111 | 18.241
| 923 | 3.3394 | 2.5708 | 7.0529 | 3.0727 | 1.5526 | 17.5884
| 924 | 3.5129 | 3.0079 | 4.7587 | 4.2134 | 1.3502 | 16.8431
| 925 | 4.0776 | 2.6164 | 5.9597 | 4.295 | 1.7032 | 18.6521
| 926 | 3.7796 | 2.4768 | 4.5735 | 3.93 | 1.5606 | 16.3205
| 927 | 4.5648 | 3.5569 | 6.1758 | 3.6627 | 1.342 | 19.3021
| 928 | 3.9079 | 2.9946 | 4.8644 | 4.1804 | 1.6112 | 17.5585
| 929 | 3.5772 | 3.5937 | 5.6283 | 4.7125 | 1.4678 | 18.9794
| 930 | 3.7938 | 3.279 | 7.9109 | 3.8799 | 1.8438 | 20.7074
| 931 | 4.0085 | 3.5483 | 4.9608 | 5.5545 | 1.4687 | 19.5407
| 932 | 4.1687 | 2.6324 | 5.7166 | 5.7546 | 1.2941 | 19.5664
| 933 | 3.5091 | 2.7307 | 6.1814 | 4.2452 | 1.5754 | 18.2418
| 934 | 4.2306 | 2.3085 | 5.0024 | 4.5407 | 1.4972 | 17.5795
| 935 | 4.1578 | 2.7358 | 4.3896 | 4.3969 | 1.4979 | 17.1781
| 936 | 3.4055 | 2.7162 | 5.4873 | 5.4713 | 1.3772 | 18.4576
| 937 | 3.9724 | 3.7659 | 6.3944 | 3.7535 | 1.0903 | 18.9764
| 938 | 4.0162 | 2.4017 | 4.6162 | 3.8882 | 1.4794 | 16.4018
| 939 | 4.6 | 3.1649 | 6.2214 | 5.0249 | 1.5934 | 20.6046
| 940 | 3.6488 | 2.6056 | 7.5466 | 4.0795 | 1.2727 | 19.1533
| 941 | 4.2931 | 3.3364 | 5.0429 | 5.0941 | 1.4901 | 19.2566
| 942 | 4.3945 | 3.6822 | 4.7833 | 3.4916 | 1.1356 | 17.4873
| 943 | 4.5058 | 3.8124 | 4.6466 | 4.1317 | 1.7536 | 18.8501
| 944 | 3.8864 | 3.148 | 5.5436 | 4.6046 | 1.5299 | 18.7124
| 945 | 4.6165 | 2.7594 | 7.2733 | 3.1676 | 1.7719 | 19.5888
| 946 | 3.8289 | 2.6688 | 4.958 | 5.6932 | 1.8639 | 19.0128
| 947 | 4.024 | 2.8843 | 6.3471 | 5.582 | 1.4904 | 20.3279
| 948 | 3.5165 | 2.7656 | 5.4082 | 4.609 | 1.8015 | 18.1008
| 949 | 4.0962 | 3.2123 | 4.346 | 3.2208 | 1.3569 | 16.2321
| 950 | 4.7389 | 2.3877 | 5.1473 | 3.211 | 1.4292 | 16.9141
| 951 | 3.5237 | 2.4598 | 5.0709 | 5.6726 | 1.3285 | 18.0554
| 952 | 4.2796 | 2.9773 | 7.1853 | 4.0248 | 1.2993 | 19.7664
| 953 | 3.7897 | 3.08 | 5.7276 | 4.7013 | 1.3371 | 18.6356
| 954 | 3.2655 | 3.694 | 5.8682 | 4.7978 | 1.5257 | 19.1512
| 955 | 3.8098 | 2.8417 | 4.9223 | 3.8149 | 1.5541 | 16.9427
| 956 | 4.0715 | 3.1207 | 4.8853 | 4.2919 | 1.7101 | 18.0795
| 957 | 3.875 | 2.9332 | 5.3581 | 3.6495 | 1.4256 | 17.2413
| 958 | 4.4213 | 2.3289 | 6.3881 | 4.4679 | 1.5405 | 19.1467
| 959 | 3.8962 | 3.6773 | 5.3545 | 4.7664 | 1.5238 | 19.2182
| 960 | 4.6534 | 3.0086 | 5.4135 | 4.3377 | 1.7211 | 19.1342
| 961 | 4.2822 | 3.1395 | 5.1293 | 3.8632 | 1.2481 | 17.6623
| 962 | 4.1464 | 2.1913 | 7.557 | 3.8163 | 1.3781 | 19.0891
| 963 | 4.3532 | 3.0004 | 4.7544 | 3.1542 | 1.858 | 17.1201
| 964 | 4.5399 | 2.2858 | 4.1339 | 3.3818 | 1.1498 | 15.4912
| 965 | 3.5896 | 3.0421 | 4.5535 | 4.0454 | 1.3651 | 16.5958
| 966 | 4.3439 | 3.152 | 5.7012 | 3.4229 | 1.14 | 17.7601
| 967 | 4.6745 | 2.999 | 5.1932 | 3.4628 | 1.0801 | 17.4096
| 968 | 4.2968 | 2.3273 | 6.4148 | 3.427 | 1.2682 | 17.7341
| 969 | 4.0514 | 3.4187 | 5.7516 | 4.3799 | 1.5549 | 19.1566
| 970 | 4.1434 | 2.7937 | 4.9394 | 5.4112 | 1.7299 | 19.0176
| 971 | 3.8227 | 2.1695 | 5.5282 | 3.5326 | 1.2814 | 16.3345
| 972 | 3.6051 | 3.1095 | 6.1311 | 3.702 | 1.2684 | 17.8161
| 973 | 4.3059 | 2.5838 | 4.806 | 4.0745 | 1.7623 | 17.5325
| 974 | 4.0359 | 3.1899 | 4.4508 | 3.4658 | 1.7359 | 16.8783
| 975 | 4.2027 | 2.717 | 5.339 | 4.5537 | 1.8696 | 18.6821
| 976 | 3.8643 | 2.8684 | 6.2969 | 4.3933 | 1.5892 | 19.0121
| 977 | 3.9613 | 3.6003 | 4.1418 | 3.5235 | 1.8763 | 17.1032
| 978 | 3.7143 | 3.4082 | 4.7038 | 4.316 | 1.6293 | 17.7715
| 979 | 4.1785 | 3.2259 | 5.4585 | 3.3669 | 1.6905 | 17.9202
| 980 | 4.1181 | 2.719 | 6.4574 | 3.1849 | 1.6543 | 18.1338
| 981 | 3.7503 | 2.9933 | 4.4659 | 4.1446 | 1.3519 | 16.7061
| 982 | 4.0435 | 3.0584 | 5.8224 | 3.5644 | 1.5699 | 18.0587
| 983 | 4.0797 | 2.7084 | 4.085 | 4.3272 | 1.7013 | 16.9015
| 984 | 4.6594 | 2.8315 | 5.2659 | 3.9644 | 1.7267 | 18.448
| 985 | 3.7283 | 2.9592 | 4.3816 | 4.5484 | 1.3688 | 16.9863
| 986 | 3.3306 | 3.4974 | 6.2641 | 4.1954 | 1.4251 | 18.7127
| 987 | 3.9404 | 3.1947 | 7.6652 | 3.9775 | 1.399 | 20.1769
| 988 | 3.6105 | 2.4732 | 6.379 | 3.504 | 1.8901 | 17.8568
| 989 | 4.0413 | 2.8073 | 6.1979 | 4.7482 | 1.6605 | 19.4551
| 990 | 3.8584 | 3.4667 | 4.6572 | 4.6184 | 1.5813 | 18.182
| 991 | 3.7564 | 2.9576 | 7.4674 | 3.5397 | 1.3642 | 19.0852
| 992 | 3.4914 | 3.3422 | 5.5548 | 4.1015 | 1.3842 | 17.8742
| 993 | 3.7031 | 2.7951 | 5.7134 | 4.7251 | 1.6584 | 18.595
| 994 | 3.9339 | 3.1688 | 4.1222 | 4.7727 | 1.6963 | 17.6939
| 995 | 4.2131 | 3.2035 | 5.0346 | 3.4465 | 1.256 | 17.1536
| 996 | 3.2766 | 2.4027 | 6.2388 | 3.7217 | 1.6706 | 17.3104
| 997 | 4.1924 | 3.0149 | 5.2029 | 5.1726 | 1.9141 | 19.4969
| 998 | 3.5225 | 3.3648 | 5.1356 | 4.5434 | 1.5485 | 18.1149
| 999 | 4.1038 | 2.7996 | 5.0586 | 4.2514 | 1.7721 | 17.9854
| 1000 | 3.9386 | 2.3482 | 5.1921 | 3.7367 | 1.3698 | 16.5854
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Risk Results 1
Navigation |  | Inputs |  |  |  |  | Outputs | Simulation Statistics |  | Output Cumulative Distributions | Output Distributions | Risk Tornado Diagram
Risk Outputs |  | Plan!$G$4 | Plan!$G$5 | Plan!$G$6 | Plan!$G$7 | Plan!$G$8 | Plan!$G$9 |  | Plan!$G$9 |  |  |  |  | Correlations - Column 1 sorted
Simulation Statistics | Iterations | RiskTriang(D4,E4,F4) | RiskTriang(D5,E5,F5) | RiskTriang(D6,E6,F6) | RiskTriang(D7,E7,F7) | RiskTriang(D8,E8,F8) | LiveDate |  | LiveDate |  |  | Select Output: | Plan!$G$9 |  | Plan!$G$9
Risk Output Percentiles | 1 | 4.5255 | 2.2973 | 6.1085 | 3.4997 | 1.4665 | 17.8974 | Mean | 18.3333 |  |  | Name: | LiveDate | Risk Inputs | LiveDate
Calculate Percent Rank | 2 | 3.6026 | 3.5247 | 5.5688 | 4.6562 | 1.6971 | 19.0494 | Median | 18.2762 |  |  | 1 |  | Plan!$G$8 | 0.15949
Correlations | 3 | 4.5917 | 3.2119 | 5.4836 | 4.3941 | 1.2737 | 18.955 | Mode | #N/A |  |  | Tornado Diagram for LiveDate (Plan!$G$9) |  | Plan!$G$4 | 0.31866
Output Cumulative Distributions | 4 | 3.637 | 3.0778 | 4.8872 | 4.3282 | 1.3748 | 17.3051 | Std. Deviation | 1.2464 |  |  |  |  | Plan!$G$5 | 0.33751
Output Distributions | 5 | 3.6709 | 2.5644 | 5.0723 | 3.7696 | 1.3429 | 16.4201 | Variance | 1.5536 |  |  |  |  | Plan!$G$7 | 0.54787
Risk Tornado Diagram | 6 | 3.4242 | 3.2987 | 5.9162 | 4.0555 | 1.2678 | 17.9623 | Kurtosis | -0.3662 |  |  |  |  | Plan!$G$6 | 0.68955
| 7 | 4.6918 | 2.8209 | 5.3451 | 3.4979 | 1.1931 | 17.5488 | Skewness | 0.21143
| 8 | 4.5797 | 3.2763 | 7.2939 | 4.8924 | 1.5692 | 21.6115 | Minimum | 15.0076
| 9 | 4.24 | 2.2846 | 4.7569 | 3.6335 | 1.4984 | 16.4133 | Maximum | 22.5516
| 10 | 3.9087 | 3.1382 | 5.1105 | 4.5456 | 1.3919 | 18.0948 | Range | 7.5441
| 11 | 3.7617 | 3.287 | 4.6548 | 3.5466 | 1.3448 | 16.5949 | Count | 1000
| 12 | 3.4625 | 2.6769 | 4.816 | 3.2845 | 1.5684 | 15.8083 | Error Count | 0
| 13 | 4.1396 | 2.8456 | 4.6044 | 5.5513 | 1.74 | 18.8807 | Std. Error | 0.039415
| 14 | 4.1208 | 3.16 | 5.4547 | 4.589 | 1.3682 | 18.6928 | Confidence Level (95%) | 0.077346
| 15 | 4.3274 | 2.9481 | 4.5767 | 3.9952 | 1.1862 | 17.0336
| 16 | 3.7307 | 2.6803 | 4.8495 | 3.503 | 1.8186 | 16.582 | Percentiles
| 17 | 4.0695 | 3.1766 | 4.7608 | 4.5051 | 1.4187 | 17.9308 |  | Plan!$G$9
| 18 | 4.1832 | 2.4662 | 4.745 | 3.6306 | 1.6115 | 16.6365 |  | LiveDate
| 19 | 4.1317 | 3.5666 | 5.964 | 3.8651 | 1.8769 | 19.4044 | 0% | 15.0076
| 20 | 4.8847 | 2.8197 | 5.2528 | 5.0985 | 1.492 | 19.5477 | 2.5% | 16.1428
| 21 | 3.9876 | 2.6883 | 5.8684 | 4.0981 | 1.3547 | 17.9971 | 5% | 16.4133
| 22 | 4.0156 | 2.7212 | 5.741 | 3.5517 | 1.3617 | 17.3912 | 7.5% | 16.5857
| 23 | 3.4089 | 3.1006 | 5.505 | 5.3882 | 1.331 | 18.7337 | 10% | 16.7239
| 24 | 4.6625 | 3.7679 | 6.2296 | 3.8492 | 1.4507 | 19.96 | 12.5% | 16.8893
| 25 | 4.3897 | 3.1669 | 4.551 | 3.9938 | 1.4856 | 17.5869 | 15% | 17.0078
| 26 | 4.5874 | 3.1276 | 5.2792 | 4.3992 | 1.4734 | 18.8668 | 17.5% | 17.1045
| 27 | 4.2907 | 3.0422 | 6.484 | 4.4103 | 1.859 | 20.0863 | 20% | 17.2301
| 28 | 4.0533 | 3.5495 | 5.742 | 4.5229 | 1.6545 | 19.5222 | 22.5% | 17.3234
| 29 | 4.6722 | 2.5997 | 6.1006 | 3.8822 | 1.8072 | 19.0618 | 25% | 17.4036
| 30 | 4.163 | 2.7505 | 7.428 | 5.0228 | 1.7891 | 21.1535 | 27.5% | 17.5045
| 31 | 4.4453 | 2.7864 | 5.909 | 3.5644 | 1.5049 | 18.2101 | 30% | 17.5681
| 32 | 3.9891 | 2.547 | 4.3121 | 3.6756 | 1.8731 | 16.3968 | 32.5% | 17.6866
| 33 | 3.742 | 3.2343 | 6.7434 | 3.6213 | 1.355 | 18.6961 | 35% | 17.7737
| 34 | 3.9981 | 2.8151 | 6.1874 | 5.8051 | 1.5647 | 20.3704 | 37.5% | 17.8606
| 35 | 3.8249 | 3.5542 | 4.0562 | 3.4548 | 1.4446 | 16.3347 | 40% | 17.9334
| 36 | 3.3236 | 3.3305 | 6.5806 | 4.8679 | 1.8652 | 19.9677 | 42.5% | 17.9913
| 37 | 3.4978 | 2.5003 | 6.3345 | 5.4003 | 1.1955 | 18.9284 | 45% | 18.0937
| 38 | 4.237 | 2.9899 | 4.5877 | 3.2209 | 1.6217 | 16.6572 | 47.5% | 18.212
| 39 | 4.492 | 3.0743 | 4.927 | 3.7682 | 1.6235 | 17.8851 | 50% | 18.2762
| 40 | 4.8619 | 2.9166 | 4.1018 | 5.262 | 1.2641 | 18.4065 | 52.5% | 18.3526
| 41 | 3.5604 | 2.8725 | 5.3362 | 4.8862 | 1.6668 | 18.3222 | 55% | 18.4323
| 42 | 4.087 | 3.2434 | 6.0402 | 3.5426 | 1.4875 | 18.4007 | 57.5% | 18.5245
| 43 | 3.9458 | 2.7823 | 6.4002 | 3.6839 | 1.7651 | 18.5773 | 60% | 18.6261
| 44 | 3.5723 | 3.365 | 5.3466 | 3.0452 | 1.4573 | 16.7863 | 62.5% | 18.7166
| 45 | 3.7345 | 2.8569 | 5.0258 | 3.7199 | 1.1801 | 16.5172 | 65% | 18.8259
| 46 | 3.2378 | 3.0755 | 6.2756 | 4.2239 | 1.5448 | 18.3576 | 67.5% | 18.9008
| 47 | 3.5459 | 2.9996 | 5.1476 | 3.556 | 1.3275 | 16.5767 | 70% | 18.9686
| 48 | 3.9432 | 2.7312 | 4.8067 | 4.7164 | 1.2745 | 17.4719 | 72.5% | 19.0841
| 49 | 3.9051 | 2.9489 | 4.8747 | 3.3167 | 1.2894 | 16.3348 | 75% | 19.1882
| 50 | 4.292 | 2.3381 | 6.4298 | 5.0768 | 1.5819 | 19.7187 | 77.5% | 19.3163
| 51 | 4.8509 | 2.9292 | 7.6416 | 3.5088 | 1.6571 | 20.5877 | 80% | 19.4502
| 52 | 4.0226 | 2.8412 | 5.3136 | 3.8287 | 1.8807 | 17.8867 | 82.5% | 19.5568
| 53 | 4.2132 | 2.1809 | 7.4592 | 4.7894 | 1.2931 | 19.9358 | 85% | 19.6643
| 54 | 4.1314 | 2.7467 | 5.6448 | 4.3486 | 1.4232 | 18.2947 | 87.5% | 19.8768
| 55 | 3.6915 | 3.8264 | 6.1816 | 3.6519 | 1.398 | 18.7494 | 90% | 20.0166
| 56 | 3.7128 | 2.0958 | 6.2069 | 4.8151 | 1.2968 | 18.1275 | 92.5% | 20.1956
| 57 | 3.7215 | 2.5723 | 5.8863 | 3.6962 | 1.7154 | 17.5918 | 95% | 20.4651
| 58 | 3.8245 | 3.8917 | 5.8145 | 4.4797 | 1.7539 | 19.7641 | 97.5% | 20.8815
| 59 | 3.8925 | 2.796 | 4.7803 | 4.1404 | 1.5991 | 17.2084 | 100% | 22.5516
| 60 | 3.4801 | 2.5763 | 6.0267 | 3.2434 | 1.5765 | 16.9031
| 61 | 4.7405 | 3.1959 | 6.6911 | 3.6763 | 1.7085 | 20.0124 | Percent Rank
| 62 | 4.1766 | 2.9835 | 4.811 | 3.7236 | 1.7623 | 17.4569 |  | Plan!$G$9
| 63 | 4.5898 | 2.968 | 5.6725 | 3.2759 | 1.6976 | 18.2037 |  | LiveDate
| 64 | 3.3205 | 3.1307 | 5.2228 | 3.5576 | 1.7298 | 16.9614 | Enter Value: | 16.4133
| 65 | 4.3279 | 3.4352 | 4.6151 | 3.3754 | 1.304 | 17.0577 | % rank: | 5%
| 66 | 3.9142 | 2.3555 | 6.2332 | 4.2112 | 1.4757 | 18.1897
| 67 | 4.2953 | 2.9272 | 6.2219 | 4.3349 | 1.4084 | 19.1876 | Correlations
| 68 | 4.2633 | 2.881 | 6.6488 | 4.0079 | 1.389 | 19.19 |  | Plan!$G$9
| 69 | 4.081 | 3.4993 | 4.2612 | 4.6782 | 1.1077 | 17.6274 | Risk Inputs | LiveDate
| 70 | 4.3814 | 3.2504 | 4.585 | 3.5113 | 1.4837 | 17.2117 | Plan!$G$4 | 0.31866
| 71 | 3.2277 | 3.3186 | 5.6969 | 5.1138 | 1.3516 | 18.7086 | Plan!$G$5 | 0.33751
| 72 | 4.0954 | 3.1046 | 6.2643 | 4.3008 | 1.4046 | 19.1697 | Plan!$G$6 | 0.68955
| 73 | 4.34 | 2.9002 | 7.357 | 4.1264 | 1.4999 | 20.2234 | Plan!$G$7 | 0.54787
| 74 | 3.5832 | 2.2509 | 5.1452 | 3.633 | 1.24 | 15.8523 | Plan!$G$8 | 0.15949
| 75 | 3.577 | 3.4595 | 5.4754 | 4.3242 | 1.4518 | 18.2879
| 76 | 3.1295 | 2.8945 | 6.1434 | 4.0033 | 1.5929 | 17.7636
| 77 | 3.6208 | 3.0906 | 5.8705 | 3.4176 | 1.5398 | 17.5394
| 78 | 3.6217 | 2.9694 | 5.5111 | 4.6517 | 1.6136 | 18.3675
| 79 | 4.2534 | 2.375 | 5.9469 | 3.6821 | 1.5438 | 17.8012
| 80 | 4.3453 | 2.4465 | 7.0402 | 3.5451 | 1.5526 | 18.9297
| 81 | 4.288 | 2.9087 | 7.2189 | 4.0782 | 1.4102 | 19.9041
| 82 | 3.9176 | 3.1286 | 4.9908 | 4.4675 | 1.2787 | 17.7831
| 83 | 4.4783 | 3.5409 | 5.6098 | 4.6477 | 1.4968 | 19.7735
| 84 | 4.2787 | 2.9875 | 5.6479 | 4.6772 | 1.6314 | 19.2228
| 85 | 4.2864 | 3.7728 | 6.38 | 3.2571 | 1.2721 | 18.9684
| 86 | 4.465 | 2.6526 | 6.5466 | 3.4847 | 1.3372 | 18.4861
| 87 | 3.7924 | 2.9663 | 6.318 | 5.6505 | 1.69 | 20.4172
| 88 | 3.8012 | 2.871 | 5.3249 | 3.641 | 1.2513 | 16.8894
| 89 | 3.9031 | 3.276 | 5.094 | 3.4274 | 1.1302 | 16.8307
| 90 | 3.3298 | 2.5409 | 4.7281 | 4.1939 | 1.14 | 15.9328
| 91 | 4.2994 | 3.1635 | 6.246 | 5.1886 | 1.6079 | 20.5055
| 92 | 4.3191 | 2.8999 | 5.3613 | 4.085 | 1.8367 | 18.502
| 93 | 4.1141 | 2.4691 | 5.7026 | 5.181 | 1.4334 | 18.9002
| 94 | 3.7153 | 3.7029 | 5.5465 | 4.0589 | 1.7364 | 18.7599
| 95 | 4.4088 | 2.824 | 5.1254 | 3.5412 | 1.4609 | 17.3603
| 96 | 3.4499 | 2.6247 | 6.7815 | 3.3029 | 1.0823 | 17.2414
| 97 | 3.3761 | 2.5586 | 7.3394 | 3.9629 | 1.4108 | 18.6477
| 98 | 4.5555 | 2.585 | 4.7354 | 3.6158 | 1.4279 | 16.9196
| 99 | 3.7034 | 3.3664 | 6.8921 | 4.6267 | 1.1421 | 19.7306
| 100 | 4.3083 | 2.4501 | 6.0907 | 5.6221 | 1.5444 | 20.0156
| 101 | 4.8178 | 3.5764 | 5.6896 | 3.698 | 1.8782 | 19.66
| 102 | 4.2522 | 2.8074 | 5.8787 | 4.7864 | 1.1879 | 18.9126
| 103 | 4.5362 | 2.8866 | 4.5672 | 4.0317 | 1.5811 | 17.6027
| 104 | 4.197 | 3.0649 | 6.0613 | 5.0197 | 1.2349 | 19.5777
| 105 | 4.006 | 3.2239 | 5.5825 | 4.2696 | 1.8201 | 18.9021
| 106 | 3.2994 | 2.7153 | 5.3485 | 3.5328 | 1.586 | 16.482
| 107 | 3.5429 | 3.2263 | 4.5918 | 4.4957 | 1.7074 | 17.5641
| 108 | 4.2074 | 2.65 | 4.8884 | 3.8032 | 1.4589 | 17.0079
| 109 | 4.281 | 2.6896 | 5.2905 | 4.0523 | 1.5213 | 17.8347
| 110 | 4.2762 | 2.8587 | 5.3869 | 3.9177 | 1.774 | 18.2134
| 111 | 3.8438 | 2.978 | 5.0343 | 5.7463 | 1.624 | 19.2264
| 112 | 4.2117 | 2.4816 | 7.4869 | 3.8163 | 1.6303 | 19.6268
| 113 | 3.738 | 3.4291 | 7.0035 | 4.1042 | 1.3265 | 19.6012
| 114 | 3.8318 | 3.1351 | 4.9571 | 3.2274 | 1.4884 | 16.6399
| 115 | 3.9264 | 3.5316 | 4.9664 | 3.6617 | 1.5093 | 17.5954
| 116 | 3.6551 | 2.6837 | 5.9217 | 4.7448 | 1.5233 | 18.5285
| 117 | 3.8548 | 2.8553 | 4.4445 | 3.826 | 1.1914 | 16.172
| 118 | 3.1192 | 3.9651 | 6.2123 | 5.6044 | 1.3815 | 20.2826
| 119 | 3.5298 | 3.5837 | 6.9227 | 5.1949 | 1.5281 | 20.7592
| 120 | 3.3391 | 2.5762 | 5.8365 | 4.1835 | 1.312 | 17.2474
| 121 | 3.5893 | 3.5899 | 4.9897 | 3.6568 | 1.645 | 17.4707
| 122 | 4.0107 | 3.473 | 5.5076 | 5.4715 | 1.6907 | 20.1536
| 123 | 4.54 | 2.7199 | 7.1447 | 4.1552 | 1.6121 | 20.1718
| 124 | 3.7832 | 2.4092 | 5.0306 | 3.5369 | 1.2013 | 15.9612
| 125 | 4.657 | 2.7635 | 7.0348 | 4.3366 | 1.8007 | 20.5925
| 126 | 4.3482 | 3.0918 | 4.8921 | 3.5525 | 1.643 | 17.5277
| 127 | 4.2464 | 3.2206 | 4.8199 | 5.2995 | 1.0881 | 18.6746
| 128 | 4.0461 | 3.6424 | 4.9014 | 3.6271 | 1.6955 | 17.9126
| 129 | 3.2745 | 2.9632 | 6.8098 | 3.3961 | 1.2553 | 17.6988
| 130 | 4.218 | 2.7718 | 7.0658 | 3.7342 | 1.5265 | 19.3163
| 131 | 4.1886 | 3.0764 | 4.1551 | 3.7779 | 1.845 | 17.0431
| 132 | 4.4683 | 3.0307 | 5.4299 | 4.5683 | 1.775 | 19.2722
| 133 | 3.5503 | 2.2747 | 5.426 | 4.4224 | 1.8956 | 17.5689
| 134 | 4.6038 | 3.2494 | 6.7497 | 3.4445 | 1.2767 | 19.3241
| 135 | 4.2087 | 2.5289 | 4.8696 | 3.4911 | 1.2548 | 16.353
| 136 | 4.7311 | 2.7405 | 5.6664 | 4.5205 | 1.9444 | 19.603
| 137 | 4.3042 | 3.3231 | 6.0709 | 4.0616 | 1.5787 | 19.3386
| 138 | 3.8091 | 3.1103 | 5.2972 | 3.5105 | 1.7781 | 17.5052
| 139 | 4.5534 | 3.3241 | 5.0033 | 3.1562 | 1.5316 | 17.5686
| 140 | 4.387 | 3.1792 | 6.5861 | 3.213 | 1.3967 | 18.762
| 141 | 4.4567 | 2.6148 | 6.9705 | 4.2981 | 1.3005 | 19.6405
| 142 | 3.8617 | 2.6534 | 7.1319 | 3.9538 | 1.2341 | 18.8349
| 143 | 3.5803 | 2.8265 | 5.3229 | 3.6524 | 1.7601 | 17.1422
| 144 | 3.8958 | 2.6823 | 4.5056 | 4.7401 | 1.5189 | 17.3426
| 145 | 4.0491 | 3.4506 | 4.4558 | 3.8967 | 1.6352 | 17.4875
| 146 | 4.3317 | 2.8912 | 5.6592 | 4.859 | 1.4406 | 19.1817
| 147 | 4.1086 | 3.9248 | 4.9766 | 3.2186 | 1.6153 | 17.844
| 148 | 4.6227 | 2.3184 | 5.0665 | 3.5826 | 1.7634 | 17.3535
| 149 | 4.4923 | 2.0415 | 4.3168 | 4.5318 | 1.3834 | 16.7659
| 150 | 3.9318 | 3.5905 | 6.1861 | 4.4899 | 1.2525 | 19.4508
| 151 | 4.1747 | 2.7683 | 6.7057 | 4.4643 | 1.388 | 19.5011
| 152 | 4.0436 | 3.3004 | 5.1546 | 5.4608 | 1.5177 | 19.4771
| 153 | 4.7808 | 3.0381 | 6.8938 | 3.2918 | 1.724 | 19.7285
| 154 | 3.7776 | 3.0958 | 7.286 | 3.5719 | 1.3536 | 19.085
| 155 | 3.7639 | 2.828 | 6.9872 | 4.3217 | 1.6486 | 19.5495
| 156 | 3.9953 | 3.672 | 4.6806 | 4.4201 | 1.6363 | 18.4043
| 157 | 3.9095 | 3.0125 | 4.3899 | 4.1986 | 1.8409 | 17.3513
| 158 | 4.808 | 2.9713 | 6.4211 | 3.6598 | 1.6823 | 19.5424
| 159 | 3.7785 | 2.6024 | 6.1239 | 4.7152 | 1.6524 | 18.8724
| 160 | 4.4723 | 2.5043 | 5.4679 | 4.16 | 1.6342 | 18.2387
| 161 | 3.8023 | 2.6543 | 5.8879 | 3.3407 | 1.2036 | 16.8888
| 162 | 4.9227 | 3.1124 | 6.5206 | 4.3116 | 1.5976 | 20.4649
| 163 | 4.2832 | 3.3335 | 5.4996 | 5.3156 | 1.7049 | 20.1368
| 164 | 4.0041 | 3.4658 | 5.1273 | 4.2259 | 1.1668 | 17.9898
| 165 | 3.2175 | 3.1417 | 6.6227 | 4.6092 | 1.4291 | 19.0202
| 166 | 4.4295 | 3.4966 | 4.6112 | 5.0592 | 1.4532 | 19.0498
| 167 | 3.8853 | 2.8081 | 5.1781 | 3.2524 | 1.5312 | 16.6551
| 168 | 3.446 | 2.8216 | 6.9208 | 4.8409 | 1.1357 | 19.165
| 169 | 3.7888 | 3.1332 | 6.9941 | 4.4445 | 1.2 | 19.5605
| 170 | 4.3006 | 2.2782 | 6.791 | 4.4926 | 1.3065 | 19.1689
| 171 | 4.5183 | 2.8601 | 6.5392 | 4.4541 | 1.5675 | 19.9391
| 172 | 4.1348 | 2.8023 | 5.1006 | 4.4426 | 1.1436 | 17.6238
| 173 | 4.2549 | 3.5875 | 5.883 | 5.2656 | 1.7364 | 20.7274
| 174 | 4.6192 | 2.687 | 6.0511 | 4.5802 | 1.4724 | 19.4098
| 175 | 3.6274 | 2.7351 | 7.3961 | 3.0609 | 1.4792 | 18.2987
| 176 | 4.2353 | 3.6262 | 4.8972 | 4.028 | 1.4027 | 18.1893
| 177 | 3.7711 | 3.4646 | 5.7228 | 3.73 | 1.473 | 18.1615
| 178 | 3.8754 | 2.5446 | 6.0804 | 5.1078 | 1.0686 | 18.6768
| 179 | 3.8067 | 3.7643 | 4.8232 | 3.9482 | 1.3047 | 17.647
| 180 | 3.733 | 3.5079 | 5.9065 | 4.0352 | 1.6603 | 18.843
| 181 | 3.1443 | 3.0298 | 5.1754 | 4.573 | 1.3597 | 17.2822
| 182 | 4.1462 | 3.2405 | 5.6146 | 3.4089 | 1.5153 | 17.9255
| 183 | 3.5479 | 2.9705 | 6.2686 | 4.4042 | 1.7339 | 18.9251
| 184 | 4.9114 | 3.7831 | 5.0478 | 3.807 | 1.5904 | 19.1396
| 185 | 3.4789 | 2.8516 | 5.0225 | 3.2496 | 1.3745 | 15.9771
| 186 | 4.1619 | 3.0001 | 6.0361 | 4.1416 | 1.8578 | 19.1975
| 187 | 3.9722 | 2.6611 | 7.0876 | 4.388 | 1.7438 | 19.8527
| 188 | 4.4943 | 2.5782 | 5.7787 | 3.5189 | 1.9074 | 18.2776
| 189 | 4.251 | 2.5111 | 7.5007 | 3.5919 | 1.954 | 19.8087
| 190 | 3.3285 | 2.6632 | 4.8689 | 3.3534 | 1.5959 | 15.8099
| 191 | 3.7436 | 2.7453 | 5.3121 | 5.7125 | 1.5237 | 19.0371
| 192 | 3.49 | 3.0464 | 7.4148 | 3.3528 | 1.4421 | 18.7461
| 193 | 3.433 | 3.0946 | 6.1485 | 4.112 | 1.7128 | 18.5008
| 194 | 4.29 | 3.1372 | 5.2141 | 4.1162 | 1.5404 | 18.298
| 195 | 3.7861 | 3.1788 | 5.5526 | 3.9299 | 1.2978 | 17.7452
| 196 | 3.3922 | 3.2636 | 5.9785 | 3.5695 | 1.3191 | 17.5229
| 197 | 4.7906 | 3.1037 | 6.2156 | 3.7455 | 1.5771 | 19.4325
| 198 | 3.3564 | 3.3955 | 4.8479 | 3.9212 | 1.5365 | 17.0574
| 199 | 3.6772 | 3.203 | 5.6555 | 4.9593 | 1.1308 | 18.6258
| 200 | 3.5686 | 3.057 | 5.7959 | 3.5788 | 1.3956 | 17.3959
| 201 | 4.5219 | 2.8768 | 7.1131 | 5.0678 | 1.313 | 20.8925
| 202 | 3.8967 | 2.9111 | 5.1631 | 3.5239 | 1.5013 | 16.9961
| 203 | 4.0991 | 3.6305 | 5.563 | 3.8142 | 1.3239 | 18.4306
| 204 | 4.1246 | 3.1158 | 5.0815 | 3.782 | 1.6094 | 17.7133
| 205 | 4.0392 | 3.039 | 5.1526 | 4.1542 | 1.344 | 17.729
| 206 | 4.3703 | 2.4546 | 5.3888 | 3.8729 | 1.7318 | 17.8185
| 207 | 4.3689 | 2.7905 | 4.8929 | 4.292 | 1.1619 | 17.5061
| 208 | 4.0924 | 2.628 | 5.015 | 3.8477 | 1.5293 | 17.1125
| 209 | 3.2683 | 2.217 | 5.9904 | 3.1615 | 1.3671 | 16.0043
| 210 | 3.8149 | 2.7425 | 5.0074 | 3.9744 | 1.7446 | 17.2839
| 211 | 4.9069 | 2.9192 | 5.0549 | 4.5042 | 1.3591 | 18.7443
| 212 | 3.1566 | 2.2113 | 5.0642 | 4.5703 | 1.0932 | 16.0957
| 213 | 4.2822 | 2.7882 | 6.2574 | 4.18 | 1.6771 | 19.1849
| 214 | 4.3352 | 2.965 | 5.2513 | 4.163 | 1.2427 | 17.9572
| 215 | 3.747 | 3.5931 | 4.3238 | 4.3446 | 1.6452 | 17.6537
| 216 | 3.84 | 3.8297 | 5.3825 | 3.5982 | 1.978 | 18.6284
| 217 | 3.924 | 2.6443 | 6.3279 | 5.6926 | 1.8471 | 20.4359
| 218 | 3.948 | 2.8359 | 5.4499 | 4.6816 | 1.7501 | 18.6653
| 219 | 4.1112 | 3.1521 | 5.8269 | 4.0447 | 1.3471 | 18.482
| 220 | 3.3794 | 2.9571 | 6.6048 | 4.3568 | 1.6424 | 18.9405
| 221 | 3.2874 | 3.8162 | 7.1174 | 3.8547 | 1.7386 | 19.8144
| 222 | 3.9776 | 2.4741 | 4.3816 | 3.9466 | 1.6798 | 16.4597
| 223 | 4.739 | 2.9299 | 4.2562 | 3.5052 | 1.7839 | 17.2142
| 224 | 3.1067 | 2.9756 | 6.0858 | 3.2932 | 1.702 | 17.1633
| 225 | 3.9211 | 2.7587 | 5.174 | 3.7387 | 1.7493 | 17.3418
| 226 | 4.7195 | 3.1071 | 6.2784 | 5.3745 | 1.5546 | 21.0341
| 227 | 3.9904 | 3.5109 | 4.9955 | 3.9667 | 1.3349 | 17.7984
| 228 | 4.451 | 2.7012 | 5.1294 | 4.4146 | 1.2611 | 17.9573
| 229 | 4.3383 | 3.338 | 7.0559 | 4.9141 | 1.4752 | 21.1215
| 230 | 3.608 | 3.3056 | 4.4938 | 4.3971 | 1.5362 | 17.3406
| 231 | 4.1151 | 3.1121 | 5.3922 | 3.938 | 1.8396 | 18.397
| 232 | 3.2019 | 2.8415 | 4.2318 | 4.6419 | 1.5204 | 16.4375
| 233 | 3.9761 | 3.0401 | 4.8807 | 4.8415 | 1.6399 | 18.3782
| 234 | 4.2397 | 2.9723 | 5.5725 | 4.2946 | 1.3879 | 18.467
| 235 | 4.3832 | 3.0828 | 5.0503 | 3.5895 | 1.5488 | 17.6546
| 236 | 3.5334 | 3.1467 | 5.8117 | 3.7471 | 1.4903 | 17.7293
| 237 | 3.973 | 2.6579 | 5.2672 | 3.9892 | 1.2651 | 17.1524
| 238 | 3.438 | 2.8089 | 5.0966 | 3.4668 | 1.5824 | 16.3926
| 239 | 4.7577 | 2.7765 | 5.1031 | 3.6634 | 1.4962 | 17.7969
| 240 | 3.9671 | 2.1651 | 5.5397 | 4.7838 | 1.4041 | 17.8599
| 241 | 4.1714 | 2.7704 | 4.6533 | 4.9231 | 1.6597 | 18.178
| 242 | 4.4347 | 3.0119 | 5.9761 | 5.3863 | 1.7173 | 20.5263
| 243 | 4.1529 | 2.4689 | 5.0747 | 3.4812 | 1.5463 | 16.7241
| 244 | 3.1784 | 2.8608 | 4.542 | 4.7231 | 1.8219 | 17.1263
| 245 | 3.3039 | 2.6338 | 7.1563 | 3.8188 | 1.328 | 18.2408
| 246 | 3.9358 | 3.4462 | 7.2125 | 4.6078 | 1.8128 | 21.0151
| 247 | 3.3668 | 2.7546 | 5.9864 | 4.9806 | 1.1232 | 18.2115
| 248 | 3.9702 | 2.1094 | 6.062 | 5.9232 | 1.5027 | 19.5674
| 249 | 3.7817 | 3.7364 | 5.3565 | 3.7323 | 1.3171 | 17.924
| 250 | 4.639 | 3.8568 | 5.4277 | 3.5625 | 1.8148 | 19.3009
| 251 | 4.5069 | 3.1919 | 7.3132 | 3.7547 | 1.2107 | 19.9775
| 252 | 4.0014 | 3.072 | 4.9062 | 5.3469 | 1.3825 | 18.7091
| 253 | 3.4643 | 3.2535 | 4.1412 | 3.347 | 1.1197 | 15.3258
| 254 | 4.4009 | 2.7243 | 6.1799 | 4.3589 | 1.6761 | 19.34
| 255 | 4.6841 | 2.4967 | 7.3267 | 3.9325 | 1.8346 | 20.2746
| 256 | 4.0558 | 2.6996 | 5.4433 | 4.2086 | 1.875 | 18.2823
| 257 | 3.9655 | 2.6479 | 5.9674 | 3.7013 | 1.1469 | 17.429
| 258 | 4.5271 | 3.2827 | 4.2032 | 3.2016 | 1.4623 | 16.6769
| 259 | 3.8163 | 3.475 | 5.2159 | 5.0625 | 1.7553 | 19.325
| 260 | 3.9187 | 3.2699 | 4.5591 | 4.0606 | 1.1388 | 16.9472
| 261 | 4.1236 | 3.0345 | 5.8757 | 4.4567 | 1.3644 | 18.8548
| 262 | 3.1496 | 2.8964 | 6.0242 | 3.6192 | 1.4098 | 17.0992
| 263 | 3.6341 | 3.0592 | 6.659 | 4.6869 | 1.4512 | 19.4904
| 264 | 3.952 | 3.2964 | 5.442 | 4.2228 | 1.8303 | 18.7434
| 265 | 4.259 | 3.3016 | 5.4803 | 5.235 | 1.2775 | 19.5534
| 266 | 4.6422 | 3.0557 | 5.4311 | 4.874 | 1.2359 | 19.239
| 267 | 3.9156 | 3.063 | 5.331 | 4.1876 | 1.5356 | 18.0328
| 268 | 3.6115 | 2.9036 | 5.5261 | 5.1285 | 1.6373 | 18.8071
| 269 | 4.1774 | 2.9108 | 5.0102 | 3.1903 | 1.7288 | 17.0175
| 270 | 4.2714 | 2.3647 | 4.9703 | 5.4962 | 1.2832 | 18.3859
| 271 | 3.3599 | 2.9452 | 5.7756 | 3.8274 | 1.4199 | 17.328
| 272 | 3.2222 | 3.2085 | 6.0476 | 5.9046 | 1.6867 | 20.0696
| 273 | 3.3476 | 3.7514 | 5.5182 | 4.7263 | 1.2009 | 18.5445
| 274 | 3.7498 | 3.0545 | 6.1214 | 3.1987 | 1.4564 | 17.5809
| 275 | 4.1339 | 2.3944 | 5.6177 | 3.2896 | 1.5908 | 17.0263
| 276 | 4.3527 | 2.2651 | 4.9131 | 4.7771 | 1.5561 | 17.864
| 277 | 4.1685 | 2.9143 | 6.2602 | 3.7861 | 1.4748 | 18.6039
| 278 | 4.4135 | 2.7271 | 4.5639 | 4.2549 | 1.2488 | 17.2082
| 279 | 4.0706 | 3.8465 | 4.7664 | 4.6341 | 1.4689 | 18.7865
| 280 | 4.2379 | 3.1401 | 6.3536 | 3.744 | 1.6751 | 19.1507
| 281 | 3.6945 | 2.6431 | 4.5972 | 5.3113 | 1.5184 | 17.7646
| 282 | 3.9552 | 3.5804 | 6.3139 | 4.4014 | 1.4951 | 19.7461
| 283 | 4.6171 | 2.8433 | 5.6942 | 3.3676 | 1.5127 | 18.0349
| 284 | 3.8951 | 3.4333 | 6.0543 | 4.9289 | 1.832 | 20.1436
| 285 | 3.2956 | 3.398 | 4.8608 | 4.9873 | 1.4932 | 18.0349
| 286 | 4.1605 | 2.8321 | 5.3915 | 3.4366 | 1.4848 | 17.3055
| 287 | 3.78 | 3.1978 | 5.0805 | 4.5105 | 1.2416 | 17.8103
| 288 | 4.0351 | 3.5567 | 6.5719 | 5.5102 | 1.4007 | 21.0745
| 289 | 4.0638 | 2.4723 | 5.3072 | 4.1974 | 1.6623 | 17.7029
| 290 | 4.1522 | 3.8886 | 6.3126 | 3.9426 | 1.7061 | 20.002
| 291 | 3.6499 | 3.108 | 6.4592 | 3.5771 | 1.2901 | 18.0845
| 292 | 4.0788 | 2.9643 | 6.0185 | 3.4332 | 1.689 | 18.1837
| 293 | 4.4657 | 3.0024 | 5.2325 | 3.2602 | 1.4618 | 17.4226
| 294 | 4.3726 | 3.3118 | 5.0213 | 4.073 | 1.5326 | 18.3114
| 295 | 4.4705 | 3.0136 | 5.8774 | 4.6381 | 1.5716 | 19.5712
| 296 | 4.2663 | 2.9599 | 5.903 | 4.3181 | 1.4815 | 18.9287
| 297 | 4.463 | 2.4328 | 6.1994 | 3.6662 | 1.3866 | 18.1479
| 298 | 3.9057 | 2.8376 | 4.7959 | 4.0916 | 1.5183 | 17.1491
| 299 | 4.009 | 2.8252 | 6.6547 | 3.7752 | 1.2373 | 18.5014
| 300 | 4.405 | 3.1548 | 5.3536 | 3.6133 | 1.7149 | 18.2416
| 301 | 3.8768 | 3.3624 | 4.546 | 4.0574 | 1.8434 | 17.6861
| 302 | 3.9687 | 3.0544 | 6.8498 | 4.0994 | 1.3416 | 19.3139
| 303 | 3.2918 | 3.0855 | 5.9153 | 3.7524 | 1.771 | 17.816
| 304 | 3.5227 | 2.718 | 4.8412 | 3.3488 | 1.6718 | 16.1025
| 305 | 4.027 | 3.719 | 7.2667 | 3.9804 | 1.2125 | 20.2055
| 306 | 3.6375 | 2.1464 | 5.1095 | 4.6154 | 1.6412 | 17.15
| 307 | 4.2277 | 3.0432 | 5.3397 | 3.6427 | 1.0219 | 17.2752
| 308 | 3.6513 | 3.1062 | 5.2393 | 3.6486 | 1.444 | 17.0893
| 309 | 3.7531 | 2.5946 | 5.7143 | 3.4387 | 1.3495 | 16.8504
| 310 | 3.9328 | 2.8395 | 4.9038 | 3.4195 | 1.2828 | 16.3784
| 311 | 4.1578 | 2.6724 | 5.9189 | 3.5287 | 1.4842 | 17.7621
| 312 | 3.9545 | 2.8522 | 7.2432 | 3.1861 | 1.3205 | 18.5564
| 313 | 4.6943 | 2.5976 | 4.7136 | 4.0263 | 1.9605 | 17.9924
| 314 | 3.5577 | 2.2412 | 5.3797 | 4.3822 | 1.6149 | 17.1757
| 315 | 3.8326 | 3.0874 | 6.3832 | 3.5305 | 1.7199 | 18.5536
| 316 | 3.4447 | 3.4076 | 4.6483 | 3.4254 | 1.4079 | 16.3338
| 317 | 3.3659 | 3.0159 | 4.4057 | 5.0831 | 1.3726 | 17.2432
| 318 | 4.0255 | 2.3727 | 5.1509 | 3.8634 | 1.3027 | 16.7152
| 319 | 4.3917 | 2.7733 | 5.5382 | 3.5739 | 1.5297 | 17.8068
| 320 | 3.5853 | 3.7088 | 6.0158 | 5.5258 | 1.5052 | 20.3409
| 321 | 4.0419 | 3.0802 | 5.3055 | 4.9284 | 1.3181 | 18.6739
| 322 | 4.3068 | 2.2459 | 4.762 | 4.6284 | 1.4194 | 17.3624
| 323 | 3.6841 | 3.0685 | 7.8181 | 4.2568 | 1.5167 | 20.3441
| 324 | 4.7659 | 2.513 | 5.5761 | 4.536 | 1.3868 | 18.7779
| 325 | 4.8773 | 2.5032 | 4.3686 | 3.4563 | 1.5503 | 16.7558
| 326 | 4.2245 | 2.6106 | 6.7399 | 3.4573 | 1.5946 | 18.6268
| 327 | 4.6508 | 2.9406 | 5.5788 | 4.252 | 1.5223 | 18.9444
| 328 | 4.0889 | 2.8856 | 6.1627 | 3.645 | 1.4176 | 18.1998
| 329 | 4.4313 | 3.3208 | 4.8576 | 3.8753 | 1.7915 | 18.2765
| 330 | 4.6507 | 2.8734 | 4.6412 | 4.2644 | 1.5494 | 17.9792
| 331 | 4.1739 | 3.1234 | 4.9852 | 4.9027 | 1.3656 | 18.5507
| 332 | 3.9917 | 2.6911 | 5.2417 | 3.8872 | 1.6734 | 17.485
| 333 | 4.7081 | 3.5441 | 6.37 | 3.841 | 1.6722 | 20.1355
| 334 | 4.5439 | 3.097 | 6.96 | 3.618 | 1.4428 | 19.6617
| 335 | 4.4191 | 3.0247 | 7.7149 | 5.1777 | 1.4319 | 21.7682
| 336 | 3.6563 | 3.0731 | 5.5158 | 5.4301 | 1.3161 | 18.9914
| 337 | 4.0577 | 3.5384 | 5.4646 | 3.5439 | 1.7217 | 18.3263
| 338 | 3.7601 | 3.5086 | 7.0084 | 4.0181 | 1.3803 | 19.6756
| 339 | 4.8579 | 3.9502 | 6.1366 | 3.924 | 1.6014 | 20.4701
| 340 | 3.9347 | 2.3298 | 4.4177 | 4.3043 | 1.23 | 16.2165
| 341 | 4.424 | 2.3367 | 5.9551 | 3.6714 | 1.2164 | 17.6036
| 342 | 3.9315 | 3.6156 | 5.1468 | 4.3685 | 1.2235 | 18.286
| 343 | 3.7203 | 3.2155 | 4.1707 | 4.1758 | 1.6627 | 16.9449
| 344 | 3.4047 | 3.1734 | 5.5607 | 3.7649 | 1.8881 | 17.7919
| 345 | 4.437 | 2.8287 | 4.7933 | 4.2484 | 1.1581 | 17.4654
| 346 | 3.3878 | 2.6238 | 4.7884 | 5.2127 | 1.1257 | 17.1384
| 347 | 3.4185 | 2.4 | 5.3338 | 3.3357 | 1.3975 | 15.8855
| 348 | 3.8942 | 2.8127 | 6.4128 | 4.9673 | 1.3154 | 19.4023
| 349 | 4.3939 | 2.7299 | 6.4928 | 4.6728 | 1.5611 | 19.8504
| 350 | 4.2725 | 3.7261 | 4.4886 | 3.2563 | 1.7828 | 17.5262
| 351 | 3.3188 | 3.2352 | 6.6258 | 3.5396 | 1.5335 | 18.2529
| 352 | 4.2238 | 3.5826 | 4.8325 | 4.1934 | 1.6437 | 18.476
| 353 | 4.8231 | 3.7475 | 4.8627 | 4.0702 | 1.4498 | 18.9532
| 354 | 3.5933 | 2.2621 | 6.2927 | 4.803 | 1.6935 | 18.6446
| 355 | 4.2802 | 3.1655 | 5.062 | 4.3187 | 1.4866 | 18.3128
| 356 | 4.0573 | 2.6455 | 7.184 | 4.048 | 1.5018 | 19.4366
| 357 | 4.1005 | 3.0837 | 7.2768 | 3.4868 | 1.7541 | 19.702
| 358 | 4.4182 | 2.4365 | 6.6158 | 3.6622 | 1.3766 | 18.5094
| 359 | 3.3711 | 3.8082 | 5.6208 | 4.5567 | 1.7248 | 19.0816
| 360 | 4.0132 | 2.8027 | 6.4757 | 4.9925 | 1.9654 | 20.2495
| 361 | 4.0288 | 3.1387 | 4.5114 | 4.0436 | 1.5702 | 17.2927
| 362 | 4.8044 | 3.0319 | 6.9092 | 3.9828 | 1.2696 | 19.9978
| 363 | 4.3164 | 2.7382 | 7.0471 | 4.8233 | 1.2584 | 20.1834
| 364 | 3.9865 | 3.3414 | 6.6713 | 3.5161 | 1.9 | 19.4154
| 365 | 3.7878 | 3.6647 | 4.3908 | 4.6959 | 1.6283 | 18.1675
| 366 | 3.9471 | 3.3848 | 5.9613 | 3.7612 | 1.5159 | 18.5703
| 367 | 4.1508 | 3.1933 | 6.6012 | 3.1784 | 1.5461 | 18.6697
| 368 | 4.3612 | 2.7338 | 7.579 | 3.2351 | 1.5578 | 19.467
| 369 | 3.6807 | 2.9603 | 7.265 | 3.4506 | 1.8489 | 19.2056
| 370 | 3.6813 | 2.5702 | 6.4477 | 4.1659 | 1.1561 | 18.0212
| 371 | 3.8222 | 3.4446 | 6.4053 | 3.3642 | 1.7729 | 18.8091
| 372 | 3.439 | 3.6561 | 5.8442 | 3.6786 | 1.618 | 18.2359
| 373 | 4.1798 | 2.9988 | 6.4177 | 5.6421 | 1.5973 | 20.8356
| 374 | 4.1954 | 3.716 | 5.3297 | 4.5515 | 1.4302 | 19.2228
| 375 | 4.584 | 2.3493 | 5.0882 | 3.9788 | 1.5389 | 17.5392
| 376 | 3.4529 | 3.501 | 6.3602 | 4.7026 | 1.486 | 19.5027
| 377 | 3.9299 | 2.9318 | 5.471 | 5.0109 | 1.6508 | 18.9944
| 378 | 4.5103 | 3.0821 | 5.0861 | 5.6868 | 1.5846 | 19.95
| 379 | 4.5315 | 2.3122 | 4.7479 | 3.7839 | 1.5868 | 16.9623
| 380 | 4.4882 | 3.6926 | 5.5009 | 4.3719 | 1.5829 | 19.6365
| 381 | 4.5807 | 3.6012 | 6.1115 | 4.5136 | 1.6269 | 20.4341
| 382 | 3.9888 | 3.1992 | 5.974 | 5.0361 | 1.0804 | 19.2783
| 383 | 4.3765 | 3.2834 | 6.033 | 5.0033 | 1.5285 | 20.2248
| 384 | 3.6334 | 2.5199 | 5.5561 | 3.7203 | 1.5036 | 16.9332
| 385 | 4.4967 | 2.9398 | 6.2411 | 4.3757 | 1.5625 | 19.6158
| 386 | 4.3243 | 3.2412 | 6.0723 | 4.1619 | 1.4248 | 19.2246
| 387 | 3.6689 | 3.6038 | 6.1056 | 4.4739 | 1.4275 | 19.2797
| 388 | 3.575 | 3.4385 | 5.7902 | 5.598 | 1.5498 | 19.9515
| 389 | 4.2444 | 3.0164 | 6.3383 | 3.9575 | 1.6913 | 19.2479
| 390 | 3.8902 | 2.5879 | 4.4736 | 5.54 | 1.4217 | 17.9133
| 391 | 4.2023 | 3.0789 | 6.8604 | 5.3329 | 1.6255 | 21.1
| 392 | 4.7445 | 2.9423 | 6.2921 | 3.8521 | 1.6816 | 19.5125
| 393 | 3.9715 | 3.1585 | 6.7154 | 5.772 | 1.6196 | 21.2371
| 394 | 4.773 | 2.8046 | 4.7201 | 4.601 | 1.5655 | 18.4642
| 395 | 4.4595 | 3.4781 | 4.77 | 4.7622 | 1.5101 | 18.9798
| 396 | 4.0026 | 3.0937 | 5.0045 | 3.5127 | 1.5882 | 17.2017
| 397 | 3.8559 | 2.8848 | 5.1834 | 3.5276 | 1.2173 | 16.669
| 398 | 4.4062 | 3.0675 | 5.9369 | 5.5841 | 1.6574 | 20.6521
| 399 | 3.9941 | 2.9055 | 6.0962 | 3.7806 | 1.6708 | 18.4472
| 400 | 3.5695 | 3.1568 | 5.2303 | 3.4772 | 1.5924 | 17.0263
| 401 | 4.8675 | 3.682 | 5.8198 | 4.068 | 1.6555 | 20.0929
| 402 | 4.6457 | 3.6576 | 4.845 | 3.7356 | 1.1026 | 17.9866
| 403 | 3.7758 | 2.4173 | 5.0764 | 4.6062 | 1.5304 | 17.4062
| 404 | 4.5465 | 3.256 | 7.0198 | 3.3227 | 1.0276 | 19.1725
| 405 | 4.0005 | 3.1095 | 4.9743 | 4.9073 | 1.813 | 18.8045
| 406 | 4.3579 | 3.0475 | 6.984 | 5.6669 | 1.412 | 21.4683
| 407 | 4.6308 | 3.8376 | 4.7545 | 3.4049 | 1.1586 | 17.7864
| 408 | 4.6408 | 3.4321 | 5.2711 | 4.1144 | 1.4882 | 18.9466
| 409 | 3.1815 | 3.5636 | 7.4444 | 5.3667 | 1.3788 | 20.935
| 410 | 3.748 | 3.1974 | 5.931 | 3.7634 | 1.568 | 18.2077
| 411 | 3.7988 | 2.5833 | 6.0769 | 4.985 | 1.4804 | 18.9244
| 412 | 3.8332 | 2.6416 | 6.8419 | 4.3667 | 1.9032 | 19.5866
| 413 | 3.8105 | 2.7046 | 6.0895 | 3.7939 | 1.5479 | 17.9464
| 414 | 4.1409 | 3.0889 | 4.6238 | 3.0993 | 1.2323 | 16.1852
| 415 | 3.1651 | 2.8799 | 5.3267 | 4.7675 | 1.122 | 17.2614
| 416 | 3.8698 | 2.8747 | 4.9601 | 3.3083 | 1.4821 | 16.495
| 417 | 4.3462 | 2.5371 | 4.8962 | 3.3814 | 1.2285 | 16.3895
| 418 | 4.6674 | 2.9544 | 5.8609 | 3.9863 | 1.2038 | 18.6727
| 419 | 4.0503 | 2.6713 | 6.3465 | 4.5275 | 1.1484 | 18.744
| 420 | 4.6111 | 2.5569 | 5.2039 | 4.39 | 1.4144 | 18.1763
| 421 | 3.8033 | 2.4912 | 5.5358 | 3.6077 | 1.4992 | 16.9372
| 422 | 4.1899 | 3.1202 | 5.2896 | 4.2328 | 1.2464 | 18.0789
| 423 | 3.1183 | 3.2679 | 4.4784 | 4.0836 | 1.6385 | 16.5868
| 424 | 4.4154 | 2.7574 | 5.352 | 3.3326 | 1.8293 | 17.6868
| 425 | 3.8506 | 2.8178 | 6.8688 | 3.5173 | 1.512 | 18.5665
| 426 | 4.2601 | 3.2915 | 6.5712 | 4.7357 | 1.1855 | 20.044
| 427 | 4.5045 | 2.8979 | 5.014 | 4.1345 | 1.5413 | 18.0922
| 428 | 3.8798 | 2.8976 | 5.1907 | 3.4132 | 1.5045 | 16.8857
| 429 | 3.818 | 3.2226 | 4.6877 | 4.4909 | 1.6534 | 17.8725
| 430 | 4.3345 | 3.2787 | 4.2225 | 5.3435 | 1.4485 | 18.6276
| 431 | 4.036 | 2.9098 | 5.8581 | 5.4365 | 1.2097 | 19.4501
| 432 | 3.8873 | 3.4825 | 5.1584 | 4.535 | 1.1773 | 18.2405
| 433 | 4.2288 | 3.4599 | 4.2718 | 4.5658 | 1.9174 | 18.4437
| 434 | 4.3327 | 3.5126 | 4.5257 | 5.0874 | 1.9147 | 19.373
| 435 | 4.2623 | 2.9944 | 5.7081 | 3.6225 | 1.4741 | 18.0613
| 436 | 3.6739 | 3.0658 | 6.6749 | 5.064 | 1.7334 | 20.2121
| 437 | 3.4119 | 2.6196 | 4.7783 | 3.3842 | 1.4536 | 15.6476
| 438 | 4.3652 | 3.3397 | 5.2941 | 3.2769 | 1.4947 | 17.7706
| 439 | 4.1558 | 3.1626 | 4.3391 | 4.4289 | 1.8182 | 17.9047
| 440 | 3.9254 | 3.2599 | 6.0208 | 5.7567 | 1.1779 | 20.1406
| 441 | 4.7592 | 3.7952 | 5.8637 | 4.0651 | 1.5744 | 20.0576
| 442 | 3.873 | 2.4529 | 5.4111 | 4.8783 | 1.2575 | 17.8727
| 443 | 3.6767 | 2.707 | 4.965 | 3.5076 | 1.7298 | 16.586
| 444 | 3.9407 | 3.5475 | 6.2061 | 3.907 | 1.5147 | 19.116
| 445 | 3.7367 | 2.7018 | 4.802 | 4.5781 | 1.5259 | 17.3444
| 446 | 3.9582 | 3.2642 | 5.8561 | 4.2616 | 1.7977 | 19.1377
| 447 | 3.9618 | 3.3036 | 5.6524 | 3.9106 | 1.8241 | 18.6525
| 448 | 3.6861 | 2.928 | 4.5548 | 3.8305 | 1.4131 | 16.4125
| 449 | 3.4251 | 2.5627 | 4.9964 | 5.0242 | 1.6144 | 17.6228
| 450 | 3.9129 | 3.1021 | 4.437 | 4.2799 | 1.559 | 17.2908
| 451 | 3.699 | 3.0616 | 6.3069 | 4.4525 | 1.5614 | 19.0814
| 452 | 4.487 | 2.7736 | 4.608 | 4.1236 | 1.7817 | 17.7738
| 453 | 3.6171 | 3.491 | 5.5257 | 5.3766 | 1.3906 | 19.4009
| 454 | 3.7517 | 3.5338 | 4.9448 | 5.0727 | 1.7794 | 19.0825
| 455 | 4.3959 | 2.226 | 4.7404 | 4.4692 | 1.259 | 17.0904
| 456 | 4.0494 | 3.0229 | 5.7611 | 5.219 | 1.5074 | 19.5598
| 457 | 4.1062 | 3.098 | 4.9718 | 5.2578 | 1.4692 | 18.9031
| 458 | 3.2559 | 3.38 | 5.6843 | 3.8531 | 1.5025 | 17.6758
| 459 | 3.7066 | 2.4279 | 4.6309 | 4.2031 | 1.7615 | 16.7299
| 460 | 4.3722 | 3.3078 | 5.3654 | 3.1817 | 1.5269 | 17.7539
| 461 | 4.5587 | 2.2585 | 4.9217 | 4.4493 | 1.4016 | 17.5898
| 462 | 3.9369 | 2.9219 | 5.5138 | 4.6618 | 1.317 | 18.3513
| 463 | 3.8427 | 2.9768 | 4.2504 | 4.9625 | 1.5122 | 17.5447
| 464 | 3.3407 | 2.5801 | 5.7527 | 4.8364 | 1.5643 | 18.0743
| 465 | 4.7246 | 2.8631 | 5.6383 | 4.6847 | 1.3319 | 19.2427
| 466 | 4.1012 | 3.0057 | 6.8405 | 3.2859 | 1.4073 | 18.6406
| 467 | 3.4668 | 2.1354 | 5.8035 | 4.005 | 1.4935 | 16.9042
| 468 | 4.4535 | 2.4836 | 5.2875 | 5.1521 | 1.6964 | 19.0732
| 469 | 4.201 | 2.2911 | 6.3502 | 4.4766 | 1.3009 | 18.6198
| 470 | 3.7044 | 2.5683 | 4.9402 | 4.2202 | 1.6588 | 17.092
| 471 | 4.0921 | 3.1561 | 7.7634 | 3.7738 | 1.4781 | 20.2635
| 472 | 4.3415 | 2.4259 | 5.2998 | 3.3895 | 1.2933 | 16.7501
| 473 | 3.1977 | 2.9527 | 5.5223 | 4.1869 | 1.6378 | 17.4974
| 474 | 4.4261 | 3.0367 | 6.217 | 5.0933 | 1.3523 | 20.1254
| 475 | 4.2971 | 2.1957 | 5.1233 | 3.6862 | 1.345 | 16.6474
| 476 | 4.5616 | 3.1433 | 5.3165 | 3.896 | 1.0648 | 17.9822
| 477 | 3.9635 | 3.3526 | 6.6092 | 4.9756 | 1.4349 | 20.3359
| 478 | 3.5378 | 2.4059 | 4.1143 | 5.4532 | 1.4396 | 16.9508
| 479 | 3.472 | 2.9919 | 4.9525 | 3.5253 | 1.5785 | 16.5203
| 480 | 3.5652 | 2.8899 | 5.5985 | 3.5684 | 1.489 | 17.111
| 481 | 4.0402 | 2.6955 | 4.9621 | 5.2106 | 1.4346 | 18.3429
| 482 | 3.6843 | 2.7528 | 4.8139 | 3.4872 | 1.173 | 15.9112
| 483 | 4.2419 | 2.7258 | 6.6345 | 3.9548 | 1.361 | 18.9179
| 484 | 4.7874 | 3.5365 | 7.8827 | 3.4072 | 1.3603 | 20.9742
| 485 | 3.9653 | 2.7097 | 6.7528 | 4.1026 | 1.3479 | 18.8782
| 486 | 4.184 | 3.4813 | 5.5536 | 3.7415 | 1.8709 | 18.8313
| 487 | 4.68 | 3.4285 | 5.116 | 3.5634 | 1.735 | 18.5229
| 488 | 4.0983 | 3.1703 | 4.9289 | 3.7873 | 1.6563 | 17.6412
| 489 | 4.2426 | 2.5239 | 5.664 | 3.2476 | 1.6649 | 17.343
| 490 | 4.2297 | 3.044 | 5.7254 | 4.6701 | 1.0988 | 18.7679
| 491 | 4.1718 | 3.3307 | 6.8786 | 3.7105 | 1.5424 | 19.6341
| 492 | 3.5322 | 3.2051 | 7.4371 | 4.2167 | 1.6068 | 19.9979
| 493 | 4.2159 | 2.7136 | 6.3649 | 4.9568 | 1.1502 | 19.4013
| 494 | 3.2822 | 3.6678 | 6.2984 | 4.2413 | 1.636 | 19.1256
| 495 | 3.7552 | 3.1325 | 5.2363 | 4.7986 | 1.34 | 18.2627
| 496 | 3.1362 | 3.4404 | 7.5112 | 4.9186 | 1.7011 | 20.7076
| 497 | 3.0982 | 3.1188 | 6.1658 | 4.1308 | 1.4598 | 17.9734
| 498 | 4.8316 | 3.575 | 5.6793 | 4.0381 | 1.4696 | 19.5937
| 499 | 4.1949 | 2.381 | 4.9367 | 4.0809 | 1.5065 | 17.1
| 500 | 4.0855 | 2.9733 | 5.2826 | 3.5355 | 1.4136 | 17.2905
| 501 | 3.4822 | 3.3689 | 5.2103 | 4.5945 | 1.6178 | 18.2736
| 502 | 4.3372 | 3.4864 | 5.3204 | 3.5145 | 1.3256 | 17.9841
| 503 | 4.2228 | 2.8118 | 6.7016 | 3.7143 | 1.2859 | 18.7363
| 504 | 4.0662 | 2.9954 | 5.4156 | 3.5597 | 1.5247 | 17.5616
| 505 | 3.776 | 2.7852 | 5.3685 | 3.3434 | 1.4823 | 16.7553
| 506 | 4.1977 | 3.0044 | 4.953 | 4.3638 | 1.4655 | 17.9844
| 507 | 4.159 | 3.219 | 5.4962 | 3.8566 | 1.6786 | 18.4094
| 508 | 3.7702 | 2.6375 | 5.604 | 3.9696 | 1.3987 | 17.3799
| 509 | 3.8634 | 3.1298 | 5.7276 | 3.6898 | 1.3136 | 17.7242
| 510 | 4.074 | 3.0498 | 6.7244 | 4.5294 | 1.3814 | 19.7589
| 511 | 3.6665 | 2.6056 | 5.4129 | 3.6548 | 1.1539 | 16.4937
| 512 | 3.5561 | 2.9314 | 7.2548 | 3.6945 | 1.4237 | 18.8606
| 513 | 3.7926 | 2.1249 | 5.4089 | 3.779 | 1.5562 | 16.6616
| 514 | 4.2059 | 2.9061 | 5.3949 | 4.4402 | 1.6337 | 18.5808
| 515 | 4.3054 | 3.3907 | 4.6004 | 4.9967 | 1.0339 | 18.3271
| 516 | 3.5984 | 3.6886 | 5.308 | 3.8393 | 1.8166 | 18.251
| 517 | 4.3114 | 2.5422 | 6.6113 | 3.6497 | 1.7407 | 18.8554
| 518 | 3.6881 | 3.2299 | 5.4589 | 4.1521 | 1.1742 | 17.7033
| 519 | 3.9859 | 3.3086 | 7.1964 | 4.1064 | 1.5206 | 20.118
| 520 | 4.4385 | 3.0519 | 4.9506 | 3.4415 | 1.6514 | 17.534
| 521 | 3.7277 | 3.4488 | 5.4706 | 5.5212 | 1.17 | 19.3383
| 522 | 3.6286 | 2.3665 | 4.8524 | 4.1287 | 1.4629 | 16.4391
| 523 | 4.4068 | 2.6201 | 7.4006 | 4.2592 | 1.2876 | 19.9742
| 524 | 3.8589 | 2.3695 | 6.3739 | 4.1373 | 1.4165 | 18.1562
| 525 | 3.7179 | 2.4418 | 6.3046 | 3.689 | 1.434 | 17.5873
| 526 | 3.739 | 2.9129 | 6.2247 | 5.0465 | 1.6331 | 19.5561
| 527 | 3.8576 | 3.1949 | 6.6806 | 3.8243 | 1.4475 | 19.0048
| 528 | 4.119 | 3.0261 | 6.7202 | 5.3209 | 1.695 | 20.8813
| 529 | 4.0617 | 3.1669 | 7.6537 | 5.1012 | 1.7707 | 21.7541
| 530 | 3.0744 | 2.7161 | 5.0976 | 5.1664 | 1.3942 | 17.4487
| 531 | 3.8997 | 3.4048 | 6.0119 | 5.2738 | 1.5137 | 20.1039
| 532 | 3.7578 | 3.7126 | 5.2066 | 4.4098 | 1.2798 | 18.3664
| 533 | 4.3125 | 2.2302 | 5.0193 | 5.2812 | 1.7265 | 18.5696
| 534 | 3.7661 | 3.153 | 5.4349 | 3.5603 | 1.5885 | 17.5026
| 535 | 4.0795 | 3.6614 | 6.1532 | 3.4157 | 1.1526 | 18.4624
| 536 | 4.6065 | 3.2015 | 5.1723 | 4.6546 | 1.7426 | 19.3775
| 537 | 3.5823 | 2.4219 | 5.8511 | 3.5728 | 1.6706 | 17.0987
| 538 | 3.949 | 2.5268 | 7.032 | 4.7554 | 1.9091 | 20.1722
| 539 | 3.902 | 3.3341 | 6.4276 | 5.0319 | 1.642 | 20.3376
| 540 | 4.6774 | 3.1169 | 5.1809 | 3.2998 | 1.2707 | 17.5457
| 541 | 3.8864 | 3.2738 | 7.6189 | 4.0212 | 1.3214 | 20.1218
| 542 | 3.3504 | 3.0662 | 6.4418 | 3.5988 | 1.275 | 17.7322
| 543 | 3.735 | 3.6225 | 5.6765 | 4.5175 | 1.2183 | 18.7698
| 544 | 3.66 | 2.6389 | 7.1295 | 4.6002 | 1.3072 | 19.3359
| 545 | 4.1368 | 3.3441 | 4.784 | 4.7968 | 1.8109 | 18.8726
| 546 | 4.1442 | 3.5144 | 4.4323 | 4.2297 | 1.6038 | 17.9244
| 547 | 4.9498 | 2.8834 | 4.6474 | 5.0076 | 1.4552 | 18.9434
| 548 | 3.8981 | 3.361 | 4.9353 | 4.2054 | 1.5795 | 17.9793
| 549 | 3.2772 | 2.693 | 5.8205 | 3.501 | 1.5532 | 16.8449
| 550 | 4.068 | 3.2098 | 6.452 | 4.2753 | 1.5667 | 19.5717
| 551 | 4.5305 | 2.6012 | 4.5698 | 3.8594 | 1.2435 | 16.8044
| 552 | 4.5709 | 2.4853 | 4.7064 | 3.6044 | 1.3487 | 16.7157
| 553 | 4.018 | 3.4058 | 6.4569 | 3.845 | 1.7773 | 19.5029
| 554 | 3.8345 | 3.5961 | 5.1999 | 4.6991 | 1.535 | 18.8646
| 555 | 4.5976 | 3.4789 | 5.4939 | 4.1101 | 1.7989 | 19.4794
| 556 | 3.9969 | 3.2939 | 4.6186 | 5.1232 | 1.5917 | 18.6243
| 557 | 4.0117 | 3.1826 | 7.2272 | 4.4387 | 1.5541 | 20.4143
| 558 | 4.0537 | 2.6125 | 4.7388 | 4.8477 | 1.8606 | 18.1134
| 559 | 3.501 | 2.6483 | 7.5444 | 4.8555 | 1.2816 | 19.8308
| 560 | 3.8898 | 3.5586 | 7.0786 | 3.4002 | 1.1945 | 19.1217
| 561 | 4.2312 | 3.0459 | 4.2883 | 3.3617 | 1.3702 | 16.2972
| 562 | 4.0641 | 3.1447 | 4.8819 | 3.5204 | 1.3853 | 16.9963
| 563 | 4.6544 | 2.4636 | 6.1903 | 4.5967 | 1.2922 | 19.1972
| 564 | 4.3207 | 3.2456 | 4.6863 | 3.7723 | 1.3896 | 17.4145
| 565 | 3.9934 | 3.1873 | 6.5384 | 3.317 | 1.2334 | 18.2696
| 566 | 4.1224 | 3.0806 | 5.158 | 4.0024 | 1.4976 | 17.8611
| 567 | 4.3664 | 2.4929 | 4.7675 | 5.2243 | 1.5941 | 18.4452
| 568 | 4.4761 | 3.217 | 4.787 | 5.5438 | 1.5987 | 19.6227
| 569 | 4.4023 | 3.4924 | 5.037 | 3.7591 | 1.3781 | 18.0689
| 570 | 3.1923 | 3.3199 | 6.3405 | 3.1028 | 1.5719 | 17.5274
| 571 | 3.9677 | 2.396 | 7.1756 | 5.5676 | 1.1811 | 20.288
| 572 | 4.1636 | 3.2445 | 6.7634 | 3.8011 | 1.7869 | 19.7595
| 573 | 4.3257 | 3.5038 | 5.1873 | 4.8887 | 1.7932 | 19.6987
| 574 | 3.5281 | 2.6155 | 4.671 | 5.8712 | 1.59 | 18.2758
| 575 | 3.7689 | 3.3398 | 5.2787 | 5.4206 | 1.2865 | 19.0945
| 576 | 4.2483 | 3.647 | 5.265 | 3.9435 | 1.3378 | 18.4416
| 577 | 3.7726 | 3.3721 | 6.2021 | 3.6029 | 1.5747 | 18.5244
| 578 | 4.2638 | 3.4378 | 5.1129 | 4.746 | 1.2852 | 18.8457
| 579 | 3.9624 | 3.6142 | 5.5846 | 3.6102 | 1.5088 | 18.2802
| 580 | 3.3857 | 3.4237 | 5.1433 | 3.8057 | 1.6192 | 17.3776
| 581 | 3.6157 | 3.4527 | 5.8486 | 3.8101 | 1.9222 | 18.6494
| 582 | 3.4734 | 3.0482 | 4.4714 | 3.9038 | 1.4222 | 16.3191
| 583 | 3.7103 | 3.0415 | 6.8015 | 3.7664 | 1.3106 | 18.6303
| 584 | 3.4275 | 2.4045 | 7.3825 | 4.0336 | 1.2766 | 18.5247
| 585 | 3.797 | 2.5484 | 5.1383 | 3.9651 | 1.0604 | 16.5092
| 586 | 3.8193 | 3.0174 | 5.5455 | 3.87 | 1.6799 | 17.9321
| 587 | 4.4613 | 2.7982 | 5.0707 | 4.482 | 1.7169 | 18.5292
| 588 | 3.6183 | 3.6487 | 4.8186 | 3.8684 | 1.7451 | 17.6991
| 589 | 3.6408 | 3.3445 | 5.4019 | 4.3005 | 1.1111 | 17.7987
| 590 | 3.4987 | 3.262 | 4.7156 | 3.8918 | 1.491 | 16.8591
| 591 | 3.5469 | 3.3877 | 7.3031 | 3.5663 | 1.6035 | 19.4076
| 592 | 4.2206 | 2.6353 | 5.1211 | 3.792 | 1.3051 | 17.0741
| 593 | 3.4949 | 2.5143 | 6.5083 | 3.0701 | 1.3622 | 16.9499
| 594 | 4.055 | 2.6747 | 4.4034 | 3.6909 | 1.711 | 16.535
| 595 | 3.3332 | 3.7618 | 5.6557 | 3.9193 | 1.1127 | 17.7827
| 596 | 4.1259 | 2.6656 | 4.5824 | 5.249 | 1.3409 | 17.9638
| 597 | 3.7958 | 2.0854 | 5.4036 | 3.6424 | 1.6407 | 16.568
| 598 | 4.0453 | 2.8543 | 6.1161 | 3.1263 | 1.2303 | 17.3722
| 599 | 4.0595 | 2.6372 | 6.1732 | 5.0485 | 1.654 | 19.5723
| 600 | 3.871 | 2.1288 | 7.0707 | 3.611 | 1.7188 | 18.4003
| 601 | 4.5749 | 3.0104 | 5.17 | 4.555 | 1.1267 | 18.437
| 602 | 3.1857 | 2.7772 | 5.9831 | 4.939 | 1.4579 | 18.343
| 603 | 4.6342 | 2.8646 | 4.6819 | 5.4786 | 1.8854 | 19.5447
| 604 | 3.4768 | 2.5541 | 5.9694 | 4.863 | 1.854 | 18.7172
| 605 | 3.9826 | 2.7038 | 6.9419 | 3.6575 | 1.5421 | 18.8279
| 606 | 4.1278 | 2.3013 | 5.338 | 3.6671 | 1.3563 | 16.7904
| 607 | 3.836 | 2.6706 | 5.4521 | 3.4931 | 1.0772 | 16.529
| 608 | 4.4112 | 2.6321 | 5.6228 | 3.0911 | 1.3146 | 17.0718
| 609 | 4.2266 | 3.058 | 5.9446 | 3.7314 | 1.758 | 18.7187
| 610 | 3.8921 | 2.4225 | 5.3028 | 3.8798 | 1.8504 | 17.3476
| 611 | 4.1039 | 3.5432 | 4.5242 | 5.3611 | 1.3933 | 18.9258
| 612 | 4.4547 | 3.0506 | 5.7487 | 3.4113 | 1.8337 | 18.499
| 613 | 4.4403 | 3.813 | 7.6223 | 3.646 | 1.3736 | 20.8952
| 614 | 3.4923 | 2.4118 | 5.8654 | 4.7058 | 1.1754 | 17.6507
| 615 | 4.0737 | 2.8339 | 5.0408 | 3.449 | 1.3247 | 16.722
| 616 | 3.937 | 3.1898 | 4.4569 | 3.2367 | 1.6273 | 16.4477
| 617 | 3.91 | 2.8005 | 5.9967 | 4.2851 | 1.4328 | 18.4251
| 618 | 3.725 | 2.3775 | 5.1079 | 4.236 | 1.8022 | 17.2486
| 619 | 3.8214 | 2.9961 | 5.4236 | 3.4698 | 1.5965 | 17.3075
| 620 | 3.7646 | 3.9183 | 5.7697 | 4.8829 | 1.4149 | 19.7506
| 621 | 3.8814 | 3.6993 | 4.6437 | 4.8109 | 1.3635 | 18.3989
| 622 | 4.1422 | 2.3524 | 4.6985 | 5.1493 | 1.5662 | 17.9086
| 623 | 4.0442 | 2.6299 | 4.6278 | 4.0106 | 1.3511 | 16.6636
| 624 | 3.953 | 3.229 | 4.5077 | 3.8207 | 1.182 | 16.6925
| 625 | 4.1539 | 3.6527 | 5.9392 | 5.4188 | 1.6101 | 20.7746
| 626 | 3.6096 | 3.2326 | 4.7018 | 3.3203 | 1.7655 | 16.6298
| 627 | 4.0761 | 2.3228 | 5.6159 | 3.9013 | 1.6075 | 17.5237
| 628 | 4.5157 | 2.9809 | 4.6635 | 4.0163 | 1.5066 | 17.683
| 629 | 4.048 | 2.7115 | 4.9877 | 4.619 | 1.2668 | 17.6329
| 630 | 4.3584 | 3.9024 | 5.8295 | 5.2787 | 1.2211 | 20.5901
| 631 | 4.0936 | 3.1263 | 5.3742 | 3.8624 | 1.4944 | 17.951
| 632 | 4.0693 | 2.2566 | 7.1072 | 3.75 | 1.0714 | 18.2545
| 633 | 4.276 | 2.7282 | 7.2352 | 3.8854 | 1.5375 | 19.6624
| 634 | 3.2301 | 3.2106 | 6.4042 | 4.6694 | 1.4548 | 18.9691
| 635 | 4.2734 | 2.9927 | 5.936 | 3.4694 | 1.046 | 17.7175
| 636 | 4.1859 | 3.0062 | 4.5322 | 4.1914 | 1.1897 | 17.1054
| 637 | 3.8467 | 2.1906 | 5.8463 | 3.8784 | 1.2717 | 17.0337
| 638 | 3.8369 | 2.4485 | 5.3424 | 3.8746 | 1.7584 | 17.2608
| 639 | 3.9972 | 3.3141 | 5.5301 | 3.5932 | 1.562 | 17.9965
| 640 | 3.4568 | 3.4621 | 5.6882 | 3.3824 | 1.8375 | 17.827
| 641 | 3.9249 | 3.5999 | 5.4868 | 4.5471 | 1.3757 | 18.9344
| 642 | 3.9926 | 3.7322 | 5.7553 | 4.6456 | 1.6921 | 19.8178
| 643 | 3.875 | 2.5354 | 6.3637 | 4.0149 | 1.6321 | 18.4211
| 644 | 4.2319 | 3.2896 | 5.9982 | 5.1865 | 1.2945 | 20.0006
| 645 | 4.2581 | 2.7442 | 5.2075 | 3.959 | 1.3253 | 17.4942
| 646 | 3.868 | 2.8558 | 5.6703 | 4.8521 | 1.3462 | 18.5925
| 647 | 3.9604 | 2.5186 | 5.4916 | 4.1713 | 1.6053 | 17.7471
| 648 | 4.1051 | 2.8443 | 5.2763 | 5.1388 | 1.4845 | 18.849
| 649 | 3.9289 | 3.1256 | 4.7322 | 4.1192 | 1.3709 | 17.2767
| 650 | 4.4791 | 2.6974 | 4.1892 | 3.6799 | 1.602 | 16.6477
| 651 | 4.084 | 3.6192 | 5.04 | 3.2097 | 1.613 | 17.566
| 652 | 4.0211 | 3.0294 | 5.7196 | 3.4279 | 1.1631 | 17.3611
| 653 | 3.8793 | 3.2852 | 5.8051 | 5.1576 | 1.3697 | 19.497
| 654 | 4.007 | 2.8168 | 4.6206 | 4.5493 | 1.9708 | 17.9645
| 655 | 4.5435 | 2.9819 | 5.7513 | 4.1568 | 1.2388 | 18.6725
| 656 | 4.4836 | 2.4382 | 4.4264 | 4.0829 | 1.576 | 17.0072
| 657 | 4.2983 | 2.656 | 4.825 | 4.1498 | 1.5228 | 17.4519
| 658 | 4.4336 | 2.3857 | 4.7303 | 3.1717 | 1.6754 | 16.3968
| 659 | 4.1497 | 3.0077 | 5.2475 | 3.8576 | 1.688 | 17.9505
| 660 | 4.4418 | 2.9591 | 6.2852 | 4.7923 | 1.5106 | 19.9891
| 661 | 3.9841 | 2.9671 | 5.1884 | 5.4815 | 1.6162 | 19.2373
| 662 | 3.6942 | 3.4099 | 5.2564 | 4.8207 | 1.0896 | 18.2708
| 663 | 3.6036 | 2.3875 | 4.3342 | 3.5862 | 1.1976 | 15.1092
| 664 | 4.2038 | 2.1156 | 5.7352 | 5.2269 | 1.211 | 18.4924
| 665 | 3.9566 | 3.0093 | 4.7529 | 4.7092 | 1.5508 | 17.9788
| 666 | 3.6259 | 2.9441 | 5.219 | 3.822 | 1.5997 | 17.2107
| 667 | 3.6307 | 3.3173 | 4.8782 | 4.2605 | 1.4761 | 17.5627
| 668 | 3.5262 | 2.9744 | 5.2615 | 4.1692 | 1.4438 | 17.3752
| 669 | 4.1382 | 2.9031 | 5.8383 | 3.6247 | 1.7463 | 18.2504
| 670 | 4.538 | 2.9458 | 4.4386 | 3.9931 | 1.5836 | 17.4991
| 671 | 3.5414 | 3.4245 | 4.3492 | 3.4798 | 1.4916 | 16.2865
| 672 | 4.5971 | 2.7607 | 5.7445 | 4.8171 | 1.479 | 19.3985
| 673 | 4.3437 | 2.9505 | 4.8533 | 3.8321 | 1.7382 | 17.7179
| 674 | 3.2631 | 2.3207 | 6.8996 | 3.4603 | 1.5256 | 17.4693
| 675 | 3.5673 | 3.4426 | 5.1948 | 3.2401 | 1.7845 | 17.2293
| 676 | 4.1922 | 3.1682 | 6.5895 | 4.9448 | 1.2079 | 20.1025
| 677 | 3.2103 | 2.6689 | 4.9311 | 3.638 | 1.7569 | 16.2051
| 678 | 3.3073 | 3.3819 | 4.5364 | 5.1737 | 1.8038 | 18.2031
| 679 | 4.1025 | 3.0607 | 4.8364 | 4.0303 | 1.9231 | 17.9529
| 680 | 4.429 | 3.2178 | 5.6068 | 4.7576 | 1.6481 | 19.6594
| 681 | 4.0956 | 3.0241 | 7.6018 | 4.0512 | 1.6231 | 20.3957
| 682 | 3.9991 | 2.5903 | 6.3235 | 4.4155 | 1.5639 | 18.8923
| 683 | 3.8595 | 3.3511 | 5.0534 | 5.164 | 1.3954 | 18.8234
| 684 | 4.3293 | 3.3856 | 5.6296 | 3.5839 | 1.8054 | 18.7338
| 685 | 3.3533 | 2.3272 | 4.4946 | 3.479 | 1.3534 | 15.0076
| 686 | 3.8719 | 3.2389 | 4.3408 | 3.7923 | 1.7944 | 17.0382
| 687 | 3.612 | 3.0144 | 4.3596 | 4.175 | 1.7254 | 16.8864
| 688 | 4.0757 | 3.7927 | 6.7128 | 4.0966 | 1.6114 | 20.2893
| 689 | 3.8292 | 2.9241 | 6.0092 | 4.0769 | 1.5858 | 18.4252
| 690 | 4.1412 | 2.849 | 5.2738 | 5.0286 | 1.7912 | 19.0837
| 691 | 4.0899 | 2.8929 | 5.8949 | 3.4829 | 1.7141 | 18.0746
| 692 | 4.55 | 2.0641 | 5.0846 | 3.9116 | 1.3086 | 16.9188
| 693 | 4.6018 | 2.9389 | 4.7736 | 5.1187 | 1.4307 | 18.8637
| 694 | 3.4851 | 2.7918 | 5.5489 | 3.7987 | 1.0552 | 16.6797
| 695 | 3.2492 | 3.3698 | 4.918 | 4.9514 | 1.5431 | 18.0315
| 696 | 3.654 | 2.5661 | 6.962 | 4.4585 | 1.4355 | 19.0762
| 697 | 3.7237 | 3.4685 | 6.0456 | 3.2795 | 1.5594 | 18.0766
| 698 | 3.0612 | 3.4146 | 5.4171 | 3.8673 | 1.7759 | 17.5361
| 699 | 3.5209 | 3.2065 | 4.8271 | 4.2071 | 1.7118 | 17.4734
| 700 | 3.6578 | 3.0894 | 4.9985 | 5.5929 | 1.5894 | 18.9281
| 701 | 4.6237 | 3.1147 | 5.7654 | 3.9677 | 1.3999 | 18.8714
| 702 | 3.2419 | 2.994 | 5.9524 | 4.4984 | 1.6506 | 18.3372
| 703 | 4.2144 | 2.4161 | 5.9593 | 4.8971 | 1.5632 | 19.0502
| 704 | 4.7498 | 3.8789 | 4.4241 | 3.7966 | 1.1333 | 17.9827
| 705 | 4.0721 | 3.1877 | 5.7376 | 4.5823 | 1.6169 | 19.1966
| 706 | 4.0071 | 2.8654 | 5.5739 | 3.9991 | 1.6106 | 18.0561
| 707 | 3.8416 | 2.5347 | 7.1678 | 3.7228 | 1.2276 | 18.4945
| 708 | 3.336 | 3.4898 | 6.1767 | 5.3359 | 1.8691 | 20.2075
| 709 | 3.7453 | 2.553 | 6.4971 | 3.7581 | 1.22 | 17.7735
| 710 | 3.7317 | 2.8483 | 5.9252 | 4.4187 | 1.7414 | 18.6653
| 711 | 3.8646 | 2.7372 | 6.5522 | 5.834 | 1.4926 | 20.4805
| 712 | 4.6995 | 3.3554 | 7.1024 | 3.9724 | 1.629 | 20.7586
| 713 | 3.9439 | 2.5229 | 6.5248 | 3.4431 | 1.7888 | 18.2234
| 714 | 4.3865 | 3.6688 | 5.3589 | 3.7082 | 1.4602 | 18.5826
| 715 | 4.5246 | 3.1589 | 5.2846 | 3.8899 | 1.4561 | 18.3141
| 716 | 4.1295 | 2.8668 | 5.0577 | 3.4303 | 1.3232 | 16.8075
| 717 | 4.3016 | 2.5296 | 5.6993 | 3.96 | 1.4651 | 17.9557
| 718 | 4.2112 | 3.4008 | 6.2355 | 4.2386 | 1.215 | 19.3011
| 719 | 3.5874 | 2.6789 | 6.1338 | 4.3637 | 1.8031 | 18.5669
| 720 | 3.9207 | 3.3366 | 6.9516 | 5.5666 | 1.5514 | 21.3269
| 721 | 3.9793 | 3.5194 | 5.2203 | 4.7787 | 1.5473 | 19.0449
| 722 | 4.4812 | 2.7806 | 5.5909 | 3.3941 | 1.6611 | 17.9079
| 723 | 3.4599 | 3.2242 | 5.6481 | 3.5544 | 1.2476 | 17.1342
| 724 | 3.7981 | 2.876 | 6.945 | 5.198 | 1.7477 | 20.5647
| 725 | 3.7737 | 3.1724 | 5.3629 | 3.3557 | 1.3832 | 17.0478
| 726 | 3.9749 | 3.3065 | 5.0894 | 3.377 | 1.3425 | 17.0903
| 727 | 4.7969 | 3.0266 | 5.7671 | 4.7116 | 1.6467 | 19.949
| 728 | 3.7539 | 2.2958 | 5.7879 | 3.8463 | 1.5099 | 17.1938
| 729 | 4.3786 | 2.9843 | 5.8162 | 4.539 | 1.5008 | 19.2189
| 730 | 3.7496 | 2.8623 | 5.7591 | 4.5922 | 1.4712 | 18.4344
| 731 | 4.2849 | 3.2363 | 6.6291 | 4.1073 | 1.6087 | 19.8663
| 732 | 4.0605 | 2.1757 | 4.7916 | 4.2344 | 1.2385 | 16.5006
| 733 | 4.2702 | 3.3109 | 5.8003 | 5.7239 | 1.1901 | 20.2953
| 734 | 4.1778 | 2.7238 | 6.3898 | 4.385 | 1.852 | 19.5283
| 735 | 3.5056 | 3.6411 | 5.7051 | 3.4739 | 1.1142 | 17.4398
| 736 | 4.2459 | 2.7967 | 5.5884 | 4.3938 | 1.251 | 18.2757
| 737 | 4.1454 | 2.4341 | 6.129 | 4.2782 | 1.5583 | 18.545
| 738 | 4.2667 | 3.0705 | 6.2387 | 3.1525 | 1.5696 | 18.298
| 739 | 4.2562 | 3.0084 | 4.6357 | 3.9518 | 1.7862 | 17.6382
| 740 | 3.8666 | 2.5888 | 4.9556 | 3.3973 | 1.3346 | 16.143
| 741 | 3.7576 | 3.0999 | 5.8335 | 4.4471 | 1.5324 | 18.6705
| 742 | 3.5737 | 2.5511 | 4.8037 | 3.3732 | 1.1708 | 15.4725
| 743 | 4.0519 | 3.1432 | 5.0166 | 4.4846 | 1.2804 | 17.9767
| 744 | 4.3543 | 3.6236 | 7.1896 | 3.3338 | 1.4361 | 19.9374
| 745 | 4.4118 | 3.3777 | 5.4633 | 5.1356 | 1.4869 | 19.8753
| 746 | 3.6735 | 2.617 | 5.3823 | 3.976 | 1.5409 | 17.1898
| 747 | 3.4137 | 2.9537 | 5.5316 | 4.6927 | 1.6209 | 18.2124
| 748 | 3.9076 | 2.5166 | 5.1313 | 4.3072 | 1.6001 | 17.4628
| 749 | 3.3131 | 2.9251 | 4.4848 | 3.8355 | 1.6855 | 16.2441
| 750 | 4.0308 | 3.2659 | 6.7865 | 3.6847 | 1.4682 | 19.2361
| 751 | 3.511 | 2.7934 | 4.3971 | 3.6005 | 1.8836 | 16.1856
| 752 | 4.0832 | 3.1616 | 5.2118 | 4.9493 | 1.5341 | 18.9399
| 753 | 3.8135 | 3.0868 | 5.1335 | 4.4327 | 1.7134 | 18.1798
| 754 | 3.8839 | 2.7793 | 4.7005 | 4.6902 | 1.43 | 17.4839
| 755 | 3.8278 | 2.7942 | 6.0433 | 3.8078 | 1.418 | 17.891
| 756 | 3.8413 | 2.4298 | 5.6124 | 4.4313 | 1.4986 | 17.8134
| 757 | 4.2166 | 2.6035 | 6.4464 | 4.6208 | 1.5877 | 19.475
| 758 | 3.9037 | 3.3496 | 5.4209 | 3.4962 | 1.2656 | 17.436
| 759 | 4.7014 | 2.4586 | 6.0301 | 4.6662 | 1.666 | 19.5223
| 760 | 4.3848 | 3.1486 | 5.2955 | 3.2676 | 1.2055 | 17.302
| 761 | 4.0859 | 2.9979 | 6.6899 | 4.0394 | 1.2566 | 19.0698
| 762 | 4.0038 | 2.9068 | 5.2433 | 3.7179 | 1.6634 | 17.5352
| 763 | 3.4873 | 2.8786 | 4.7767 | 3.6052 | 1.5304 | 16.2782
| 764 | 3.2462 | 3.4111 | 5.9498 | 3.1311 | 1.2618 | 17
| 765 | 4.6076 | 2.6756 | 6.1939 | 4.0492 | 1.4584 | 18.9847
| 766 | 3.8461 | 3.0526 | 5.8244 | 4.1467 | 1.7007 | 18.5705
| 767 | 4.6697 | 2.3144 | 6.0568 | 4.2002 | 1.552 | 18.7931
| 768 | 3.4053 | 2.4429 | 6.3029 | 5.2386 | 1.4426 | 18.8324
| 769 | 4.0335 | 2.8 | 6.7604 | 3.4916 | 1.4464 | 18.5319
| 770 | 3.3735 | 2.7748 | 5.7117 | 3.3912 | 1.6692 | 16.9204
| 771 | 4.722 | 3.3736 | 6.4803 | 3.5482 | 1.0505 | 19.1746
| 772 | 4.0821 | 2.8104 | 5.6338 | 3.1655 | 1.6838 | 17.3755
| 773 | 4.1811 | 3.5648 | 5.7156 | 5.49 | 1.9386 | 20.8901
| 774 | 3.7082 | 2.8885 | 6.7988 | 4.5867 | 1.6672 | 19.6493
| 775 | 3.9806 | 2.5616 | 5.476 | 4.2139 | 1.4831 | 17.7151
| 776 | 4.03 | 3.6853 | 5.3717 | 3.6736 | 1.1684 | 17.9289
| 777 | 4.8337 | 3.0636 | 5.4368 | 4.8037 | 1.7099 | 19.8477
| 778 | 4.3155 | 2.9357 | 6.9378 | 3.707 | 1.6782 | 19.5742
| 779 | 3.5966 | 2.9614 | 6.8627 | 4.809 | 1.5113 | 19.741
| 780 | 3.6704 | 2.4883 | 6.8317 | 3.6998 | 1.581 | 18.2712
| 781 | 3.5983 | 3.2517 | 6.5643 | 4.3802 | 1.3664 | 19.1609
| 782 | 3.9002 | 3.3945 | 4.466 | 3.9227 | 1.2263 | 16.9097
| 783 | 3.5188 | 2.1599 | 5.4491 | 3.5753 | 1.7692 | 16.4724
| 784 | 3.7413 | 2.479 | 6.5571 | 3.6371 | 1.4955 | 17.9101
| 785 | 4.5087 | 2.3458 | 7.0943 | 4.7747 | 1.8087 | 20.5323
| 786 | 4.1934 | 3.3587 | 6.5598 | 3.9782 | 1.311 | 19.4013
| 787 | 4.7152 | 3.4843 | 7.2056 | 5.4469 | 1.6997 | 22.5516
| 788 | 3.2594 | 2.9904 | 4.2105 | 4.1329 | 1.9329 | 16.5261
| 789 | 3.7125 | 2.7473 | 5.6308 | 4.8299 | 1.3339 | 18.2544
| 790 | 3.9226 | 3.5163 | 4.8657 | 3.3668 | 1.58 | 17.2515
| 791 | 4.2091 | 3.355 | 6.156 | 5.0141 | 1.291 | 20.0252
| 792 | 4.356 | 3.258 | 5.5972 | 3.4748 | 1.2846 | 17.9705
| 793 | 3.5026 | 2.6854 | 4.6758 | 3.8994 | 1.2629 | 16.0261
| 794 | 4.4845 | 3.1202 | 4.7079 | 4.559 | 1.3674 | 18.239
| 795 | 3.8055 | 2.3035 | 6.5934 | 4.7648 | 1.402 | 18.8692
| 796 | 4.4477 | 3.2805 | 6.3946 | 5.2403 | 1.8913 | 21.2544
| 797 | 3.8381 | 3.2553 | 5.0462 | 3.6292 | 1.2497 | 17.0185
| 798 | 4.6618 | 3.4475 | 5.7819 | 5.2959 | 1.373 | 20.56
| 799 | 3.5547 | 3.4554 | 5.626 | 4.6326 | 1.5343 | 18.803
| 800 | 3.4418 | 2.3616 | 6.7791 | 4.9101 | 1.4637 | 18.9563
| 801 | 4.3998 | 2.2331 | 7.1595 | 5.1459 | 1.1607 | 20.099
| 802 | 3.6054 | 3.3477 | 5.7715 | 4.4351 | 1.467 | 18.6266
| 803 | 4.3181 | 2.046 | 5.7942 | 3.4037 | 1.425 | 16.987
| 804 | 3.6655 | 2.8473 | 5.5592 | 3.5491 | 1.2953 | 16.9163
| 805 | 4.0282 | 3.3247 | 5.3999 | 4.3398 | 1.2599 | 18.3525
| 806 | 3.8042 | 2.9144 | 7.6994 | 5.0536 | 1.2454 | 20.717
| 807 | 4.768 | 2.8055 | 5.2583 | 4.0943 | 1.4267 | 18.3528
| 808 | 4.0626 | 2.5728 | 5.5417 | 3.0858 | 1.4776 | 16.7405
| 809 | 4.4225 | 2.6634 | 4.5961 | 3.9313 | 1.7802 | 17.3935
| 810 | 4.4501 | 3.2276 | 4.9806 | 4.022 | 1.9347 | 18.615
| 811 | 3.1714 | 3.6752 | 4.8732 | 3.7712 | 1.5937 | 17.0848
| 812 | 3.945 | 2.6926 | 5.567 | 4.625 | 1.1019 | 17.9315
| 813 | 3.697 | 3.3462 | 6.146 | 4.0127 | 1.7193 | 18.9211
| 814 | 3.4217 | 2.9767 | 5.1934 | 4.1179 | 1.6846 | 17.3943
| 815 | 3.7282 | 3.6104 | 7.3686 | 3.1203 | 1.0965 | 18.924
| 816 | 3.6901 | 2.7627 | 5.06 | 5.3019 | 1.6495 | 18.4641
| 817 | 3.5527 | 3.6953 | 6.0816 | 5.3548 | 1.3649 | 20.0492
| 818 | 4.2194 | 3.3756 | 5.9104 | 4.1271 | 1.6931 | 19.3256
| 819 | 3.8887 | 2.7645 | 5.4381 | 3.4458 | 1.2237 | 16.7608
| 820 | 4.0198 | 3.2479 | 5.8419 | 3.7042 | 1.5469 | 18.3607
| 821 | 3.8786 | 3.416 | 5.5205 | 3.432 | 1.6873 | 17.9344
| 822 | 3.7839 | 3.607 | 5.0272 | 3.4524 | 1.4259 | 17.2964
| 823 | 3.6985 | 3.4941 | 4.7989 | 4.1459 | 1.4003 | 17.5377
| 824 | 4.157 | 3.0196 | 5.26 | 3.902 | 1.4368 | 17.7753
| 825 | 4.1821 | 3.8026 | 5.9824 | 5.8166 | 1.4706 | 21.2543
| 826 | 4.1477 | 3.1709 | 4.992 | 3.5947 | 1.3472 | 17.2524
| 827 | 4.0243 | 2.3992 | 4.7216 | 3.8343 | 1.1645 | 16.144
| 828 | 4.8128 | 2.7592 | 5.0679 | 3.7277 | 1.7603 | 18.1278
| 829 | 3.94 | 3.6371 | 6.732 | 3.7423 | 1.7961 | 19.8476
| 830 | 3.9786 | 3.3576 | 7.0239 | 3.9152 | 1.4262 | 19.7015
| 831 | 3.5906 | 3.8447 | 6.9146 | 3.1402 | 1.4155 | 18.9054
| 832 | 4.3977 | 3.0283 | 5.1684 | 3.2719 | 1.5538 | 17.4201
| 833 | 3.3463 | 3.5058 | 6.5179 | 5.2541 | 1.3567 | 19.9807
| 834 | 4.0243 | 3.5525 | 6.8246 | 4.8483 | 1.5952 | 20.845
| 835 | 4.0377 | 3.1493 | 4.9468 | 4.7539 | 1.1062 | 17.9938
| 836 | 3.9597 | 2.4876 | 6.0991 | 5.623 | 1.3218 | 19.4912
| 837 | 4.0164 | 3.3831 | 6.8188 | 3.4236 | 1.517 | 19.1589
| 838 | 3.5387 | 2.7398 | 6.7745 | 4.6138 | 1.5552 | 19.2219
| 839 | 4.1352 | 2.8388 | 4.9424 | 4.5199 | 1.3847 | 17.821
| 840 | 3.5355 | 3.4194 | 5.2691 | 4.1222 | 1.4377 | 17.7839
| 841 | 3.3026 | 2.71 | 6.0046 | 4.5762 | 1.2991 | 17.8924
| 842 | 3.6243 | 3.1505 | 6.5107 | 3.3065 | 1.7522 | 18.3443
| 843 | 3.3622 | 2.6964 | 5.1396 | 3.7566 | 1.4643 | 16.4191
| 844 | 4.1999 | 2.8694 | 4.8849 | 3.9987 | 1.4391 | 17.392
| 845 | 4.5664 | 2.8504 | 5.503 | 4.2897 | 1.406 | 18.6155
| 846 | 3.5784 | 2.6675 | 5.4899 | 3.2303 | 1.3926 | 16.3586
| 847 | 4.1265 | 2.9887 | 5.2267 | 4.3119 | 1.3791 | 18.0329
| 848 | 3.981 | 3.2383 | 4.8582 | 3.4892 | 1.2214 | 16.7882
| 849 | 4.2495 | 2.6099 | 5.461 | 3.1161 | 1.5084 | 16.9448
| 850 | 4.1134 | 3.1746 | 6.6948 | 3.3299 | 1.7966 | 19.1093
| 851 | 4.5204 | 3.7581 | 7.6852 | 3.3395 | 1.8234 | 21.1266
| 852 | 4.5767 | 3.1245 | 7.7894 | 3.1966 | 1.3574 | 20.0446
| 853 | 3.5926 | 3.2007 | 5.4807 | 3.7504 | 1.363 | 17.3875
| 854 | 4.1646 | 2.5094 | 6.0676 | 4.9749 | 1.7519 | 19.4684
| 855 | 4.0318 | 2.8702 | 4.5734 | 4.0877 | 1.6676 | 17.2307
| 856 | 4.7846 | 3.5286 | 4.6735 | 4.0744 | 1.7682 | 18.8293
| 857 | 3.3127 | 3.7772 | 7.7369 | 4.4855 | 1.2143 | 20.5266
| 858 | 3.2717 | 2.5953 | 5.136 | 3.6937 | 1.3331 | 16.0299
| 859 | 3.8536 | 2.3905 | 6.2726 | 3.8433 | 1.6059 | 17.9659
| 860 | 3.9113 | 2.5829 | 5.662 | 4.2902 | 1.631 | 18.0774
| 861 | 3.7166 | 2.9332 | 4.9198 | 4.5417 | 1.3 | 17.4113
| 862 | 3.9832 | 2.1727 | 5.4055 | 3.4726 | 1.5369 | 16.5709
| 863 | 4.5629 | 2.938 | 5.3767 | 3.4946 | 1.4614 | 17.8336
| 864 | 4.6272 | 3.5232 | 6.5496 | 3.3446 | 1.4807 | 19.5253
| 865 | 3.7261 | 3.7436 | 5.3695 | 3.1752 | 1.1965 | 17.2108
| 866 | 3.9388 | 2.894 | 4.4626 | 4.9987 | 1.8976 | 18.1917
| 867 | 4.8965 | 2.6273 | 4.4991 | 3.8144 | 1.6251 | 17.4624
| 868 | 3.285 | 3.7231 | 4.3533 | 3.3701 | 1.5197 | 16.2511
| 869 | 4.0125 | 2.9795 | 4.8995 | 4.3605 | 1.4227 | 17.6746
| 870 | 3.7911 | 2.209 | 6.6418 | 4.2721 | 1.5149 | 18.4288
| 871 | 3.5628 | 2.622 | 5.1202 | 4.0667 | 1.6684 | 17.0401
| 872 | 4.5928 | 3.3887 | 4.9798 | 4.5621 | 1.3077 | 18.8311
| 873 | 4.1491 | 2.2212 | 4.9091 | 3.3575 | 1.2961 | 15.9329
| 874 | 3.6401 | 3.2673 | 6.1142 | 4.249 | 1.6585 | 18.929
| 875 | 4.499 | 3.393 | 6.3441 | 3.3104 | 1.6261 | 19.1726
| 876 | 3.9574 | 2.89 | 4.6916 | 3.7367 | 1.2064 | 16.4822
| 877 | 3.974 | 2.1896 | 4.9239 | 3.5338 | 1.3389 | 15.9602
| 878 | 4.6875 | 3.469 | 7.3165 | 3.297 | 1.4633 | 20.2333
| 879 | 4.6815 | 3.5711 | 5.2501 | 4.2274 | 1.6297 | 19.3598
| 880 | 3.5086 | 3.4026 | 4.1914 | 3.7136 | 1.5454 | 16.3617
| 881 | 3.9275 | 2.937 | 4.2436 | 4.2874 | 1.6473 | 17.0427
| 882 | 4.0903 | 2.2005 | 4.726 | 4.3541 | 1.9269 | 17.2978
| 883 | 4.1096 | 2.5071 | 5.6761 | 3.2059 | 1.4702 | 16.9689
| 884 | 4.1696 | 2.1522 | 5.078 | 4.4606 | 1.9488 | 17.8092
| 885 | 3.8138 | 3.0015 | 5.7288 | 3.7036 | 1.5219 | 17.7697
| 886 | 3.8694 | 3.2712 | 5.7833 | 3.3793 | 1.8667 | 18.1699
| 887 | 4.4219 | 2.4771 | 6.6532 | 4.2666 | 1.4092 | 19.228
| 888 | 3.7872 | 2.7891 | 6.4693 | 3.2642 | 1.3945 | 17.7043
| 889 | 3.6641 | 2.7494 | 4.54 | 3.4657 | 1.5777 | 15.997
| 890 | 4.7036 | 3.0329 | 6.252 | 4.8985 | 1.7272 | 20.6143
| 891 | 3.8202 | 2.9472 | 6.3756 | 3.0237 | 1.5723 | 17.739
| 892 | 4.1676 | 2.7554 | 5.593 | 3.6145 | 1.8947 | 18.0252
| 893 | 4.0184 | 3.4219 | 6.6399 | 4.1689 | 1.3904 | 19.6395
| 894 | 3.4669 | 2.5386 | 4.9832 | 3.4362 | 1.3306 | 15.7555
| 895 | 4.1658 | 3.8705 | 4.9333 | 4.282 | 1.4897 | 18.7413
| 896 | 3.4886 | 3.3985 | 4.3696 | 4.4709 | 1.8281 | 17.5557
| 897 | 4.129 | 2.3468 | 5.5873 | 3.3143 | 1.3394 | 16.7168
| 898 | 3.3958 | 2.9802 | 5.0924 | 5.0423 | 1.6009 | 18.1117
| 899 | 3.8264 | 3.3148 | 6.8727 | 3.6087 | 1.8554 | 19.478
| 900 | 3.6452 | 3.426 | 6.6641 | 4.8764 | 1.3693 | 19.981
| 901 | 4.7548 | 2.8826 | 5.0429 | 5.2886 | 1.6464 | 19.6152
| 902 | 4.1177 | 3.1468 | 5.1984 | 5.4409 | 1.1171 | 19.021
| 903 | 4.0972 | 3.2311 | 4.5151 | 3.2701 | 1.5603 | 16.6738
| 904 | 3.8476 | 2.823 | 5.0508 | 3.5228 | 1.3775 | 16.6216
| 905 | 3.2078 | 3.7058 | 4.3087 | 4.315 | 1.2689 | 16.8063
| 906 | 3.454 | 3.1355 | 5.0003 | 3.581 | 1.9112 | 17.082
| 907 | 4.8435 | 3.1838 | 5.6411 | 3.5044 | 1.6642 | 18.8369
| 908 | 3.5603 | 2.5312 | 4.4491 | 3.8886 | 1.7081 | 16.1373
| 909 | 3.8525 | 2.9157 | 6.9287 | 3.2229 | 1.4717 | 18.3914
| 910 | 4.2032 | 3.2973 | 4.519 | 3.302 | 1.5136 | 16.835
| 911 | 4.1119 | 3.2043 | 4.9685 | 3.145 | 1.184 | 16.6138
| 912 | 4.6152 | 3.5605 | 6.6835 | 3.8832 | 1.1452 | 19.8876
| 913 | 3.9146 | 3.3631 | 6.3917 | 3.9411 | 1.7058 | 19.3164
| 914 | 4.4445 | 2.7666 | 7.47 | 3.8368 | 1.4114 | 19.9293
| 915 | 4.504 | 3.4127 | 4.4141 | 4.3738 | 1.5734 | 18.2779
| 916 | 4.7132 | 3.0351 | 7.4849 | 4.3421 | 1.4315 | 21.0068
| 917 | 4.2932 | 3.5693 | 6.8132 | 5.1315 | 1.329 | 21.1363
| 918 | 3.3811 | 3.74 | 6.4333 | 4.3328 | 1.4371 | 19.3244
| 919 | 3.794 | 2.3081 | 4.6685 | 3.3861 | 1.4161 | 15.5729
| 920 | 3.6481 | 2.2874 | 6.9969 | 5.3989 | 1.7208 | 20.052
| 921 | 4.1871 | 3.2134 | 7.9021 | 4.1826 | 1.3294 | 20.8147
| 922 | 3.4494 | 3.022 | 7.5295 | 4.9688 | 1.2252 | 20.1948
| 923 | 3.3937 | 3.2911 | 7.0627 | 4.7199 | 1.6985 | 20.1658
| 924 | 3.5248 | 3.0205 | 7.372 | 3.4591 | 1.4676 | 18.844
| 925 | 3.6466 | 2.3584 | 5.009 | 4.4067 | 1.0438 | 16.4644
| 926 | 4.5672 | 2.9511 | 4.9397 | 4.5025 | 1.4285 | 18.389
| 927 | 3.8825 | 3.2792 | 4.1448 | 5.6613 | 1.2531 | 18.2209
| 928 | 3.8115 | 3.6314 | 6.4631 | 4.3468 | 1.723 | 19.9757
| 929 | 4.0381 | 2.6067 | 6.3244 | 3.9269 | 1.557 | 18.4531
| 930 | 4.0423 | 3.5302 | 6.8538 | 4.0087 | 1.8265 | 20.2615
| 931 | 4.0776 | 2.4581 | 6.5265 | 3.5315 | 1.4774 | 18.0709
| 932 | 4.0344 | 3.1757 | 5.0328 | 3.9352 | 1.3501 | 17.5282
| 933 | 4.5014 | 2.7832 | 5.8071 | 4.0411 | 1.3363 | 18.4691
| 934 | 4.3516 | 3.7867 | 4.6605 | 4.3511 | 1.3097 | 18.4596
| 935 | 3.7028 | 2.3421 | 6.1604 | 3.9899 | 1.3718 | 17.5669
| 936 | 3.4012 | 3.122 | 6.1406 | 3.7267 | 1.3197 | 17.7102
| 937 | 3.7186 | 2.9204 | 6.128 | 3.3885 | 1.7485 | 17.9039
| 938 | 3.4156 | 3.4715 | 6.4356 | 4.2168 | 1.5384 | 19.078
| 939 | 4.3092 | 2.5561 | 5.1604 | 3.9142 | 1.5848 | 17.5247
| 940 | 3.6445 | 2.8681 | 5.9935 | 4.9177 | 1.7038 | 19.1275
| 941 | 4.0091 | 2.9431 | 6.7293 | 5.4094 | 1.4454 | 20.5363
| 942 | 4.1197 | 3.4576 | 5.2351 | 3.8125 | 1.685 | 18.3098
| 943 | 3.8488 | 2.8299 | 5.0287 | 3.1358 | 1.5757 | 16.4188
| 944 | 3.398 | 2.8142 | 4.9149 | 3.3244 | 1.6026 | 16.0541
| 945 | 3.4297 | 3.036 | 5.8963 | 4.7321 | 1.5394 | 18.6335
| 946 | 4.1909 | 2.7077 | 4.2975 | 5.3285 | 1.3582 | 17.8828
| 947 | 4.3139 | 3.0034 | 7.567 | 5.5027 | 1.4063 | 21.7932
| 948 | 4.015 | 2.7335 | 4.8384 | 4.8648 | 1.7031 | 18.1549
| 949 | 3.8512 | 3.2879 | 5.7331 | 3.6696 | 1.4973 | 18.0391
| 950 | 3.9168 | 3.4182 | 5.2253 | 4.6408 | 1.8896 | 19.0907
| 951 | 4.5135 | 2.5925 | 6.8266 | 3.4018 | 1.4905 | 18.8249
| 952 | 3.9422 | 3.2468 | 5.7871 | 3.9491 | 1.5004 | 18.4257
| 953 | 4.363 | 3.522 | 6.8846 | 4.243 | 1.4798 | 20.4924
| 954 | 3.8083 | 3.185 | 6.5021 | 3.4626 | 1.4544 | 18.4123
| 955 | 3.513 | 2.956 | 4.6341 | 4.4262 | 1.4489 | 16.9783
| 956 | 3.6141 | 3.2729 | 5.1048 | 3.9283 | 1.6222 | 17.5424
| 957 | 3.3843 | 3.1138 | 5.1175 | 3.3603 | 1.8637 | 16.8396
| 958 | 4.3928 | 2.4143 | 5.2445 | 3.7898 | 1.4053 | 17.2466
| 959 | 3.6008 | 2.9256 | 4.6952 | 3.9839 | 1.7313 | 16.9368
| 960 | 3.7603 | 3.2142 | 5.9008 | 3.9078 | 1.447 | 18.2301
| 961 | 3.7677 | 3.2592 | 6.4721 | 4.3267 | 1.2441 | 19.0696
| 962 | 3.6431 | 2.7842 | 5.317 | 4.833 | 1.6201 | 18.1973
| 963 | 3.6612 | 2.955 | 5.6819 | 5.2042 | 1.5076 | 19.01
| 964 | 4.0214 | 3.0184 | 6.2485 | 4.7276 | 1.4766 | 19.4925
| 965 | 3.0851 | 3.6083 | 5.1846 | 4.3306 | 1.8453 | 18.054
| 966 | 4.0656 | 3.8614 | 4.7505 | 4.1437 | 1.4126 | 18.2338
| 967 | 3.4348 | 2.2703 | 6.2859 | 3.4149 | 1.4033 | 16.8092
| 968 | 3.4708 | 2.4951 | 6.5778 | 4.7507 | 1.4385 | 18.7328
| 969 | 4.3748 | 3.0696 | 4.29 | 4.7714 | 1.4208 | 17.9265
| 970 | 3.8655 | 2.4612 | 7.3439 | 4.309 | 1.448 | 19.4276
| 971 | 4.473 | 3.1863 | 4.0883 | 4.1784 | 1.4661 | 17.3921
| 972 | 3.5163 | 2.2403 | 6.4111 | 4.7385 | 1.81 | 18.7162
| 973 | 4.3502 | 3.2943 | 4.6573 | 4.0895 | 1.4403 | 17.8317
| 974 | 4.5519 | 2.7681 | 5.201 | 3.7993 | 1.5056 | 17.826
| 975 | 4.2332 | 2.7518 | 6.5011 | 4.941 | 1.3359 | 19.7631
| 976 | 3.8611 | 2.8345 | 4.558 | 4.8255 | 1.2889 | 17.3679
| 977 | 4.2681 | 3.3283 | 4.3743 | 3.5859 | 1.6737 | 17.2303
| 978 | 3.6898 | 2.9346 | 5.7019 | 3.7162 | 1.6393 | 17.6818
| 979 | 4.3799 | 2.9869 | 6.7698 | 3.4483 | 1.5241 | 19.1091
| 980 | 3.7012 | 3.6362 | 6.265 | 3.8936 | 1.5277 | 19.0237
| 981 | 4.5342 | 3.1807 | 5.9287 | 5.7358 | 1.6807 | 21.0601
| 982 | 3.6789 | 2.9179 | 4.8085 | 4.6608 | 1.0853 | 17.1513
| 983 | 4.3232 | 2.9854 | 6.1671 | 5.1087 | 1.4206 | 20.005
| 984 | 3.2349 | 3.3748 | 7.5579 | 4.2463 | 1.571 | 19.9849
| 985 | 4.5731 | 2.3823 | 6.4862 | 4.3783 | 1.3916 | 19.2115
| 986 | 3.0288 | 3.0927 | 5.1647 | 3.937 | 1.5736 | 16.7967
| 987 | 3.5153 | 3.7301 | 4.2824 | 3.6716 | 1.4503 | 16.6497
| 988 | 3.8305 | 3.3274 | 5.6358 | 3.6267 | 1.56 | 17.9804
| 989 | 4.7342 | 2.8307 | 4.8424 | 4.5081 | 1.3799 | 18.2953
| 990 | 4.9564 | 2.3346 | 6.0022 | 3.7088 | 1.3859 | 18.3879
| 991 | 3.5069 | 2.8789 | 7.1419 | 3.5878 | 1.4414 | 18.5569
| 992 | 4.6336 | 2.9222 | 5.8912 | 4.2735 | 1.457 | 19.1775
| 993 | 3.6621 | 3.6792 | 4.9101 | 3.4213 | 1.5032 | 17.1759
| 994 | 3.6316 | 2.6597 | 4.8318 | 4.9324 | 1.1369 | 17.1924
| 995 | 4.3625 | 2.9016 | 6.9751 | 3.5968 | 1.3025 | 19.1385
| 996 | 4.1067 | 2.7193 | 4.7108 | 3.3266 | 1.7672 | 16.6306
| 997 | 3.9504 | 2.2812 | 5.6023 | 5.0905 | 1.4527 | 18.3771
| 998 | 4.1166 | 3.1028 | 5.3974 | 4.0245 | 1.6045 | 18.246
| 999 | 3.7089 | 3.1907 | 5.4465 | 3.4635 | 1.446 | 17.2555
| 1000 | 3.9515 | 2.4988 | 6.5323 | 3.636 | 1.3991 | 18.0178
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Risk Results 3
Navigation |  | Inputs |  |  |  |  | Outputs | Simulation Statistics |  | Output Cumulative Distributions | Output Distributions | Risk Tornado Diagram
Risk Outputs |  | Plan!$G$4 | Plan!$G$5 | Plan!$G$6 | Plan!$G$7 | Plan!$G$8 | Plan!$G$9 |  | Plan!$G$9 |  |  |  |  | Correlations - Column 1 sorted
Simulation Statistics | Iterations | RiskTriang(D4,E4,F4) | RiskTriang(D5,E5,F5) | RiskTriang(D6,E6,F6) | RiskTriang(D7,E7,F7) | RiskTriang(D8,E8,F8) | LiveDate |  | LiveDate |  |  | Select Output: | Plan!$G$9 |  | Plan!$G$9
Risk Output Percentiles | 1 | 4.518 | 2.714 | 6.4122 | 4.4845 | 1.7625 | 19.8911 | Mean | 18.3333 |  |  | Name: | LiveDate | Risk Inputs | LiveDate
Calculate Percent Rank | 2 | 4.0951 | 3.0957 | 5.2155 | 4.3738 | 1.4405 | 18.2206 | Median | 18.2487 |  |  | 1 |  | Plan!$G$8 | 0.18152
Correlations | 3 | 4.0885 | 2.6354 | 4.9221 | 4.5361 | 1.2122 | 17.3943 | Mode | #N/A |  |  | Tornado Diagram for LiveDate (Plan!$G$9) |  | Plan!$G$5 | 0.32584
Output Cumulative Distributions | 4 | 3.6591 | 3.0528 | 5.1855 | 4.1313 | 1.5602 | 17.5889 | Std. Deviation | 1.2313 |  |  |  |  | Plan!$G$4 | 0.32598
Output Distributions | 5 | 3.8173 | 3.2734 | 5.0567 | 3.3648 | 1.4271 | 16.9393 | Variance | 1.5161 |  |  |  |  | Plan!$G$7 | 0.53272
Risk Tornado Diagram | 6 | 3.6175 | 3.7358 | 5.4483 | 3.785 | 1.7647 | 18.3512 | Kurtosis | -0.22646 |  |  |  |  | Plan!$G$6 | 0.68002
| 7 | 3.0659 | 2.9204 | 5.0779 | 5.1795 | 1.4137 | 17.6575 | Skewness | 0.17289
| 8 | 4.4824 | 3.0584 | 4.9556 | 5.528 | 1.4846 | 19.509 | Minimum | 14.4589
| 9 | 3.6409 | 2.4551 | 7.6002 | 3.2903 | 1.2145 | 18.201 | Maximum | 22.2398
| 10 | 3.25 | 3.6223 | 4.8966 | 3.473 | 1.7636 | 17.0056 | Range | 7.7809
| 11 | 4.1753 | 3.3164 | 6.1046 | 3.6228 | 1.5507 | 18.7698 | Count | 1000
| 12 | 3.7934 | 3.0089 | 5.6563 | 3.7492 | 1.4527 | 17.6605 | Error Count | 0
| 13 | 4.1406 | 2.8673 | 5.5636 | 5.1976 | 1.6452 | 19.4144 | Std. Error | 0.038937
| 14 | 4.2436 | 3.3273 | 7.0596 | 3.7387 | 1.7352 | 20.1044 | Confidence Level (95%) | 0.076407
| 15 | 3.1045 | 3.3797 | 6.0626 | 3.2407 | 1.4897 | 17.2772
| 16 | 3.5127 | 3.642 | 5.7208 | 3.6377 | 1.6117 | 18.1249 | Percentiles
| 17 | 4.1045 | 2.8506 | 5.2626 | 3.2678 | 1.1329 | 16.6183 |  | Plan!$G$9
| 18 | 3.6882 | 2.3358 | 5.6771 | 5.0273 | 1.3682 | 18.0966 |  | LiveDate
| 19 | 3.6771 | 2.6583 | 5.5777 | 3.4635 | 1.5416 | 16.9182 | 0% | 14.4589
| 20 | 4.3623 | 2.4677 | 5.8078 | 4.4416 | 1.3984 | 18.4779 | 2.5% | 16.0632
| 21 | 4.239 | 3.0688 | 4.5941 | 4.8965 | 1.5482 | 18.3466 | 5% | 16.3622
| 22 | 4.4962 | 3.0113 | 5.3653 | 3.3692 | 1.5119 | 17.7539 | 7.5% | 16.579
| 23 | 3.7234 | 3.0343 | 5.3177 | 3.7958 | 1.6494 | 17.5207 | 10% | 16.8145
| 24 | 4.4698 | 2.3603 | 5.1892 | 4.567 | 1.307 | 17.8932 | 12.5% | 16.9217
| 25 | 3.7875 | 2.8297 | 6.639 | 3.5838 | 1.3852 | 18.2252 | 15% | 17.068
| 26 | 3.8738 | 3.3218 | 6.1157 | 3.9266 | 1.7331 | 18.971 | 17.5% | 17.1709
| 27 | 4.3828 | 3.3133 | 6.7513 | 4.4211 | 1.6228 | 20.4914 | 20% | 17.2745
| 28 | 4.1232 | 2.7687 | 6.2038 | 3.8873 | 1.2748 | 18.2578 | 22.5% | 17.3506
| 29 | 4.1848 | 2.8511 | 5.8152 | 4.4392 | 1.6894 | 18.9797 | 25% | 17.4682
| 30 | 3.9326 | 3.181 | 4.2511 | 5.2851 | 1.2725 | 17.9224 | 27.5% | 17.5574
| 31 | 4.0366 | 3.2536 | 6.0654 | 3.9155 | 1.5393 | 18.8105 | 30% | 17.6293
| 32 | 3.9656 | 3.5045 | 5.0455 | 4.0045 | 1.4623 | 17.9823 | 32.5% | 17.7273
| 33 | 4.5767 | 3.8325 | 6.82 | 3.3207 | 1.2734 | 19.8233 | 35% | 17.8073
| 34 | 3.6958 | 2.5717 | 4.828 | 3.6006 | 1.4915 | 16.1876 | 37.5% | 17.8752
| 35 | 3.9744 | 2.9528 | 4.9231 | 4.0409 | 1.5586 | 17.4497 | 40% | 17.9399
| 36 | 3.5705 | 3.2821 | 6.8908 | 4.1199 | 1.7742 | 19.6374 | 42.5% | 18.0305
| 37 | 3.4448 | 3.3653 | 5.4614 | 4.5663 | 1.6675 | 18.5054 | 45% | 18.1067
| 38 | 3.7703 | 2.8233 | 4.9755 | 4.0194 | 1.23 | 16.8185 | 47.5% | 18.1725
| 39 | 4.0319 | 2.8688 | 4.4369 | 3.8108 | 1.4487 | 16.5973 | 50% | 18.2487
| 40 | 4.3125 | 3.1329 | 5.566 | 4.8217 | 1.4553 | 19.2884 | 52.5% | 18.3454
| 41 | 3.9259 | 3.0758 | 6.8489 | 4.3843 | 1.294 | 19.5289 | 55% | 18.4611
| 42 | 3.2721 | 2.8094 | 5.2478 | 3.6606 | 1.2499 | 16.2397 | 57.5% | 18.5467
| 43 | 3.6666 | 3.1904 | 5.9824 | 4.1576 | 1.3807 | 18.3777 | 60% | 18.6172
| 44 | 3.7297 | 2.662 | 5.0358 | 3.8027 | 1.4923 | 16.7225 | 62.5% | 18.7262
| 45 | 3.8217 | 3.6259 | 5.4207 | 5.2392 | 1.4304 | 19.5379 | 65% | 18.8019
| 46 | 4.4169 | 2.4267 | 5.9632 | 3.1942 | 1.1728 | 17.1739 | 67.5% | 18.875
| 47 | 4.2251 | 2.3425 | 5.9793 | 3.3219 | 1.4089 | 17.2777 | 70% | 18.9821
| 48 | 4.3585 | 3.5988 | 4.6402 | 3.7751 | 1.7949 | 18.1674 | 72.5% | 19.088
| 49 | 4.3608 | 3.4929 | 5.3381 | 3.7095 | 1.7507 | 18.6519 | 75% | 19.1982
| 50 | 3.5428 | 3.3428 | 5.8406 | 4.1789 | 1.2214 | 18.1264 | 77.5% | 19.2888
| 51 | 3.7099 | 3.4739 | 6.3103 | 3.7372 | 1.3385 | 18.5698 | 80% | 19.3977
| 52 | 3.895 | 2.5932 | 6.0917 | 4.6941 | 1.2041 | 18.4782 | 82.5% | 19.5382
| 53 | 4.2535 | 2.782 | 5.7424 | 4.7855 | 1.4737 | 19.0371 | 85% | 19.6626
| 54 | 4.1507 | 2.707 | 4.6035 | 3.6427 | 1.7845 | 16.8883 | 87.5% | 19.8159
| 55 | 4.219 | 3.4449 | 6.0802 | 3.7252 | 1.3799 | 18.8491 | 90% | 19.9242
| 56 | 3.4497 | 3.4054 | 6.1061 | 4.1235 | 1.7864 | 18.8711 | 92.5% | 20.1185
| 57 | 3.5108 | 3.2733 | 6.981 | 3.396 | 1.5787 | 18.7397 | 95% | 20.4025
| 58 | 3.6311 | 2.6807 | 5.191 | 3.9609 | 1.1242 | 16.5878 | 97.5% | 20.8273
| 59 | 3.8234 | 2.4453 | 4.8336 | 4.2192 | 1.626 | 16.9474 | 100% | 22.2398
| 60 | 3.9214 | 2.9781 | 6.6837 | 4.399 | 1.9075 | 19.8899
| 61 | 4.8157 | 3.2801 | 5.3081 | 3.5426 | 1.9373 | 18.8839 | Percent Rank
| 62 | 3.5984 | 2.8285 | 6.2287 | 4.5526 | 1.3294 | 18.5375 |  | Plan!$G$9
| 63 | 3.5162 | 2.4138 | 6.4651 | 3.5158 | 1.3735 | 17.2844 |  | LiveDate
| 64 | 4.3062 | 2.2194 | 5.4068 | 5.5698 | 1.8823 | 19.3845 | Enter Value: | 16.3622
| 65 | 3.6756 | 3.4291 | 4.6582 | 4.9201 | 1.4793 | 18.1623 | % rank: | 5%
| 66 | 3.8596 | 2.9411 | 5.4946 | 3.6316 | 1.7028 | 17.6297
| 67 | 3.5192 | 2.169 | 6.2116 | 3.3728 | 1.4669 | 16.7394 | Correlations
| 68 | 4.3753 | 3.1867 | 6.305 | 5.1188 | 1.5901 | 20.576 |  | Plan!$G$9
| 69 | 3.8587 | 3.1298 | 5.2362 | 3.7406 | 1.3569 | 17.3222 | Risk Inputs | LiveDate
| 70 | 3.8063 | 3.6614 | 5.1282 | 4.6866 | 1.276 | 18.5585 | Plan!$G$4 | 0.32598
| 71 | 3.5565 | 2.6464 | 5.0528 | 3.6489 | 1.1125 | 16.0171 | Plan!$G$5 | 0.32584
| 72 | 4.204 | 2.3763 | 7.6088 | 4.3002 | 1.7782 | 20.2674 | Plan!$G$6 | 0.68002
| 73 | 3.9065 | 3.3722 | 6.5406 | 3.4103 | 1.3763 | 18.6059 | Plan!$G$7 | 0.53272
| 74 | 4.9054 | 2.4875 | 4.7343 | 4.2413 | 1.484 | 17.8523 | Plan!$G$8 | 0.18152
| 75 | 3.4629 | 2.5432 | 4.9795 | 3.793 | 1.3257 | 16.1043
| 76 | 3.4518 | 2.6613 | 5.1539 | 4.9642 | 1.301 | 17.5321
| 77 | 3.8012 | 3.4019 | 5.3842 | 3.8641 | 1.183 | 17.6344
| 78 | 4.0186 | 3.688 | 5.3916 | 5.3718 | 1.269 | 19.7391
| 79 | 4.4716 | 3.6371 | 4.8355 | 3.5409 | 1.361 | 17.8461
| 80 | 4.0537 | 3.1522 | 5.5201 | 5.2527 | 1.6867 | 19.6654
| 81 | 4.843 | 2.5502 | 6.1698 | 3.9009 | 1.574 | 19.038
| 82 | 4.5007 | 2.8948 | 6.7142 | 3.7478 | 1.2625 | 19.12
| 83 | 3.8139 | 2.6403 | 7.5638 | 3.6982 | 1.7249 | 19.4411
| 84 | 4.3552 | 3.2308 | 5.2646 | 3.1431 | 1.3484 | 17.3421
| 85 | 4.0067 | 3.1426 | 5.6695 | 4.2248 | 1.4413 | 18.4849
| 86 | 4.3664 | 3.2085 | 5.6242 | 4.2511 | 1.7801 | 19.2303
| 87 | 3.5027 | 2.8891 | 5.2879 | 4.2351 | 1.7052 | 17.6199
| 88 | 3.5491 | 2.739 | 5.2449 | 3.3947 | 1.4428 | 16.3705
| 89 | 3.9315 | 3.595 | 6.1107 | 3.9777 | 1.5383 | 19.1533
| 90 | 4.0975 | 2.3251 | 4.4744 | 3.3969 | 1.7703 | 16.0642
| 91 | 4.4467 | 3.2958 | 4.457 | 4.3201 | 1.6679 | 18.1875
| 92 | 3.1284 | 2.6565 | 7.4325 | 5.5098 | 1.5611 | 20.2883
| 93 | 4.1785 | 3.3732 | 4.8188 | 3.6692 | 1.9905 | 18.0302
| 94 | 4.0129 | 3.0421 | 7.373 | 3.4934 | 1.6351 | 19.5565
| 95 | 4.721 | 3.2356 | 5.1585 | 4.2114 | 1.5106 | 18.8371
| 96 | 3.3118 | 2.8209 | 5.5987 | 4.2833 | 1.4823 | 17.497
| 97 | 4.026 | 2.9794 | 5.2161 | 3.4977 | 1.8232 | 17.5424
| 98 | 4.2021 | 2.8936 | 5.2582 | 4.7822 | 1.406 | 18.5421
| 99 | 4.2723 | 2.4813 | 6.13 | 5.6791 | 1.415 | 19.9777
| 100 | 4.5302 | 2.5542 | 6.3085 | 4.5489 | 1.4899 | 19.4318
| 101 | 3.1099 | 2.7368 | 5.3101 | 4.2933 | 1.3724 | 16.8225
| 102 | 3.4567 | 3.2112 | 4.5039 | 3.5553 | 1.219 | 15.9461
| 103 | 4.1925 | 2.5572 | 6.2906 | 3.5228 | 1.5653 | 18.1285
| 104 | 4.1044 | 3.3894 | 7.3549 | 4.3955 | 1.3949 | 20.6391
| 105 | 4.0374 | 3.6124 | 5.8251 | 5.8247 | 1.1473 | 20.4468
| 106 | 4.2304 | 2.9425 | 7.6653 | 3.1985 | 1.5132 | 19.5499
| 107 | 4.5612 | 3.3129 | 6.4243 | 4.1846 | 1.6123 | 20.0953
| 108 | 3.6191 | 3.4172 | 4.7402 | 3.8783 | 1.2333 | 16.8882
| 109 | 3.4131 | 2.8439 | 4.9306 | 4.517 | 1.282 | 16.9867
| 110 | 4.8828 | 3.6867 | 5.8858 | 4.7707 | 1.6008 | 20.8267
| 111 | 4.4119 | 2.5491 | 5.44 | 4.2464 | 1.4317 | 18.0791
| 112 | 3.6843 | 2.5098 | 5.9305 | 4.0023 | 1.4706 | 17.5974
| 113 | 3.5819 | 3.4314 | 6.4752 | 3.6088 | 1.5739 | 18.6712
| 114 | 4.2752 | 3.0591 | 5.7346 | 3.4367 | 1.3932 | 17.8989
| 115 | 3.8463 | 2.8156 | 6.7952 | 4.3078 | 1.1627 | 18.9276
| 116 | 4.5869 | 3.1609 | 5.6263 | 4.0387 | 1.8455 | 19.2583
| 117 | 4.1419 | 3.0384 | 7.1404 | 4.3403 | 1.42 | 20.081
| 118 | 3.9306 | 3.3985 | 4.9004 | 3.9227 | 1.682 | 17.8341
| 119 | 4.6194 | 2.708 | 6.4437 | 5.1616 | 1.1805 | 20.1132
| 120 | 3.9169 | 2.6972 | 6.0862 | 4.7345 | 1.2907 | 18.7254
| 121 | 3.3441 | 3.4851 | 6.7848 | 4.0968 | 1.6501 | 19.3609
| 122 | 4.1933 | 3.7654 | 5.0546 | 3.7781 | 1.4633 | 18.2546
| 123 | 4.3951 | 2.5875 | 5.2531 | 3.5971 | 1.461 | 17.2938
| 124 | 4.5464 | 2.6049 | 4.3536 | 3.6872 | 1.6093 | 16.8013
| 125 | 3.5884 | 3.0987 | 4.376 | 3.3579 | 1.4491 | 15.8701
| 126 | 3.9225 | 2.6102 | 4.6005 | 3.9094 | 1.5883 | 16.6309
| 127 | 4.2328 | 2.9889 | 5.7283 | 4.1031 | 1.4984 | 18.5514
| 128 | 3.724 | 3.4199 | 4.8416 | 5.7215 | 1.3637 | 19.0708
| 129 | 4.0355 | 3.0515 | 5.1373 | 4.7262 | 1.4094 | 18.3598
| 130 | 4.2419 | 2.961 | 6.4979 | 5.4145 | 1.7529 | 20.8683
| 131 | 4.0981 | 2.4767 | 6.8782 | 3.9905 | 1.7436 | 19.1871
| 132 | 4.1715 | 3.3914 | 6.9315 | 3.405 | 1.4848 | 19.3842
| 133 | 4.558 | 3.3452 | 4.8109 | 3.4834 | 1.6807 | 17.8782
| 134 | 3.4804 | 3.0064 | 6.5361 | 4.167 | 1.3775 | 18.5674
| 135 | 3.714 | 2.9615 | 5.2838 | 3.9385 | 1.3643 | 17.2621
| 136 | 4.5782 | 2.7757 | 4.9682 | 4.6076 | 1.4512 | 18.3809
| 137 | 3.792 | 3.3592 | 4.9021 | 5.9453 | 1.362 | 19.3607
| 138 | 4.7569 | 2.976 | 6.617 | 3.6942 | 1.4243 | 19.4685
| 139 | 3.375 | 2.7851 | 6.5295 | 5.1389 | 1.4273 | 19.2558
| 140 | 3.6118 | 2.9678 | 4.5117 | 4.0445 | 1.6848 | 16.8206
| 141 | 3.3585 | 2.3897 | 6.0431 | 4.4487 | 1.4482 | 17.6882
| 142 | 4.5491 | 2.3739 | 6.1662 | 4.4952 | 1.3598 | 18.9442
| 143 | 3.8992 | 2.3774 | 4.8509 | 3.434 | 1.4452 | 16.0067
| 144 | 4.1728 | 2.4581 | 4.7488 | 4.2273 | 1.855 | 17.462
| 145 | 4.6076 | 3.6075 | 6.3822 | 3.8663 | 1.3371 | 19.8007
| 146 | 3.7409 | 2.917 | 4.9895 | 3.335 | 1.4072 | 16.3896
| 147 | 3.608 | 3.4001 | 5.0499 | 5.4078 | 1.5302 | 18.996
| 148 | 3.6087 | 3.0286 | 4.6559 | 3.3102 | 1.0904 | 15.6938
| 149 | 4.5243 | 2.4393 | 6.725 | 4.1669 | 1.5222 | 19.3776
| 150 | 4.1431 | 2.9651 | 7.1054 | 3.8985 | 1.2474 | 19.3594
| 151 | 4.1698 | 2.5987 | 4.8883 | 4.722 | 1.5591 | 17.9379
| 152 | 4.1804 | 3.2573 | 5.3243 | 4.0315 | 1.3535 | 18.147
| 153 | 4.5329 | 2.3404 | 6.6926 | 3.1866 | 1.5523 | 18.3048
| 154 | 3.6891 | 2.9481 | 4.731 | 3.9924 | 1.5806 | 16.9412
| 155 | 4.2934 | 2.6291 | 5.96 | 3.7803 | 1.2696 | 17.9324
| 156 | 3.1433 | 3.328 | 6.7344 | 4.9661 | 1.3891 | 19.561
| 157 | 3.2849 | 2.9592 | 4.9265 | 5.3975 | 1.1663 | 17.7344
| 158 | 3.751 | 3.404 | 4.8408 | 3.4462 | 1.6653 | 17.1073
| 159 | 4.6135 | 2.3859 | 6.776 | 4.177 | 1.6066 | 19.5591
| 160 | 4.4817 | 2.7864 | 7.2274 | 3.9298 | 1.4468 | 19.8721
| 161 | 3.7751 | 3.0304 | 6.3854 | 5.113 | 1.0355 | 19.3394
| 162 | 3.4005 | 3.3851 | 7.6344 | 3.8233 | 1.572 | 19.8153
| 163 | 3.8668 | 2.878 | 5.6467 | 3.3539 | 1.7685 | 17.514
| 164 | 3.7888 | 2.8747 | 6.1571 | 3.982 | 1.6081 | 18.4106
| 165 | 4.3191 | 3.0005 | 5.5089 | 4.1714 | 1.4677 | 18.4676
| 166 | 3.2477 | 2.8575 | 6.0295 | 3.3869 | 1.8523 | 17.3739
| 167 | 4.1494 | 3.6163 | 5.935 | 3.8558 | 1.3839 | 18.9405
| 168 | 3.9514 | 2.65 | 6.7038 | 3.6575 | 1.3842 | 18.3469
| 169 | 3.8724 | 2.8925 | 6.7603 | 4.5435 | 1.31 | 19.3787
| 170 | 3.7796 | 3.853 | 4.7222 | 3.7678 | 1.7304 | 17.853
| 171 | 4.6505 | 3.4102 | 5.1808 | 4.2369 | 1.8667 | 19.3452
| 172 | 4.2445 | 3.339 | 5.1099 | 4.8439 | 1.7604 | 19.2979
| 173 | 4.0866 | 3.4167 | 5.9261 | 4.8039 | 1.8795 | 20.1129
| 174 | 4.5038 | 2.7891 | 6.2841 | 3.6672 | 1.3457 | 18.5899
| 175 | 3.8288 | 2.6486 | 4.9631 | 3.7334 | 1.6939 | 16.8678
| 176 | 3.7369 | 3.6303 | 6.6027 | 3.3296 | 1.4836 | 18.7831
| 177 | 3.6995 | 2.7981 | 5.1704 | 4.906 | 1.6419 | 18.2158
| 178 | 4.256 | 2.8538 | 5.8548 | 3.5345 | 1.6216 | 18.1207
| 179 | 3.831 | 3.0696 | 6.7715 | 5.1108 | 1.3334 | 20.1162
| 180 | 3.7575 | 2.5334 | 6.1149 | 3.3817 | 1.606 | 17.3936
| 181 | 3.4853 | 3.0274 | 5.9707 | 4.8703 | 1.792 | 19.1458
| 182 | 3.9575 | 2.771 | 5.111 | 4.8619 | 1.2851 | 17.9866
| 183 | 4.2827 | 2.5938 | 5.3301 | 4.0155 | 1.4592 | 17.6812
| 184 | 4.3807 | 3.0313 | 6.5665 | 3.9887 | 1.8212 | 19.7884
| 185 | 3.739 | 2.4659 | 6.4191 | 3.2969 | 1.226 | 17.1468
| 186 | 4.4687 | 2.3935 | 5.6843 | 4.2275 | 1.8042 | 18.5782
| 187 | 3.7821 | 3.1628 | 5.5554 | 4.0881 | 1.6158 | 18.2042
| 188 | 4.1363 | 2.9463 | 7.0194 | 4.0847 | 1.4051 | 19.5918
| 189 | 3.9583 | 2.8524 | 4.4121 | 3.5274 | 1.8076 | 16.5578
| 190 | 3.6584 | 2.42 | 5.0023 | 3.2158 | 1.641 | 15.9376
| 191 | 4.5128 | 3.0367 | 4.6998 | 3.8712 | 1.2361 | 17.3565
| 192 | 3.43 | 3.1445 | 5.4986 | 4.1087 | 1.7152 | 17.8971
| 193 | 4.2126 | 3.0939 | 4.4549 | 3.8142 | 1.6111 | 17.1867
| 194 | 4.4247 | 2.8588 | 5.8141 | 4.6776 | 1.3792 | 19.1545
| 195 | 3.8053 | 2.665 | 6.1734 | 4.3598 | 1.247 | 18.2505
| 196 | 3.5473 | 3.4913 | 6.9005 | 4.0925 | 1.8706 | 19.9023
| 197 | 4.7844 | 2.4602 | 5.266 | 3.5887 | 1.4004 | 17.4997
| 198 | 4.7055 | 3.1133 | 5.1312 | 5.1324 | 1.1579 | 19.2402
| 199 | 4.1641 | 2.9273 | 4.8498 | 5.152 | 1.7069 | 18.8001
| 200 | 4.3331 | 2.8078 | 5.7496 | 3.6355 | 1.126 | 17.652
| 201 | 4.691 | 3.0726 | 5.0626 | 4.7018 | 1.466 | 18.9941
| 202 | 4.0086 | 3.2451 | 6.3971 | 3.2507 | 1.6524 | 18.5539
| 203 | 3.9022 | 2.6693 | 6.4856 | 4.739 | 1.2959 | 19.092
| 204 | 3.8026 | 2.7542 | 4.4463 | 4.6018 | 1.5774 | 17.1823
| 205 | 4.4934 | 3.0151 | 5.528 | 3.5771 | 1.3353 | 17.9488
| 206 | 4.4941 | 3.9054 | 5.0692 | 3.9714 | 1.5914 | 19.0314
| 207 | 3.5666 | 3.107 | 5.4415 | 3.9196 | 1.3186 | 17.3532
| 208 | 4.5626 | 2.6312 | 5.098 | 3.8531 | 1.2548 | 17.3998
| 209 | 4.2919 | 2.2687 | 5.8831 | 3.7038 | 1.0798 | 17.2274
| 210 | 4.6604 | 2.6533 | 5.3629 | 4.4186 | 1.6596 | 18.7548
| 211 | 4.279 | 3.1245 | 4.9284 | 4.7582 | 1.4521 | 18.5422
| 212 | 3.9475 | 3.4406 | 6.9587 | 5.081 | 1.695 | 21.1228
| 213 | 4.2644 | 2.8985 | 6.9204 | 3.4017 | 1.3816 | 18.8665
| 214 | 3.9818 | 2.5671 | 5.5235 | 3.9941 | 1.5432 | 17.6097
| 215 | 4.1061 | 2.9369 | 4.3835 | 3.4908 | 1.4163 | 16.3337
| 216 | 4.7068 | 2.6369 | 5.3686 | 4.1391 | 1.7822 | 18.6336
| 217 | 4.0782 | 3.2918 | 5.4277 | 5.2983 | 1.5306 | 19.6267
| 218 | 4.0045 | 3.7077 | 6.2612 | 4.5709 | 1.1995 | 19.7439
| 219 | 4.4011 | 2.7944 | 7.5164 | 4.8309 | 1.8571 | 21.3999
| 220 | 3.4964 | 3.2004 | 4.5199 | 5.074 | 1.471 | 17.7617
| 221 | 3.8849 | 3.4971 | 7.4222 | 3.2335 | 1.3313 | 19.3689
| 222 | 3.8445 | 3.4258 | 5.1157 | 3.9072 | 1.5084 | 17.8017
| 223 | 3.509 | 3.2222 | 4.8681 | 3.8552 | 1.4118 | 16.8664
| 224 | 3.9484 | 3.4586 | 5.8193 | 3.511 | 1.5966 | 18.3339
| 225 | 3.5388 | 3.0037 | 5.593 | 3.7518 | 1.3402 | 17.2275
| 226 | 3.745 | 3.0136 | 6.3914 | 4.8107 | 1.6169 | 19.5776
| 227 | 3.4111 | 2.9916 | 5.7948 | 5.1559 | 1.2519 | 18.6054
| 228 | 4.074 | 2.8666 | 6.3381 | 4.257 | 1.2379 | 18.7736
| 229 | 4.2618 | 3.7049 | 7.1523 | 3.6804 | 1.6322 | 20.4316
| 230 | 3.4602 | 3.7324 | 6.6633 | 4.825 | 1.2485 | 19.9294
| 231 | 3.5582 | 3.244 | 6.6889 | 3.4229 | 1.2957 | 18.2096
| 232 | 3.9189 | 3.0868 | 5.8105 | 5.1432 | 1.4957 | 19.4551
| 233 | 3.9858 | 3.1579 | 5.1998 | 3.94 | 1.6994 | 17.9829
| 234 | 4.2364 | 3.2384 | 5.6329 | 4.8137 | 1.8092 | 19.7305
| 235 | 3.6009 | 2.4619 | 5.9199 | 4.731 | 1.4177 | 18.1315
| 236 | 3.9111 | 2.9996 | 5.581 | 5.4026 | 1.2613 | 19.1557
| 237 | 3.1645 | 3.1286 | 5.6641 | 4.4081 | 1.3299 | 17.6952
| 238 | 3.6142 | 3.3824 | 7.2159 | 3.5359 | 1.2977 | 19.0461
| 239 | 3.504 | 2.5268 | 5.6998 | 3.985 | 1.3661 | 17.0817
| 240 | 4.1009 | 3.3081 | 4.5751 | 3.378 | 1.5436 | 16.9057
| 241 | 4.2736 | 3.5685 | 6.0052 | 3.5953 | 1.3188 | 18.7614
| 242 | 3.5979 | 2.1924 | 5.4254 | 3.6195 | 1.4646 | 16.2998
| 243 | 3.9091 | 3.7701 | 5.5504 | 4.372 | 1.7465 | 19.3482
| 244 | 4.4557 | 2.881 | 5.1685 | 4.4886 | 1.5982 | 18.5921
| 245 | 3.9914 | 3.1572 | 6.3228 | 3.1599 | 1.2142 | 17.8455
| 246 | 4.5416 | 3.8865 | 5.3424 | 4.4132 | 1.4995 | 19.6832
| 247 | 4.2262 | 3.4225 | 5.3492 | 3.7444 | 1.8425 | 18.5849
| 248 | 4.0605 | 2.9073 | 4.4917 | 4.9588 | 1.5874 | 18.0057
| 249 | 4.1087 | 3.0894 | 4.5469 | 3.8482 | 1.2232 | 16.8163
| 250 | 3.472 | 2.5286 | 4.7192 | 3.4884 | 1.5352 | 15.7433
| 251 | 4.7285 | 2.8417 | 6.2734 | 3.9486 | 1.5337 | 19.3259
| 252 | 3.7202 | 3.005 | 5.1649 | 5.5926 | 1.3452 | 18.8278
| 253 | 4.1129 | 2.492 | 5.8872 | 3.7909 | 1.102 | 17.385
| 254 | 4.1158 | 3.8728 | 5.1206 | 4.403 | 1.6696 | 19.1819
| 255 | 4.5285 | 2.9258 | 5.4002 | 4.1356 | 1.4587 | 18.4488
| 256 | 3.5932 | 3.2149 | 6.4696 | 4.7204 | 1.6047 | 19.6029
| 257 | 3.2977 | 2.9936 | 5.135 | 3.7955 | 1.6704 | 16.8922
| 258 | 4.04 | 3.1027 | 5.4154 | 3.3273 | 1.5501 | 17.4354
| 259 | 3.4032 | 2.4992 | 4.914 | 3.7238 | 1.2248 | 15.7649
| 260 | 3.6827 | 3.2333 | 5.4232 | 3.4254 | 1.741 | 17.5056
| 261 | 4.6415 | 3.1434 | 6.6757 | 4.0907 | 1.1549 | 19.7062
| 262 | 4.799 | 2.8737 | 5.2602 | 4.0215 | 1.6379 | 18.5922
| 263 | 3.267 | 3.4696 | 4.5485 | 4.2162 | 1.4463 | 16.9476
| 264 | 4.5999 | 3.0224 | 5.8605 | 3.6708 | 1.495 | 18.6486
| 265 | 3.7009 | 2.3159 | 5.2045 | 3.5213 | 1.4142 | 16.1568
| 266 | 4.3105 | 2.6004 | 6.9212 | 4.0944 | 1.1286 | 19.0552
| 267 | 4.0391 | 3.5364 | 4.7041 | 4.0723 | 1.6097 | 17.9616
| 268 | 3.8129 | 2.4845 | 4.9325 | 3.4926 | 1.3954 | 16.1179
| 269 | 4.4426 | 2.9089 | 5.7778 | 3.5372 | 1.2811 | 17.9475
| 270 | 3.8323 | 3.4122 | 5.4337 | 3.5255 | 1.9614 | 18.165
| 271 | 3.7078 | 3.2205 | 7.1283 | 3.5004 | 1.3707 | 18.9278
| 272 | 3.9067 | 3.7019 | 6.1898 | 3.8197 | 1.4971 | 19.1152
| 273 | 4.0623 | 2.5782 | 4.4208 | 4.0066 | 1.5467 | 16.6147
| 274 | 3.8021 | 3.4376 | 4.62 | 3.6587 | 1.7216 | 17.24
| 275 | 3.6057 | 2.2044 | 5.9396 | 4.1911 | 1.3431 | 17.2838
| 276 | 3.5906 | 3.0124 | 4.4399 | 3.839 | 1.4357 | 16.3176
| 277 | 4.1872 | 2.821 | 6.7898 | 3.86 | 1.2586 | 18.9167
| 278 | 4.1301 | 2.8995 | 7.1156 | 4.1246 | 1.5932 | 19.863
| 279 | 3.2624 | 3.0624 | 4.9848 | 3.4615 | 1.664 | 16.4351
| 280 | 4.1072 | 2.5381 | 6.121 | 3.7733 | 1.4602 | 17.9997
| 281 | 3.9503 | 2.9967 | 4.7983 | 5.1916 | 1.2066 | 18.1434
| 282 | 4.457 | 3.6716 | 6.1511 | 4.0374 | 1.7228 | 20.0398
| 283 | 4.6962 | 3.0799 | 7.4817 | 5.2309 | 1.6933 | 22.182
| 284 | 4.8654 | 3.1768 | 5.9079 | 4.0767 | 1.7519 | 19.7787
| 285 | 4.4319 | 2.6184 | 7.2711 | 3.663 | 1.827 | 19.8114
| 286 | 3.3301 | 2.9634 | 4.8723 | 4.0597 | 1.2114 | 16.4368
| 287 | 4.5209 | 2.5207 | 4.8818 | 4.2775 | 1.4012 | 17.6021
| 288 | 3.5156 | 3.4812 | 5.4139 | 4.3027 | 1.7562 | 18.4696
| 289 | 4.0093 | 2.9388 | 5.1939 | 4.6266 | 1.4035 | 18.1722
| 290 | 4.3441 | 3.4484 | 5.7992 | 5.2729 | 1.7748 | 20.6394
| 291 | 4.0681 | 3.0439 | 5.8753 | 3.2367 | 1.4714 | 17.6954
| 292 | 4.6522 | 3.0055 | 5.8686 | 4.5077 | 1.2452 | 19.2793
| 293 | 3.357 | 3.2772 | 5.636 | 3.6059 | 1.333 | 17.209
| 294 | 3.4659 | 3.3519 | 5.4578 | 3.5443 | 1.9366 | 17.7564
| 295 | 4.1189 | 2.8141 | 4.5287 | 5.4309 | 1.5093 | 18.4019
| 296 | 3.4286 | 3.4637 | 4.3024 | 4.547 | 1.6986 | 17.4403
| 297 | 4.6178 | 2.6027 | 5.2392 | 4.4546 | 1.3719 | 18.2862
| 298 | 4.2577 | 2.5653 | 5.7388 | 3.7045 | 1.5568 | 17.8231
| 299 | 3.2356 | 3.2074 | 5.9168 | 4.1708 | 1.6017 | 18.1322
| 300 | 4.3174 | 3.7499 | 6.9612 | 3.2228 | 1.6723 | 19.9237
| 301 | 3.7798 | 3.0999 | 6.4576 | 5.6729 | 1.6709 | 20.681
| 302 | 3.9861 | 3.3867 | 5.8526 | 4.1883 | 1.4741 | 18.8879
| 303 | 3.5789 | 3.6955 | 5.6932 | 3.4577 | 1.7238 | 18.1491
| 304 | 4.4771 | 2.9514 | 5.1823 | 4.074 | 1.6636 | 18.3484
| 305 | 3.6533 | 2.4505 | 4.9472 | 5.3585 | 1.8144 | 18.224
| 306 | 3.5623 | 3.3236 | 6.0615 | 3.3915 | 1.3911 | 17.7299
| 307 | 3.7636 | 3.5573 | 5.0242 | 3.7819 | 1.6312 | 17.7583
| 308 | 3.8938 | 3.2488 | 6.4495 | 4.8669 | 1.7274 | 20.1864
| 309 | 3.5864 | 2.3906 | 6.6621 | 3.3754 | 1.3362 | 17.3508
| 310 | 3.9403 | 3.4282 | 5.1184 | 4.3426 | 1.5073 | 18.3368
| 311 | 4.2702 | 3.0153 | 4.6716 | 5.5499 | 1.3734 | 18.8804
| 312 | 4.194 | 2.763 | 5.5615 | 3.3388 | 1.16 | 17.0172
| 313 | 3.9799 | 2.6525 | 4.9461 | 5.4521 | 1.3927 | 18.4233
| 314 | 3.7737 | 2.7989 | 6.3897 | 3.5512 | 1.8177 | 18.3313
| 315 | 4.4022 | 3.1176 | 7.2989 | 4.5578 | 1.8249 | 21.2015
| 316 | 3.6813 | 2.7656 | 4.6912 | 3.6852 | 1.4865 | 16.3099
| 317 | 4.0274 | 3.1095 | 6.4279 | 4.4334 | 1.8116 | 19.8098
| 318 | 4.5524 | 3.3572 | 5.2902 | 3.6303 | 1.6386 | 18.4687
| 319 | 3.384 | 2.0869 | 5.9964 | 3.0588 | 1.5962 | 16.1222
| 320 | 3.642 | 2.1644 | 5.6069 | 4.1121 | 1.3019 | 16.8272
| 321 | 3.4939 | 3.3459 | 5.4682 | 3.8735 | 1.8985 | 18.0799
| 322 | 4.5646 | 3.6326 | 6.2504 | 5.3085 | 1.5003 | 21.2564
| 323 | 3.3177 | 3.2054 | 4.7076 | 3.3596 | 1.5272 | 16.1175
| 324 | 4.3793 | 3.5733 | 6.0189 | 4.1002 | 1.4383 | 19.51
| 325 | 4.0698 | 3.5953 | 4.8927 | 3.3033 | 1.4308 | 17.2918
| 326 | 4.0557 | 3.0817 | 4.6664 | 3.6016 | 1.067 | 16.4724
| 327 | 4.0496 | 2.8652 | 4.7955 | 3.2706 | 1.1561 | 16.137
| 328 | 3.0845 | 3.1707 | 5.0876 | 3.2065 | 1.3507 | 15.9
| 329 | 3.8483 | 2.9222 | 5.8394 | 4.8339 | 1.5853 | 19.029
| 330 | 3.9974 | 2.7559 | 4.136 | 4.3164 | 1.152 | 16.3577
| 331 | 3.5006 | 2.3994 | 6.3266 | 4.0864 | 1.2646 | 17.5776
| 332 | 4.2839 | 2.8973 | 5.7117 | 3.4484 | 1.5242 | 17.8655
| 333 | 4.3467 | 2.9665 | 4.8969 | 4.4163 | 1.45 | 18.0764
| 334 | 3.6563 | 3.2504 | 4.9359 | 4.7616 | 1.7115 | 18.3157
| 335 | 4.1591 | 3.9278 | 5.0192 | 4.6167 | 1.6197 | 19.3426
| 336 | 3.8243 | 3.1066 | 6.5007 | 4.3459 | 1.4904 | 19.2679
| 337 | 3.5441 | 2.6735 | 5.8958 | 3.7233 | 1.3964 | 17.2332
| 338 | 4.5913 | 3.1821 | 6.4065 | 4.3262 | 1.4535 | 19.9595
| 339 | 4.2379 | 2.0104 | 4.8237 | 4.2682 | 1.4745 | 16.8146
| 340 | 4.6262 | 2.9278 | 6.4614 | 4.5118 | 1.4014 | 19.9286
| 341 | 3.8755 | 3.4209 | 5.8212 | 3.7204 | 1.7888 | 18.6269
| 342 | 4.3389 | 3.2245 | 7.0003 | 4.8991 | 1.4814 | 20.9441
| 343 | 4.1105 | 3.1648 | 4.3297 | 5.7806 | 1.8316 | 19.2171
| 344 | 4.4631 | 3.2259 | 7.1778 | 4.3119 | 1.4803 | 20.659
| 345 | 4.4733 | 2.2654 | 6.8058 | 3.4165 | 1.6555 | 18.6165
| 346 | 3.719 | 3.5828 | 5.6324 | 3.4128 | 1.4656 | 17.8128
| 347 | 3.7498 | 3.4552 | 5.1563 | 3.9756 | 1.7134 | 18.0504
| 348 | 4.4158 | 2.1457 | 5.2708 | 4.2755 | 1.7479 | 17.8558
| 349 | 4.2101 | 2.6668 | 5.4735 | 5.2579 | 1.3027 | 18.911
| 350 | 3.709 | 3.1353 | 6.9772 | 3.0067 | 1.0407 | 17.869
| 351 | 3.8902 | 2.7952 | 4.7148 | 4.8894 | 1.513 | 17.8025
| 352 | 4.3076 | 2.9057 | 5.1442 | 4.5205 | 1.5911 | 18.4691
| 353 | 4.0595 | 2.8637 | 6.6677 | 3.9489 | 1.5949 | 19.1348
| 354 | 3.5353 | 2.8697 | 5.5523 | 4.8942 | 1.8602 | 18.7116
| 355 | 3.4174 | 2.6555 | 5.2504 | 4 | 1.6389 | 16.9622
| 356 | 4.5082 | 2.971 | 7.4544 | 5.0603 | 1.3142 | 21.3081
| 357 | 4.0671 | 3.1407 | 6.9118 | 5.4927 | 1.41 | 21.0221
| 358 | 3.6911 | 2.4117 | 6.7056 | 4.5391 | 1.8418 | 19.1893
| 359 | 4.0726 | 3.6535 | 5.648 | 4.9135 | 1.5204 | 19.808
| 360 | 3.9614 | 3.349 | 6.3583 | 4.2893 | 1.4558 | 19.4138
| 361 | 3.8517 | 3.4664 | 4.848 | 3.4434 | 1.4564 | 17.0658
| 362 | 4.4336 | 2.745 | 6.5547 | 4.3976 | 1.0528 | 19.1837
| 363 | 3.9102 | 3.7979 | 7.1908 | 4.1976 | 1.3232 | 20.4197
| 364 | 3.3158 | 3.1702 | 6.0696 | 3.8589 | 1.8375 | 18.2521
| 365 | 3.1849 | 3.1976 | 4.5368 | 5.049 | 1.505 | 17.4733
| 366 | 4.2608 | 3.2877 | 5.8645 | 4.427 | 1.4242 | 19.2642
| 367 | 4.3517 | 2.5474 | 6.1758 | 3.8372 | 1.8766 | 18.7888
| 368 | 3.8979 | 3.5913 | 6.3664 | 5.2409 | 1.7833 | 20.8798
| 369 | 4.2504 | 2.8866 | 5.0082 | 4.1825 | 1.3551 | 17.6828
| 370 | 4.2476 | 2.3064 | 6.6341 | 5.2955 | 1.5007 | 19.9843
| 371 | 4.3278 | 3.0073 | 4.7587 | 3.2152 | 1.4756 | 16.7846
| 372 | 3.9559 | 2.4907 | 4.8042 | 3.1654 | 1.6922 | 16.1083
| 373 | 4.6852 | 2.7343 | 4.1647 | 5.3511 | 1.5152 | 18.4505
| 374 | 4.3571 | 2.6424 | 5.0326 | 4.4617 | 1.4258 | 17.9197
| 375 | 4.3099 | 2.8358 | 5.1465 | 3.8258 | 1.4396 | 17.5575
| 376 | 3.733 | 3.2618 | 6.8751 | 5.0325 | 1.4178 | 20.3202
| 377 | 3.6044 | 2.8352 | 5.8333 | 4.7135 | 1.1153 | 18.1018
| 378 | 4.2518 | 3.2568 | 7.0293 | 5.628 | 1.7077 | 21.8736
| 379 | 4.223 | 2.7429 | 5.4844 | 4.7555 | 1.2675 | 18.4733
| 380 | 4.3782 | 3.0162 | 5.106 | 5.4964 | 1.3652 | 19.362
| 381 | 4.3224 | 3.2294 | 6.5094 | 4.6899 | 1.2024 | 19.9534
| 382 | 3.9901 | 2.9037 | 6.0552 | 5.1054 | 1.5318 | 19.5861
| 383 | 4.6019 | 2.6856 | 6.0501 | 3.4653 | 1.1418 | 17.9447
| 384 | 3.9244 | 3.4759 | 4.976 | 3.3989 | 1.457 | 17.2322
| 385 | 3.7583 | 2.2602 | 5.8425 | 4.0622 | 1.5646 | 17.4878
| 386 | 4.2225 | 2.8804 | 5.5746 | 3.3 | 1.6613 | 17.6388
| 387 | 3.8373 | 2.3695 | 6.3447 | 3.2039 | 1.3238 | 17.0792
| 388 | 4.287 | 2.3635 | 5.6662 | 3.9973 | 1.5622 | 17.8762
| 389 | 4.1905 | 3.4842 | 5.1645 | 4.3767 | 1.7966 | 19.0125
| 390 | 3.8299 | 3.0371 | 4.8647 | 3.462 | 1.4579 | 16.6516
| 391 | 3.8772 | 2.8545 | 7.7533 | 4.9037 | 1.4819 | 20.8706
| 392 | 3.4343 | 2.4836 | 6.0329 | 4.1011 | 1.4784 | 17.5304
| 393 | 4.0335 | 2.9859 | 5.369 | 5.0458 | 1.2779 | 18.7121
| 394 | 3.5689 | 2.5152 | 5.6168 | 4.6532 | 1.3867 | 17.7408
| 395 | 3.9709 | 3.0725 | 5.3788 | 3.6147 | 1.5714 | 17.6082
| 396 | 4.6377 | 3.8095 | 4.7275 | 4.9424 | 1.2795 | 19.3966
| 397 | 4.3682 | 2.7148 | 4.5527 | 3.7201 | 1.5988 | 16.9546
| 398 | 4.6123 | 3.0475 | 7.5576 | 3.6276 | 1.355 | 20.2
| 399 | 4.5961 | 3.5408 | 5.1235 | 3.2304 | 1.531 | 18.0217
| 400 | 4.0533 | 3.5607 | 6.2659 | 4.5802 | 1.6366 | 20.0967
| 401 | 3.9654 | 2.2945 | 4.6434 | 5.0028 | 1.8159 | 17.722
| 402 | 3.3891 | 3.3551 | 5.3967 | 4.0121 | 1.2367 | 17.3897
| 403 | 4.1219 | 2.91 | 5.195 | 4.5007 | 1.6761 | 18.4037
| 404 | 4.4996 | 2.9293 | 5.0428 | 3.9655 | 1.5061 | 17.9432
| 405 | 4.4904 | 2.0548 | 5.4959 | 4.9881 | 1.541 | 18.5701
| 406 | 3.7176 | 3.333 | 4.4496 | 3.1488 | 1.4417 | 16.0907
| 407 | 4.2307 | 3.6824 | 5.5416 | 4.599 | 1.5756 | 19.6291
| 408 | 4.3503 | 2.9921 | 5.2259 | 3.7291 | 1.6484 | 17.9459
| 409 | 3.1186 | 2.9594 | 4.7437 | 4.8796 | 1.6486 | 17.35
| 410 | 3.0429 | 3.6641 | 5.6205 | 5.3925 | 1.5375 | 19.2576
| 411 | 4.8048 | 2.5026 | 6.3612 | 3.3403 | 1.2008 | 18.2098
| 412 | 4.0248 | 3.083 | 6.7399 | 3.2885 | 1.0619 | 18.1981
| 413 | 3.5729 | 3.2521 | 4.636 | 4.5143 | 1.7998 | 17.7751
| 414 | 4.0073 | 2.8457 | 6.9473 | 4.1284 | 1.7421 | 19.6707
| 415 | 3.9265 | 3.0635 | 5.0405 | 4.7437 | 1.4446 | 18.2187
| 416 | 4.0847 | 3.6195 | 6.2221 | 3.4699 | 1.5922 | 18.9883
| 417 | 3.4381 | 2.0925 | 6.7609 | 3.8363 | 1.8854 | 18.0132
| 418 | 4.1566 | 2.3802 | 4.7728 | 4.6607 | 1.6668 | 17.637
| 419 | 3.4386 | 3.8114 | 4.8072 | 3.3255 | 1.397 | 16.7796
| 420 | 4.4231 | 2.5126 | 6.0883 | 3.6407 | 1.3743 | 18.039
| 421 | 3.4615 | 2.8413 | 7.1816 | 5.4617 | 1.5113 | 20.4574
| 422 | 3.294 | 2.7034 | 6.077 | 3.6655 | 1.3355 | 17.0753
| 423 | 4.2027 | 3.8201 | 6.1503 | 3.7895 | 1.475 | 19.4377
| 424 | 4.6697 | 3.5528 | 4.878 | 4.1374 | 1.5144 | 18.7523
| 425 | 4.0486 | 3.3002 | 4.5677 | 3.4223 | 1.6293 | 16.9681
| 426 | 3.7335 | 3.0914 | 4.7674 | 3.8896 | 1.6788 | 17.1607
| 427 | 3.8577 | 2.2238 | 4.3043 | 4.0257 | 1.8639 | 16.2755
| 428 | 3.2932 | 2.5552 | 5.9536 | 3.9594 | 1.4 | 17.1614
| 429 | 4.4587 | 2.6449 | 6.1273 | 5.6039 | 1.6336 | 20.4685
| 430 | 4.4411 | 2.5251 | 4.821 | 4.6057 | 1.5098 | 17.9027
| 431 | 3.4481 | 2.4952 | 6.2345 | 5.151 | 1.1 | 18.4287
| 432 | 4.5896 | 3.1495 | 6.1465 | 5.1873 | 1.6566 | 20.7295
| 433 | 3.5264 | 3.1223 | 5.0872 | 4.3668 | 1.2666 | 17.3693
| 434 | 3.5516 | 2.7512 | 6.2883 | 5.8369 | 1.4542 | 19.8823
| 435 | 4.4787 | 2.1301 | 4.6634 | 4.5768 | 1.6881 | 17.5371
| 436 | 4.7376 | 3.5856 | 6.185 | 3.8306 | 1.6743 | 20.0131
| 437 | 4.7177 | 3.3695 | 5.419 | 4.2089 | 1.8437 | 19.5587
| 438 | 4.2356 | 3.3606 | 4.9607 | 3.6158 | 1.3407 | 17.5133
| 439 | 4.2882 | 3.3032 | 5.3907 | 4.4985 | 1.7757 | 19.2564
| 440 | 4.542 | 3.1535 | 4.8703 | 4.0802 | 1.5138 | 18.1599
| 441 | 4.1672 | 3.1377 | 7.7944 | 3.6248 | 1.5371 | 20.2612
| 442 | 4.3033 | 3.2896 | 6.1394 | 3.431 | 1.1348 | 18.298
| 443 | 3.3045 | 3.2998 | 4.3741 | 4.0541 | 1.8898 | 16.9222
| 444 | 4.2992 | 2.3182 | 7.1635 | 4.1207 | 1.074 | 18.9757
| 445 | 4.6724 | 3.3524 | 5.3739 | 3.8826 | 1.321 | 18.6022
| 446 | 3.7285 | 2.8329 | 5.2956 | 4.788 | 1.3524 | 17.9974
| 447 | 4.5081 | 3.151 | 4.6755 | 5.0366 | 1.4332 | 18.8044
| 448 | 3.9632 | 2.7012 | 4.6943 | 4.9929 | 1.5651 | 17.9167
| 449 | 3.1772 | 2.2557 | 6.4409 | 3.652 | 1.4185 | 16.9443
| 450 | 3.6152 | 3.0932 | 5.5335 | 3.1846 | 1.3096 | 16.7361
| 451 | 3.5327 | 2.9153 | 7.0463 | 3.4885 | 1.5722 | 18.5551
| 452 | 3.9446 | 3.7586 | 4.6109 | 3.8334 | 1.4477 | 17.5951
| 453 | 4.0684 | 2.4022 | 5.41 | 3.8933 | 1.3271 | 17.101
| 454 | 4.1439 | 3.0418 | 5.8464 | 3.497 | 1.2555 | 17.7845
| 455 | 3.6939 | 3.5552 | 5.881 | 3.9527 | 1.2601 | 18.3427
| 456 | 4.2211 | 3.2931 | 4.8548 | 3.57 | 1.6538 | 17.5928
| 457 | 4.0177 | 3.6666 | 5.1266 | 4.3312 | 1.5797 | 18.7218
| 458 | 4.109 | 3.25 | 5.243 | 5.345 | 1.5732 | 19.5201
| 459 | 4.4511 | 2.9449 | 4.2446 | 3.5198 | 1.6512 | 16.8116
| 460 | 3.7689 | 3.5833 | 7.2554 | 3.4666 | 1.3465 | 19.4206
| 461 | 4.0291 | 2.84 | 5.211 | 4.8852 | 1.2871 | 18.2524
| 462 | 3.8258 | 2.2452 | 5.7066 | 4.2944 | 1.3264 | 17.3984
| 463 | 4.0057 | 2.95 | 4.9111 | 3.6737 | 1.2892 | 16.8297
| 464 | 4.6236 | 2.4645 | 6.2164 | 5.224 | 1.3783 | 19.9069
| 465 | 4.1208 | 3.5641 | 5.6032 | 4.5845 | 1.4598 | 19.3324
| 466 | 4.3989 | 3.6494 | 5.8275 | 4.0247 | 1.8746 | 19.775
| 467 | 4.3893 | 2.8264 | 5.3869 | 3.7075 | 1.3035 | 17.6136
| 468 | 3.7664 | 2.5231 | 6.8845 | 4.1527 | 1.425 | 18.7517
| 469 | 4.847 | 3.445 | 7.3378 | 3.8508 | 1.6623 | 21.1429
| 470 | 4.4067 | 3.3537 | 6.0356 | 3.9417 | 1.3053 | 19.0429
| 471 | 4.3445 | 3.0551 | 6.7203 | 3.7687 | 1.6733 | 19.5619
| 472 | 4.2457 | 2.3281 | 4.6163 | 4.3519 | 1.6002 | 17.1423
| 473 | 4.19 | 2.9533 | 5.5862 | 4.4457 | 1.5161 | 18.6913
| 474 | 4.0429 | 3.3255 | 5.7298 | 3.5137 | 1.4775 | 18.0893
| 475 | 4.0445 | 2.9132 | 5.5588 | 4.5284 | 1.4798 | 18.5247
| 476 | 3.8502 | 3.5802 | 6.6215 | 4.7985 | 1.7008 | 20.5512
| 477 | 4.5194 | 2.207 | 7.0675 | 5.645 | 1.4124 | 20.8514
| 478 | 3.866 | 3.6131 | 7.5358 | 4.0348 | 1.3392 | 20.3889
| 479 | 4.2768 | 2.5968 | 4.7475 | 3.995 | 1.5213 | 17.1374
| 480 | 4.2285 | 3.2419 | 6.5623 | 3.7145 | 1.4768 | 19.224
| 481 | 4.5547 | 3.2858 | 6.1017 | 4.8384 | 1.8345 | 20.6151
| 482 | 4.7604 | 3.3206 | 6.5197 | 4.6831 | 1.8566 | 21.1404
| 483 | 4.4394 | 2.2143 | 5.297 | 3.8947 | 1.9699 | 17.8152
| 484 | 4.1968 | 3.2092 | 4.3962 | 5.6362 | 1.3499 | 18.7884
| 485 | 3.9344 | 3.0025 | 6.5503 | 4.393 | 1.1511 | 19.0314
| 486 | 3.6443 | 3.3106 | 5.9274 | 5.079 | 1.4106 | 19.3719
| 487 | 4.163 | 2.7288 | 5.7238 | 4.1429 | 1.2093 | 17.9678
| 488 | 4.1763 | 2.7578 | 5.4298 | 4.1501 | 1.6798 | 18.1939
| 489 | 3.8437 | 3.0706 | 4.3684 | 4.6338 | 1.5555 | 17.472
| 490 | 4.3246 | 2.9693 | 6.8707 | 3.4038 | 1.5812 | 19.1497
| 491 | 3.8923 | 2.5623 | 6.0209 | 4.3368 | 1.1166 | 17.9288
| 492 | 3.7154 | 3.3618 | 4.9439 | 4.0962 | 1.5563 | 17.6737
| 493 | 3.8648 | 2.8331 | 6.8558 | 4.0819 | 1.5618 | 19.1974
| 494 | 3.9369 | 2.8169 | 5.382 | 4.4065 | 1.5286 | 18.071
| 495 | 3.6235 | 2.3618 | 5.6796 | 3.5811 | 1.4606 | 16.7065
| 496 | 4.201 | 3.4513 | 5.6632 | 4.0292 | 1.369 | 18.7137
| 497 | 4.6469 | 3.5006 | 4.9417 | 4.5426 | 1.503 | 19.1349
| 498 | 4.0218 | 3.6036 | 7.8778 | 5.1695 | 1.5671 | 22.2398
| 499 | 3.9835 | 3.2367 | 5.9517 | 5.5147 | 1.6072 | 20.2939
| 500 | 4.0473 | 3.132 | 5.4357 | 4.6453 | 1.8086 | 19.069
| 501 | 4.4289 | 2.7879 | 7.6885 | 3.6472 | 1.7095 | 20.262
| 502 | 4.3485 | 3.4097 | 4.6171 | 4.0652 | 1.6854 | 18.126
| 503 | 3.8922 | 2.9827 | 6.4359 | 4.4249 | 1.7155 | 19.4512
| 504 | 3.587 | 3.197 | 5.4431 | 3.8816 | 1.6825 | 17.7912
| 505 | 4.7122 | 2.7536 | 4.6609 | 4.6747 | 1.9312 | 18.7325
| 506 | 3.9206 | 3.6537 | 4.5778 | 5.5184 | 1.5038 | 19.1742
| 507 | 3.5771 | 3.337 | 6.6254 | 4.9481 | 1.734 | 20.2217
| 508 | 3.7418 | 3.4495 | 4.651 | 4.9744 | 1.9286 | 18.7453
| 509 | 4.1989 | 3.7525 | 4.5222 | 5.6539 | 1.3588 | 19.4863
| 510 | 4.1171 | 2.9564 | 5.7179 | 4.487 | 1.59 | 18.8685
| 511 | 3.5838 | 3.3147 | 5.1175 | 3.944 | 1.6564 | 17.6165
| 512 | 4.4753 | 2.9971 | 6.8441 | 5.1026 | 1.2099 | 20.629
| 513 | 4.0036 | 2.7103 | 6.5453 | 4.2815 | 1.4505 | 18.9912
| 514 | 4.1264 | 3.5193 | 4.8746 | 3.44 | 1.4967 | 17.457
| 515 | 4.1135 | 2.9897 | 5.3212 | 4.5047 | 1.3615 | 18.2906
| 516 | 4.18 | 2.9729 | 6.2008 | 4.7277 | 1.6039 | 19.6853
| 517 | 3.9961 | 2.7267 | 5.2804 | 5.7365 | 1.465 | 19.2047
| 518 | 4.0409 | 2.2722 | 5.1395 | 3.6138 | 1.7265 | 16.793
| 519 | 3.3957 | 2.416 | 5.028 | 4.4722 | 1.7584 | 17.0703
| 520 | 4.4345 | 3.2652 | 5.2812 | 3.904 | 1.3437 | 18.2286
| 521 | 3.9705 | 3.3875 | 4.955 | 5.0877 | 1.57 | 18.9706
| 522 | 4.5828 | 3.1852 | 6.2074 | 3.3173 | 1.6466 | 18.9393
| 523 | 4.1537 | 3.1764 | 5.3458 | 3.3081 | 1.1705 | 17.1544
| 524 | 4.3256 | 3.2705 | 4.2654 | 4.2055 | 1.2389 | 17.3059
| 525 | 3.7479 | 3.127 | 4.3889 | 3.6295 | 1.6803 | 16.5736
| 526 | 4.131 | 3.5078 | 4.4775 | 4.1737 | 1.1876 | 17.4777
| 527 | 4.6991 | 2.4792 | 5.0598 | 3.4855 | 1.408 | 17.1316
| 528 | 4.0826 | 3.1042 | 5.0321 | 3.5787 | 1.5177 | 17.3153
| 529 | 4.6672 | 3.4999 | 5.5957 | 3.8883 | 1.5802 | 19.2313
| 530 | 3.879 | 2.2339 | 5.4532 | 4.2705 | 1.4506 | 17.2871
| 531 | 4.593 | 3.6252 | 4.9809 | 3.4358 | 1.5534 | 18.1883
| 532 | 3.976 | 3.1341 | 4.6866 | 4.716 | 1.518 | 18.0307
| 533 | 4.1542 | 3.239 | 4.89 | 4.9082 | 1.621 | 18.8124
| 534 | 4.2082 | 2.7259 | 4.9094 | 3.7504 | 1.487 | 17.0809
| 535 | 4.6589 | 3.1101 | 4.7405 | 4.8376 | 1.678 | 19.0252
| 536 | 3.935 | 3.216 | 5.8289 | 4.5246 | 1.524 | 19.0286
| 537 | 4.1821 | 3.1594 | 4.4959 | 3.5895 | 1.5291 | 16.956
| 538 | 3.5809 | 3.2016 | 5.0673 | 3.9019 | 1.5296 | 17.2813
| 539 | 3.8865 | 3.3951 | 7.0566 | 3.4775 | 1.2505 | 19.0662
| 540 | 4.1358 | 2.8003 | 5.1308 | 3.7763 | 1.4809 | 17.324
| 541 | 4.0016 | 3.0332 | 7.0217 | 4.6571 | 1.5219 | 20.2355
| 542 | 4.8982 | 2.5609 | 6.8623 | 4.0035 | 1.455 | 19.7799
| 543 | 3.9677 | 2.9944 | 4.2738 | 3.307 | 1.4293 | 15.9722
| 544 | 4.4264 | 2.9354 | 6.9687 | 5.0563 | 1.4381 | 20.825
| 545 | 4.0613 | 2.5603 | 5.7731 | 3.3523 | 1.4019 | 17.149
| 546 | 4.8377 | 2.4067 | 4.5429 | 3.4079 | 1.696 | 16.8912
| 547 | 3.2293 | 2.8175 | 4.9185 | 5.5587 | 1.5451 | 18.0691
| 548 | 4.5109 | 3.0444 | 4.1762 | 3.8845 | 1.7669 | 17.3829
| 549 | 4.7715 | 3.3763 | 5.4722 | 5.3368 | 1.3901 | 20.3468
| 550 | 4.3008 | 3.3755 | 4.83 | 3.7009 | 1.5325 | 17.7396
| 551 | 3.6216 | 3.6364 | 5.0224 | 3.4387 | 1.5014 | 17.2206
| 552 | 3.7381 | 3.4622 | 5.1355 | 3.9802 | 1.4913 | 17.8074
| 553 | 4.1856 | 3.5257 | 5.5242 | 4.0467 | 1.6688 | 18.9511
| 554 | 4.1621 | 2.6794 | 5.3594 | 3.0975 | 1.2348 | 16.5331
| 555 | 3.3916 | 3.4432 | 7.7711 | 4.2592 | 1.5365 | 20.4016
| 556 | 3.4091 | 2.9054 | 6.5815 | 3.5326 | 1.1433 | 17.5719
| 557 | 3.8414 | 2.6998 | 5.6736 | 3.6641 | 1.3571 | 17.2359
| 558 | 3.8701 | 2.9808 | 5.659 | 5.3024 | 1.6251 | 19.4372
| 559 | 4.2596 | 2.8857 | 5.6445 | 4.2631 | 1.6144 | 18.6672
| 560 | 4.4634 | 3.849 | 6.5779 | 3.1544 | 1.5698 | 19.6145
| 561 | 3.9756 | 3.0186 | 5.357 | 3.6921 | 1.8267 | 17.8701
| 562 | 3.7838 | 3.5314 | 5.5889 | 4.6496 | 1.5464 | 19.1001
| 563 | 4.6288 | 2.7927 | 5.7092 | 3.642 | 1.3118 | 18.0845
| 564 | 3.3816 | 2.346 | 5.5002 | 4.8547 | 1.5057 | 17.5882
| 565 | 3.8607 | 2.7836 | 6.589 | 5.4564 | 1.5442 | 20.2338
| 566 | 4.545 | 3.7271 | 6.2775 | 3.7802 | 1.5208 | 19.8506
| 567 | 3.3214 | 2.8491 | 5.7638 | 3.2931 | 1.7204 | 16.9478
| 568 | 3.7224 | 3.3184 | 5.8053 | 4.493 | 1.4938 | 18.833
| 569 | 4.0798 | 3.1918 | 5.2331 | 3.5645 | 1.4683 | 17.5376
| 570 | 3.3071 | 3.4953 | 6.6798 | 4.8504 | 1.7547 | 20.0872
| 571 | 3.3614 | 2.9551 | 5.6546 | 4.2539 | 1.5079 | 17.733
| 572 | 4.1961 | 3.0104 | 5.3144 | 5.1237 | 1.2945 | 18.9391
| 573 | 4.7011 | 3.1374 | 5.2059 | 5.7934 | 1.5418 | 20.3796
| 574 | 3.3477 | 2.1968 | 4.1538 | 3.3615 | 1.3991 | 14.4589
| 575 | 3.4451 | 2.6779 | 4.9907 | 5.2115 | 1.7171 | 18.0423
| 576 | 3.199 | 2.9846 | 5.1757 | 3.9569 | 1.7442 | 17.0604
| 577 | 3.6332 | 3.1476 | 6.9912 | 5.4221 | 1.3343 | 20.5284
| 578 | 4.4303 | 2.8373 | 4.7107 | 3.699 | 1.5863 | 17.2636
| 579 | 3.3422 | 3.7183 | 6.833 | 3.5677 | 1.6252 | 19.0865
| 580 | 3.9544 | 3.0267 | 5.0901 | 3.6336 | 1.3605 | 17.0653
| 581 | 4.0878 | 3.213 | 7.094 | 4.934 | 1.1582 | 20.4869
| 582 | 4.241 | 3.2867 | 4.5171 | 4.9449 | 1.5939 | 18.5835
| 583 | 3.8386 | 2.6407 | 7.0724 | 3.8502 | 1.5273 | 18.9292
| 584 | 3.5621 | 2.8136 | 7.3514 | 3.4431 | 1.8012 | 18.9713
| 585 | 3.7015 | 2.8114 | 5.0926 | 3.5614 | 1.1955 | 16.3624
| 586 | 4.3206 | 3.0502 | 5.9058 | 4.5061 | 1.4722 | 19.2549
| 587 | 3.2423 | 2.8851 | 6.4215 | 4.4117 | 1.1756 | 18.1362
| 588 | 3.9933 | 2.7499 | 5.5094 | 3.5069 | 1.259 | 17.0185
| 589 | 3.6914 | 2.8883 | 6.132 | 5.6882 | 1.4439 | 19.8439
| 590 | 3.9426 | 3.6576 | 6.812 | 3.3561 | 1.3426 | 19.1109
| 591 | 3.7851 | 2.2631 | 7.167 | 5.0209 | 1.3303 | 19.5664
| 592 | 3.8546 | 3.8022 | 5.3333 | 4.1326 | 1.2273 | 18.35
| 593 | 4.0466 | 3.2588 | 5.5307 | 5.2756 | 1.5821 | 19.6937
| 594 | 3.3017 | 2.7605 | 4.8161 | 4.8735 | 1.7454 | 17.4972
| 595 | 3.3646 | 3.5702 | 6.3405 | 4.4293 | 1.555 | 19.2597
| 596 | 4.2184 | 3.0655 | 4.189 | 3.684 | 1.6845 | 16.8413
| 597 | 3.88 | 3.7411 | 5.6018 | 4.2808 | 1.7726 | 19.2763
| 598 | 3.8115 | 2.9373 | 6.3761 | 4.0568 | 1.2402 | 18.4218
| 599 | 3.7469 | 3.775 | 4.0584 | 3.8273 | 1.8909 | 17.2984
| 600 | 4.37 | 2.8234 | 5.5452 | 4.5182 | 1.6285 | 18.8853
| 601 | 4.1244 | 3.2787 | 5.6192 | 3.8055 | 1.5329 | 18.3606
| 602 | 4.2857 | 3.0866 | 5.5685 | 3.979 | 1.9451 | 18.8649
| 603 | 4.7537 | 3.1259 | 6.2601 | 5.0071 | 1.4685 | 20.6154
| 604 | 3.7655 | 3.5162 | 5.48 | 4.1922 | 1.5997 | 18.5535
| 605 | 3.9882 | 2.9541 | 6.0081 | 4.9948 | 1.4132 | 19.3584
| 606 | 4.6437 | 2.9313 | 6.5045 | 4.593 | 1.1498 | 19.8222
| 607 | 4.0163 | 3.1047 | 6.0983 | 5.3178 | 1.5641 | 20.1012
| 608 | 4.0995 | 3.0672 | 4.7539 | 5.1925 | 1.7063 | 18.8194
| 609 | 4.3052 | 2.883 | 7.7021 | 3.6783 | 1.6327 | 20.2014
| 610 | 4.0659 | 3.4613 | 5.24 | 3.7363 | 1.3138 | 17.8173
| 611 | 3.6811 | 2.2995 | 5.612 | 4.6699 | 1.3537 | 17.6162
| 612 | 4.1976 | 2.1178 | 6.3014 | 3.7124 | 1.5844 | 17.9137
| 613 | 3.5075 | 3.4339 | 6.9891 | 3.7991 | 1.2907 | 19.0204
| 614 | 3.9521 | 2.8247 | 6.0471 | 4.2308 | 1.5747 | 18.6294
| 615 | 3.783 | 3.0249 | 4.9939 | 4.2325 | 1.526 | 17.5603
| 616 | 4.6644 | 3.6092 | 4.6261 | 5.2689 | 1.7183 | 19.8869
| 617 | 4.3401 | 3.6999 | 4.9824 | 3.2795 | 1.2716 | 17.5735
| 618 | 3.8049 | 3.8939 | 7.8233 | 3.2639 | 1.4732 | 20.2592
| 619 | 3.8525 | 2.7406 | 4.5018 | 4.7068 | 1.266 | 17.0676
| 620 | 3.9561 | 3.039 | 6.296 | 3.5985 | 1.2162 | 18.1058
| 621 | 3.4904 | 2.7356 | 4.8662 | 5.4832 | 1.3413 | 17.9167
| 622 | 3.8455 | 2.8837 | 5.0766 | 4.4728 | 1.1222 | 17.4009
| 623 | 4.1586 | 2.9658 | 5.5843 | 3.3698 | 1.4046 | 17.4831
| 624 | 4.248 | 3.3091 | 6.5104 | 4.6853 | 1.263 | 20.0158
| 625 | 4.5354 | 2.7437 | 4.9077 | 4.6374 | 1.2207 | 18.045
| 626 | 3.2017 | 2.5453 | 5.7458 | 3.6535 | 1.3449 | 16.4912
| 627 | 4.0766 | 3.1394 | 4.9722 | 4.4675 | 1.5556 | 18.2113
| 628 | 3.889 | 3.2469 | 5.7667 | 3.9334 | 1.1633 | 17.9993
| 629 | 4.295 | 2.747 | 5.2289 | 4.4241 | 1.4778 | 18.1728
| 630 | 3.5597 | 2.5041 | 4.4017 | 3.349 | 1.8734 | 15.688
| 631 | 4.5835 | 2.9755 | 5.9918 | 4.1509 | 1.7042 | 19.4059
| 632 | 3.3777 | 2.3337 | 5.0944 | 3.3361 | 1.2571 | 15.3991
| 633 | 3.8843 | 2.2764 | 5.7813 | 3.2549 | 1.6234 | 16.8202
| 634 | 3.703 | 3.2679 | 5.4709 | 3.277 | 1.4934 | 17.2121
| 635 | 4.4085 | 2.3472 | 4.6301 | 3.682 | 1.3084 | 16.3762
| 636 | 3.5341 | 2.9811 | 5.9226 | 4.2501 | 1.4926 | 18.1805
| 637 | 3.6725 | 3.142 | 4.5873 | 4.9292 | 1.5581 | 17.8891
| 638 | 3.6209 | 3.1019 | 4.6743 | 3.1178 | 1.1059 | 15.6208
| 639 | 3.7965 | 3.2804 | 7.4662 | 5.5578 | 1.2802 | 21.3811
| 640 | 4.4883 | 3.0856 | 5.5059 | 4.0497 | 1.5232 | 18.6526
| 641 | 4.0648 | 2.9025 | 4.3388 | 4.6297 | 1.7319 | 17.6676
| 642 | 4.3542 | 3.6914 | 4.7887 | 4.6402 | 1.2529 | 18.7275
| 643 | 4.1395 | 3.0205 | 5.0375 | 5.3685 | 1.3065 | 18.8724
| 644 | 4.2175 | 2.9078 | 6.7274 | 3.7458 | 1.9192 | 19.5178
| 645 | 4.0112 | 3.1085 | 4.7243 | 3.7874 | 1.5667 | 17.1981
| 646 | 3.3706 | 2.6967 | 5.7535 | 4.3321 | 1.719 | 17.8719
| 647 | 3.9055 | 3.0968 | 4.3508 | 4.13 | 1.5229 | 17.0059
| 648 | 4.4039 | 3.8588 | 4.9526 | 3.7423 | 1.5362 | 18.4938
| 649 | 4.7336 | 2.8049 | 5.3463 | 3.2113 | 1.489 | 17.585
| 650 | 4.6813 | 2.2158 | 5.8504 | 4.2984 | 1.3161 | 18.3619
| 651 | 4.0503 | 2.8053 | 5.9991 | 3.6757 | 1.597 | 18.1275
| 652 | 4.0298 | 3.1692 | 5.9744 | 3.4189 | 1.3164 | 17.9087
| 653 | 3.6645 | 3.1309 | 5.7606 | 4.1416 | 1.3696 | 18.0673
| 654 | 3.6869 | 3.7126 | 4.2349 | 4.2079 | 1.0103 | 16.8526
| 655 | 3.7759 | 2.5677 | 7.2068 | 3.4953 | 1.8682 | 18.9139
| 656 | 4.0345 | 2.668 | 5.7874 | 4.1566 | 1.6748 | 18.3211
| 657 | 4.0231 | 2.856 | 6.5159 | 5.4784 | 1.4724 | 20.3458
| 658 | 4.8291 | 3.0256 | 5.6287 | 4.8077 | 1.6396 | 19.9308
| 659 | 3.3351 | 3.1794 | 5.7829 | 5.2169 | 1.7218 | 19.2362
| 660 | 4.0555 | 2.2441 | 5.6531 | 3.9173 | 1.3657 | 17.2356
| 661 | 4.2637 | 2.283 | 6.9325 | 4.6646 | 1.7257 | 19.8695
| 662 | 3.8829 | 2.1789 | 5.2312 | 3.5936 | 1.1374 | 16.024
| 663 | 4.7863 | 2.1847 | 4.1008 | 3.818 | 1.5196 | 16.4093
| 664 | 3.2882 | 2.586 | 6.8986 | 4.8758 | 1.6241 | 19.2727
| 665 | 3.942 | 3.0348 | 6.8609 | 4.0698 | 1.637 | 19.5445
| 666 | 3.6955 | 2.5822 | 5.5369 | 5.2464 | 1.4979 | 18.5589
| 667 | 3.3933 | 2.932 | 4.6471 | 4.3034 | 1.2651 | 16.541
| 668 | 4.3418 | 2.1261 | 6.4911 | 4.3352 | 1.4884 | 18.7826
| 669 | 3.7597 | 3.2325 | 4.257 | 3.5123 | 1.7775 | 16.5391
| 670 | 4.3293 | 2.6174 | 4.6882 | 4.8025 | 1.8197 | 18.257
| 671 | 4.5396 | 2.6852 | 7.0093 | 4.7687 | 1.1077 | 20.1105
| 672 | 3.9135 | 3.3474 | 5.7411 | 3.4749 | 1.6303 | 18.1072
| 673 | 3.871 | 3.6705 | 5.5024 | 4.5637 | 1.2242 | 18.8319
| 674 | 4.3142 | 2.7177 | 4.5623 | 5.0872 | 1.4042 | 18.0856
| 675 | 4.947 | 3.2427 | 6.1962 | 5.4666 | 1.5153 | 21.3677
| 676 | 3.6631 | 2.4439 | 6.6582 | 4.62 | 1.5424 | 18.9276
| 677 | 4.3157 | 2.5526 | 5.3959 | 4.059 | 1.0447 | 17.3679
| 678 | 3.5537 | 2.6874 | 7.4502 | 4.9536 | 1.2322 | 19.8771
| 679 | 3.9032 | 3.8752 | 6.6466 | 3.0832 | 1.6403 | 19.1485
| 680 | 3.961 | 3.9649 | 5.0838 | 3.8414 | 1.4861 | 18.3372
| 681 | 3.5942 | 2.5165 | 4.9582 | 3.4587 | 1.7869 | 16.3146
| 682 | 4.1191 | 3.3349 | 4.8254 | 3.4086 | 1.4987 | 17.1867
| 683 | 4.1329 | 3.0464 | 5.0965 | 4.034 | 1.8643 | 18.174
| 684 | 3.2175 | 3.4682 | 4.9864 | 3.5603 | 1.6719 | 16.9042
| 685 | 4.4207 | 3.7217 | 4.7919 | 4.3572 | 1.4692 | 18.7607
| 686 | 3.6707 | 3.4573 | 7.3266 | 3.7269 | 1.5933 | 19.7749
| 687 | 3.4767 | 2.1609 | 6.0138 | 4.4052 | 1.5531 | 17.6096
| 688 | 4.3022 | 3.4144 | 4.9378 | 3.2749 | 1.613 | 17.5423
| 689 | 3.6302 | 3.6425 | 5.9497 | 4.9815 | 1.5629 | 19.7669
| 690 | 3.386 | 2.608 | 5.89 | 3.9618 | 1.2973 | 17.1431
| 691 | 4.3755 | 2.7731 | 4.5088 | 3.5234 | 1.5474 | 16.7282
| 692 | 3.6548 | 3.2039 | 5.8719 | 4.3704 | 1.7175 | 18.8184
| 693 | 4.3929 | 2.33 | 5.7744 | 5.7563 | 1.0701 | 19.3237
| 694 | 4.0519 | 3.4781 | 5.639 | 3.5814 | 1.2033 | 17.9538
| 695 | 3.9231 | 2.3023 | 5.7566 | 5.2257 | 1.4874 | 18.695
| 696 | 3.2713 | 3.1546 | 4.4088 | 4.9991 | 1.5404 | 17.3742
| 697 | 3.795 | 2.4334 | 7.5273 | 3.9523 | 1.2055 | 18.9136
| 698 | 3.8401 | 2.5063 | 5.7578 | 5.136 | 1.6138 | 18.8541
| 699 | 4.2911 | 2.7842 | 5.2744 | 4.199 | 1.957 | 18.5057
| 700 | 4.3168 | 3.5377 | 6.0941 | 4.6806 | 1.1912 | 19.8205
| 701 | 3.7308 | 2.6254 | 5.1433 | 3.6887 | 1.5576 | 16.7458
| 702 | 4.5716 | 3.9151 | 5.0798 | 4.3144 | 1.2425 | 19.1234
| 703 | 3.2815 | 3.5021 | 5.2231 | 3.4314 | 1.4637 | 16.9018
| 704 | 3.6017 | 3.1613 | 7.3087 | 5.4412 | 1.8494 | 21.3624
| 705 | 4.3263 | 3.1113 | 4.3157 | 4.5275 | 1.3474 | 17.6283
| 706 | 4.0197 | 2.3575 | 4.737 | 3.4515 | 1.375 | 15.9406
| 707 | 3.8535 | 2.4523 | 5.9038 | 3.5718 | 1.4157 | 17.1971
| 708 | 3.2408 | 3.2401 | 6.1577 | 4.1055 | 1.3771 | 18.1213
| 709 | 4.5045 | 2.863 | 6.1788 | 4.6619 | 1.6219 | 19.8302
| 710 | 4.7246 | 2.3129 | 6.2189 | 5.3263 | 1.9108 | 20.4935
| 711 | 4.2342 | 2.9333 | 7.0822 | 3.4717 | 1.6517 | 19.3732
| 712 | 4.8054 | 3.1211 | 4.5811 | 3.6389 | 1.4339 | 17.5803
| 713 | 4.6326 | 2.6934 | 6.5755 | 3.8464 | 1.3125 | 19.0603
| 714 | 3.1795 | 2.4885 | 4.5852 | 3.2856 | 1.6912 | 15.2301
| 715 | 4.1479 | 2.6742 | 4.8849 | 3.8143 | 1.2883 | 16.8096
| 716 | 3.7267 | 3.4871 | 7.2887 | 4.7723 | 1.2708 | 20.5456
| 717 | 3.3247 | 2.4253 | 5.9471 | 4.9848 | 1.5762 | 18.2581
| 718 | 3.9992 | 3.5523 | 4.5618 | 3.5754 | 1.6431 | 17.3319
| 719 | 4.2892 | 2.8758 | 5.6869 | 4.6142 | 1.3044 | 18.7705
| 720 | 3.5413 | 2.9625 | 5.9379 | 4.9255 | 1.3976 | 18.7648
| 721 | 3.6285 | 2.3831 | 6.3482 | 3.8763 | 1.2343 | 17.4703
| 722 | 3.978 | 3.0321 | 4.7627 | 4.451 | 1.6982 | 17.9219
| 723 | 4.415 | 2.9953 | 4.9488 | 5.748 | 1.7573 | 19.8644
| 724 | 3.1345 | 2.6829 | 6.6136 | 4.7782 | 1.5635 | 18.7727
| 725 | 4.0897 | 3.0194 | 5.4119 | 3.4839 | 1.6459 | 17.6508
| 726 | 3.3385 | 3.3783 | 4.7837 | 5.8908 | 1.2873 | 18.6786
| 727 | 3.6783 | 2.7015 | 6.2554 | 4.7463 | 1.3255 | 18.7069
| 728 | 4.7158 | 3.7296 | 6.9498 | 4.3108 | 1.3882 | 21.0942
| 729 | 4.3982 | 3.4084 | 5.9863 | 4.0282 | 1.2829 | 19.104
| 730 | 3.8866 | 3.0569 | 6.5553 | 3.8108 | 1.3077 | 18.6174
| 731 | 4.7634 | 3.4248 | 5.5175 | 5.1775 | 1.3957 | 20.2791
| 732 | 3.6497 | 3.3309 | 4.598 | 3.7059 | 1.6953 | 16.9798
| 733 | 3.8964 | 3.4901 | 6.4798 | 3.5152 | 1.6356 | 19.0171
| 734 | 4.4082 | 3.046 | 5.0164 | 4.0658 | 1.5358 | 18.0722
| 735 | 3.483 | 3.0505 | 5.0518 | 4.2032 | 1.1648 | 16.9534
| 736 | 3.762 | 2.9726 | 5.5708 | 3.8294 | 1.7592 | 17.8939
| 737 | 4.2709 | 3.3949 | 6.5677 | 3.4808 | 1.6549 | 19.3692
| 738 | 4.2806 | 2.7117 | 5.1495 | 3.7534 | 1.8388 | 17.7339
| 739 | 3.9722 | 3.002 | 5.2562 | 3.3841 | 1.6344 | 17.2489
| 740 | 4.2492 | 2.4709 | 4.1968 | 4.6112 | 1.6437 | 17.1719
| 741 | 4.6877 | 2.2868 | 6.2394 | 4.1141 | 1.4285 | 18.7565
| 742 | 3.9441 | 2.4361 | 4.4306 | 3.7703 | 1.7047 | 16.2858
| 743 | 3.7773 | 2.5181 | 5.8768 | 4.7948 | 1.4786 | 18.4456
| 744 | 3.9003 | 2.8437 | 4.6355 | 3.0417 | 1.3631 | 15.7843
| 745 | 4.0237 | 2.977 | 5.2084 | 3.0766 | 1.0279 | 16.3137
| 746 | 3.7679 | 2.5845 | 5.3008 | 3.1726 | 1.6268 | 16.4526
| 747 | 4.1609 | 2.1762 | 4.2169 | 4.6688 | 1.1849 | 16.4076
| 748 | 4.0935 | 3.0761 | 4.6969 | 4.3801 | 1.5865 | 17.833
| 749 | 3.7254 | 2.5701 | 7.2975 | 4.5556 | 1.0742 | 19.2229
| 750 | 4.0151 | 3.8336 | 5.3885 | 5.8661 | 1.8871 | 20.9902
| 751 | 3.1717 | 2.6275 | 4.7163 | 3.3157 | 1.7293 | 15.5605
| 752 | 4.8251 | 2.7704 | 5.0394 | 3.9236 | 1.1941 | 17.7525
| 753 | 3.9493 | 3.2598 | 5.0127 | 4.2725 | 1.5488 | 18.043
| 754 | 3.8881 | 2.6713 | 5.5158 | 3.8217 | 1.1768 | 17.0736
| 755 | 4.0578 | 3.2914 | 6.026 | 3.8175 | 1.8934 | 19.0861
| 756 | 4.2141 | 2.7677 | 6.5973 | 4.6979 | 1.6107 | 19.8877
| 757 | 3.4167 | 2.5421 | 6.5234 | 3.2429 | 1.5334 | 17.2584
| 758 | 4.0022 | 3.6468 | 6.3496 | 5.017 | 1.1974 | 20.2129
| 759 | 3.7161 | 2.6954 | 6.9391 | 3.8072 | 1.5256 | 18.6835
| 760 | 3.2091 | 2.4181 | 5.3056 | 5.5811 | 1.4235 | 17.9374
| 761 | 3.9637 | 3.5124 | 4.6814 | 4.3073 | 1.6087 | 18.0736
| 762 | 3.5241 | 2.3512 | 4.6535 | 3.9697 | 1.739 | 16.2374
| 763 | 3.7359 | 2.9467 | 6.451 | 4.1154 | 1.6146 | 18.8635
| 764 | 3.863 | 2.5308 | 4.9655 | 5.2871 | 1.1699 | 17.8163
| 765 | 3.6492 | 3.3665 | 6.6522 | 3.5045 | 1.4669 | 18.6393
| 766 | 3.7063 | 2.2515 | 5.2185 | 3.8687 | 1.5191 | 16.564
| 767 | 3.9598 | 3.196 | 4.9045 | 4.26 | 1.4422 | 17.7625
| 768 | 3.8775 | 3.7842 | 5.9842 | 3.8803 | 1.4343 | 18.9606
| 769 | 3.816 | 2.8918 | 7.2426 | 3.4791 | 1.2769 | 18.7064
| 770 | 3.9899 | 2.6058 | 5.8943 | 3.3662 | 1.8026 | 17.6589
| 771 | 4.7461 | 3.5231 | 4.6783 | 3.5304 | 1.6036 | 18.0815
| 772 | 3.3732 | 2.7211 | 7.0055 | 4.48 | 1.88 | 19.4598
| 773 | 4.3879 | 3.8244 | 4.8445 | 3.7561 | 1.4948 | 18.3077
| 774 | 3.6749 | 2.4353 | 5.0015 | 4.4813 | 1.4205 | 17.0135
| 775 | 3.819 | 2.5401 | 6.0243 | 3.9363 | 1.44 | 17.7596
| 776 | 3.9329 | 3.0398 | 4.7815 | 4.7803 | 1.9453 | 18.4798
| 777 | 3.1925 | 3.1559 | 4.5344 | 3.968 | 1.7286 | 16.5794
| 778 | 4.0756 | 3.4712 | 5.1868 | 3.6723 | 1.2931 | 17.699
| 779 | 4.2658 | 3.2034 | 4.1226 | 3.9127 | 1.5977 | 17.1022
| 780 | 3.6342 | 2.9232 | 6.2522 | 3.868 | 1.5106 | 18.1881
| 781 | 3.7526 | 3.2644 | 5.5767 | 4.3563 | 1.5884 | 18.5385
| 782 | 3.8972 | 3.439 | 7.0846 | 5.3559 | 1.2997 | 21.0764
| 783 | 3.743 | 3.0242 | 6.5932 | 4.5878 | 1.7399 | 19.6881
| 784 | 3.9145 | 2.7224 | 5.1606 | 3.1065 | 1.5849 | 16.4889
| 785 | 3.4062 | 2.9005 | 4.9969 | 3.8976 | 1.2417 | 16.443
| 786 | 3.7988 | 2.2816 | 4.8076 | 4.0442 | 1.9091 | 16.8413
| 787 | 3.7046 | 2.7099 | 4.7705 | 3.6206 | 1.4226 | 16.2282
| 788 | 4.3351 | 2.9156 | 5.2515 | 4.322 | 1.5894 | 18.4136
| 789 | 3.4212 | 3.0776 | 5.0481 | 4.9223 | 1.392 | 17.8611
| 790 | 4.1114 | 3.0954 | 5.4867 | 3.5315 | 1.426 | 17.651
| 791 | 3.6513 | 2.8625 | 7.3642 | 5.2629 | 1.8018 | 20.9427
| 792 | 4.4874 | 2.7192 | 4.0882 | 3.5668 | 1.6604 | 16.5219
| 793 | 4.031 | 3.1641 | 6.6057 | 3.2534 | 1.4618 | 18.516
| 794 | 3.4895 | 2.6116 | 4.9633 | 4.2439 | 1.8513 | 17.1597
| 795 | 4.4858 | 3.229 | 5.2748 | 3.3765 | 1.2281 | 17.5942
| 796 | 3.5953 | 3.714 | 6.7433 | 3.3007 | 1.6967 | 19.05
| 797 | 4.2554 | 3.6747 | 6.2933 | 4.3847 | 1.2837 | 19.8918
| 798 | 3.4997 | 3.1892 | 4.839 | 3.5181 | 1.5168 | 16.5629
| 799 | 4.8683 | 3.2835 | 4.295 | 5.1657 | 1.8054 | 19.4178
| 800 | 3.277 | 3.0889 | 7.4077 | 4.5793 | 1.3897 | 19.7426
| 801 | 3.8687 | 2.9445 | 5.974 | 3.4185 | 1.4698 | 17.6754
| 802 | 3.9386 | 3.2192 | 6.7477 | 3.9548 | 1.7715 | 19.6318
| 803 | 3.3318 | 2.7234 | 4.7514 | 4.4461 | 1.5664 | 16.8191
| 804 | 3.7615 | 3.1271 | 4.8862 | 3.9644 | 1.5769 | 17.3162
| 805 | 3.8494 | 3.5215 | 5.321 | 3.5542 | 1.4455 | 17.6916
| 806 | 3.9941 | 3.0173 | 6.768 | 4.9368 | 1.658 | 20.3743
| 807 | 4.0385 | 2.4026 | 7.04 | 3.4145 | 1.9214 | 18.8169
| 808 | 3.6481 | 2.7646 | 4.276 | 3.4476 | 1.6024 | 15.7387
| 809 | 3.9279 | 2.9989 | 5.4036 | 3.5291 | 1.924 | 17.7837
| 810 | 4.1257 | 3.1741 | 6.004 | 3.7655 | 1.7312 | 18.8006
| 811 | 3.5655 | 3.5486 | 5.4876 | 3.502 | 1.2537 | 17.3574
| 812 | 4.7925 | 2.2398 | 5.5903 | 5.6212 | 1.1184 | 19.3623
| 813 | 3.8563 | 2.9021 | 6.2409 | 3.9316 | 1.3113 | 18.2422
| 814 | 3.808 | 3.2679 | 5.7325 | 4.5592 | 1.4435 | 18.8111
| 815 | 3.8263 | 3.9474 | 4.7066 | 3.5855 | 1.383 | 17.4489
| 816 | 4.0957 | 2.7056 | 5.9578 | 3.7162 | 1.5016 | 17.9769
| 817 | 4.0205 | 2.8797 | 4.9401 | 4.1873 | 1.4855 | 17.5131
| 818 | 3.2199 | 2.3666 | 6.1246 | 4.2008 | 1.4992 | 17.4111
| 819 | 4.1024 | 3.0216 | 5.4028 | 3.5527 | 1.4207 | 17.5003
| 820 | 3.5716 | 2.3974 | 5.3402 | 3.734 | 1.184 | 16.2271
| 821 | 3.4953 | 3.5779 | 5.3598 | 3.6505 | 1.7976 | 17.8811
| 822 | 4.6223 | 2.6477 | 5.3163 | 4.1951 | 1.7935 | 18.575
| 823 | 4.0821 | 2.6593 | 4.4631 | 4.4343 | 1.432 | 17.0709
| 824 | 4.1656 | 2.8187 | 5.5461 | 5.4345 | 1.631 | 19.5959
| 825 | 4.2162 | 3.4803 | 5.4916 | 3.6958 | 1.4282 | 18.3121
| 826 | 3.5224 | 2.7304 | 5.1712 | 3.6103 | 1.5514 | 16.5858
| 827 | 4.2783 | 2.6894 | 6.1421 | 4.4699 | 1.7105 | 19.2903
| 828 | 3.8745 | 2.6377 | 5.8018 | 5.0941 | 1.4192 | 18.8274
| 829 | 4.1662 | 2.5763 | 5.3365 | 3.9113 | 1.5951 | 17.5854
| 830 | 4.5747 | 3.1236 | 4.5296 | 4.1473 | 1.4028 | 17.778
| 831 | 4.2673 | 2.7793 | 5.3523 | 4.5725 | 1.5389 | 18.5103
| 832 | 4.6555 | 3.1677 | 5.0049 | 4.3649 | 1.3502 | 18.5432
| 833 | 4.8576 | 2.7735 | 5.7026 | 3.1574 | 1.7377 | 18.2288
| 834 | 3.3275 | 2.7383 | 7.7161 | 3.3472 | 1.5489 | 18.6779
| 835 | 3.9671 | 2.7915 | 6.3548 | 3.4517 | 1.3208 | 17.8859
| 836 | 4.9818 | 3.1832 | 4.2265 | 4.2873 | 1.5682 | 18.247
| 837 | 3.4705 | 2.5964 | 5.278 | 4.1617 | 1.6592 | 17.1658
| 838 | 4.1685 | 2.6902 | 5.2938 | 4.3479 | 1.0567 | 17.5572
| 839 | 4.0933 | 2.8103 | 5.6407 | 4.1077 | 1.5783 | 18.2302
| 840 | 3.4221 | 2.7332 | 5.063 | 4.5928 | 1.8966 | 17.7076
| 841 | 4.4525 | 3.1149 | 6.3315 | 4.7047 | 1.7656 | 20.3692
| 842 | 3.5758 | 2.9399 | 5.6744 | 3.9735 | 1.8359 | 17.9995
| 843 | 4.1291 | 3.3354 | 7.4879 | 3.592 | 1.4829 | 20.0272
| 844 | 3.6249 | 2.9858 | 5.2214 | 3.8318 | 1.4352 | 17.0991
| 845 | 4.466 | 2.4728 | 6.2685 | 4.01 | 1.1098 | 18.3271
| 846 | 4.7761 | 2.575 | 5.0065 | 3.5637 | 1.3874 | 17.3087
| 847 | 4.2069 | 2.8278 | 5.2285 | 4.4638 | 1.1034 | 17.8304
| 848 | 3.973 | 2.5099 | 4.8611 | 5.7097 | 1.4165 | 18.4703
| 849 | 4.5688 | 2.9705 | 7.3208 | 3.5873 | 1.4218 | 19.8692
| 850 | 3.4408 | 2.9118 | 5.531 | 4.969 | 1.2791 | 18.1318
| 851 | 3.3544 | 3.3293 | 7.5767 | 3.9275 | 1.3516 | 19.5395
| 852 | 4.7507 | 2.8481 | 6.0823 | 3.6187 | 1.2193 | 18.5191
| 853 | 3.9821 | 3.2547 | 7.2251 | 4.2472 | 1.4371 | 20.1462
| 854 | 3.8333 | 3.0843 | 7.0979 | 3.3902 | 1.463 | 18.8687
| 855 | 3.6368 | 2.5357 | 6.8404 | 5.2083 | 1.6833 | 19.9045
| 856 | 3.1492 | 2.5893 | 4.4245 | 4.8471 | 1.2747 | 16.2848
| 857 | 4.4115 | 3.1198 | 6.4894 | 4.2385 | 1.7124 | 19.9716
| 858 | 4.3837 | 2.8603 | 5.2688 | 4.0532 | 1.5401 | 18.1061
| 859 | 3.7872 | 3.1724 | 5.1058 | 3.2471 | 1.1735 | 16.4861
| 860 | 3.55 | 3.8425 | 5.1772 | 5.5394 | 1.1307 | 19.2399
| 861 | 3.6683 | 2.3545 | 7.6497 | 4.3622 | 1.8305 | 19.8653
| 862 | 4.5678 | 2.7593 | 5.4465 | 4.1808 | 1.5041 | 18.4585
| 863 | 4.3381 | 3.0641 | 5.4501 | 3.7984 | 1.5184 | 18.1692
| 864 | 3.7558 | 3.0535 | 4.2088 | 3.5059 | 1.3007 | 15.8246
| 865 | 4.1456 | 3.0612 | 5.6917 | 4.4566 | 1.6191 | 18.9742
| 866 | 4.3321 | 3.1188 | 5.353 | 3.3462 | 1.1462 | 17.2963
| 867 | 3.2253 | 3.2954 | 5.9444 | 3.8082 | 1.6624 | 17.9357
| 868 | 3.6403 | 3.175 | 4.7867 | 5.3201 | 1.5708 | 18.4928
| 869 | 4.2976 | 3.2761 | 7.2386 | 3.3812 | 1.7908 | 19.9842
| 870 | 3.1583 | 3.0605 | 4.9951 | 4.6525 | 1.3861 | 17.2525
| 871 | 3.4781 | 2.958 | 4.4858 | 4.3285 | 1.3854 | 16.6358
| 872 | 3.9982 | 2.8462 | 6.2312 | 4.492 | 1.8288 | 19.3964
| 873 | 3.9285 | 3.3043 | 5.0287 | 4.1641 | 1.736 | 18.1617
| 874 | 4.1736 | 2.7309 | 6.3743 | 3.3138 | 1.2446 | 17.8372
| 875 | 4.0732 | 2.3088 | 6.4024 | 4.8515 | 1.5343 | 19.1702
| 876 | 4.091 | 2.9489 | 5.464 | 4.8279 | 1.4082 | 18.74
| 877 | 3.6378 | 2.2903 | 4.7777 | 3.7607 | 1.1674 | 15.6339
| 878 | 3.6276 | 2.9188 | 4.8559 | 5.0664 | 1.4964 | 17.965
| 879 | 3.4544 | 3.5292 | 5.7916 | 3.6041 | 1.7487 | 18.1278
| 880 | 3.9397 | 3.1487 | 5.2008 | 3.5726 | 1.2862 | 17.148
| 881 | 3.5202 | 2.9181 | 5.3713 | 3.5394 | 1.0869 | 16.4358
| 882 | 3.8163 | 2.8035 | 7.5084 | 3.1771 | 1.5086 | 18.8139
| 883 | 3.8809 | 2.4473 | 6.0105 | 3.6545 | 1.5248 | 17.5179
| 884 | 4.3711 | 3.3022 | 5.6975 | 3.3439 | 1.4221 | 18.1369
| 885 | 4.1348 | 3.3198 | 5.2129 | 4.6249 | 1.4944 | 18.7867
| 886 | 3.8209 | 3.049 | 6.7905 | 3.7583 | 1.7617 | 19.1804
| 887 | 3.9043 | 3.5277 | 7.1478 | 3.509 | 1.5264 | 19.6152
| 888 | 3.3985 | 2.9909 | 4.4698 | 4.2186 | 1.6287 | 16.7064
| 889 | 4.352 | 3.0811 | 6.3697 | 3.1271 | 1.4577 | 18.3877
| 890 | 3.6109 | 3.0908 | 7.1193 | 4.9177 | 1.4115 | 20.1501
| 891 | 4.9245 | 2.7157 | 5.021 | 5.041 | 1.7693 | 19.4715
| 892 | 3.7711 | 3.6015 | 6.8264 | 3.9197 | 1.6887 | 19.8076
| 893 | 4.1019 | 2.7768 | 5.9001 | 3.1335 | 1.3917 | 17.3039
| 894 | 3.9688 | 2.616 | 4.2852 | 3.2616 | 1.7811 | 15.9127
| 895 | 4.0807 | 2.6819 | 7.2636 | 3.5495 | 1.8332 | 19.409
| 896 | 3.0993 | 3.545 | 7.9731 | 5.3317 | 1.8136 | 21.7626
| 897 | 4.0846 | 2.4968 | 6.2258 | 3.8436 | 1.4365 | 18.0872
| 898 | 4.2127 | 2.43 | 4.6081 | 4.7486 | 1.3821 | 17.3815
| 899 | 4.0109 | 3.2171 | 6.8026 | 4.587 | 1.9013 | 20.5188
| 900 | 4.7407 | 2.0645 | 6.6949 | 5.0689 | 1.2986 | 19.8677
| 901 | 3.0493 | 3.7901 | 7.3907 | 3.3317 | 1.6475 | 19.2093
| 902 | 3.9797 | 2.7457 | 6.4711 | 3.5573 | 1.56 | 18.3138
| 903 | 3.9959 | 3.7944 | 6.8212 | 5.5989 | 1.5518 | 21.7622
| 904 | 3.4739 | 2.9346 | 5.0104 | 3.1899 | 1.3196 | 15.9284
| 905 | 4.0778 | 3.2238 | 6.1813 | 3.6931 | 1.7537 | 18.9297
| 906 | 3.5273 | 2.6766 | 5.462 | 3.765 | 1.5029 | 16.9338
| 907 | 3.2555 | 2.62 | 5.0815 | 3.8918 | 1.1281 | 15.9769
| 908 | 3.2598 | 2.5908 | 4.8131 | 4.8164 | 1.3677 | 16.8478
| 909 | 4.0576 | 2.9211 | 5.1552 | 3.907 | 1.2917 | 17.3326
| 910 | 4.0439 | 2.7964 | 6.5311 | 3.6116 | 1.6446 | 18.6276
| 911 | 4.4606 | 2.9417 | 6.0465 | 3.762 | 1.4062 | 18.617
| 912 | 3.2115 | 3.3417 | 4.4189 | 4.9519 | 1.7093 | 17.6333
| 913 | 4.6753 | 3.5093 | 6.6441 | 4.0196 | 1.5824 | 20.4308
| 914 | 3.9929 | 3.2719 | 4.486 | 5.0519 | 1.1386 | 17.9413
| 915 | 4.4435 | 3.7792 | 5.1009 | 4.7412 | 1.0926 | 19.1575
| 916 | 3.7953 | 3.1989 | 4.793 | 5.376 | 1.4391 | 18.6022
| 917 | 4.4378 | 3.2974 | 5.0651 | 3.5959 | 1.6532 | 18.0493
| 918 | 4.2061 | 3.1137 | 5.554 | 3.6568 | 1.2171 | 17.7477
| 919 | 4.5336 | 2.5808 | 5.683 | 3.69 | 1.8617 | 18.3492
| 920 | 3.9464 | 2.7489 | 5.1517 | 4.3454 | 1.6203 | 17.8128
| 921 | 3.9185 | 2.6088 | 5.3758 | 3.6769 | 1.9149 | 17.4948
| 922 | 4.1318 | 2.4232 | 4.8023 | 4.4766 | 1.1796 | 17.0134
| 923 | 3.5306 | 3.306 | 4.3228 | 4.7648 | 1.7955 | 17.7196
| 924 | 4.4187 | 2.5005 | 7.4142 | 3.1783 | 1.476 | 18.9877
| 925 | 3.8105 | 2.6299 | 5.614 | 4.5343 | 1.7556 | 18.3443
| 926 | 3.7907 | 3.5428 | 4.3447 | 4.3875 | 1.3674 | 17.4331
| 927 | 4.155 | 3.116 | 5.7856 | 3.2199 | 1.5447 | 17.8212
| 928 | 4.6026 | 2.4744 | 7.0357 | 3.389 | 1.7139 | 19.2156
| 929 | 4.001 | 3.0095 | 5.0745 | 4.8597 | 1.6424 | 18.5871
| 930 | 3.8616 | 3.0679 | 5.9672 | 4.6441 | 1.618 | 19.1589
| 931 | 3.7124 | 2.3214 | 6.9049 | 4.1596 | 1.1981 | 18.2963
| 932 | 3.8093 | 3.3803 | 5.6086 | 3.6065 | 1.546 | 17.9508
| 933 | 4.3946 | 2.7624 | 5.302 | 3.2286 | 1.0859 | 16.7735
| 934 | 4.0152 | 3.3983 | 6.1375 | 4.3235 | 1.6028 | 19.4773
| 935 | 4.6785 | 2.6231 | 4.9147 | 4.2656 | 1.6649 | 18.1468
| 936 | 4.8106 | 2.8382 | 5.1739 | 4.2916 | 1.3937 | 18.508
| 937 | 3.798 | 3.7619 | 5.4766 | 5.1293 | 1.4532 | 19.619
| 938 | 3.4688 | 2.9248 | 5.4317 | 4.5315 | 1.5167 | 17.8734
| 939 | 4.6066 | 2.831 | 5.995 | 3.0901 | 1.3813 | 17.904
| 940 | 3.7493 | 3.5481 | 5.6948 | 5.0154 | 1.5688 | 19.5763
| 941 | 3.9132 | 3.0744 | 4.3918 | 3.6267 | 1.3381 | 16.3442
| 942 | 4.4494 | 2.8602 | 6.433 | 4.2129 | 1.6877 | 19.6433
| 943 | 4.3902 | 2.7911 | 5.4546 | 4.7002 | 1.3243 | 18.6604
| 944 | 4.0633 | 2.8726 | 6.6282 | 5.031 | 1.5123 | 20.1073
| 945 | 4.448 | 3.2117 | 6.0561 | 3.4539 | 1.6908 | 18.8604
| 946 | 3.773 | 3.4534 | 6.1994 | 3.5585 | 1.6278 | 18.612
| 947 | 4.0914 | 2.5737 | 5.1131 | 3.8446 | 1.1905 | 16.8134
| 948 | 4.2964 | 2.8964 | 5.8571 | 4.5965 | 1.554 | 19.2004
| 949 | 4.0132 | 3.5113 | 7.1354 | 3.8013 | 1.2433 | 19.7046
| 950 | 4.2105 | 2.8773 | 5.7163 | 4.4589 | 1.5677 | 18.8306
| 951 | 3.8279 | 2.6641 | 6.4008 | 3.759 | 1.8125 | 18.4643
| 952 | 4.1522 | 2.7573 | 5.8345 | 3.5015 | 1.095 | 17.3405
| 953 | 3.9876 | 2.4091 | 6.314 | 4.079 | 1.6165 | 18.4061
| 954 | 3.3516 | 3.3689 | 6.3308 | 3.7177 | 1.7895 | 18.5584
| 955 | 4.1455 | 2.8073 | 6.7107 | 4.9764 | 1.5829 | 20.2228
| 956 | 4.3852 | 3.3408 | 6.5885 | 5.0979 | 1.3561 | 20.7685
| 957 | 4.1483 | 3.5183 | 6.0717 | 4.0107 | 1.7499 | 19.4989
| 958 | 4.1771 | 2.6146 | 4.3206 | 3.9459 | 1.3324 | 16.3906
| 959 | 4.1272 | 2.7772 | 5.2875 | 4.1459 | 1.7367 | 18.0744
| 960 | 4.2685 | 2.9142 | 6.0375 | 4.6317 | 1.5499 | 19.4018
| 961 | 3.6984 | 3.0782 | 4.859 | 3.4796 | 1.3759 | 16.4911
| 962 | 3.9844 | 2.7799 | 4.9983 | 3.5737 | 1.528 | 16.8643
| 963 | 3.6723 | 3.179 | 4.4684 | 5.2024 | 1.6758 | 18.198
| 964 | 4.525 | 3.195 | 4.9198 | 3.8719 | 1.4883 | 18
| 965 | 4.3729 | 3.0563 | 4.5703 | 3.9344 | 1.2569 | 17.1908
| 966 | 3.7539 | 3.5738 | 5.1967 | 3.2572 | 1.3285 | 17.11
| 967 | 4.227 | 3.1844 | 5.8667 | 5.0115 | 1.7795 | 20.0691
| 968 | 3.8421 | 3.565 | 6.3184 | 4.6195 | 1.3171 | 19.6622
| 969 | 3.9371 | 3.2278 | 5.5137 | 4.0688 | 1.6176 | 18.3651
| 970 | 3.8343 | 2.1538 | 6.2457 | 4.2219 | 1.4327 | 17.8885
| 971 | 4.0711 | 2.9739 | 5.305 | 4.7907 | 1.178 | 18.3186
| 972 | 3.9085 | 2.5315 | 7.2794 | 4.2676 | 1.8211 | 19.808
| 973 | 3.3678 | 3.1881 | 6.4141 | 3.6448 | 1.1897 | 17.8046
| 974 | 3.8358 | 2.633 | 5.5402 | 5.3862 | 1.43 | 18.8252
| 975 | 3.9775 | 3.1662 | 6.1626 | 3.7858 | 1.584 | 18.6761
| 976 | 4.1832 | 2.6217 | 5.9137 | 3.7113 | 1.2075 | 17.6374
| 977 | 3.6459 | 2.9829 | 7.196 | 3.283 | 1.6577 | 18.7655
| 978 | 3.9157 | 3.2637 | 5.3272 | 3.4294 | 1.8482 | 17.7842
| 979 | 4.1151 | 3.6776 | 4.5917 | 3.4565 | 1.4364 | 17.2774
| 980 | 3.6662 | 2.6921 | 5.0709 | 4.8812 | 1.5025 | 17.8128
| 981 | 4.5569 | 2.8907 | 4.3608 | 4.4369 | 1.3713 | 17.6165
| 982 | 4.027 | 2.9301 | 5.7966 | 4.05 | 1.0827 | 17.8864
| 983 | 4.9195 | 2.7248 | 4.7659 | 3.1393 | 1.7015 | 17.2511
| 984 | 3.4868 | 2.8717 | 5.9111 | 3.546 | 1.5055 | 17.3211
| 985 | 4.5159 | 2.2291 | 7.3819 | 4.3906 | 1.3146 | 19.8321
| 986 | 3.4254 | 3.7454 | 4.9709 | 3.112 | 1.9527 | 17.2064
| 987 | 3.8675 | 3.3633 | 5.0141 | 3.7316 | 1.5779 | 17.5545
| 988 | 3.5371 | 3.1004 | 5.7514 | 4.7523 | 1.6052 | 18.7464
| 989 | 4.6359 | 3.1926 | 6.2816 | 4.3529 | 1.1934 | 19.6564
| 990 | 4.3636 | 2.9873 | 5.4817 | 3.4681 | 1.5066 | 17.8073
| 991 | 3.4325 | 3.2188 | 4.6231 | 4.1167 | 1.6769 | 17.0681
| 992 | 4.3358 | 3.5893 | 4.8804 | 3.8615 | 1.3224 | 17.9894
| 993 | 4.1379 | 2.1345 | 5.7145 | 3.5485 | 1.3487 | 16.8842
| 994 | 4.3657 | 2.8015 | 6.193 | 3.9861 | 1.9039 | 19.2503
| 995 | 4.0456 | 3.1467 | 5.7692 | 3.4277 | 1.2305 | 17.6197
| 996 | 3.9538 | 3.4347 | 4.7605 | 3.2724 | 1.3578 | 16.7792
| 997 | 3.6612 | 3.393 | 5.3323 | 4.7097 | 1.1407 | 18.2369
| 998 | 4.7805 | 2.4414 | 4.7765 | 3.5448 | 1.743 | 17.2862
| 999 | 4.1878 | 3.5339 | 4.558 | 4.3786 | 1.1869 | 17.8452
| 1000 | 4.8758 | 2.1018 | 5.1033 | 4.0166 | 1.7018 | 17.7993
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.