## Plan
| Minimum | Most Likely | Maximum | Duration | Risk Note
Analyze | 3 | 4 | 5 | 4
Design | 2 | 3 | 4 | 3
Build | 4 | 5 | 8 | 5.6667 | NF Requirements (IM, IS, HR, …)
Test | 3 | 3.5 | 6 | 4.1667 | UAT iteration risk
Deploy | 1 | 1.5 | 2 | 1.5
Go Live Date |  |  |  | 18.3333
RiskNormal, RiskCormat
https://github.com/pyscripter/XLRisk/wiki/CorrelatedInputsExample

## XLRisk
Simulation Settings |  | Simulation Inputs |  | Simulation Outputs
Seed | 0
Update Screen | FALSE | Range | Formula | Range | Name
Iterations | 1000 | Plan!$G$6 | RiskTriang(D6,E6,F6) | Plan!$G$11 | LiveDate
Latin Hypercube | TRUE | Plan!$G$7 | RiskTriang(D7,E7,F7)
Calculate data dables during simulation | TRUE | Plan!$G$8 | RiskTriang(D8,E8,F8)
|  | Plan!$G$9 | RiskTriang(D9,E9,F9)
|  | Plan!$G$10 | RiskTriang(D10,E10,F10)
Macro to run before each iteration
Macro to run after each iteration

## Risk Results 1
Navigation |  | Inputs |  |  |  |  | Outputs | Simulation Statistics |  | Output Cumulative Distributions | Output Distributions | Risk Tornado Diagram
Risk Outputs |  | Plan!$G$6 | Plan!$G$7 | Plan!$G$8 | Plan!$G$9 | Plan!$G$10 | Plan!$G$11 |  | Plan!$G$11 |  |  |  |  | Correlations - Column 1 sorted
Simulation Statistics | Iterations | RiskTriang(D6,E6,F6) | RiskTriang(D7,E7,F7) | RiskTriang(D8,E8,F8) | RiskTriang(D9,E9,F9) | RiskTriang(D10,E10,F10) | LiveDate |  | LiveDate |  |  | Select Output: | Plan!$G$11 |  | Plan!$G$11
Risk Output Percentiles | 1 | 4.5255 | 2.2973 | 6.1085 | 3.4997 | 1.4665 | 17.8974 | Mean | 18.3333 |  |  | Name: | LiveDate | Risk Inputs | LiveDate
Calculate Percent Rank | 2 | 3.6026 | 3.5247 | 5.5688 | 4.6562 | 1.6971 | 19.0494 | Median | 18.2762 |  |  | 1 |  | Plan!$G$10 | 0.15949
Correlations | 3 | 4.5917 | 3.2119 | 5.4836 | 4.3941 | 1.2737 | 18.955 | Mode | #N/A |  |  | Tornado Diagram for LiveDate (Plan!$G$11) |  | Plan!$G$6 | 0.31866
Output Cumulative Distributions | 4 | 3.637 | 3.0778 | 4.8872 | 4.3282 | 1.3748 | 17.3051 | Std. Deviation | 1.2464 |  |  |  |  | Plan!$G$7 | 0.33751
Output Distributions | 5 | 3.6709 | 2.5644 | 5.0723 | 3.7696 | 1.3429 | 16.4201 | Variance | 1.5536 |  |  |  |  | Plan!$G$9 | 0.54787
Risk Tornado Diagram | 6 | 3.4242 | 3.2987 | 5.9162 | 4.0555 | 1.2678 | 17.9623 | Kurtosis | -0.3662 |  |  |  |  | Plan!$G$8 | 0.68955
| 7 | 4.6918 | 2.8209 | 5.3451 | 3.4979 | 1.1931 | 17.5488 | Skewness | 0.21143
| 8 | 4.5797 | 3.2763 | 7.2939 | 4.8924 | 1.5692 | 21.6115 | Minimum | 15.0076
| 9 | 4.24 | 2.2846 | 4.7569 | 3.6335 | 1.4984 | 16.4133 | Maximum | 22.5516
| 10 | 3.9087 | 3.1382 | 5.1105 | 4.5456 | 1.3919 | 18.0948 | Range | 7.5441
| 11 | 3.7617 | 3.287 | 4.6548 | 3.5466 | 1.3448 | 16.5949 | Count | 1000
| 12 | 3.4625 | 2.6769 | 4.816 | 3.2845 | 1.5684 | 15.8083 | Error Count | 0
| 13 | 4.1396 | 2.8456 | 4.6044 | 5.5513 | 1.74 | 18.8807 | Std. Error | 0.039415
| 14 | 4.1208 | 3.16 | 5.4547 | 4.589 | 1.3682 | 18.6928 | Confidence Level (95%) | 0.077346
| 15 | 4.3274 | 2.9481 | 4.5767 | 3.9952 | 1.1862 | 17.0336
| 16 | 3.7307 | 2.6803 | 4.8495 | 3.503 | 1.8186 | 16.582 | Percentiles
| 17 | 4.0695 | 3.1766 | 4.7608 | 4.5051 | 1.4187 | 17.9308 |  | Plan!$G$11
| 18 | 4.1832 | 2.4662 | 4.745 | 3.6306 | 1.6115 | 16.6365 |  | LiveDate
| 19 | 4.1317 | 3.5666 | 5.964 | 3.8651 | 1.8769 | 19.4044 | 0% | 15.0076
| 20 | 4.8847 | 2.8197 | 5.2528 | 5.0985 | 1.492 | 19.5477 | 2.5% | 16.1428
| 21 | 3.9876 | 2.6883 | 5.8684 | 4.0981 | 1.3547 | 17.9971 | 5% | 16.4133
| 22 | 4.0156 | 2.7212 | 5.741 | 3.5517 | 1.3617 | 17.3912 | 7.5% | 16.5857
| 23 | 3.4089 | 3.1006 | 5.505 | 5.3882 | 1.331 | 18.7337 | 10% | 16.7239
| 24 | 4.6625 | 3.7679 | 6.2296 | 3.8492 | 1.4507 | 19.96 | 12.5% | 16.8893
| 25 | 4.3897 | 3.1669 | 4.551 | 3.9938 | 1.4856 | 17.5869 | 15% | 17.0078
| 26 | 4.5874 | 3.1276 | 5.2792 | 4.3992 | 1.4734 | 18.8668 | 17.5% | 17.1045
| 27 | 4.2907 | 3.0422 | 6.484 | 4.4103 | 1.859 | 20.0863 | 20% | 17.2301
| 28 | 4.0533 | 3.5495 | 5.742 | 4.5229 | 1.6545 | 19.5222 | 22.5% | 17.3234
| 29 | 4.6722 | 2.5997 | 6.1006 | 3.8822 | 1.8072 | 19.0618 | 25% | 17.4036
| 30 | 4.163 | 2.7505 | 7.428 | 5.0228 | 1.7891 | 21.1535 | 27.5% | 17.5045
| 31 | 4.4453 | 2.7864 | 5.909 | 3.5644 | 1.5049 | 18.2101 | 30% | 17.5681
| 32 | 3.9891 | 2.547 | 4.3121 | 3.6756 | 1.8731 | 16.3968 | 32.5% | 17.6866
| 33 | 3.742 | 3.2343 | 6.7434 | 3.6213 | 1.355 | 18.6961 | 35% | 17.7737
| 34 | 3.9981 | 2.8151 | 6.1874 | 5.8051 | 1.5647 | 20.3704 | 37.5% | 17.8606
| 35 | 3.8249 | 3.5542 | 4.0562 | 3.4548 | 1.4446 | 16.3347 | 40% | 17.9334
| 36 | 3.3236 | 3.3305 | 6.5806 | 4.8679 | 1.8652 | 19.9677 | 42.5% | 17.9913
| 37 | 3.4978 | 2.5003 | 6.3345 | 5.4003 | 1.1955 | 18.9284 | 45% | 18.0937
| 38 | 4.237 | 2.9899 | 4.5877 | 3.2209 | 1.6217 | 16.6572 | 47.5% | 18.212
| 39 | 4.492 | 3.0743 | 4.927 | 3.7682 | 1.6235 | 17.8851 | 50% | 18.2762
| 40 | 4.8619 | 2.9166 | 4.1018 | 5.262 | 1.2641 | 18.4065 | 52.5% | 18.3526
| 41 | 3.5604 | 2.8725 | 5.3362 | 4.8862 | 1.6668 | 18.3222 | 55% | 18.4323
| 42 | 4.087 | 3.2434 | 6.0402 | 3.5426 | 1.4875 | 18.4007 | 57.5% | 18.5245
| 43 | 3.9458 | 2.7823 | 6.4002 | 3.6839 | 1.7651 | 18.5773 | 60% | 18.6261
| 44 | 3.5723 | 3.365 | 5.3466 | 3.0452 | 1.4573 | 16.7863 | 62.5% | 18.7166
| 45 | 3.7345 | 2.8569 | 5.0258 | 3.7199 | 1.1801 | 16.5172 | 65% | 18.8259
| 46 | 3.2378 | 3.0755 | 6.2756 | 4.2239 | 1.5448 | 18.3576 | 67.5% | 18.9008
| 47 | 3.5459 | 2.9996 | 5.1476 | 3.556 | 1.3275 | 16.5767 | 70% | 18.9686
| 48 | 3.9432 | 2.7312 | 4.8067 | 4.7164 | 1.2745 | 17.4719 | 72.5% | 19.0841
| 49 | 3.9051 | 2.9489 | 4.8747 | 3.3167 | 1.2894 | 16.3348 | 75% | 19.1882
| 50 | 4.292 | 2.3381 | 6.4298 | 5.0768 | 1.5819 | 19.7187 | 77.5% | 19.3163
| 51 | 4.8509 | 2.9292 | 7.6416 | 3.5088 | 1.6571 | 20.5877 | 80% | 19.4502
| 52 | 4.0226 | 2.8412 | 5.3136 | 3.8287 | 1.8807 | 17.8867 | 82.5% | 19.5568
| 53 | 4.2132 | 2.1809 | 7.4592 | 4.7894 | 1.2931 | 19.9358 | 85% | 19.6643
| 54 | 4.1314 | 2.7467 | 5.6448 | 4.3486 | 1.4232 | 18.2947 | 87.5% | 19.8768
| 55 | 3.6915 | 3.8264 | 6.1816 | 3.6519 | 1.398 | 18.7494 | 90% | 20.0166
| 56 | 3.7128 | 2.0958 | 6.2069 | 4.8151 | 1.2968 | 18.1275 | 92.5% | 20.1956
| 57 | 3.7215 | 2.5723 | 5.8863 | 3.6962 | 1.7154 | 17.5918 | 95% | 20.4651
| 58 | 3.8245 | 3.8917 | 5.8145 | 4.4797 | 1.7539 | 19.7641 | 97.5% | 20.8815
| 59 | 3.8925 | 2.796 | 4.7803 | 4.1404 | 1.5991 | 17.2084 | 100% | 22.5516
| 60 | 3.4801 | 2.5763 | 6.0267 | 3.2434 | 1.5765 | 16.9031
| 61 | 4.7405 | 3.1959 | 6.6911 | 3.6763 | 1.7085 | 20.0124 | Percent Rank
| 62 | 4.1766 | 2.9835 | 4.811 | 3.7236 | 1.7623 | 17.4569 |  | Plan!$G$11
| 63 | 4.5898 | 2.968 | 5.6725 | 3.2759 | 1.6976 | 18.2037 |  | LiveDate
| 64 | 3.3205 | 3.1307 | 5.2228 | 3.5576 | 1.7298 | 16.9614 | Enter Value: | 16.4133
| 65 | 4.3279 | 3.4352 | 4.6151 | 3.3754 | 1.304 | 17.0577 | % rank: | 5%
| 66 | 3.9142 | 2.3555 | 6.2332 | 4.2112 | 1.4757 | 18.1897
| 67 | 4.2953 | 2.9272 | 6.2219 | 4.3349 | 1.4084 | 19.1876 | Correlations
| 68 | 4.2633 | 2.881 | 6.6488 | 4.0079 | 1.389 | 19.19 |  | Plan!$G$11
| 69 | 4.081 | 3.4993 | 4.2612 | 4.6782 | 1.1077 | 17.6274 | Risk Inputs | LiveDate
| 70 | 4.3814 | 3.2504 | 4.585 | 3.5113 | 1.4837 | 17.2117 | Plan!$G$6 | 0.31866
| 71 | 3.2277 | 3.3186 | 5.6969 | 5.1138 | 1.3516 | 18.7086 | Plan!$G$7 | 0.33751
| 72 | 4.0954 | 3.1046 | 6.2643 | 4.3008 | 1.4046 | 19.1697 | Plan!$G$8 | 0.68955
| 73 | 4.34 | 2.9002 | 7.357 | 4.1264 | 1.4999 | 20.2234 | Plan!$G$9 | 0.54787
| 74 | 3.5832 | 2.2509 | 5.1452 | 3.633 | 1.24 | 15.8523 | Plan!$G$10 | 0.15949
| 75 | 3.577 | 3.4595 | 5.4754 | 4.3242 | 1.4518 | 18.2879
| 76 | 3.1295 | 2.8945 | 6.1434 | 4.0033 | 1.5929 | 17.7636
| 77 | 3.6208 | 3.0906 | 5.8705 | 3.4176 | 1.5398 | 17.5394
| 78 | 3.6217 | 2.9694 | 5.5111 | 4.6517 | 1.6136 | 18.3675
| 79 | 4.2534 | 2.375 | 5.9469 | 3.6821 | 1.5438 | 17.8012
| 80 | 4.3453 | 2.4465 | 7.0402 | 3.5451 | 1.5526 | 18.9297
| 81 | 4.288 | 2.9087 | 7.2189 | 4.0782 | 1.4102 | 19.9041
| 82 | 3.9176 | 3.1286 | 4.9908 | 4.4675 | 1.2787 | 17.7831
| 83 | 4.4783 | 3.5409 | 5.6098 | 4.6477 | 1.4968 | 19.7735
| 84 | 4.2787 | 2.9875 | 5.6479 | 4.6772 | 1.6314 | 19.2228
| 85 | 4.2864 | 3.7728 | 6.38 | 3.2571 | 1.2721 | 18.9684
| 86 | 4.465 | 2.6526 | 6.5466 | 3.4847 | 1.3372 | 18.4861
| 87 | 3.7924 | 2.9663 | 6.318 | 5.6505 | 1.69 | 20.4172
| 88 | 3.8012 | 2.871 | 5.3249 | 3.641 | 1.2513 | 16.8894
| 89 | 3.9031 | 3.276 | 5.094 | 3.4274 | 1.1302 | 16.8307
| 90 | 3.3298 | 2.5409 | 4.7281 | 4.1939 | 1.14 | 15.9328
| 91 | 4.2994 | 3.1635 | 6.246 | 5.1886 | 1.6079 | 20.5055
| 92 | 4.3191 | 2.8999 | 5.3613 | 4.085 | 1.8367 | 18.502
| 93 | 4.1141 | 2.4691 | 5.7026 | 5.181 | 1.4334 | 18.9002
| 94 | 3.7153 | 3.7029 | 5.5465 | 4.0589 | 1.7364 | 18.7599
| 95 | 4.4088 | 2.824 | 5.1254 | 3.5412 | 1.4609 | 17.3603
| 96 | 3.4499 | 2.6247 | 6.7815 | 3.3029 | 1.0823 | 17.2414
| 97 | 3.3761 | 2.5586 | 7.3394 | 3.9629 | 1.4108 | 18.6477
| 98 | 4.5555 | 2.585 | 4.7354 | 3.6158 | 1.4279 | 16.9196
| 99 | 3.7034 | 3.3664 | 6.8921 | 4.6267 | 1.1421 | 19.7306
| 100 | 4.3083 | 2.4501 | 6.0907 | 5.6221 | 1.5444 | 20.0156
| 101 | 4.8178 | 3.5764 | 5.6896 | 3.698 | 1.8782 | 19.66
| 102 | 4.2522 | 2.8074 | 5.8787 | 4.7864 | 1.1879 | 18.9126
| 103 | 4.5362 | 2.8866 | 4.5672 | 4.0317 | 1.5811 | 17.6027
| 104 | 4.197 | 3.0649 | 6.0613 | 5.0197 | 1.2349 | 19.5777
| 105 | 4.006 | 3.2239 | 5.5825 | 4.2696 | 1.8201 | 18.9021
| 106 | 3.2994 | 2.7153 | 5.3485 | 3.5328 | 1.586 | 16.482
| 107 | 3.5429 | 3.2263 | 4.5918 | 4.4957 | 1.7074 | 17.5641
| 108 | 4.2074 | 2.65 | 4.8884 | 3.8032 | 1.4589 | 17.0079
| 109 | 4.281 | 2.6896 | 5.2905 | 4.0523 | 1.5213 | 17.8347
| 110 | 4.2762 | 2.8587 | 5.3869 | 3.9177 | 1.774 | 18.2134
| 111 | 3.8438 | 2.978 | 5.0343 | 5.7463 | 1.624 | 19.2264
| 112 | 4.2117 | 2.4816 | 7.4869 | 3.8163 | 1.6303 | 19.6268
| 113 | 3.738 | 3.4291 | 7.0035 | 4.1042 | 1.3265 | 19.6012
| 114 | 3.8318 | 3.1351 | 4.9571 | 3.2274 | 1.4884 | 16.6399
| 115 | 3.9264 | 3.5316 | 4.9664 | 3.6617 | 1.5093 | 17.5954
| 116 | 3.6551 | 2.6837 | 5.9217 | 4.7448 | 1.5233 | 18.5285
| 117 | 3.8548 | 2.8553 | 4.4445 | 3.826 | 1.1914 | 16.172
| 118 | 3.1192 | 3.9651 | 6.2123 | 5.6044 | 1.3815 | 20.2826
| 119 | 3.5298 | 3.5837 | 6.9227 | 5.1949 | 1.5281 | 20.7592
| 120 | 3.3391 | 2.5762 | 5.8365 | 4.1835 | 1.312 | 17.2474
| 121 | 3.5893 | 3.5899 | 4.9897 | 3.6568 | 1.645 | 17.4707
| 122 | 4.0107 | 3.473 | 5.5076 | 5.4715 | 1.6907 | 20.1536
| 123 | 4.54 | 2.7199 | 7.1447 | 4.1552 | 1.6121 | 20.1718
| 124 | 3.7832 | 2.4092 | 5.0306 | 3.5369 | 1.2013 | 15.9612
| 125 | 4.657 | 2.7635 | 7.0348 | 4.3366 | 1.8007 | 20.5925
| 126 | 4.3482 | 3.0918 | 4.8921 | 3.5525 | 1.643 | 17.5277
| 127 | 4.2464 | 3.2206 | 4.8199 | 5.2995 | 1.0881 | 18.6746
| 128 | 4.0461 | 3.6424 | 4.9014 | 3.6271 | 1.6955 | 17.9126
| 129 | 3.2745 | 2.9632 | 6.8098 | 3.3961 | 1.2553 | 17.6988
| 130 | 4.218 | 2.7718 | 7.0658 | 3.7342 | 1.5265 | 19.3163
| 131 | 4.1886 | 3.0764 | 4.1551 | 3.7779 | 1.845 | 17.0431
| 132 | 4.4683 | 3.0307 | 5.4299 | 4.5683 | 1.775 | 19.2722
| 133 | 3.5503 | 2.2747 | 5.426 | 4.4224 | 1.8956 | 17.5689
| 134 | 4.6038 | 3.2494 | 6.7497 | 3.4445 | 1.2767 | 19.3241
| 135 | 4.2087 | 2.5289 | 4.8696 | 3.4911 | 1.2548 | 16.353
| 136 | 4.7311 | 2.7405 | 5.6664 | 4.5205 | 1.9444 | 19.603
| 137 | 4.3042 | 3.3231 | 6.0709 | 4.0616 | 1.5787 | 19.3386
| 138 | 3.8091 | 3.1103 | 5.2972 | 3.5105 | 1.7781 | 17.5052
| 139 | 4.5534 | 3.3241 | 5.0033 | 3.1562 | 1.5316 | 17.5686
| 140 | 4.387 | 3.1792 | 6.5861 | 3.213 | 1.3967 | 18.762
| 141 | 4.4567 | 2.6148 | 6.9705 | 4.2981 | 1.3005 | 19.6405
| 142 | 3.8617 | 2.6534 | 7.1319 | 3.9538 | 1.2341 | 18.8349
| 143 | 3.5803 | 2.8265 | 5.3229 | 3.6524 | 1.7601 | 17.1422
| 144 | 3.8958 | 2.6823 | 4.5056 | 4.7401 | 1.5189 | 17.3426
| 145 | 4.0491 | 3.4506 | 4.4558 | 3.8967 | 1.6352 | 17.4875
| 146 | 4.3317 | 2.8912 | 5.6592 | 4.859 | 1.4406 | 19.1817
| 147 | 4.1086 | 3.9248 | 4.9766 | 3.2186 | 1.6153 | 17.844
| 148 | 4.6227 | 2.3184 | 5.0665 | 3.5826 | 1.7634 | 17.3535
| 149 | 4.4923 | 2.0415 | 4.3168 | 4.5318 | 1.3834 | 16.7659
| 150 | 3.9318 | 3.5905 | 6.1861 | 4.4899 | 1.2525 | 19.4508
| 151 | 4.1747 | 2.7683 | 6.7057 | 4.4643 | 1.388 | 19.5011
| 152 | 4.0436 | 3.3004 | 5.1546 | 5.4608 | 1.5177 | 19.4771
| 153 | 4.7808 | 3.0381 | 6.8938 | 3.2918 | 1.724 | 19.7285
| 154 | 3.7776 | 3.0958 | 7.286 | 3.5719 | 1.3536 | 19.085
| 155 | 3.7639 | 2.828 | 6.9872 | 4.3217 | 1.6486 | 19.5495
| 156 | 3.9953 | 3.672 | 4.6806 | 4.4201 | 1.6363 | 18.4043
| 157 | 3.9095 | 3.0125 | 4.3899 | 4.1986 | 1.8409 | 17.3513
| 158 | 4.808 | 2.9713 | 6.4211 | 3.6598 | 1.6823 | 19.5424
| 159 | 3.7785 | 2.6024 | 6.1239 | 4.7152 | 1.6524 | 18.8724
| 160 | 4.4723 | 2.5043 | 5.4679 | 4.16 | 1.6342 | 18.2387
| 161 | 3.8023 | 2.6543 | 5.8879 | 3.3407 | 1.2036 | 16.8888
| 162 | 4.9227 | 3.1124 | 6.5206 | 4.3116 | 1.5976 | 20.4649
| 163 | 4.2832 | 3.3335 | 5.4996 | 5.3156 | 1.7049 | 20.1368
| 164 | 4.0041 | 3.4658 | 5.1273 | 4.2259 | 1.1668 | 17.9898
| 165 | 3.2175 | 3.1417 | 6.6227 | 4.6092 | 1.4291 | 19.0202
| 166 | 4.4295 | 3.4966 | 4.6112 | 5.0592 | 1.4532 | 19.0498
| 167 | 3.8853 | 2.8081 | 5.1781 | 3.2524 | 1.5312 | 16.6551
| 168 | 3.446 | 2.8216 | 6.9208 | 4.8409 | 1.1357 | 19.165
| 169 | 3.7888 | 3.1332 | 6.9941 | 4.4445 | 1.2 | 19.5605
| 170 | 4.3006 | 2.2782 | 6.791 | 4.4926 | 1.3065 | 19.1689
| 171 | 4.5183 | 2.8601 | 6.5392 | 4.4541 | 1.5675 | 19.9391
| 172 | 4.1348 | 2.8023 | 5.1006 | 4.4426 | 1.1436 | 17.6238
| 173 | 4.2549 | 3.5875 | 5.883 | 5.2656 | 1.7364 | 20.7274
| 174 | 4.6192 | 2.687 | 6.0511 | 4.5802 | 1.4724 | 19.4098
| 175 | 3.6274 | 2.7351 | 7.3961 | 3.0609 | 1.4792 | 18.2987
| 176 | 4.2353 | 3.6262 | 4.8972 | 4.028 | 1.4027 | 18.1893
| 177 | 3.7711 | 3.4646 | 5.7228 | 3.73 | 1.473 | 18.1615
| 178 | 3.8754 | 2.5446 | 6.0804 | 5.1078 | 1.0686 | 18.6768
| 179 | 3.8067 | 3.7643 | 4.8232 | 3.9482 | 1.3047 | 17.647
| 180 | 3.733 | 3.5079 | 5.9065 | 4.0352 | 1.6603 | 18.843
| 181 | 3.1443 | 3.0298 | 5.1754 | 4.573 | 1.3597 | 17.2822
| 182 | 4.1462 | 3.2405 | 5.6146 | 3.4089 | 1.5153 | 17.9255
| 183 | 3.5479 | 2.9705 | 6.2686 | 4.4042 | 1.7339 | 18.9251
| 184 | 4.9114 | 3.7831 | 5.0478 | 3.807 | 1.5904 | 19.1396
| 185 | 3.4789 | 2.8516 | 5.0225 | 3.2496 | 1.3745 | 15.9771
| 186 | 4.1619 | 3.0001 | 6.0361 | 4.1416 | 1.8578 | 19.1975
| 187 | 3.9722 | 2.6611 | 7.0876 | 4.388 | 1.7438 | 19.8527
| 188 | 4.4943 | 2.5782 | 5.7787 | 3.5189 | 1.9074 | 18.2776
| 189 | 4.251 | 2.5111 | 7.5007 | 3.5919 | 1.954 | 19.8087
| 190 | 3.3285 | 2.6632 | 4.8689 | 3.3534 | 1.5959 | 15.8099
| 191 | 3.7436 | 2.7453 | 5.3121 | 5.7125 | 1.5237 | 19.0371
| 192 | 3.49 | 3.0464 | 7.4148 | 3.3528 | 1.4421 | 18.7461
| 193 | 3.433 | 3.0946 | 6.1485 | 4.112 | 1.7128 | 18.5008
| 194 | 4.29 | 3.1372 | 5.2141 | 4.1162 | 1.5404 | 18.298
| 195 | 3.7861 | 3.1788 | 5.5526 | 3.9299 | 1.2978 | 17.7452
| 196 | 3.3922 | 3.2636 | 5.9785 | 3.5695 | 1.3191 | 17.5229
| 197 | 4.7906 | 3.1037 | 6.2156 | 3.7455 | 1.5771 | 19.4325
| 198 | 3.3564 | 3.3955 | 4.8479 | 3.9212 | 1.5365 | 17.0574
| 199 | 3.6772 | 3.203 | 5.6555 | 4.9593 | 1.1308 | 18.6258
| 200 | 3.5686 | 3.057 | 5.7959 | 3.5788 | 1.3956 | 17.3959
| 201 | 4.5219 | 2.8768 | 7.1131 | 5.0678 | 1.313 | 20.8925
| 202 | 3.8967 | 2.9111 | 5.1631 | 3.5239 | 1.5013 | 16.9961
| 203 | 4.0991 | 3.6305 | 5.563 | 3.8142 | 1.3239 | 18.4306
| 204 | 4.1246 | 3.1158 | 5.0815 | 3.782 | 1.6094 | 17.7133
| 205 | 4.0392 | 3.039 | 5.1526 | 4.1542 | 1.344 | 17.729
| 206 | 4.3703 | 2.4546 | 5.3888 | 3.8729 | 1.7318 | 17.8185
| 207 | 4.3689 | 2.7905 | 4.8929 | 4.292 | 1.1619 | 17.5061
| 208 | 4.0924 | 2.628 | 5.015 | 3.8477 | 1.5293 | 17.1125
| 209 | 3.2683 | 2.217 | 5.9904 | 3.1615 | 1.3671 | 16.0043
| 210 | 3.8149 | 2.7425 | 5.0074 | 3.9744 | 1.7446 | 17.2839
| 211 | 4.9069 | 2.9192 | 5.0549 | 4.5042 | 1.3591 | 18.7443
| 212 | 3.1566 | 2.2113 | 5.0642 | 4.5703 | 1.0932 | 16.0957
| 213 | 4.2822 | 2.7882 | 6.2574 | 4.18 | 1.6771 | 19.1849
| 214 | 4.3352 | 2.965 | 5.2513 | 4.163 | 1.2427 | 17.9572
| 215 | 3.747 | 3.5931 | 4.3238 | 4.3446 | 1.6452 | 17.6537
| 216 | 3.84 | 3.8297 | 5.3825 | 3.5982 | 1.978 | 18.6284
| 217 | 3.924 | 2.6443 | 6.3279 | 5.6926 | 1.8471 | 20.4359
| 218 | 3.948 | 2.8359 | 5.4499 | 4.6816 | 1.7501 | 18.6653
| 219 | 4.1112 | 3.1521 | 5.8269 | 4.0447 | 1.3471 | 18.482
| 220 | 3.3794 | 2.9571 | 6.6048 | 4.3568 | 1.6424 | 18.9405
| 221 | 3.2874 | 3.8162 | 7.1174 | 3.8547 | 1.7386 | 19.8144
| 222 | 3.9776 | 2.4741 | 4.3816 | 3.9466 | 1.6798 | 16.4597
| 223 | 4.739 | 2.9299 | 4.2562 | 3.5052 | 1.7839 | 17.2142
| 224 | 3.1067 | 2.9756 | 6.0858 | 3.2932 | 1.702 | 17.1633
| 225 | 3.9211 | 2.7587 | 5.174 | 3.7387 | 1.7493 | 17.3418
| 226 | 4.7195 | 3.1071 | 6.2784 | 5.3745 | 1.5546 | 21.0341
| 227 | 3.9904 | 3.5109 | 4.9955 | 3.9667 | 1.3349 | 17.7984
| 228 | 4.451 | 2.7012 | 5.1294 | 4.4146 | 1.2611 | 17.9573
| 229 | 4.3383 | 3.338 | 7.0559 | 4.9141 | 1.4752 | 21.1215
| 230 | 3.608 | 3.3056 | 4.4938 | 4.3971 | 1.5362 | 17.3406
| 231 | 4.1151 | 3.1121 | 5.3922 | 3.938 | 1.8396 | 18.397
| 232 | 3.2019 | 2.8415 | 4.2318 | 4.6419 | 1.5204 | 16.4375
| 233 | 3.9761 | 3.0401 | 4.8807 | 4.8415 | 1.6399 | 18.3782
| 234 | 4.2397 | 2.9723 | 5.5725 | 4.2946 | 1.3879 | 18.467
| 235 | 4.3832 | 3.0828 | 5.0503 | 3.5895 | 1.5488 | 17.6546
| 236 | 3.5334 | 3.1467 | 5.8117 | 3.7471 | 1.4903 | 17.7293
| 237 | 3.973 | 2.6579 | 5.2672 | 3.9892 | 1.2651 | 17.1524
| 238 | 3.438 | 2.8089 | 5.0966 | 3.4668 | 1.5824 | 16.3926
| 239 | 4.7577 | 2.7765 | 5.1031 | 3.6634 | 1.4962 | 17.7969
| 240 | 3.9671 | 2.1651 | 5.5397 | 4.7838 | 1.4041 | 17.8599
| 241 | 4.1714 | 2.7704 | 4.6533 | 4.9231 | 1.6597 | 18.178
| 242 | 4.4347 | 3.0119 | 5.9761 | 5.3863 | 1.7173 | 20.5263
| 243 | 4.1529 | 2.4689 | 5.0747 | 3.4812 | 1.5463 | 16.7241
| 244 | 3.1784 | 2.8608 | 4.542 | 4.7231 | 1.8219 | 17.1263
| 245 | 3.3039 | 2.6338 | 7.1563 | 3.8188 | 1.328 | 18.2408
| 246 | 3.9358 | 3.4462 | 7.2125 | 4.6078 | 1.8128 | 21.0151
| 247 | 3.3668 | 2.7546 | 5.9864 | 4.9806 | 1.1232 | 18.2115
| 248 | 3.9702 | 2.1094 | 6.062 | 5.9232 | 1.5027 | 19.5674
| 249 | 3.7817 | 3.7364 | 5.3565 | 3.7323 | 1.3171 | 17.924
| 250 | 4.639 | 3.8568 | 5.4277 | 3.5625 | 1.8148 | 19.3009
| 251 | 4.5069 | 3.1919 | 7.3132 | 3.7547 | 1.2107 | 19.9775
| 252 | 4.0014 | 3.072 | 4.9062 | 5.3469 | 1.3825 | 18.7091
| 253 | 3.4643 | 3.2535 | 4.1412 | 3.347 | 1.1197 | 15.3258
| 254 | 4.4009 | 2.7243 | 6.1799 | 4.3589 | 1.6761 | 19.34
| 255 | 4.6841 | 2.4967 | 7.3267 | 3.9325 | 1.8346 | 20.2746
| 256 | 4.0558 | 2.6996 | 5.4433 | 4.2086 | 1.875 | 18.2823
| 257 | 3.9655 | 2.6479 | 5.9674 | 3.7013 | 1.1469 | 17.429
| 258 | 4.5271 | 3.2827 | 4.2032 | 3.2016 | 1.4623 | 16.6769
| 259 | 3.8163 | 3.475 | 5.2159 | 5.0625 | 1.7553 | 19.325
| 260 | 3.9187 | 3.2699 | 4.5591 | 4.0606 | 1.1388 | 16.9472
| 261 | 4.1236 | 3.0345 | 5.8757 | 4.4567 | 1.3644 | 18.8548
| 262 | 3.1496 | 2.8964 | 6.0242 | 3.6192 | 1.4098 | 17.0992
| 263 | 3.6341 | 3.0592 | 6.659 | 4.6869 | 1.4512 | 19.4904
| 264 | 3.952 | 3.2964 | 5.442 | 4.2228 | 1.8303 | 18.7434
| 265 | 4.259 | 3.3016 | 5.4803 | 5.235 | 1.2775 | 19.5534
| 266 | 4.6422 | 3.0557 | 5.4311 | 4.874 | 1.2359 | 19.239
| 267 | 3.9156 | 3.063 | 5.331 | 4.1876 | 1.5356 | 18.0328
| 268 | 3.6115 | 2.9036 | 5.5261 | 5.1285 | 1.6373 | 18.8071
| 269 | 4.1774 | 2.9108 | 5.0102 | 3.1903 | 1.7288 | 17.0175
| 270 | 4.2714 | 2.3647 | 4.9703 | 5.4962 | 1.2832 | 18.3859
| 271 | 3.3599 | 2.9452 | 5.7756 | 3.8274 | 1.4199 | 17.328
| 272 | 3.2222 | 3.2085 | 6.0476 | 5.9046 | 1.6867 | 20.0696
| 273 | 3.3476 | 3.7514 | 5.5182 | 4.7263 | 1.2009 | 18.5445
| 274 | 3.7498 | 3.0545 | 6.1214 | 3.1987 | 1.4564 | 17.5809
| 275 | 4.1339 | 2.3944 | 5.6177 | 3.2896 | 1.5908 | 17.0263
| 276 | 4.3527 | 2.2651 | 4.9131 | 4.7771 | 1.5561 | 17.864
| 277 | 4.1685 | 2.9143 | 6.2602 | 3.7861 | 1.4748 | 18.6039
| 278 | 4.4135 | 2.7271 | 4.5639 | 4.2549 | 1.2488 | 17.2082
| 279 | 4.0706 | 3.8465 | 4.7664 | 4.6341 | 1.4689 | 18.7865
| 280 | 4.2379 | 3.1401 | 6.3536 | 3.744 | 1.6751 | 19.1507
| 281 | 3.6945 | 2.6431 | 4.5972 | 5.3113 | 1.5184 | 17.7646
| 282 | 3.9552 | 3.5804 | 6.3139 | 4.4014 | 1.4951 | 19.7461
| 283 | 4.6171 | 2.8433 | 5.6942 | 3.3676 | 1.5127 | 18.0349
| 284 | 3.8951 | 3.4333 | 6.0543 | 4.9289 | 1.832 | 20.1436
| 285 | 3.2956 | 3.398 | 4.8608 | 4.9873 | 1.4932 | 18.0349
| 286 | 4.1605 | 2.8321 | 5.3915 | 3.4366 | 1.4848 | 17.3055
| 287 | 3.78 | 3.1978 | 5.0805 | 4.5105 | 1.2416 | 17.8103
| 288 | 4.0351 | 3.5567 | 6.5719 | 5.5102 | 1.4007 | 21.0745
| 289 | 4.0638 | 2.4723 | 5.3072 | 4.1974 | 1.6623 | 17.7029
| 290 | 4.1522 | 3.8886 | 6.3126 | 3.9426 | 1.7061 | 20.002
| 291 | 3.6499 | 3.108 | 6.4592 | 3.5771 | 1.2901 | 18.0845
| 292 | 4.0788 | 2.9643 | 6.0185 | 3.4332 | 1.689 | 18.1837
| 293 | 4.4657 | 3.0024 | 5.2325 | 3.2602 | 1.4618 | 17.4226
| 294 | 4.3726 | 3.3118 | 5.0213 | 4.073 | 1.5326 | 18.3114
| 295 | 4.4705 | 3.0136 | 5.8774 | 4.6381 | 1.5716 | 19.5712
| 296 | 4.2663 | 2.9599 | 5.903 | 4.3181 | 1.4815 | 18.9287
| 297 | 4.463 | 2.4328 | 6.1994 | 3.6662 | 1.3866 | 18.1479
| 298 | 3.9057 | 2.8376 | 4.7959 | 4.0916 | 1.5183 | 17.1491
| 299 | 4.009 | 2.8252 | 6.6547 | 3.7752 | 1.2373 | 18.5014
| 300 | 4.405 | 3.1548 | 5.3536 | 3.6133 | 1.7149 | 18.2416
| 301 | 3.8768 | 3.3624 | 4.546 | 4.0574 | 1.8434 | 17.6861
| 302 | 3.9687 | 3.0544 | 6.8498 | 4.0994 | 1.3416 | 19.3139
| 303 | 3.2918 | 3.0855 | 5.9153 | 3.7524 | 1.771 | 17.816
| 304 | 3.5227 | 2.718 | 4.8412 | 3.3488 | 1.6718 | 16.1025
| 305 | 4.027 | 3.719 | 7.2667 | 3.9804 | 1.2125 | 20.2055
| 306 | 3.6375 | 2.1464 | 5.1095 | 4.6154 | 1.6412 | 17.15
| 307 | 4.2277 | 3.0432 | 5.3397 | 3.6427 | 1.0219 | 17.2752
| 308 | 3.6513 | 3.1062 | 5.2393 | 3.6486 | 1.444 | 17.0893
| 309 | 3.7531 | 2.5946 | 5.7143 | 3.4387 | 1.3495 | 16.8504
| 310 | 3.9328 | 2.8395 | 4.9038 | 3.4195 | 1.2828 | 16.3784
| 311 | 4.1578 | 2.6724 | 5.9189 | 3.5287 | 1.4842 | 17.7621
| 312 | 3.9545 | 2.8522 | 7.2432 | 3.1861 | 1.3205 | 18.5564
| 313 | 4.6943 | 2.5976 | 4.7136 | 4.0263 | 1.9605 | 17.9924
| 314 | 3.5577 | 2.2412 | 5.3797 | 4.3822 | 1.6149 | 17.1757
| 315 | 3.8326 | 3.0874 | 6.3832 | 3.5305 | 1.7199 | 18.5536
| 316 | 3.4447 | 3.4076 | 4.6483 | 3.4254 | 1.4079 | 16.3338
| 317 | 3.3659 | 3.0159 | 4.4057 | 5.0831 | 1.3726 | 17.2432
| 318 | 4.0255 | 2.3727 | 5.1509 | 3.8634 | 1.3027 | 16.7152
| 319 | 4.3917 | 2.7733 | 5.5382 | 3.5739 | 1.5297 | 17.8068
| 320 | 3.5853 | 3.7088 | 6.0158 | 5.5258 | 1.5052 | 20.3409
| 321 | 4.0419 | 3.0802 | 5.3055 | 4.9284 | 1.3181 | 18.6739
| 322 | 4.3068 | 2.2459 | 4.762 | 4.6284 | 1.4194 | 17.3624
| 323 | 3.6841 | 3.0685 | 7.8181 | 4.2568 | 1.5167 | 20.3441
| 324 | 4.7659 | 2.513 | 5.5761 | 4.536 | 1.3868 | 18.7779
| 325 | 4.8773 | 2.5032 | 4.3686 | 3.4563 | 1.5503 | 16.7558
| 326 | 4.2245 | 2.6106 | 6.7399 | 3.4573 | 1.5946 | 18.6268
| 327 | 4.6508 | 2.9406 | 5.5788 | 4.252 | 1.5223 | 18.9444
| 328 | 4.0889 | 2.8856 | 6.1627 | 3.645 | 1.4176 | 18.1998
| 329 | 4.4313 | 3.3208 | 4.8576 | 3.8753 | 1.7915 | 18.2765
| 330 | 4.6507 | 2.8734 | 4.6412 | 4.2644 | 1.5494 | 17.9792
| 331 | 4.1739 | 3.1234 | 4.9852 | 4.9027 | 1.3656 | 18.5507
| 332 | 3.9917 | 2.6911 | 5.2417 | 3.8872 | 1.6734 | 17.485
| 333 | 4.7081 | 3.5441 | 6.37 | 3.841 | 1.6722 | 20.1355
| 334 | 4.5439 | 3.097 | 6.96 | 3.618 | 1.4428 | 19.6617
| 335 | 4.4191 | 3.0247 | 7.7149 | 5.1777 | 1.4319 | 21.7682
| 336 | 3.6563 | 3.0731 | 5.5158 | 5.4301 | 1.3161 | 18.9914
| 337 | 4.0577 | 3.5384 | 5.4646 | 3.5439 | 1.7217 | 18.3263
| 338 | 3.7601 | 3.5086 | 7.0084 | 4.0181 | 1.3803 | 19.6756
| 339 | 4.8579 | 3.9502 | 6.1366 | 3.924 | 1.6014 | 20.4701
| 340 | 3.9347 | 2.3298 | 4.4177 | 4.3043 | 1.23 | 16.2165
| 341 | 4.424 | 2.3367 | 5.9551 | 3.6714 | 1.2164 | 17.6036
| 342 | 3.9315 | 3.6156 | 5.1468 | 4.3685 | 1.2235 | 18.286
| 343 | 3.7203 | 3.2155 | 4.1707 | 4.1758 | 1.6627 | 16.9449
| 344 | 3.4047 | 3.1734 | 5.5607 | 3.7649 | 1.8881 | 17.7919
| 345 | 4.437 | 2.8287 | 4.7933 | 4.2484 | 1.1581 | 17.4654
| 346 | 3.3878 | 2.6238 | 4.7884 | 5.2127 | 1.1257 | 17.1384
| 347 | 3.4185 | 2.4 | 5.3338 | 3.3357 | 1.3975 | 15.8855
| 348 | 3.8942 | 2.8127 | 6.4128 | 4.9673 | 1.3154 | 19.4023
| 349 | 4.3939 | 2.7299 | 6.4928 | 4.6728 | 1.5611 | 19.8504
| 350 | 4.2725 | 3.7261 | 4.4886 | 3.2563 | 1.7828 | 17.5262
| 351 | 3.3188 | 3.2352 | 6.6258 | 3.5396 | 1.5335 | 18.2529
| 352 | 4.2238 | 3.5826 | 4.8325 | 4.1934 | 1.6437 | 18.476
| 353 | 4.8231 | 3.7475 | 4.8627 | 4.0702 | 1.4498 | 18.9532
| 354 | 3.5933 | 2.2621 | 6.2927 | 4.803 | 1.6935 | 18.6446
| 355 | 4.2802 | 3.1655 | 5.062 | 4.3187 | 1.4866 | 18.3128
| 356 | 4.0573 | 2.6455 | 7.184 | 4.048 | 1.5018 | 19.4366
| 357 | 4.1005 | 3.0837 | 7.2768 | 3.4868 | 1.7541 | 19.702
| 358 | 4.4182 | 2.4365 | 6.6158 | 3.6622 | 1.3766 | 18.5094
| 359 | 3.3711 | 3.8082 | 5.6208 | 4.5567 | 1.7248 | 19.0816
| 360 | 4.0132 | 2.8027 | 6.4757 | 4.9925 | 1.9654 | 20.2495
| 361 | 4.0288 | 3.1387 | 4.5114 | 4.0436 | 1.5702 | 17.2927
| 362 | 4.8044 | 3.0319 | 6.9092 | 3.9828 | 1.2696 | 19.9978
| 363 | 4.3164 | 2.7382 | 7.0471 | 4.8233 | 1.2584 | 20.1834
| 364 | 3.9865 | 3.3414 | 6.6713 | 3.5161 | 1.9 | 19.4154
| 365 | 3.7878 | 3.6647 | 4.3908 | 4.6959 | 1.6283 | 18.1675
| 366 | 3.9471 | 3.3848 | 5.9613 | 3.7612 | 1.5159 | 18.5703
| 367 | 4.1508 | 3.1933 | 6.6012 | 3.1784 | 1.5461 | 18.6697
| 368 | 4.3612 | 2.7338 | 7.579 | 3.2351 | 1.5578 | 19.467
| 369 | 3.6807 | 2.9603 | 7.265 | 3.4506 | 1.8489 | 19.2056
| 370 | 3.6813 | 2.5702 | 6.4477 | 4.1659 | 1.1561 | 18.0212
| 371 | 3.8222 | 3.4446 | 6.4053 | 3.3642 | 1.7729 | 18.8091
| 372 | 3.439 | 3.6561 | 5.8442 | 3.6786 | 1.618 | 18.2359
| 373 | 4.1798 | 2.9988 | 6.4177 | 5.6421 | 1.5973 | 20.8356
| 374 | 4.1954 | 3.716 | 5.3297 | 4.5515 | 1.4302 | 19.2228
| 375 | 4.584 | 2.3493 | 5.0882 | 3.9788 | 1.5389 | 17.5392
| 376 | 3.4529 | 3.501 | 6.3602 | 4.7026 | 1.486 | 19.5027
| 377 | 3.9299 | 2.9318 | 5.471 | 5.0109 | 1.6508 | 18.9944
| 378 | 4.5103 | 3.0821 | 5.0861 | 5.6868 | 1.5846 | 19.95
| 379 | 4.5315 | 2.3122 | 4.7479 | 3.7839 | 1.5868 | 16.9623
| 380 | 4.4882 | 3.6926 | 5.5009 | 4.3719 | 1.5829 | 19.6365
| 381 | 4.5807 | 3.6012 | 6.1115 | 4.5136 | 1.6269 | 20.4341
| 382 | 3.9888 | 3.1992 | 5.974 | 5.0361 | 1.0804 | 19.2783
| 383 | 4.3765 | 3.2834 | 6.033 | 5.0033 | 1.5285 | 20.2248
| 384 | 3.6334 | 2.5199 | 5.5561 | 3.7203 | 1.5036 | 16.9332
| 385 | 4.4967 | 2.9398 | 6.2411 | 4.3757 | 1.5625 | 19.6158
| 386 | 4.3243 | 3.2412 | 6.0723 | 4.1619 | 1.4248 | 19.2246
| 387 | 3.6689 | 3.6038 | 6.1056 | 4.4739 | 1.4275 | 19.2797
| 388 | 3.575 | 3.4385 | 5.7902 | 5.598 | 1.5498 | 19.9515
| 389 | 4.2444 | 3.0164 | 6.3383 | 3.9575 | 1.6913 | 19.2479
| 390 | 3.8902 | 2.5879 | 4.4736 | 5.54 | 1.4217 | 17.9133
| 391 | 4.2023 | 3.0789 | 6.8604 | 5.3329 | 1.6255 | 21.1
| 392 | 4.7445 | 2.9423 | 6.2921 | 3.8521 | 1.6816 | 19.5125
| 393 | 3.9715 | 3.1585 | 6.7154 | 5.772 | 1.6196 | 21.2371
| 394 | 4.773 | 2.8046 | 4.7201 | 4.601 | 1.5655 | 18.4642
| 395 | 4.4595 | 3.4781 | 4.77 | 4.7622 | 1.5101 | 18.9798
| 396 | 4.0026 | 3.0937 | 5.0045 | 3.5127 | 1.5882 | 17.2017
| 397 | 3.8559 | 2.8848 | 5.1834 | 3.5276 | 1.2173 | 16.669
| 398 | 4.4062 | 3.0675 | 5.9369 | 5.5841 | 1.6574 | 20.6521
| 399 | 3.9941 | 2.9055 | 6.0962 | 3.7806 | 1.6708 | 18.4472
| 400 | 3.5695 | 3.1568 | 5.2303 | 3.4772 | 1.5924 | 17.0263
| 401 | 4.8675 | 3.682 | 5.8198 | 4.068 | 1.6555 | 20.0929
| 402 | 4.6457 | 3.6576 | 4.845 | 3.7356 | 1.1026 | 17.9866
| 403 | 3.7758 | 2.4173 | 5.0764 | 4.6062 | 1.5304 | 17.4062
| 404 | 4.5465 | 3.256 | 7.0198 | 3.3227 | 1.0276 | 19.1725
| 405 | 4.0005 | 3.1095 | 4.9743 | 4.9073 | 1.813 | 18.8045
| 406 | 4.3579 | 3.0475 | 6.984 | 5.6669 | 1.412 | 21.4683
| 407 | 4.6308 | 3.8376 | 4.7545 | 3.4049 | 1.1586 | 17.7864
| 408 | 4.6408 | 3.4321 | 5.2711 | 4.1144 | 1.4882 | 18.9466
| 409 | 3.1815 | 3.5636 | 7.4444 | 5.3667 | 1.3788 | 20.935
| 410 | 3.748 | 3.1974 | 5.931 | 3.7634 | 1.568 | 18.2077
| 411 | 3.7988 | 2.5833 | 6.0769 | 4.985 | 1.4804 | 18.9244
| 412 | 3.8332 | 2.6416 | 6.8419 | 4.3667 | 1.9032 | 19.5866
| 413 | 3.8105 | 2.7046 | 6.0895 | 3.7939 | 1.5479 | 17.9464
| 414 | 4.1409 | 3.0889 | 4.6238 | 3.0993 | 1.2323 | 16.1852
| 415 | 3.1651 | 2.8799 | 5.3267 | 4.7675 | 1.122 | 17.2614
| 416 | 3.8698 | 2.8747 | 4.9601 | 3.3083 | 1.4821 | 16.495
| 417 | 4.3462 | 2.5371 | 4.8962 | 3.3814 | 1.2285 | 16.3895
| 418 | 4.6674 | 2.9544 | 5.8609 | 3.9863 | 1.2038 | 18.6727
| 419 | 4.0503 | 2.6713 | 6.3465 | 4.5275 | 1.1484 | 18.744
| 420 | 4.6111 | 2.5569 | 5.2039 | 4.39 | 1.4144 | 18.1763
| 421 | 3.8033 | 2.4912 | 5.5358 | 3.6077 | 1.4992 | 16.9372
| 422 | 4.1899 | 3.1202 | 5.2896 | 4.2328 | 1.2464 | 18.0789
| 423 | 3.1183 | 3.2679 | 4.4784 | 4.0836 | 1.6385 | 16.5868
| 424 | 4.4154 | 2.7574 | 5.352 | 3.3326 | 1.8293 | 17.6868
| 425 | 3.8506 | 2.8178 | 6.8688 | 3.5173 | 1.512 | 18.5665
| 426 | 4.2601 | 3.2915 | 6.5712 | 4.7357 | 1.1855 | 20.044
| 427 | 4.5045 | 2.8979 | 5.014 | 4.1345 | 1.5413 | 18.0922
| 428 | 3.8798 | 2.8976 | 5.1907 | 3.4132 | 1.5045 | 16.8857
| 429 | 3.818 | 3.2226 | 4.6877 | 4.4909 | 1.6534 | 17.8725
| 430 | 4.3345 | 3.2787 | 4.2225 | 5.3435 | 1.4485 | 18.6276
| 431 | 4.036 | 2.9098 | 5.8581 | 5.4365 | 1.2097 | 19.4501
| 432 | 3.8873 | 3.4825 | 5.1584 | 4.535 | 1.1773 | 18.2405
| 433 | 4.2288 | 3.4599 | 4.2718 | 4.5658 | 1.9174 | 18.4437
| 434 | 4.3327 | 3.5126 | 4.5257 | 5.0874 | 1.9147 | 19.373
| 435 | 4.2623 | 2.9944 | 5.7081 | 3.6225 | 1.4741 | 18.0613
| 436 | 3.6739 | 3.0658 | 6.6749 | 5.064 | 1.7334 | 20.2121
| 437 | 3.4119 | 2.6196 | 4.7783 | 3.3842 | 1.4536 | 15.6476
| 438 | 4.3652 | 3.3397 | 5.2941 | 3.2769 | 1.4947 | 17.7706
| 439 | 4.1558 | 3.1626 | 4.3391 | 4.4289 | 1.8182 | 17.9047
| 440 | 3.9254 | 3.2599 | 6.0208 | 5.7567 | 1.1779 | 20.1406
| 441 | 4.7592 | 3.7952 | 5.8637 | 4.0651 | 1.5744 | 20.0576
| 442 | 3.873 | 2.4529 | 5.4111 | 4.8783 | 1.2575 | 17.8727
| 443 | 3.6767 | 2.707 | 4.965 | 3.5076 | 1.7298 | 16.586
| 444 | 3.9407 | 3.5475 | 6.2061 | 3.907 | 1.5147 | 19.116
| 445 | 3.7367 | 2.7018 | 4.802 | 4.5781 | 1.5259 | 17.3444
| 446 | 3.9582 | 3.2642 | 5.8561 | 4.2616 | 1.7977 | 19.1377
| 447 | 3.9618 | 3.3036 | 5.6524 | 3.9106 | 1.8241 | 18.6525
| 448 | 3.6861 | 2.928 | 4.5548 | 3.8305 | 1.4131 | 16.4125
| 449 | 3.4251 | 2.5627 | 4.9964 | 5.0242 | 1.6144 | 17.6228
| 450 | 3.9129 | 3.1021 | 4.437 | 4.2799 | 1.559 | 17.2908
| 451 | 3.699 | 3.0616 | 6.3069 | 4.4525 | 1.5614 | 19.0814
| 452 | 4.487 | 2.7736 | 4.608 | 4.1236 | 1.7817 | 17.7738
| 453 | 3.6171 | 3.491 | 5.5257 | 5.3766 | 1.3906 | 19.4009
| 454 | 3.7517 | 3.5338 | 4.9448 | 5.0727 | 1.7794 | 19.0825
| 455 | 4.3959 | 2.226 | 4.7404 | 4.4692 | 1.259 | 17.0904
| 456 | 4.0494 | 3.0229 | 5.7611 | 5.219 | 1.5074 | 19.5598
| 457 | 4.1062 | 3.098 | 4.9718 | 5.2578 | 1.4692 | 18.9031
| 458 | 3.2559 | 3.38 | 5.6843 | 3.8531 | 1.5025 | 17.6758
| 459 | 3.7066 | 2.4279 | 4.6309 | 4.2031 | 1.7615 | 16.7299
| 460 | 4.3722 | 3.3078 | 5.3654 | 3.1817 | 1.5269 | 17.7539
| 461 | 4.5587 | 2.2585 | 4.9217 | 4.4493 | 1.4016 | 17.5898
| 462 | 3.9369 | 2.9219 | 5.5138 | 4.6618 | 1.317 | 18.3513
| 463 | 3.8427 | 2.9768 | 4.2504 | 4.9625 | 1.5122 | 17.5447
| 464 | 3.3407 | 2.5801 | 5.7527 | 4.8364 | 1.5643 | 18.0743
| 465 | 4.7246 | 2.8631 | 5.6383 | 4.6847 | 1.3319 | 19.2427
| 466 | 4.1012 | 3.0057 | 6.8405 | 3.2859 | 1.4073 | 18.6406
| 467 | 3.4668 | 2.1354 | 5.8035 | 4.005 | 1.4935 | 16.9042
| 468 | 4.4535 | 2.4836 | 5.2875 | 5.1521 | 1.6964 | 19.0732
| 469 | 4.201 | 2.2911 | 6.3502 | 4.4766 | 1.3009 | 18.6198
| 470 | 3.7044 | 2.5683 | 4.9402 | 4.2202 | 1.6588 | 17.092
| 471 | 4.0921 | 3.1561 | 7.7634 | 3.7738 | 1.4781 | 20.2635
| 472 | 4.3415 | 2.4259 | 5.2998 | 3.3895 | 1.2933 | 16.7501
| 473 | 3.1977 | 2.9527 | 5.5223 | 4.1869 | 1.6378 | 17.4974
| 474 | 4.4261 | 3.0367 | 6.217 | 5.0933 | 1.3523 | 20.1254
| 475 | 4.2971 | 2.1957 | 5.1233 | 3.6862 | 1.345 | 16.6474
| 476 | 4.5616 | 3.1433 | 5.3165 | 3.896 | 1.0648 | 17.9822
| 477 | 3.9635 | 3.3526 | 6.6092 | 4.9756 | 1.4349 | 20.3359
| 478 | 3.5378 | 2.4059 | 4.1143 | 5.4532 | 1.4396 | 16.9508
| 479 | 3.472 | 2.9919 | 4.9525 | 3.5253 | 1.5785 | 16.5203
| 480 | 3.5652 | 2.8899 | 5.5985 | 3.5684 | 1.489 | 17.111
| 481 | 4.0402 | 2.6955 | 4.9621 | 5.2106 | 1.4346 | 18.3429
| 482 | 3.6843 | 2.7528 | 4.8139 | 3.4872 | 1.173 | 15.9112
| 483 | 4.2419 | 2.7258 | 6.6345 | 3.9548 | 1.361 | 18.9179
| 484 | 4.7874 | 3.5365 | 7.8827 | 3.4072 | 1.3603 | 20.9742
| 485 | 3.9653 | 2.7097 | 6.7528 | 4.1026 | 1.3479 | 18.8782
| 486 | 4.184 | 3.4813 | 5.5536 | 3.7415 | 1.8709 | 18.8313
| 487 | 4.68 | 3.4285 | 5.116 | 3.5634 | 1.735 | 18.5229
| 488 | 4.0983 | 3.1703 | 4.9289 | 3.7873 | 1.6563 | 17.6412
| 489 | 4.2426 | 2.5239 | 5.664 | 3.2476 | 1.6649 | 17.343
| 490 | 4.2297 | 3.044 | 5.7254 | 4.6701 | 1.0988 | 18.7679
| 491 | 4.1718 | 3.3307 | 6.8786 | 3.7105 | 1.5424 | 19.6341
| 492 | 3.5322 | 3.2051 | 7.4371 | 4.2167 | 1.6068 | 19.9979
| 493 | 4.2159 | 2.7136 | 6.3649 | 4.9568 | 1.1502 | 19.4013
| 494 | 3.2822 | 3.6678 | 6.2984 | 4.2413 | 1.636 | 19.1256
| 495 | 3.7552 | 3.1325 | 5.2363 | 4.7986 | 1.34 | 18.2627
| 496 | 3.1362 | 3.4404 | 7.5112 | 4.9186 | 1.7011 | 20.7076
| 497 | 3.0982 | 3.1188 | 6.1658 | 4.1308 | 1.4598 | 17.9734
| 498 | 4.8316 | 3.575 | 5.6793 | 4.0381 | 1.4696 | 19.5937
| 499 | 4.1949 | 2.381 | 4.9367 | 4.0809 | 1.5065 | 17.1
| 500 | 4.0855 | 2.9733 | 5.2826 | 3.5355 | 1.4136 | 17.2905
| 501 | 3.4822 | 3.3689 | 5.2103 | 4.5945 | 1.6178 | 18.2736
| 502 | 4.3372 | 3.4864 | 5.3204 | 3.5145 | 1.3256 | 17.9841
| 503 | 4.2228 | 2.8118 | 6.7016 | 3.7143 | 1.2859 | 18.7363
| 504 | 4.0662 | 2.9954 | 5.4156 | 3.5597 | 1.5247 | 17.5616
| 505 | 3.776 | 2.7852 | 5.3685 | 3.3434 | 1.4823 | 16.7553
| 506 | 4.1977 | 3.0044 | 4.953 | 4.3638 | 1.4655 | 17.9844
| 507 | 4.159 | 3.219 | 5.4962 | 3.8566 | 1.6786 | 18.4094
| 508 | 3.7702 | 2.6375 | 5.604 | 3.9696 | 1.3987 | 17.3799
| 509 | 3.8634 | 3.1298 | 5.7276 | 3.6898 | 1.3136 | 17.7242
| 510 | 4.074 | 3.0498 | 6.7244 | 4.5294 | 1.3814 | 19.7589
| 511 | 3.6665 | 2.6056 | 5.4129 | 3.6548 | 1.1539 | 16.4937
| 512 | 3.5561 | 2.9314 | 7.2548 | 3.6945 | 1.4237 | 18.8606
| 513 | 3.7926 | 2.1249 | 5.4089 | 3.779 | 1.5562 | 16.6616
| 514 | 4.2059 | 2.9061 | 5.3949 | 4.4402 | 1.6337 | 18.5808
| 515 | 4.3054 | 3.3907 | 4.6004 | 4.9967 | 1.0339 | 18.3271
| 516 | 3.5984 | 3.6886 | 5.308 | 3.8393 | 1.8166 | 18.251
| 517 | 4.3114 | 2.5422 | 6.6113 | 3.6497 | 1.7407 | 18.8554
| 518 | 3.6881 | 3.2299 | 5.4589 | 4.1521 | 1.1742 | 17.7033
| 519 | 3.9859 | 3.3086 | 7.1964 | 4.1064 | 1.5206 | 20.118
| 520 | 4.4385 | 3.0519 | 4.9506 | 3.4415 | 1.6514 | 17.534
| 521 | 3.7277 | 3.4488 | 5.4706 | 5.5212 | 1.17 | 19.3383
| 522 | 3.6286 | 2.3665 | 4.8524 | 4.1287 | 1.4629 | 16.4391
| 523 | 4.4068 | 2.6201 | 7.4006 | 4.2592 | 1.2876 | 19.9742
| 524 | 3.8589 | 2.3695 | 6.3739 | 4.1373 | 1.4165 | 18.1562
| 525 | 3.7179 | 2.4418 | 6.3046 | 3.689 | 1.434 | 17.5873
| 526 | 3.739 | 2.9129 | 6.2247 | 5.0465 | 1.6331 | 19.5561
| 527 | 3.8576 | 3.1949 | 6.6806 | 3.8243 | 1.4475 | 19.0048
| 528 | 4.119 | 3.0261 | 6.7202 | 5.3209 | 1.695 | 20.8813
| 529 | 4.0617 | 3.1669 | 7.6537 | 5.1012 | 1.7707 | 21.7541
| 530 | 3.0744 | 2.7161 | 5.0976 | 5.1664 | 1.3942 | 17.4487
| 531 | 3.8997 | 3.4048 | 6.0119 | 5.2738 | 1.5137 | 20.1039
| 532 | 3.7578 | 3.7126 | 5.2066 | 4.4098 | 1.2798 | 18.3664
| 533 | 4.3125 | 2.2302 | 5.0193 | 5.2812 | 1.7265 | 18.5696
| 534 | 3.7661 | 3.153 | 5.4349 | 3.5603 | 1.5885 | 17.5026
| 535 | 4.0795 | 3.6614 | 6.1532 | 3.4157 | 1.1526 | 18.4624
| 536 | 4.6065 | 3.2015 | 5.1723 | 4.6546 | 1.7426 | 19.3775
| 537 | 3.5823 | 2.4219 | 5.8511 | 3.5728 | 1.6706 | 17.0987
| 538 | 3.949 | 2.5268 | 7.032 | 4.7554 | 1.9091 | 20.1722
| 539 | 3.902 | 3.3341 | 6.4276 | 5.0319 | 1.642 | 20.3376
| 540 | 4.6774 | 3.1169 | 5.1809 | 3.2998 | 1.2707 | 17.5457
| 541 | 3.8864 | 3.2738 | 7.6189 | 4.0212 | 1.3214 | 20.1218
| 542 | 3.3504 | 3.0662 | 6.4418 | 3.5988 | 1.275 | 17.7322
| 543 | 3.735 | 3.6225 | 5.6765 | 4.5175 | 1.2183 | 18.7698
| 544 | 3.66 | 2.6389 | 7.1295 | 4.6002 | 1.3072 | 19.3359
| 545 | 4.1368 | 3.3441 | 4.784 | 4.7968 | 1.8109 | 18.8726
| 546 | 4.1442 | 3.5144 | 4.4323 | 4.2297 | 1.6038 | 17.9244
| 547 | 4.9498 | 2.8834 | 4.6474 | 5.0076 | 1.4552 | 18.9434
| 548 | 3.8981 | 3.361 | 4.9353 | 4.2054 | 1.5795 | 17.9793
| 549 | 3.2772 | 2.693 | 5.8205 | 3.501 | 1.5532 | 16.8449
| 550 | 4.068 | 3.2098 | 6.452 | 4.2753 | 1.5667 | 19.5717
| 551 | 4.5305 | 2.6012 | 4.5698 | 3.8594 | 1.2435 | 16.8044
| 552 | 4.5709 | 2.4853 | 4.7064 | 3.6044 | 1.3487 | 16.7157
| 553 | 4.018 | 3.4058 | 6.4569 | 3.845 | 1.7773 | 19.5029
| 554 | 3.8345 | 3.5961 | 5.1999 | 4.6991 | 1.535 | 18.8646
| 555 | 4.5976 | 3.4789 | 5.4939 | 4.1101 | 1.7989 | 19.4794
| 556 | 3.9969 | 3.2939 | 4.6186 | 5.1232 | 1.5917 | 18.6243
| 557 | 4.0117 | 3.1826 | 7.2272 | 4.4387 | 1.5541 | 20.4143
| 558 | 4.0537 | 2.6125 | 4.7388 | 4.8477 | 1.8606 | 18.1134
| 559 | 3.501 | 2.6483 | 7.5444 | 4.8555 | 1.2816 | 19.8308
| 560 | 3.8898 | 3.5586 | 7.0786 | 3.4002 | 1.1945 | 19.1217
| 561 | 4.2312 | 3.0459 | 4.2883 | 3.3617 | 1.3702 | 16.2972
| 562 | 4.0641 | 3.1447 | 4.8819 | 3.5204 | 1.3853 | 16.9963
| 563 | 4.6544 | 2.4636 | 6.1903 | 4.5967 | 1.2922 | 19.1972
| 564 | 4.3207 | 3.2456 | 4.6863 | 3.7723 | 1.3896 | 17.4145
| 565 | 3.9934 | 3.1873 | 6.5384 | 3.317 | 1.2334 | 18.2696
| 566 | 4.1224 | 3.0806 | 5.158 | 4.0024 | 1.4976 | 17.8611
| 567 | 4.3664 | 2.4929 | 4.7675 | 5.2243 | 1.5941 | 18.4452
| 568 | 4.4761 | 3.217 | 4.787 | 5.5438 | 1.5987 | 19.6227
| 569 | 4.4023 | 3.4924 | 5.037 | 3.7591 | 1.3781 | 18.0689
| 570 | 3.1923 | 3.3199 | 6.3405 | 3.1028 | 1.5719 | 17.5274
| 571 | 3.9677 | 2.396 | 7.1756 | 5.5676 | 1.1811 | 20.288
| 572 | 4.1636 | 3.2445 | 6.7634 | 3.8011 | 1.7869 | 19.7595
| 573 | 4.3257 | 3.5038 | 5.1873 | 4.8887 | 1.7932 | 19.6987
| 574 | 3.5281 | 2.6155 | 4.671 | 5.8712 | 1.59 | 18.2758
| 575 | 3.7689 | 3.3398 | 5.2787 | 5.4206 | 1.2865 | 19.0945
| 576 | 4.2483 | 3.647 | 5.265 | 3.9435 | 1.3378 | 18.4416
| 577 | 3.7726 | 3.3721 | 6.2021 | 3.6029 | 1.5747 | 18.5244
| 578 | 4.2638 | 3.4378 | 5.1129 | 4.746 | 1.2852 | 18.8457
| 579 | 3.9624 | 3.6142 | 5.5846 | 3.6102 | 1.5088 | 18.2802
| 580 | 3.3857 | 3.4237 | 5.1433 | 3.8057 | 1.6192 | 17.3776
| 581 | 3.6157 | 3.4527 | 5.8486 | 3.8101 | 1.9222 | 18.6494
| 582 | 3.4734 | 3.0482 | 4.4714 | 3.9038 | 1.4222 | 16.3191
| 583 | 3.7103 | 3.0415 | 6.8015 | 3.7664 | 1.3106 | 18.6303
| 584 | 3.4275 | 2.4045 | 7.3825 | 4.0336 | 1.2766 | 18.5247
| 585 | 3.797 | 2.5484 | 5.1383 | 3.9651 | 1.0604 | 16.5092
| 586 | 3.8193 | 3.0174 | 5.5455 | 3.87 | 1.6799 | 17.9321
| 587 | 4.4613 | 2.7982 | 5.0707 | 4.482 | 1.7169 | 18.5292
| 588 | 3.6183 | 3.6487 | 4.8186 | 3.8684 | 1.7451 | 17.6991
| 589 | 3.6408 | 3.3445 | 5.4019 | 4.3005 | 1.1111 | 17.7987
| 590 | 3.4987 | 3.262 | 4.7156 | 3.8918 | 1.491 | 16.8591
| 591 | 3.5469 | 3.3877 | 7.3031 | 3.5663 | 1.6035 | 19.4076
| 592 | 4.2206 | 2.6353 | 5.1211 | 3.792 | 1.3051 | 17.0741
| 593 | 3.4949 | 2.5143 | 6.5083 | 3.0701 | 1.3622 | 16.9499
| 594 | 4.055 | 2.6747 | 4.4034 | 3.6909 | 1.711 | 16.535
| 595 | 3.3332 | 3.7618 | 5.6557 | 3.9193 | 1.1127 | 17.7827
| 596 | 4.1259 | 2.6656 | 4.5824 | 5.249 | 1.3409 | 17.9638
| 597 | 3.7958 | 2.0854 | 5.4036 | 3.6424 | 1.6407 | 16.568
| 598 | 4.0453 | 2.8543 | 6.1161 | 3.1263 | 1.2303 | 17.3722
| 599 | 4.0595 | 2.6372 | 6.1732 | 5.0485 | 1.654 | 19.5723
| 600 | 3.871 | 2.1288 | 7.0707 | 3.611 | 1.7188 | 18.4003
| 601 | 4.5749 | 3.0104 | 5.17 | 4.555 | 1.1267 | 18.437
| 602 | 3.1857 | 2.7772 | 5.9831 | 4.939 | 1.4579 | 18.343
| 603 | 4.6342 | 2.8646 | 4.6819 | 5.4786 | 1.8854 | 19.5447
| 604 | 3.4768 | 2.5541 | 5.9694 | 4.863 | 1.854 | 18.7172
| 605 | 3.9826 | 2.7038 | 6.9419 | 3.6575 | 1.5421 | 18.8279
| 606 | 4.1278 | 2.3013 | 5.338 | 3.6671 | 1.3563 | 16.7904
| 607 | 3.836 | 2.6706 | 5.4521 | 3.4931 | 1.0772 | 16.529
| 608 | 4.4112 | 2.6321 | 5.6228 | 3.0911 | 1.3146 | 17.0718
| 609 | 4.2266 | 3.058 | 5.9446 | 3.7314 | 1.758 | 18.7187
| 610 | 3.8921 | 2.4225 | 5.3028 | 3.8798 | 1.8504 | 17.3476
| 611 | 4.1039 | 3.5432 | 4.5242 | 5.3611 | 1.3933 | 18.9258
| 612 | 4.4547 | 3.0506 | 5.7487 | 3.4113 | 1.8337 | 18.499
| 613 | 4.4403 | 3.813 | 7.6223 | 3.646 | 1.3736 | 20.8952
| 614 | 3.4923 | 2.4118 | 5.8654 | 4.7058 | 1.1754 | 17.6507
| 615 | 4.0737 | 2.8339 | 5.0408 | 3.449 | 1.3247 | 16.722
| 616 | 3.937 | 3.1898 | 4.4569 | 3.2367 | 1.6273 | 16.4477
| 617 | 3.91 | 2.8005 | 5.9967 | 4.2851 | 1.4328 | 18.4251
| 618 | 3.725 | 2.3775 | 5.1079 | 4.236 | 1.8022 | 17.2486
| 619 | 3.8214 | 2.9961 | 5.4236 | 3.4698 | 1.5965 | 17.3075
| 620 | 3.7646 | 3.9183 | 5.7697 | 4.8829 | 1.4149 | 19.7506
| 621 | 3.8814 | 3.6993 | 4.6437 | 4.8109 | 1.3635 | 18.3989
| 622 | 4.1422 | 2.3524 | 4.6985 | 5.1493 | 1.5662 | 17.9086
| 623 | 4.0442 | 2.6299 | 4.6278 | 4.0106 | 1.3511 | 16.6636
| 624 | 3.953 | 3.229 | 4.5077 | 3.8207 | 1.182 | 16.6925
| 625 | 4.1539 | 3.6527 | 5.9392 | 5.4188 | 1.6101 | 20.7746
| 626 | 3.6096 | 3.2326 | 4.7018 | 3.3203 | 1.7655 | 16.6298
| 627 | 4.0761 | 2.3228 | 5.6159 | 3.9013 | 1.6075 | 17.5237
| 628 | 4.5157 | 2.9809 | 4.6635 | 4.0163 | 1.5066 | 17.683
| 629 | 4.048 | 2.7115 | 4.9877 | 4.619 | 1.2668 | 17.6329
| 630 | 4.3584 | 3.9024 | 5.8295 | 5.2787 | 1.2211 | 20.5901
| 631 | 4.0936 | 3.1263 | 5.3742 | 3.8624 | 1.4944 | 17.951
| 632 | 4.0693 | 2.2566 | 7.1072 | 3.75 | 1.0714 | 18.2545
| 633 | 4.276 | 2.7282 | 7.2352 | 3.8854 | 1.5375 | 19.6624
| 634 | 3.2301 | 3.2106 | 6.4042 | 4.6694 | 1.4548 | 18.9691
| 635 | 4.2734 | 2.9927 | 5.936 | 3.4694 | 1.046 | 17.7175
| 636 | 4.1859 | 3.0062 | 4.5322 | 4.1914 | 1.1897 | 17.1054
| 637 | 3.8467 | 2.1906 | 5.8463 | 3.8784 | 1.2717 | 17.0337
| 638 | 3.8369 | 2.4485 | 5.3424 | 3.8746 | 1.7584 | 17.2608
| 639 | 3.9972 | 3.3141 | 5.5301 | 3.5932 | 1.562 | 17.9965
| 640 | 3.4568 | 3.4621 | 5.6882 | 3.3824 | 1.8375 | 17.827
| 641 | 3.9249 | 3.5999 | 5.4868 | 4.5471 | 1.3757 | 18.9344
| 642 | 3.9926 | 3.7322 | 5.7553 | 4.6456 | 1.6921 | 19.8178
| 643 | 3.875 | 2.5354 | 6.3637 | 4.0149 | 1.6321 | 18.4211
| 644 | 4.2319 | 3.2896 | 5.9982 | 5.1865 | 1.2945 | 20.0006
| 645 | 4.2581 | 2.7442 | 5.2075 | 3.959 | 1.3253 | 17.4942
| 646 | 3.868 | 2.8558 | 5.6703 | 4.8521 | 1.3462 | 18.5925
| 647 | 3.9604 | 2.5186 | 5.4916 | 4.1713 | 1.6053 | 17.7471
| 648 | 4.1051 | 2.8443 | 5.2763 | 5.1388 | 1.4845 | 18.849
| 649 | 3.9289 | 3.1256 | 4.7322 | 4.1192 | 1.3709 | 17.2767
| 650 | 4.4791 | 2.6974 | 4.1892 | 3.6799 | 1.602 | 16.6477
| 651 | 4.084 | 3.6192 | 5.04 | 3.2097 | 1.613 | 17.566
| 652 | 4.0211 | 3.0294 | 5.7196 | 3.4279 | 1.1631 | 17.3611
| 653 | 3.8793 | 3.2852 | 5.8051 | 5.1576 | 1.3697 | 19.497
| 654 | 4.007 | 2.8168 | 4.6206 | 4.5493 | 1.9708 | 17.9645
| 655 | 4.5435 | 2.9819 | 5.7513 | 4.1568 | 1.2388 | 18.6725
| 656 | 4.4836 | 2.4382 | 4.4264 | 4.0829 | 1.576 | 17.0072
| 657 | 4.2983 | 2.656 | 4.825 | 4.1498 | 1.5228 | 17.4519
| 658 | 4.4336 | 2.3857 | 4.7303 | 3.1717 | 1.6754 | 16.3968
| 659 | 4.1497 | 3.0077 | 5.2475 | 3.8576 | 1.688 | 17.9505
| 660 | 4.4418 | 2.9591 | 6.2852 | 4.7923 | 1.5106 | 19.9891
| 661 | 3.9841 | 2.9671 | 5.1884 | 5.4815 | 1.6162 | 19.2373
| 662 | 3.6942 | 3.4099 | 5.2564 | 4.8207 | 1.0896 | 18.2708
| 663 | 3.6036 | 2.3875 | 4.3342 | 3.5862 | 1.1976 | 15.1092
| 664 | 4.2038 | 2.1156 | 5.7352 | 5.2269 | 1.211 | 18.4924
| 665 | 3.9566 | 3.0093 | 4.7529 | 4.7092 | 1.5508 | 17.9788
| 666 | 3.6259 | 2.9441 | 5.219 | 3.822 | 1.5997 | 17.2107
| 667 | 3.6307 | 3.3173 | 4.8782 | 4.2605 | 1.4761 | 17.5627
| 668 | 3.5262 | 2.9744 | 5.2615 | 4.1692 | 1.4438 | 17.3752
| 669 | 4.1382 | 2.9031 | 5.8383 | 3.6247 | 1.7463 | 18.2504
| 670 | 4.538 | 2.9458 | 4.4386 | 3.9931 | 1.5836 | 17.4991
| 671 | 3.5414 | 3.4245 | 4.3492 | 3.4798 | 1.4916 | 16.2865
| 672 | 4.5971 | 2.7607 | 5.7445 | 4.8171 | 1.479 | 19.3985
| 673 | 4.3437 | 2.9505 | 4.8533 | 3.8321 | 1.7382 | 17.7179
| 674 | 3.2631 | 2.3207 | 6.8996 | 3.4603 | 1.5256 | 17.4693
| 675 | 3.5673 | 3.4426 | 5.1948 | 3.2401 | 1.7845 | 17.2293
| 676 | 4.1922 | 3.1682 | 6.5895 | 4.9448 | 1.2079 | 20.1025
| 677 | 3.2103 | 2.6689 | 4.9311 | 3.638 | 1.7569 | 16.2051
| 678 | 3.3073 | 3.3819 | 4.5364 | 5.1737 | 1.8038 | 18.2031
| 679 | 4.1025 | 3.0607 | 4.8364 | 4.0303 | 1.9231 | 17.9529
| 680 | 4.429 | 3.2178 | 5.6068 | 4.7576 | 1.6481 | 19.6594
| 681 | 4.0956 | 3.0241 | 7.6018 | 4.0512 | 1.6231 | 20.3957
| 682 | 3.9991 | 2.5903 | 6.3235 | 4.4155 | 1.5639 | 18.8923
| 683 | 3.8595 | 3.3511 | 5.0534 | 5.164 | 1.3954 | 18.8234
| 684 | 4.3293 | 3.3856 | 5.6296 | 3.5839 | 1.8054 | 18.7338
| 685 | 3.3533 | 2.3272 | 4.4946 | 3.479 | 1.3534 | 15.0076
| 686 | 3.8719 | 3.2389 | 4.3408 | 3.7923 | 1.7944 | 17.0382
| 687 | 3.612 | 3.0144 | 4.3596 | 4.175 | 1.7254 | 16.8864
| 688 | 4.0757 | 3.7927 | 6.7128 | 4.0966 | 1.6114 | 20.2893
| 689 | 3.8292 | 2.9241 | 6.0092 | 4.0769 | 1.5858 | 18.4252
| 690 | 4.1412 | 2.849 | 5.2738 | 5.0286 | 1.7912 | 19.0837
| 691 | 4.0899 | 2.8929 | 5.8949 | 3.4829 | 1.7141 | 18.0746
| 692 | 4.55 | 2.0641 | 5.0846 | 3.9116 | 1.3086 | 16.9188
| 693 | 4.6018 | 2.9389 | 4.7736 | 5.1187 | 1.4307 | 18.8637
| 694 | 3.4851 | 2.7918 | 5.5489 | 3.7987 | 1.0552 | 16.6797
| 695 | 3.2492 | 3.3698 | 4.918 | 4.9514 | 1.5431 | 18.0315
| 696 | 3.654 | 2.5661 | 6.962 | 4.4585 | 1.4355 | 19.0762
| 697 | 3.7237 | 3.4685 | 6.0456 | 3.2795 | 1.5594 | 18.0766
| 698 | 3.0612 | 3.4146 | 5.4171 | 3.8673 | 1.7759 | 17.5361
| 699 | 3.5209 | 3.2065 | 4.8271 | 4.2071 | 1.7118 | 17.4734
| 700 | 3.6578 | 3.0894 | 4.9985 | 5.5929 | 1.5894 | 18.9281
| 701 | 4.6237 | 3.1147 | 5.7654 | 3.9677 | 1.3999 | 18.8714
| 702 | 3.2419 | 2.994 | 5.9524 | 4.4984 | 1.6506 | 18.3372
| 703 | 4.2144 | 2.4161 | 5.9593 | 4.8971 | 1.5632 | 19.0502
| 704 | 4.7498 | 3.8789 | 4.4241 | 3.7966 | 1.1333 | 17.9827
| 705 | 4.0721 | 3.1877 | 5.7376 | 4.5823 | 1.6169 | 19.1966
| 706 | 4.0071 | 2.8654 | 5.5739 | 3.9991 | 1.6106 | 18.0561
| 707 | 3.8416 | 2.5347 | 7.1678 | 3.7228 | 1.2276 | 18.4945
| 708 | 3.336 | 3.4898 | 6.1767 | 5.3359 | 1.8691 | 20.2075
| 709 | 3.7453 | 2.553 | 6.4971 | 3.7581 | 1.22 | 17.7735
| 710 | 3.7317 | 2.8483 | 5.9252 | 4.4187 | 1.7414 | 18.6653
| 711 | 3.8646 | 2.7372 | 6.5522 | 5.834 | 1.4926 | 20.4805
| 712 | 4.6995 | 3.3554 | 7.1024 | 3.9724 | 1.629 | 20.7586
| 713 | 3.9439 | 2.5229 | 6.5248 | 3.4431 | 1.7888 | 18.2234
| 714 | 4.3865 | 3.6688 | 5.3589 | 3.7082 | 1.4602 | 18.5826
| 715 | 4.5246 | 3.1589 | 5.2846 | 3.8899 | 1.4561 | 18.3141
| 716 | 4.1295 | 2.8668 | 5.0577 | 3.4303 | 1.3232 | 16.8075
| 717 | 4.3016 | 2.5296 | 5.6993 | 3.96 | 1.4651 | 17.9557
| 718 | 4.2112 | 3.4008 | 6.2355 | 4.2386 | 1.215 | 19.3011
| 719 | 3.5874 | 2.6789 | 6.1338 | 4.3637 | 1.8031 | 18.5669
| 720 | 3.9207 | 3.3366 | 6.9516 | 5.5666 | 1.5514 | 21.3269
| 721 | 3.9793 | 3.5194 | 5.2203 | 4.7787 | 1.5473 | 19.0449
| 722 | 4.4812 | 2.7806 | 5.5909 | 3.3941 | 1.6611 | 17.9079
| 723 | 3.4599 | 3.2242 | 5.6481 | 3.5544 | 1.2476 | 17.1342
| 724 | 3.7981 | 2.876 | 6.945 | 5.198 | 1.7477 | 20.5647
| 725 | 3.7737 | 3.1724 | 5.3629 | 3.3557 | 1.3832 | 17.0478
| 726 | 3.9749 | 3.3065 | 5.0894 | 3.377 | 1.3425 | 17.0903
| 727 | 4.7969 | 3.0266 | 5.7671 | 4.7116 | 1.6467 | 19.949
| 728 | 3.7539 | 2.2958 | 5.7879 | 3.8463 | 1.5099 | 17.1938
| 729 | 4.3786 | 2.9843 | 5.8162 | 4.539 | 1.5008 | 19.2189
| 730 | 3.7496 | 2.8623 | 5.7591 | 4.5922 | 1.4712 | 18.4344
| 731 | 4.2849 | 3.2363 | 6.6291 | 4.1073 | 1.6087 | 19.8663
| 732 | 4.0605 | 2.1757 | 4.7916 | 4.2344 | 1.2385 | 16.5006
| 733 | 4.2702 | 3.3109 | 5.8003 | 5.7239 | 1.1901 | 20.2953
| 734 | 4.1778 | 2.7238 | 6.3898 | 4.385 | 1.852 | 19.5283
| 735 | 3.5056 | 3.6411 | 5.7051 | 3.4739 | 1.1142 | 17.4398
| 736 | 4.2459 | 2.7967 | 5.5884 | 4.3938 | 1.251 | 18.2757
| 737 | 4.1454 | 2.4341 | 6.129 | 4.2782 | 1.5583 | 18.545
| 738 | 4.2667 | 3.0705 | 6.2387 | 3.1525 | 1.5696 | 18.298
| 739 | 4.2562 | 3.0084 | 4.6357 | 3.9518 | 1.7862 | 17.6382
| 740 | 3.8666 | 2.5888 | 4.9556 | 3.3973 | 1.3346 | 16.143
| 741 | 3.7576 | 3.0999 | 5.8335 | 4.4471 | 1.5324 | 18.6705
| 742 | 3.5737 | 2.5511 | 4.8037 | 3.3732 | 1.1708 | 15.4725
| 743 | 4.0519 | 3.1432 | 5.0166 | 4.4846 | 1.2804 | 17.9767
| 744 | 4.3543 | 3.6236 | 7.1896 | 3.3338 | 1.4361 | 19.9374
| 745 | 4.4118 | 3.3777 | 5.4633 | 5.1356 | 1.4869 | 19.8753
| 746 | 3.6735 | 2.617 | 5.3823 | 3.976 | 1.5409 | 17.1898
| 747 | 3.4137 | 2.9537 | 5.5316 | 4.6927 | 1.6209 | 18.2124
| 748 | 3.9076 | 2.5166 | 5.1313 | 4.3072 | 1.6001 | 17.4628
| 749 | 3.3131 | 2.9251 | 4.4848 | 3.8355 | 1.6855 | 16.2441
| 750 | 4.0308 | 3.2659 | 6.7865 | 3.6847 | 1.4682 | 19.2361
| 751 | 3.511 | 2.7934 | 4.3971 | 3.6005 | 1.8836 | 16.1856
| 752 | 4.0832 | 3.1616 | 5.2118 | 4.9493 | 1.5341 | 18.9399
| 753 | 3.8135 | 3.0868 | 5.1335 | 4.4327 | 1.7134 | 18.1798
| 754 | 3.8839 | 2.7793 | 4.7005 | 4.6902 | 1.43 | 17.4839
| 755 | 3.8278 | 2.7942 | 6.0433 | 3.8078 | 1.418 | 17.891
| 756 | 3.8413 | 2.4298 | 5.6124 | 4.4313 | 1.4986 | 17.8134
| 757 | 4.2166 | 2.6035 | 6.4464 | 4.6208 | 1.5877 | 19.475
| 758 | 3.9037 | 3.3496 | 5.4209 | 3.4962 | 1.2656 | 17.436
| 759 | 4.7014 | 2.4586 | 6.0301 | 4.6662 | 1.666 | 19.5223
| 760 | 4.3848 | 3.1486 | 5.2955 | 3.2676 | 1.2055 | 17.302
| 761 | 4.0859 | 2.9979 | 6.6899 | 4.0394 | 1.2566 | 19.0698
| 762 | 4.0038 | 2.9068 | 5.2433 | 3.7179 | 1.6634 | 17.5352
| 763 | 3.4873 | 2.8786 | 4.7767 | 3.6052 | 1.5304 | 16.2782
| 764 | 3.2462 | 3.4111 | 5.9498 | 3.1311 | 1.2618 | 17
| 765 | 4.6076 | 2.6756 | 6.1939 | 4.0492 | 1.4584 | 18.9847
| 766 | 3.8461 | 3.0526 | 5.8244 | 4.1467 | 1.7007 | 18.5705
| 767 | 4.6697 | 2.3144 | 6.0568 | 4.2002 | 1.552 | 18.7931
| 768 | 3.4053 | 2.4429 | 6.3029 | 5.2386 | 1.4426 | 18.8324
| 769 | 4.0335 | 2.8 | 6.7604 | 3.4916 | 1.4464 | 18.5319
| 770 | 3.3735 | 2.7748 | 5.7117 | 3.3912 | 1.6692 | 16.9204
| 771 | 4.722 | 3.3736 | 6.4803 | 3.5482 | 1.0505 | 19.1746
| 772 | 4.0821 | 2.8104 | 5.6338 | 3.1655 | 1.6838 | 17.3755
| 773 | 4.1811 | 3.5648 | 5.7156 | 5.49 | 1.9386 | 20.8901
| 774 | 3.7082 | 2.8885 | 6.7988 | 4.5867 | 1.6672 | 19.6493
| 775 | 3.9806 | 2.5616 | 5.476 | 4.2139 | 1.4831 | 17.7151
| 776 | 4.03 | 3.6853 | 5.3717 | 3.6736 | 1.1684 | 17.9289
| 777 | 4.8337 | 3.0636 | 5.4368 | 4.8037 | 1.7099 | 19.8477
| 778 | 4.3155 | 2.9357 | 6.9378 | 3.707 | 1.6782 | 19.5742
| 779 | 3.5966 | 2.9614 | 6.8627 | 4.809 | 1.5113 | 19.741
| 780 | 3.6704 | 2.4883 | 6.8317 | 3.6998 | 1.581 | 18.2712
| 781 | 3.5983 | 3.2517 | 6.5643 | 4.3802 | 1.3664 | 19.1609
| 782 | 3.9002 | 3.3945 | 4.466 | 3.9227 | 1.2263 | 16.9097
| 783 | 3.5188 | 2.1599 | 5.4491 | 3.5753 | 1.7692 | 16.4724
| 784 | 3.7413 | 2.479 | 6.5571 | 3.6371 | 1.4955 | 17.9101
| 785 | 4.5087 | 2.3458 | 7.0943 | 4.7747 | 1.8087 | 20.5323
| 786 | 4.1934 | 3.3587 | 6.5598 | 3.9782 | 1.311 | 19.4013
| 787 | 4.7152 | 3.4843 | 7.2056 | 5.4469 | 1.6997 | 22.5516
| 788 | 3.2594 | 2.9904 | 4.2105 | 4.1329 | 1.9329 | 16.5261
| 789 | 3.7125 | 2.7473 | 5.6308 | 4.8299 | 1.3339 | 18.2544
| 790 | 3.9226 | 3.5163 | 4.8657 | 3.3668 | 1.58 | 17.2515
| 791 | 4.2091 | 3.355 | 6.156 | 5.0141 | 1.291 | 20.0252
| 792 | 4.356 | 3.258 | 5.5972 | 3.4748 | 1.2846 | 17.9705
| 793 | 3.5026 | 2.6854 | 4.6758 | 3.8994 | 1.2629 | 16.0261
| 794 | 4.4845 | 3.1202 | 4.7079 | 4.559 | 1.3674 | 18.239
| 795 | 3.8055 | 2.3035 | 6.5934 | 4.7648 | 1.402 | 18.8692
| 796 | 4.4477 | 3.2805 | 6.3946 | 5.2403 | 1.8913 | 21.2544
| 797 | 3.8381 | 3.2553 | 5.0462 | 3.6292 | 1.2497 | 17.0185
| 798 | 4.6618 | 3.4475 | 5.7819 | 5.2959 | 1.373 | 20.56
| 799 | 3.5547 | 3.4554 | 5.626 | 4.6326 | 1.5343 | 18.803
| 800 | 3.4418 | 2.3616 | 6.7791 | 4.9101 | 1.4637 | 18.9563
| 801 | 4.3998 | 2.2331 | 7.1595 | 5.1459 | 1.1607 | 20.099
| 802 | 3.6054 | 3.3477 | 5.7715 | 4.4351 | 1.467 | 18.6266
| 803 | 4.3181 | 2.046 | 5.7942 | 3.4037 | 1.425 | 16.987
| 804 | 3.6655 | 2.8473 | 5.5592 | 3.5491 | 1.2953 | 16.9163
| 805 | 4.0282 | 3.3247 | 5.3999 | 4.3398 | 1.2599 | 18.3525
| 806 | 3.8042 | 2.9144 | 7.6994 | 5.0536 | 1.2454 | 20.717
| 807 | 4.768 | 2.8055 | 5.2583 | 4.0943 | 1.4267 | 18.3528
| 808 | 4.0626 | 2.5728 | 5.5417 | 3.0858 | 1.4776 | 16.7405
| 809 | 4.4225 | 2.6634 | 4.5961 | 3.9313 | 1.7802 | 17.3935
| 810 | 4.4501 | 3.2276 | 4.9806 | 4.022 | 1.9347 | 18.615
| 811 | 3.1714 | 3.6752 | 4.8732 | 3.7712 | 1.5937 | 17.0848
| 812 | 3.945 | 2.6926 | 5.567 | 4.625 | 1.1019 | 17.9315
| 813 | 3.697 | 3.3462 | 6.146 | 4.0127 | 1.7193 | 18.9211
| 814 | 3.4217 | 2.9767 | 5.1934 | 4.1179 | 1.6846 | 17.3943
| 815 | 3.7282 | 3.6104 | 7.3686 | 3.1203 | 1.0965 | 18.924
| 816 | 3.6901 | 2.7627 | 5.06 | 5.3019 | 1.6495 | 18.4641
| 817 | 3.5527 | 3.6953 | 6.0816 | 5.3548 | 1.3649 | 20.0492
| 818 | 4.2194 | 3.3756 | 5.9104 | 4.1271 | 1.6931 | 19.3256
| 819 | 3.8887 | 2.7645 | 5.4381 | 3.4458 | 1.2237 | 16.7608
| 820 | 4.0198 | 3.2479 | 5.8419 | 3.7042 | 1.5469 | 18.3607
| 821 | 3.8786 | 3.416 | 5.5205 | 3.432 | 1.6873 | 17.9344
| 822 | 3.7839 | 3.607 | 5.0272 | 3.4524 | 1.4259 | 17.2964
| 823 | 3.6985 | 3.4941 | 4.7989 | 4.1459 | 1.4003 | 17.5377
| 824 | 4.157 | 3.0196 | 5.26 | 3.902 | 1.4368 | 17.7753
| 825 | 4.1821 | 3.8026 | 5.9824 | 5.8166 | 1.4706 | 21.2543
| 826 | 4.1477 | 3.1709 | 4.992 | 3.5947 | 1.3472 | 17.2524
| 827 | 4.0243 | 2.3992 | 4.7216 | 3.8343 | 1.1645 | 16.144
| 828 | 4.8128 | 2.7592 | 5.0679 | 3.7277 | 1.7603 | 18.1278
| 829 | 3.94 | 3.6371 | 6.732 | 3.7423 | 1.7961 | 19.8476
| 830 | 3.9786 | 3.3576 | 7.0239 | 3.9152 | 1.4262 | 19.7015
| 831 | 3.5906 | 3.8447 | 6.9146 | 3.1402 | 1.4155 | 18.9054
| 832 | 4.3977 | 3.0283 | 5.1684 | 3.2719 | 1.5538 | 17.4201
| 833 | 3.3463 | 3.5058 | 6.5179 | 5.2541 | 1.3567 | 19.9807
| 834 | 4.0243 | 3.5525 | 6.8246 | 4.8483 | 1.5952 | 20.845
| 835 | 4.0377 | 3.1493 | 4.9468 | 4.7539 | 1.1062 | 17.9938
| 836 | 3.9597 | 2.4876 | 6.0991 | 5.623 | 1.3218 | 19.4912
| 837 | 4.0164 | 3.3831 | 6.8188 | 3.4236 | 1.517 | 19.1589
| 838 | 3.5387 | 2.7398 | 6.7745 | 4.6138 | 1.5552 | 19.2219
| 839 | 4.1352 | 2.8388 | 4.9424 | 4.5199 | 1.3847 | 17.821
| 840 | 3.5355 | 3.4194 | 5.2691 | 4.1222 | 1.4377 | 17.7839
| 841 | 3.3026 | 2.71 | 6.0046 | 4.5762 | 1.2991 | 17.8924
| 842 | 3.6243 | 3.1505 | 6.5107 | 3.3065 | 1.7522 | 18.3443
| 843 | 3.3622 | 2.6964 | 5.1396 | 3.7566 | 1.4643 | 16.4191
| 844 | 4.1999 | 2.8694 | 4.8849 | 3.9987 | 1.4391 | 17.392
| 845 | 4.5664 | 2.8504 | 5.503 | 4.2897 | 1.406 | 18.6155
| 846 | 3.5784 | 2.6675 | 5.4899 | 3.2303 | 1.3926 | 16.3586
| 847 | 4.1265 | 2.9887 | 5.2267 | 4.3119 | 1.3791 | 18.0329
| 848 | 3.981 | 3.2383 | 4.8582 | 3.4892 | 1.2214 | 16.7882
| 849 | 4.2495 | 2.6099 | 5.461 | 3.1161 | 1.5084 | 16.9448
| 850 | 4.1134 | 3.1746 | 6.6948 | 3.3299 | 1.7966 | 19.1093
| 851 | 4.5204 | 3.7581 | 7.6852 | 3.3395 | 1.8234 | 21.1266
| 852 | 4.5767 | 3.1245 | 7.7894 | 3.1966 | 1.3574 | 20.0446
| 853 | 3.5926 | 3.2007 | 5.4807 | 3.7504 | 1.363 | 17.3875
| 854 | 4.1646 | 2.5094 | 6.0676 | 4.9749 | 1.7519 | 19.4684
| 855 | 4.0318 | 2.8702 | 4.5734 | 4.0877 | 1.6676 | 17.2307
| 856 | 4.7846 | 3.5286 | 4.6735 | 4.0744 | 1.7682 | 18.8293
| 857 | 3.3127 | 3.7772 | 7.7369 | 4.4855 | 1.2143 | 20.5266
| 858 | 3.2717 | 2.5953 | 5.136 | 3.6937 | 1.3331 | 16.0299
| 859 | 3.8536 | 2.3905 | 6.2726 | 3.8433 | 1.6059 | 17.9659
| 860 | 3.9113 | 2.5829 | 5.662 | 4.2902 | 1.631 | 18.0774
| 861 | 3.7166 | 2.9332 | 4.9198 | 4.5417 | 1.3 | 17.4113
| 862 | 3.9832 | 2.1727 | 5.4055 | 3.4726 | 1.5369 | 16.5709
| 863 | 4.5629 | 2.938 | 5.3767 | 3.4946 | 1.4614 | 17.8336
| 864 | 4.6272 | 3.5232 | 6.5496 | 3.3446 | 1.4807 | 19.5253
| 865 | 3.7261 | 3.7436 | 5.3695 | 3.1752 | 1.1965 | 17.2108
| 866 | 3.9388 | 2.894 | 4.4626 | 4.9987 | 1.8976 | 18.1917
| 867 | 4.8965 | 2.6273 | 4.4991 | 3.8144 | 1.6251 | 17.4624
| 868 | 3.285 | 3.7231 | 4.3533 | 3.3701 | 1.5197 | 16.2511
| 869 | 4.0125 | 2.9795 | 4.8995 | 4.3605 | 1.4227 | 17.6746
| 870 | 3.7911 | 2.209 | 6.6418 | 4.2721 | 1.5149 | 18.4288
| 871 | 3.5628 | 2.622 | 5.1202 | 4.0667 | 1.6684 | 17.0401
| 872 | 4.5928 | 3.3887 | 4.9798 | 4.5621 | 1.3077 | 18.8311
| 873 | 4.1491 | 2.2212 | 4.9091 | 3.3575 | 1.2961 | 15.9329
| 874 | 3.6401 | 3.2673 | 6.1142 | 4.249 | 1.6585 | 18.929
| 875 | 4.499 | 3.393 | 6.3441 | 3.3104 | 1.6261 | 19.1726
| 876 | 3.9574 | 2.89 | 4.6916 | 3.7367 | 1.2064 | 16.4822
| 877 | 3.974 | 2.1896 | 4.9239 | 3.5338 | 1.3389 | 15.9602
| 878 | 4.6875 | 3.469 | 7.3165 | 3.297 | 1.4633 | 20.2333
| 879 | 4.6815 | 3.5711 | 5.2501 | 4.2274 | 1.6297 | 19.3598
| 880 | 3.5086 | 3.4026 | 4.1914 | 3.7136 | 1.5454 | 16.3617
| 881 | 3.9275 | 2.937 | 4.2436 | 4.2874 | 1.6473 | 17.0427
| 882 | 4.0903 | 2.2005 | 4.726 | 4.3541 | 1.9269 | 17.2978
| 883 | 4.1096 | 2.5071 | 5.6761 | 3.2059 | 1.4702 | 16.9689
| 884 | 4.1696 | 2.1522 | 5.078 | 4.4606 | 1.9488 | 17.8092
| 885 | 3.8138 | 3.0015 | 5.7288 | 3.7036 | 1.5219 | 17.7697
| 886 | 3.8694 | 3.2712 | 5.7833 | 3.3793 | 1.8667 | 18.1699
| 887 | 4.4219 | 2.4771 | 6.6532 | 4.2666 | 1.4092 | 19.228
| 888 | 3.7872 | 2.7891 | 6.4693 | 3.2642 | 1.3945 | 17.7043
| 889 | 3.6641 | 2.7494 | 4.54 | 3.4657 | 1.5777 | 15.997
| 890 | 4.7036 | 3.0329 | 6.252 | 4.8985 | 1.7272 | 20.6143
| 891 | 3.8202 | 2.9472 | 6.3756 | 3.0237 | 1.5723 | 17.739
| 892 | 4.1676 | 2.7554 | 5.593 | 3.6145 | 1.8947 | 18.0252
| 893 | 4.0184 | 3.4219 | 6.6399 | 4.1689 | 1.3904 | 19.6395
| 894 | 3.4669 | 2.5386 | 4.9832 | 3.4362 | 1.3306 | 15.7555
| 895 | 4.1658 | 3.8705 | 4.9333 | 4.282 | 1.4897 | 18.7413
| 896 | 3.4886 | 3.3985 | 4.3696 | 4.4709 | 1.8281 | 17.5557
| 897 | 4.129 | 2.3468 | 5.5873 | 3.3143 | 1.3394 | 16.7168
| 898 | 3.3958 | 2.9802 | 5.0924 | 5.0423 | 1.6009 | 18.1117
| 899 | 3.8264 | 3.3148 | 6.8727 | 3.6087 | 1.8554 | 19.478
| 900 | 3.6452 | 3.426 | 6.6641 | 4.8764 | 1.3693 | 19.981
| 901 | 4.7548 | 2.8826 | 5.0429 | 5.2886 | 1.6464 | 19.6152
| 902 | 4.1177 | 3.1468 | 5.1984 | 5.4409 | 1.1171 | 19.021
| 903 | 4.0972 | 3.2311 | 4.5151 | 3.2701 | 1.5603 | 16.6738
| 904 | 3.8476 | 2.823 | 5.0508 | 3.5228 | 1.3775 | 16.6216
| 905 | 3.2078 | 3.7058 | 4.3087 | 4.315 | 1.2689 | 16.8063
| 906 | 3.454 | 3.1355 | 5.0003 | 3.581 | 1.9112 | 17.082
| 907 | 4.8435 | 3.1838 | 5.6411 | 3.5044 | 1.6642 | 18.8369
| 908 | 3.5603 | 2.5312 | 4.4491 | 3.8886 | 1.7081 | 16.1373
| 909 | 3.8525 | 2.9157 | 6.9287 | 3.2229 | 1.4717 | 18.3914
| 910 | 4.2032 | 3.2973 | 4.519 | 3.302 | 1.5136 | 16.835
| 911 | 4.1119 | 3.2043 | 4.9685 | 3.145 | 1.184 | 16.6138
| 912 | 4.6152 | 3.5605 | 6.6835 | 3.8832 | 1.1452 | 19.8876
| 913 | 3.9146 | 3.3631 | 6.3917 | 3.9411 | 1.7058 | 19.3164
| 914 | 4.4445 | 2.7666 | 7.47 | 3.8368 | 1.4114 | 19.9293
| 915 | 4.504 | 3.4127 | 4.4141 | 4.3738 | 1.5734 | 18.2779
| 916 | 4.7132 | 3.0351 | 7.4849 | 4.3421 | 1.4315 | 21.0068
| 917 | 4.2932 | 3.5693 | 6.8132 | 5.1315 | 1.329 | 21.1363
| 918 | 3.3811 | 3.74 | 6.4333 | 4.3328 | 1.4371 | 19.3244
| 919 | 3.794 | 2.3081 | 4.6685 | 3.3861 | 1.4161 | 15.5729
| 920 | 3.6481 | 2.2874 | 6.9969 | 5.3989 | 1.7208 | 20.052
| 921 | 4.1871 | 3.2134 | 7.9021 | 4.1826 | 1.3294 | 20.8147
| 922 | 3.4494 | 3.022 | 7.5295 | 4.9688 | 1.2252 | 20.1948
| 923 | 3.3937 | 3.2911 | 7.0627 | 4.7199 | 1.6985 | 20.1658
| 924 | 3.5248 | 3.0205 | 7.372 | 3.4591 | 1.4676 | 18.844
| 925 | 3.6466 | 2.3584 | 5.009 | 4.4067 | 1.0438 | 16.4644
| 926 | 4.5672 | 2.9511 | 4.9397 | 4.5025 | 1.4285 | 18.389
| 927 | 3.8825 | 3.2792 | 4.1448 | 5.6613 | 1.2531 | 18.2209
| 928 | 3.8115 | 3.6314 | 6.4631 | 4.3468 | 1.723 | 19.9757
| 929 | 4.0381 | 2.6067 | 6.3244 | 3.9269 | 1.557 | 18.4531
| 930 | 4.0423 | 3.5302 | 6.8538 | 4.0087 | 1.8265 | 20.2615
| 931 | 4.0776 | 2.4581 | 6.5265 | 3.5315 | 1.4774 | 18.0709
| 932 | 4.0344 | 3.1757 | 5.0328 | 3.9352 | 1.3501 | 17.5282
| 933 | 4.5014 | 2.7832 | 5.8071 | 4.0411 | 1.3363 | 18.4691
| 934 | 4.3516 | 3.7867 | 4.6605 | 4.3511 | 1.3097 | 18.4596
| 935 | 3.7028 | 2.3421 | 6.1604 | 3.9899 | 1.3718 | 17.5669
| 936 | 3.4012 | 3.122 | 6.1406 | 3.7267 | 1.3197 | 17.7102
| 937 | 3.7186 | 2.9204 | 6.128 | 3.3885 | 1.7485 | 17.9039
| 938 | 3.4156 | 3.4715 | 6.4356 | 4.2168 | 1.5384 | 19.078
| 939 | 4.3092 | 2.5561 | 5.1604 | 3.9142 | 1.5848 | 17.5247
| 940 | 3.6445 | 2.8681 | 5.9935 | 4.9177 | 1.7038 | 19.1275
| 941 | 4.0091 | 2.9431 | 6.7293 | 5.4094 | 1.4454 | 20.5363
| 942 | 4.1197 | 3.4576 | 5.2351 | 3.8125 | 1.685 | 18.3098
| 943 | 3.8488 | 2.8299 | 5.0287 | 3.1358 | 1.5757 | 16.4188
| 944 | 3.398 | 2.8142 | 4.9149 | 3.3244 | 1.6026 | 16.0541
| 945 | 3.4297 | 3.036 | 5.8963 | 4.7321 | 1.5394 | 18.6335
| 946 | 4.1909 | 2.7077 | 4.2975 | 5.3285 | 1.3582 | 17.8828
| 947 | 4.3139 | 3.0034 | 7.567 | 5.5027 | 1.4063 | 21.7932
| 948 | 4.015 | 2.7335 | 4.8384 | 4.8648 | 1.7031 | 18.1549
| 949 | 3.8512 | 3.2879 | 5.7331 | 3.6696 | 1.4973 | 18.0391
| 950 | 3.9168 | 3.4182 | 5.2253 | 4.6408 | 1.8896 | 19.0907
| 951 | 4.5135 | 2.5925 | 6.8266 | 3.4018 | 1.4905 | 18.8249
| 952 | 3.9422 | 3.2468 | 5.7871 | 3.9491 | 1.5004 | 18.4257
| 953 | 4.363 | 3.522 | 6.8846 | 4.243 | 1.4798 | 20.4924
| 954 | 3.8083 | 3.185 | 6.5021 | 3.4626 | 1.4544 | 18.4123
| 955 | 3.513 | 2.956 | 4.6341 | 4.4262 | 1.4489 | 16.9783
| 956 | 3.6141 | 3.2729 | 5.1048 | 3.9283 | 1.6222 | 17.5424
| 957 | 3.3843 | 3.1138 | 5.1175 | 3.3603 | 1.8637 | 16.8396
| 958 | 4.3928 | 2.4143 | 5.2445 | 3.7898 | 1.4053 | 17.2466
| 959 | 3.6008 | 2.9256 | 4.6952 | 3.9839 | 1.7313 | 16.9368
| 960 | 3.7603 | 3.2142 | 5.9008 | 3.9078 | 1.447 | 18.2301
| 961 | 3.7677 | 3.2592 | 6.4721 | 4.3267 | 1.2441 | 19.0696
| 962 | 3.6431 | 2.7842 | 5.317 | 4.833 | 1.6201 | 18.1973
| 963 | 3.6612 | 2.955 | 5.6819 | 5.2042 | 1.5076 | 19.01
| 964 | 4.0214 | 3.0184 | 6.2485 | 4.7276 | 1.4766 | 19.4925
| 965 | 3.0851 | 3.6083 | 5.1846 | 4.3306 | 1.8453 | 18.054
| 966 | 4.0656 | 3.8614 | 4.7505 | 4.1437 | 1.4126 | 18.2338
| 967 | 3.4348 | 2.2703 | 6.2859 | 3.4149 | 1.4033 | 16.8092
| 968 | 3.4708 | 2.4951 | 6.5778 | 4.7507 | 1.4385 | 18.7328
| 969 | 4.3748 | 3.0696 | 4.29 | 4.7714 | 1.4208 | 17.9265
| 970 | 3.8655 | 2.4612 | 7.3439 | 4.309 | 1.448 | 19.4276
| 971 | 4.473 | 3.1863 | 4.0883 | 4.1784 | 1.4661 | 17.3921
| 972 | 3.5163 | 2.2403 | 6.4111 | 4.7385 | 1.81 | 18.7162
| 973 | 4.3502 | 3.2943 | 4.6573 | 4.0895 | 1.4403 | 17.8317
| 974 | 4.5519 | 2.7681 | 5.201 | 3.7993 | 1.5056 | 17.826
| 975 | 4.2332 | 2.7518 | 6.5011 | 4.941 | 1.3359 | 19.7631
| 976 | 3.8611 | 2.8345 | 4.558 | 4.8255 | 1.2889 | 17.3679
| 977 | 4.2681 | 3.3283 | 4.3743 | 3.5859 | 1.6737 | 17.2303
| 978 | 3.6898 | 2.9346 | 5.7019 | 3.7162 | 1.6393 | 17.6818
| 979 | 4.3799 | 2.9869 | 6.7698 | 3.4483 | 1.5241 | 19.1091
| 980 | 3.7012 | 3.6362 | 6.265 | 3.8936 | 1.5277 | 19.0237
| 981 | 4.5342 | 3.1807 | 5.9287 | 5.7358 | 1.6807 | 21.0601
| 982 | 3.6789 | 2.9179 | 4.8085 | 4.6608 | 1.0853 | 17.1513
| 983 | 4.3232 | 2.9854 | 6.1671 | 5.1087 | 1.4206 | 20.005
| 984 | 3.2349 | 3.3748 | 7.5579 | 4.2463 | 1.571 | 19.9849
| 985 | 4.5731 | 2.3823 | 6.4862 | 4.3783 | 1.3916 | 19.2115
| 986 | 3.0288 | 3.0927 | 5.1647 | 3.937 | 1.5736 | 16.7967
| 987 | 3.5153 | 3.7301 | 4.2824 | 3.6716 | 1.4503 | 16.6497
| 988 | 3.8305 | 3.3274 | 5.6358 | 3.6267 | 1.56 | 17.9804
| 989 | 4.7342 | 2.8307 | 4.8424 | 4.5081 | 1.3799 | 18.2953
| 990 | 4.9564 | 2.3346 | 6.0022 | 3.7088 | 1.3859 | 18.3879
| 991 | 3.5069 | 2.8789 | 7.1419 | 3.5878 | 1.4414 | 18.5569
| 992 | 4.6336 | 2.9222 | 5.8912 | 4.2735 | 1.457 | 19.1775
| 993 | 3.6621 | 3.6792 | 4.9101 | 3.4213 | 1.5032 | 17.1759
| 994 | 3.6316 | 2.6597 | 4.8318 | 4.9324 | 1.1369 | 17.1924
| 995 | 4.3625 | 2.9016 | 6.9751 | 3.5968 | 1.3025 | 19.1385
| 996 | 4.1067 | 2.7193 | 4.7108 | 3.3266 | 1.7672 | 16.6306
| 997 | 3.9504 | 2.2812 | 5.6023 | 5.0905 | 1.4527 | 18.3771
| 998 | 4.1166 | 3.1028 | 5.3974 | 4.0245 | 1.6045 | 18.246
| 999 | 3.7089 | 3.1907 | 5.4465 | 3.4635 | 1.446 | 17.2555
| 1000 | 3.9515 | 2.4988 | 6.5323 | 3.636 | 1.3991 | 18.0178
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Risk Results 2
Navigation |  | Inputs |  |  |  |  | Outputs | Simulation Statistics |  | Output Cumulative Distributions | Output Distributions | Risk Tornado Diagram
Risk Outputs |  | Plan!$G$6 | Plan!$G$7 | Plan!$G$8 | Plan!$G$9 | Plan!$G$10 | Plan!$G$11 |  | Plan!$G$11 |  |  |  |  | Correlations - Column 1 sorted
Simulation Statistics | Iterations | RiskTriang(D6,E6,F6) | RiskTriang(D7,E7,F7) | RiskTriang(D8,E8,F8) | RiskTriang(D9,E9,F9) | RiskTriang(D10,E10,F10) | LiveDate |  | LiveDate |  |  | Select Output: | Plan!$G$11 |  | Plan!$G$11
Risk Output Percentiles | 1 | 3.3385 | 3.2607 | 6.8496 | 4.1944 | 1.2099 | 18.8531 | Mean | 18.3333 |  |  | Name: | LiveDate | Risk Inputs | LiveDate
Calculate Percent Rank | 2 | 4.2767 | 3.9029 | 4.5014 | 4.1346 | 1.3014 | 18.1172 | Median | 18.2436 |  |  | 1 |  | Plan!$G$10 | 0.20975
Correlations | 3 | 4.2686 | 3.8365 | 5.4688 | 3.6979 | 1.7018 | 18.9736 | Mode | #N/A |  |  | Tornado Diagram for LiveDate (Plan!$G$11) |  | Plan!$G$6 | 0.3109
Output Cumulative Distributions | 4 | 4.1976 | 2.8745 | 6.0875 | 3.8733 | 1.2366 | 18.2695 | Std. Deviation | 1.2015 |  |  |  |  | Plan!$G$7 | 0.31192
Output Distributions | 5 | 3.7522 | 3.2961 | 6.6896 | 4.5146 | 1.4002 | 19.6527 | Variance | 1.4435 |  |  |  |  | Plan!$G$9 | 0.49798
Risk Tornado Diagram | 6 | 3.4849 | 3.5332 | 4.758 | 3.9473 | 1.7054 | 17.4289 | Kurtosis | -0.12217 |  |  |  |  | Plan!$G$8 | 0.679
| 7 | 4.3264 | 2.2538 | 5.0614 | 3.8352 | 1.5329 | 17.0098 | Skewness | 0.24903
| 8 | 3.8192 | 2.8049 | 5.6321 | 4.5542 | 1.2627 | 18.0731 | Minimum | 15.3148
| 9 | 3.3023 | 2.9966 | 5.8254 | 3.6684 | 1.6688 | 17.4616 | Maximum | 22.1628
| 10 | 4.4065 | 3.302 | 4.8888 | 4.4289 | 1.7291 | 18.7553 | Range | 6.8479
| 11 | 3.8387 | 3.1865 | 6.6606 | 3.5446 | 1.351 | 18.5813 | Count | 1000
| 12 | 4.51 | 3.7923 | 4.8752 | 3.8884 | 1.1458 | 18.2117 | Error Count | 0
| 13 | 4.0153 | 3.0882 | 7.0129 | 3.4188 | 1.7867 | 19.3217 | Std. Error | 0.037994
| 14 | 3.9106 | 2.7136 | 6.2118 | 3.848 | 1.8438 | 18.5279 | Confidence Level (95%) | 0.074557
| 15 | 3.5116 | 3.1793 | 4.9497 | 3.7607 | 1.3665 | 16.7678
| 16 | 4.0451 | 3.3433 | 6.1853 | 4.3964 | 1.5629 | 19.5331 | Percentiles
| 17 | 4.1261 | 3.3823 | 5.2918 | 4.6584 | 1.3872 | 18.8459 |  | Plan!$G$11
| 18 | 3.9523 | 3.157 | 6.8566 | 3.944 | 1.3184 | 19.2283 |  | LiveDate
| 19 | 3.8244 | 3.0591 | 5.7255 | 3.8048 | 1.1829 | 17.5967 | 0% | 15.3148
| 20 | 4.4667 | 2.9457 | 7.5194 | 3.1783 | 1.2502 | 19.3604 | 2.5% | 16.1599
| 21 | 3.976 | 2.2412 | 5.1915 | 4.8828 | 1.1619 | 17.4534 | 5% | 16.4607
| 22 | 3.7968 | 2.74 | 4.2016 | 5.2428 | 1.3936 | 17.3748 | 7.5% | 16.6793
| 23 | 4.5951 | 2.8791 | 5.6635 | 3.5987 | 1.6943 | 18.4306 | 10% | 16.7936
| 24 | 3.7757 | 2.4214 | 4.7015 | 5.1855 | 1.2516 | 17.3357 | 12.5% | 16.9524
| 25 | 4.1221 | 2.9432 | 5.562 | 3.9841 | 1.8718 | 18.4832 | 15% | 17.09
| 26 | 3.515 | 3.459 | 4.9316 | 4.3369 | 1.6445 | 17.8869 | 17.5% | 17.2093
| 27 | 3.9741 | 3.5648 | 7.0782 | 4.8617 | 1.4039 | 20.8827 | 20% | 17.3014
| 28 | 4.4845 | 2.8111 | 6.3387 | 3.6939 | 1.1443 | 18.4724 | 22.5% | 17.4076
| 29 | 4.1878 | 2.7359 | 6.3009 | 3.7255 | 1.5786 | 18.5287 | 25% | 17.5128
| 30 | 4.5493 | 3.4558 | 4.5091 | 3.4497 | 1.9377 | 17.9016 | 27.5% | 17.5674
| 31 | 4.1507 | 2.9074 | 6.8542 | 4.4199 | 1.816 | 20.1483 | 30% | 17.6592
| 32 | 4.2277 | 3.5295 | 5.0586 | 4.9476 | 1.436 | 19.1995 | 32.5% | 17.7323
| 33 | 4.2698 | 3.6216 | 5.2893 | 5.235 | 1.3761 | 19.7919 | 35% | 17.8246
| 34 | 3.8812 | 3.4095 | 5.4978 | 5.2257 | 1.449 | 19.4632 | 37.5% | 17.8945
| 35 | 3.7867 | 3.2279 | 4.6507 | 3.8024 | 1.6391 | 17.1067 | 40% | 17.9691
| 36 | 3.4329 | 2.7239 | 4.6389 | 4.4101 | 1.5015 | 16.7073 | 42.5% | 18.059
| 37 | 4.1473 | 2.5306 | 6.5041 | 5.8096 | 1.6533 | 20.6448 | 45% | 18.1171
| 38 | 4.2978 | 3.1721 | 4.7234 | 5.033 | 1.1763 | 18.4026 | 47.5% | 18.1693
| 39 | 4.72 | 3.164 | 5.0751 | 3.7916 | 1.1126 | 17.8634 | 50% | 18.2436
| 40 | 3.7832 | 2.5255 | 5.8846 | 3.9581 | 1.5167 | 17.6681 | 52.5% | 18.3198
| 41 | 4.1005 | 3.4829 | 4.7928 | 4.0671 | 1.2742 | 17.7175 | 55% | 18.4273
| 42 | 3.8773 | 3.6707 | 4.3705 | 4.7519 | 1.1997 | 17.87 | 57.5% | 18.5244
| 43 | 4.6063 | 2.7371 | 6.1693 | 3.3841 | 1.4 | 18.2969 | 60% | 18.5983
| 44 | 3.6095 | 3.009 | 4.7117 | 5.6956 | 1.1304 | 18.1562 | 62.5% | 18.695
| 45 | 3.1469 | 2.1375 | 5.266 | 4.5936 | 1.9201 | 17.0641 | 65% | 18.758
| 46 | 3.7395 | 2.5735 | 5.1712 | 4.1497 | 1.5146 | 17.1485 | 67.5% | 18.8377
| 47 | 4.3127 | 3.7901 | 5.9093 | 4.1766 | 1.5531 | 19.7418 | 70% | 18.9253
| 48 | 3.8887 | 3.3163 | 7.0164 | 4.0617 | 1.2409 | 19.524 | 72.5% | 19.0585
| 49 | 4.8044 | 2.6261 | 5.0046 | 4.7942 | 1.308 | 18.5374 | 75% | 19.145
| 50 | 4.1463 | 2.6742 | 6.4042 | 3.1817 | 1.5737 | 17.9801 | 77.5% | 19.2523
| 51 | 4.0936 | 2.7803 | 5.6686 | 4.6775 | 1.4746 | 18.6945 | 80% | 19.3369
| 52 | 3.9943 | 3.7444 | 4.8408 | 4.2469 | 1.5132 | 18.3396 | 82.5% | 19.4622
| 53 | 4.061 | 2.7236 | 5.0479 | 3.2342 | 1.3109 | 16.3777 | 85% | 19.5735
| 54 | 4.208 | 3.354 | 7.1829 | 5.217 | 1.6718 | 21.6339 | 87.5% | 19.731
| 55 | 3.6618 | 2.9736 | 4.903 | 5.01 | 1.4328 | 17.9812 | 90% | 19.888
| 56 | 3.6825 | 3.5841 | 6.6541 | 5.014 | 1.5661 | 20.5008 | 92.5% | 20.1131
| 57 | 3.6374 | 3.0693 | 5.2742 | 4.3087 | 1.6907 | 17.9803 | 95% | 20.3991
| 58 | 3.8344 | 3.5224 | 6.8081 | 4.718 | 1.6262 | 20.5091 | 97.5% | 20.8836
| 59 | 4.041 | 2.7964 | 6.737 | 5.0605 | 1.4892 | 20.1241 | 100% | 22.1628
| 60 | 4.0821 | 2.6064 | 5.9129 | 3.951 | 1.6066 | 18.159
| 61 | 4.8393 | 3.6864 | 5.2289 | 4.562 | 1.7489 | 20.0654 | Percent Rank
| 62 | 3.5607 | 3.0185 | 7.3484 | 4.9463 | 1.6008 | 20.4747 |  | Plan!$G$11
| 63 | 4.678 | 3.6513 | 4.675 | 3.6539 | 1.287 | 17.9453 |  | LiveDate
| 64 | 4.3219 | 2.7051 | 5.7267 | 3.9387 | 1.3633 | 18.0556 | Enter Value: | 16.4607
| 65 | 4.0699 | 2.6944 | 5.6473 | 3.6588 | 1.493 | 17.5634 | % rank: | 5%
| 66 | 3.5541 | 3.7175 | 5.4593 | 3.5618 | 1.5322 | 17.8247
| 67 | 3.0934 | 2.542 | 7.4098 | 4.9956 | 1.3561 | 19.3969 | Correlations
| 68 | 4.4152 | 3.2525 | 4.4512 | 4.056 | 1.5468 | 17.7217 |  | Plan!$G$11
| 69 | 4.0358 | 2.5434 | 5.0519 | 4.2273 | 1.2638 | 17.1222 | Risk Inputs | LiveDate
| 70 | 3.716 | 2.715 | 4.2196 | 4.74 | 1.0988 | 16.4894 | Plan!$G$6 | 0.3109
| 71 | 4.1648 | 3.1984 | 5.4721 | 3.1603 | 1.3948 | 17.3905 | Plan!$G$7 | 0.31192
| 72 | 4.3054 | 2.3341 | 5.476 | 3.9687 | 1.4589 | 17.5431 | Plan!$G$8 | 0.679
| 73 | 3.7417 | 3.4245 | 6.3571 | 3.504 | 1.4897 | 18.5171 | Plan!$G$9 | 0.49798
| 74 | 4.3841 | 2.7943 | 7.0935 | 4.7057 | 1.8271 | 20.8048 | Plan!$G$10 | 0.20975
| 75 | 3.8659 | 3.0353 | 6.3883 | 4.3741 | 1.6032 | 19.2667
| 76 | 4.0148 | 2.7555 | 6.2379 | 4.5462 | 1.6132 | 19.1677
| 77 | 3.8673 | 2.4388 | 4.7891 | 4.7249 | 1.5334 | 17.3535
| 78 | 4.4955 | 2.5591 | 5.9637 | 3.8458 | 1.3448 | 18.2088
| 79 | 3.5202 | 2.482 | 5.0405 | 4.5831 | 1.3059 | 16.9317
| 80 | 4.4325 | 3.5053 | 6.0679 | 3.5633 | 1.6306 | 19.1996
| 81 | 4.2868 | 2.9401 | 6.8733 | 4.1897 | 1.6419 | 19.9319
| 82 | 3.4136 | 3.8503 | 6.0223 | 3.9765 | 1.4052 | 18.668
| 83 | 3.9282 | 3.0449 | 5.3157 | 5.537 | 1.5041 | 19.3298
| 84 | 3.9355 | 2.3733 | 7.6688 | 3.6001 | 1.1927 | 18.7704
| 85 | 4.4543 | 2.8696 | 4.4739 | 4.0581 | 1.4008 | 17.2567
| 86 | 3.5356 | 3.3295 | 7.2847 | 3.4546 | 1.5134 | 19.1178
| 87 | 4.2718 | 3.1371 | 5.8711 | 3.7513 | 1.6164 | 18.6478
| 88 | 4.5998 | 3.0103 | 4.9566 | 3.531 | 1.2571 | 17.3548
| 89 | 4.3728 | 3.3256 | 6.7532 | 3.2974 | 1.5391 | 19.2881
| 90 | 3.9066 | 2.1853 | 5.9329 | 4.8583 | 1.3939 | 18.2769
| 91 | 4.13 | 2.9681 | 5.9388 | 4.172 | 1.252 | 18.4611
| 92 | 4.1495 | 2.3523 | 6.3258 | 3.4556 | 1.5889 | 17.8721
| 93 | 4.5047 | 3.1466 | 5.4964 | 3.5112 | 1.5052 | 18.1641
| 94 | 4.3595 | 2.9895 | 4.928 | 3.0816 | 1.8686 | 17.2271
| 95 | 4.0167 | 2.7847 | 5.0846 | 3.5261 | 1.0848 | 16.497
| 96 | 4.0906 | 2.9305 | 6.0825 | 4.641 | 1.6743 | 19.4189
| 97 | 4.4766 | 2.9125 | 5.1372 | 4.2287 | 1.2655 | 18.0204
| 98 | 4.1272 | 2.8553 | 6.1492 | 4.0291 | 1.9151 | 19.0759
| 99 | 3.6355 | 2.9253 | 5.8112 | 4.8886 | 1.7158 | 18.9764
| 100 | 3.8073 | 2.839 | 5.1042 | 3.8096 | 1.1189 | 16.6791
| 101 | 3.6646 | 3.1966 | 5.2783 | 4.696 | 1.6951 | 18.5306
| 102 | 3.7496 | 3.0549 | 6.6955 | 5.4275 | 1.4708 | 20.3983
| 103 | 3.567 | 2.9634 | 5.3346 | 5.3151 | 1.5463 | 18.7264
| 104 | 4.2377 | 3.4042 | 5.645 | 5.169 | 1.5899 | 20.0459
| 105 | 3.883 | 2.6088 | 6.4308 | 3.4638 | 1.5174 | 17.9038
| 106 | 3.977 | 3.4199 | 5.4033 | 3.8824 | 1.4968 | 18.1793
| 107 | 4.7524 | 2.8115 | 4.9404 | 3.7139 | 1.6489 | 17.8671
| 108 | 3.9662 | 3.2722 | 5.1836 | 4.4579 | 1.5478 | 18.4276
| 109 | 4.601 | 3.0987 | 6.1269 | 5.9448 | 1.4103 | 21.1817
| 110 | 4.7054 | 2.9816 | 5.1647 | 4.9169 | 1.7224 | 19.491
| 111 | 4.2824 | 2.2948 | 4.4786 | 4.2372 | 1.3054 | 16.5984
| 112 | 4.3346 | 3.2745 | 7.1224 | 3.3933 | 1.415 | 19.5398
| 113 | 3.9664 | 2.7788 | 6.3101 | 3.9129 | 1.4176 | 18.3858
| 114 | 3.0828 | 3.2356 | 4.4963 | 3.7979 | 1.3745 | 15.9872
| 115 | 3.5508 | 3.4348 | 4.7759 | 4.5337 | 1.8337 | 18.129
| 116 | 3.2992 | 2.7602 | 4.4264 | 5.1521 | 1.7558 | 17.3937
| 117 | 4.2071 | 2.9566 | 7.2037 | 3.6368 | 1.3912 | 19.3953
| 118 | 3.3801 | 3.096 | 5.7062 | 3.2253 | 1.4884 | 16.8961
| 119 | 4.4477 | 3.2619 | 5.985 | 3.9806 | 1.5021 | 19.1773
| 120 | 3.9844 | 2.6808 | 5.1841 | 3.8968 | 1.242 | 16.9882
| 121 | 4.8568 | 2.4314 | 5.0673 | 5.3996 | 1.2213 | 18.9765
| 122 | 4.565 | 2.9878 | 5.1519 | 5.3411 | 1.3413 | 19.3872
| 123 | 3.4986 | 2.7725 | 6.5064 | 5.3512 | 1.2758 | 19.4044
| 124 | 3.9369 | 3.2197 | 5.0362 | 4.1482 | 1.2966 | 17.6376
| 125 | 4.341 | 3.4892 | 5.6052 | 3.7017 | 1.5695 | 18.7066
| 126 | 3.0344 | 2.4783 | 6.367 | 5.3297 | 1.5615 | 18.7709
| 127 | 3.4256 | 2.5926 | 4.2109 | 5.4457 | 1.2096 | 16.8844
| 128 | 3.6961 | 3.8755 | 5.7842 | 3.2549 | 1.4374 | 18.0481
| 129 | 4.1771 | 2.5086 | 4.6612 | 5.5854 | 1.6669 | 18.5993
| 130 | 3.9967 | 2.8478 | 4.7255 | 4.0449 | 1.481 | 17.0958
| 131 | 3.6727 | 3.3983 | 5.5992 | 3.099 | 1.3366 | 17.1058
| 132 | 3.8137 | 3.324 | 5.3758 | 3.1675 | 1.5346 | 17.2156
| 133 | 3.6463 | 3.2494 | 4.4682 | 4.826 | 1.6525 | 17.8424
| 134 | 4.1309 | 3.0712 | 5.2746 | 5.3905 | 1.5811 | 19.4483
| 135 | 3.1304 | 3.1709 | 5.5816 | 4.5821 | 1.6204 | 18.0855
| 136 | 4.429 | 3.2661 | 6.7047 | 3.7837 | 1.081 | 19.2644
| 137 | 3.44 | 3.6974 | 4.6328 | 3.8059 | 1.1682 | 16.7442
| 138 | 3.8369 | 3.465 | 6.6138 | 3.3005 | 1.757 | 18.9732
| 139 | 3.8524 | 2.435 | 5.1208 | 3.8525 | 1.4027 | 16.6633
| 140 | 4.0836 | 2.7156 | 4.9547 | 4.0675 | 1.5657 | 17.3871
| 141 | 4.7296 | 3.2462 | 5.3579 | 4.986 | 1.3701 | 19.6898
| 142 | 3.7028 | 3.191 | 7.0612 | 3.4342 | 1.2846 | 18.6738
| 143 | 4.0348 | 2.04 | 6.3188 | 3.8952 | 1.3401 | 17.6289
| 144 | 3.4767 | 2.744 | 4.6043 | 4.0712 | 1.4157 | 16.3119
| 145 | 4.6555 | 2.5318 | 5.9707 | 4.7369 | 1.6414 | 19.5364
| 146 | 3.875 | 3.3807 | 5.6753 | 3.7824 | 1.4582 | 18.1715
| 147 | 3.9244 | 2.6403 | 4.984 | 4.8853 | 1.5379 | 17.972
| 148 | 4.0497 | 2.1156 | 4.1473 | 3.6097 | 1.4775 | 15.3998
| 149 | 3.9265 | 2.4582 | 5.8091 | 3.7073 | 1.4749 | 17.376
| 150 | 4.5699 | 2.8157 | 6.8803 | 4.321 | 1.4779 | 20.0649
| 151 | 3.6703 | 3.7093 | 5.6903 | 4.0648 | 1.5339 | 18.6687
| 152 | 3.9781 | 3.0943 | 5.6184 | 3.6176 | 1.4923 | 17.8007
| 153 | 3.4601 | 2.134 | 6.728 | 4.5029 | 1.7728 | 18.5977
| 154 | 4.9202 | 3.5679 | 6.2617 | 5.5992 | 1.2705 | 21.6195
| 155 | 4.0725 | 3.0153 | 5.3814 | 4.9504 | 1.5358 | 18.9553
| 156 | 4.012 | 2.9161 | 6.3216 | 3.9121 | 1.2445 | 18.4063
| 157 | 3.5023 | 2.7572 | 5.0124 | 3.949 | 1.4839 | 16.7048
| 158 | 4.5476 | 2.5021 | 5.7382 | 3.2361 | 1.2564 | 17.2804
| 159 | 3.699 | 3.2585 | 5.208 | 4.3048 | 1.655 | 18.1253
| 160 | 4.3159 | 2.8728 | 5.3168 | 3.986 | 1.171 | 17.6624
| 161 | 3.5318 | 3.6813 | 4.2493 | 4.3114 | 1.4516 | 17.2254
| 162 | 4.2756 | 2.5838 | 7.1042 | 4.1175 | 1.5245 | 19.6056
| 163 | 4.3764 | 2.9612 | 4.4353 | 4.3476 | 1.4692 | 17.5897
| 164 | 4.4519 | 2.8174 | 5.2518 | 5.4935 | 1.25 | 19.2645
| 165 | 3.5897 | 3.7373 | 5.7981 | 3.513 | 1.6709 | 18.3091
| 166 | 4.7007 | 3.3213 | 4.4725 | 3.2177 | 1.524 | 17.2363
| 167 | 3.9343 | 3.2476 | 4.2533 | 3.3346 | 1.5089 | 16.2786
| 168 | 3.8794 | 2.7869 | 5.8546 | 4.0832 | 1.2699 | 17.874
| 169 | 3.7312 | 2.5793 | 7.2983 | 3.8415 | 1.6329 | 19.0832
| 170 | 4.1066 | 2.5004 | 5.3379 | 5.7575 | 1.7626 | 19.4649
| 171 | 3.9317 | 3.6497 | 7.2496 | 3.7203 | 1.2885 | 19.8398
| 172 | 3.7296 | 3.7819 | 6.0548 | 3.3677 | 1.3819 | 18.3159
| 173 | 4.2538 | 2.8401 | 5.9411 | 4.3918 | 1.4628 | 18.8895
| 174 | 4.3203 | 3.104 | 4.6384 | 3.4578 | 1.5979 | 17.1184
| 175 | 4.7604 | 3.4138 | 7.446 | 3.3244 | 1.4696 | 20.4141
| 176 | 3.7085 | 2.7213 | 4.7078 | 3.6143 | 1.8308 | 16.5828
| 177 | 4.2582 | 2.9453 | 5.2398 | 5.3768 | 1.4323 | 19.2525
| 178 | 4.1611 | 2.4053 | 6.8633 | 3.5303 | 1.7781 | 18.7381
| 179 | 4.7139 | 2.6869 | 6.7879 | 3.9734 | 1.887 | 20.0491
| 180 | 3.9711 | 3.4853 | 7.3941 | 4.1512 | 1.6856 | 20.6874
| 181 | 4.1364 | 3.2315 | 5.3236 | 3.4949 | 1.7104 | 17.8968
| 182 | 3.2429 | 2.1482 | 6.5195 | 4.5249 | 1.4332 | 17.8686
| 183 | 3.8918 | 3.6878 | 5.3421 | 3.2 | 1.6384 | 17.7601
| 184 | 4.7635 | 2.8488 | 5.4093 | 4.9408 | 1.5633 | 19.5257
| 185 | 4.1838 | 3.6735 | 4.3039 | 3.2618 | 1.2995 | 16.7226
| 186 | 4.6264 | 2.6735 | 6.6173 | 4.0855 | 1.7609 | 19.7637
| 187 | 4.6918 | 2.6612 | 5.3848 | 4.9652 | 1.3526 | 19.0556
| 188 | 4.3093 | 2.3829 | 5.9873 | 3.5772 | 1.5432 | 17.7999
| 189 | 3.7376 | 3.3788 | 6.2601 | 4.0927 | 1.2257 | 18.695
| 190 | 4.8673 | 3.7109 | 5.4158 | 3.892 | 1.884 | 19.77
| 191 | 3.4301 | 2.8626 | 5.9332 | 3.8615 | 1.8611 | 17.9485
| 192 | 4.1176 | 2.764 | 5.5436 | 4.4696 | 1.5555 | 18.4503
| 193 | 4.4718 | 2.8976 | 4.963 | 4.4009 | 1.1484 | 17.8817
| 194 | 3.8211 | 3.8126 | 5.3702 | 4.7894 | 1.6183 | 19.4116
| 195 | 4.2127 | 2.7546 | 4.6706 | 3.8749 | 1.4126 | 16.9255
| 196 | 3.4652 | 3.1045 | 5.7605 | 4.7682 | 1.5682 | 18.6666
| 197 | 4.0185 | 2.6602 | 4.8579 | 3.4286 | 1.2344 | 16.1996
| 198 | 4.273 | 3.3082 | 5.7442 | 5.3672 | 1.5958 | 20.2884
| 199 | 3.8182 | 3.4224 | 5.5095 | 4.314 | 1.6652 | 18.7293
| 200 | 3.7611 | 3.3714 | 5.6273 | 3.6746 | 1.6338 | 18.0682
| 201 | 3.5168 | 2.5638 | 4.6025 | 4.5875 | 1.7713 | 17.0419
| 202 | 4.0374 | 2.473 | 4.6953 | 3.9332 | 1.7893 | 16.9282
| 203 | 4.5864 | 2.5652 | 6.5295 | 3.619 | 1.5355 | 18.8356
| 204 | 3.9849 | 2.4243 | 5.3066 | 5.1768 | 1.2077 | 18.1003
| 205 | 4.0481 | 3.243 | 7.0652 | 4.1676 | 1.3166 | 19.8406
| 206 | 3.3748 | 3.3697 | 5.4353 | 3.4766 | 1.3338 | 16.9901
| 207 | 3.4033 | 3.6057 | 5.8754 | 3.359 | 1.5749 | 17.8183
| 208 | 3.9643 | 2.3101 | 5.3684 | 3.5863 | 1.0717 | 16.3008
| 209 | 3.5247 | 2.7813 | 5.1036 | 3.9453 | 1.4666 | 16.8215
| 210 | 4.6126 | 2.3661 | 6.4644 | 3.6084 | 1.6599 | 18.7113
| 211 | 4.7361 | 2.4996 | 5.0104 | 4.3585 | 1.0255 | 17.6302
| 212 | 4.1641 | 2.9218 | 4.5486 | 4.1465 | 1.6992 | 17.4802
| 213 | 3.5636 | 2.6479 | 5.0486 | 4.0995 | 1.3424 | 16.702
| 214 | 3.999 | 2.4502 | 6.0751 | 5.6154 | 1.1799 | 19.3196
| 215 | 3.8132 | 2.9582 | 6.9886 | 3.8205 | 1.8062 | 19.3867
| 216 | 3.9554 | 3.5629 | 4.5447 | 3.4942 | 1.7326 | 17.2898
| 217 | 4.2873 | 3.4163 | 6.3052 | 4.5509 | 1.7524 | 20.3121
| 218 | 4.0394 | 3.0491 | 6.525 | 5.0704 | 1.4235 | 20.1074
| 219 | 3.3785 | 2.9845 | 6.9192 | 5.4164 | 1.5879 | 20.2865
| 220 | 4.399 | 3.4971 | 4.8232 | 3.4887 | 1.6642 | 17.8722
| 221 | 3.355 | 2.1829 | 6.2228 | 3.5212 | 1.8249 | 17.1069
| 222 | 4.3647 | 2.9117 | 6.1317 | 4.1397 | 1.5725 | 19.1204
| 223 | 3.9971 | 2.9796 | 5.7558 | 3.5702 | 1.5162 | 17.8189
| 224 | 4.8207 | 2.5241 | 6.7436 | 5.2605 | 1.576 | 20.9249
| 225 | 4.6028 | 3.6469 | 5.7756 | 5.0797 | 1.4952 | 20.6002
| 226 | 4.8255 | 2.486 | 5.6717 | 3.6276 | 1.2918 | 17.9026
| 227 | 3.9868 | 2.7323 | 5.3324 | 5.2897 | 1.7925 | 19.1337
| 228 | 4.0073 | 2.6326 | 4.8982 | 4.7934 | 1.3318 | 17.6633
| 229 | 3.5915 | 3.2122 | 4.597 | 3.8275 | 1.7245 | 16.9528
| 230 | 4.1729 | 3.3471 | 4.529 | 4.4303 | 1.4859 | 17.9652
| 231 | 4.3177 | 2.8884 | 6.5179 | 3.5644 | 1.7789 | 19.0673
| 232 | 4.3109 | 3.5466 | 6.0218 | 3.3161 | 1.2823 | 18.4776
| 233 | 3.2154 | 2.7861 | 6.8959 | 4.4066 | 1.5911 | 18.8952
| 234 | 3.6183 | 3.1554 | 5.8137 | 4.2716 | 1.6724 | 18.5314
| 235 | 4.7753 | 2.9188 | 5.1246 | 3.2888 | 1.5692 | 17.6768
| 236 | 4.4729 | 2.219 | 6.7662 | 3.9221 | 1.2766 | 18.6568
| 237 | 3.9179 | 3.0932 | 5.2962 | 3.9654 | 1.5111 | 17.7838
| 238 | 4.0199 | 3.4432 | 5.9991 | 3.4382 | 1.3172 | 18.2175
| 239 | 3.5754 | 2.8282 | 6.2282 | 3.6259 | 1.4498 | 17.7076
| 240 | 3.8292 | 2.8143 | 6.2099 | 4.7439 | 1.8483 | 19.4455
| 241 | 3.6534 | 3.3225 | 5.0822 | 3.2154 | 1.233 | 16.5065
| 242 | 3.2737 | 3.1073 | 4.8997 | 5.145 | 1.4596 | 17.8853
| 243 | 4.4607 | 2.6431 | 5.977 | 4.1445 | 1.4078 | 18.6332
| 244 | 3.6014 | 2.2967 | 5.5934 | 4.7781 | 1.3035 | 17.5731
| 245 | 3.4517 | 3.4453 | 5.1772 | 3.3142 | 1.3118 | 16.7002
| 246 | 4.7848 | 2.9509 | 4.6789 | 4.8301 | 1.5439 | 18.7886
| 247 | 4.2608 | 2.7469 | 4.5737 | 4.2235 | 1.7422 | 17.5472
| 248 | 4.5257 | 2.3437 | 6.0043 | 4.3284 | 1.5289 | 18.7309
| 249 | 4.5556 | 3.1579 | 5.6595 | 5.5756 | 1.612 | 20.5606
| 250 | 3.6361 | 2.2927 | 6.0375 | 3.1164 | 1.5118 | 16.5945
| 251 | 3.7444 | 2.4975 | 6.0802 | 4.4837 | 1.4459 | 18.2517
| 252 | 3.8501 | 3.0134 | 6.1936 | 4.1614 | 1.6901 | 18.9086
| 253 | 4.686 | 3.3347 | 4.9166 | 5.2847 | 1.378 | 19.6
| 254 | 3.7891 | 3.2439 | 4.9067 | 3.3718 | 1.398 | 16.7094
| 255 | 3.8154 | 3.0378 | 5.6004 | 4.568 | 1.5944 | 18.6159
| 256 | 3.8609 | 3.5119 | 5.4203 | 5.275 | 1.4965 | 19.5646
| 257 | 3.7508 | 3.275 | 5.7476 | 3.7432 | 1.3883 | 17.9049
| 258 | 3.5371 | 2.4691 | 5.3447 | 4.4231 | 1.4397 | 17.2137
| 259 | 4.1778 | 3.5153 | 5.0643 | 3.7342 | 1.4911 | 17.9827
| 260 | 3.723 | 3.3358 | 4.9684 | 3.4168 | 1.6602 | 17.1042
| 261 | 3.5689 | 3.1855 | 6.0611 | 3.5461 | 1.1324 | 17.4939
| 262 | 4.0853 | 3.5325 | 4.2343 | 4.8723 | 1.4014 | 18.1258
| 263 | 3.8464 | 3.3393 | 6.4501 | 3.8674 | 1.3783 | 18.8815
| 264 | 3.6141 | 3.6263 | 5.9443 | 4.1383 | 1.5712 | 18.8942
| 265 | 3.9259 | 3.7035 | 6.9303 | 4.7354 | 1.8759 | 21.1711
| 266 | 3.6329 | 3.4564 | 5.4797 | 3.5819 | 1.469 | 17.62
| 267 | 4.6356 | 3.6041 | 5.3131 | 4.854 | 1.4577 | 19.8644
| 268 | 4.0809 | 2.6839 | 6.0526 | 3.3769 | 1.9626 | 18.1569
| 269 | 3.8566 | 3.1289 | 6.0932 | 4.2127 | 1.6186 | 18.9101
| 270 | 3.3926 | 2.7126 | 4.8856 | 4.4857 | 1.4248 | 16.9013
| 271 | 3.6903 | 2.4479 | 6.4164 | 3.9197 | 1.5218 | 17.9961
| 272 | 4.2962 | 2.2247 | 4.5616 | 3.596 | 1.8046 | 16.4831
| 273 | 3.1564 | 2.932 | 6.7008 | 4.3319 | 1.4762 | 18.5972
| 274 | 3.7589 | 3.0043 | 4.4305 | 3.7641 | 1.7341 | 16.6918
| 275 | 3.6265 | 3.5855 | 4.7002 | 4.6226 | 1.4943 | 18.0291
| 276 | 4.1288 | 3.8323 | 5.5044 | 3.6347 | 1.5988 | 18.699
| 277 | 4.076 | 3.1946 | 7.2302 | 4.4111 | 1.5352 | 20.4471
| 278 | 4.9065 | 2.5609 | 5.3971 | 3.0926 | 1.4643 | 17.4214
| 279 | 3.7952 | 2.4593 | 4.706 | 3.7581 | 1.5593 | 16.2779
| 280 | 4.2953 | 3.5231 | 5.5905 | 3.9268 | 1.5065 | 18.8421
| 281 | 4.1814 | 3.3203 | 4.8219 | 3.6619 | 1.5565 | 17.542
| 282 | 4.5349 | 2.9138 | 7.1445 | 4.2029 | 1.4986 | 20.2947
| 283 | 3.6543 | 3.0722 | 5.1973 | 5.005 | 1.4087 | 18.3375
| 284 | 4.358 | 3.7543 | 4.7846 | 4.7206 | 1.3459 | 18.9634
| 285 | 4.3825 | 3.5909 | 4.9601 | 4.9239 | 1.6041 | 19.4616
| 286 | 4.687 | 3.1998 | 5.715 | 4.376 | 1.2611 | 19.2389
| 287 | 3.4422 | 3.4365 | 6.603 | 4.1417 | 1.5105 | 19.1339
| 288 | 3.6682 | 3.1228 | 4.829 | 4.1301 | 1.0057 | 16.7558
| 289 | 3.9213 | 2.6853 | 5.1939 | 4.0935 | 1.4817 | 17.3757
| 290 | 4.0276 | 3.6604 | 6.1404 | 4.5719 | 1.557 | 19.9572
| 291 | 4.1378 | 3.5604 | 6.7105 | 4.8184 | 1.654 | 20.8812
| 292 | 4.3493 | 3.7495 | 4.8518 | 3.3032 | 1.3069 | 17.5607
| 293 | 3.5862 | 2.517 | 5.803 | 4.6491 | 1.1739 | 17.7292
| 294 | 4.3425 | 3.2921 | 5.3553 | 3.028 | 1.6321 | 17.65
| 295 | 3.804 | 2.5102 | 5.5671 | 5.5313 | 1.315 | 18.7275
| 296 | 3.5559 | 3.1694 | 5.094 | 3.3894 | 1.4501 | 16.6588
| 297 | 4.1735 | 3.0576 | 5.4458 | 4.6318 | 1.316 | 18.6247
| 298 | 4.3334 | 3.1144 | 4.8007 | 3.7249 | 1.3789 | 17.3523
| 299 | 4.0054 | 3.1882 | 5.6213 | 4.0962 | 1.2296 | 18.1406
| 300 | 4.694 | 2.2491 | 7.4223 | 4.0238 | 1.1506 | 19.5399
| 301 | 4.1164 | 2.4127 | 6.1566 | 3.6679 | 1.5886 | 17.9422
| 302 | 4.0241 | 2.9174 | 5.5707 | 3.2049 | 1.4528 | 17.17
| 303 | 3.5793 | 2.6923 | 4.9523 | 3.7594 | 1.6831 | 16.6664
| 304 | 4.2289 | 3.8667 | 4.6294 | 4.9142 | 1.8975 | 19.5366
| 305 | 4.1683 | 2.7282 | 7.4898 | 5.4022 | 1.7127 | 21.501
| 306 | 4.3666 | 2.4416 | 5.7397 | 5.1499 | 1.5708 | 19.2685
| 307 | 3.7633 | 2.6354 | 6.7222 | 4.3522 | 1.3506 | 18.8238
| 308 | 3.9936 | 3.3061 | 4.9437 | 4.3244 | 1.5986 | 18.1663
| 309 | 4.6721 | 2.9271 | 4.9461 | 3.8502 | 1.1522 | 17.5477
| 310 | 4.8113 | 2.5151 | 5.8169 | 3.3378 | 1.6363 | 18.1174
| 311 | 4.415 | 2.67 | 6.2688 | 3.5725 | 1.7957 | 18.7219
| 312 | 4.733 | 2.2307 | 5.7327 | 3.9358 | 1.428 | 18.0602
| 313 | 3.5869 | 3.8246 | 5.0533 | 3.5025 | 1.4845 | 17.4518
| 314 | 3.8924 | 3.0032 | 5.3935 | 3.9604 | 1.2811 | 17.5307
| 315 | 3.8012 | 2.6759 | 7.461 | 4.7862 | 1.4824 | 20.2067
| 316 | 4.4631 | 2.8614 | 4.4887 | 5.6717 | 1.8751 | 19.36
| 317 | 3.3534 | 2.9557 | 6.0162 | 4.5112 | 1.713 | 18.5496
| 318 | 4.7893 | 2.9531 | 4.5957 | 3.9555 | 1.6027 | 17.8963
| 319 | 4.0684 | 2.7533 | 5.8572 | 4.3186 | 1.5732 | 18.5708
| 320 | 4.0999 | 2.4176 | 6.5349 | 4.7546 | 1.3864 | 19.1934
| 321 | 4.0554 | 3.3524 | 5.6875 | 5.0509 | 1.5313 | 19.6775
| 322 | 4.2797 | 2.7106 | 4.9079 | 4.1891 | 1.7038 | 17.7911
| 323 | 3.2558 | 2.651 | 4.8688 | 5.043 | 1.7549 | 17.5736
| 324 | 3.7367 | 2.539 | 6.6494 | 4.3542 | 1.4857 | 18.765
| 325 | 3.8416 | 3.1423 | 6.0693 | 3.405 | 1.6589 | 18.1171
| 326 | 3.6402 | 3.0364 | 5.1958 | 5.0208 | 1.4285 | 18.3217
| 327 | 3.4923 | 2.9245 | 4.9228 | 4.6847 | 1.2775 | 17.302
| 328 | 3.3902 | 2.9407 | 6.2244 | 4.4635 | 1.7407 | 18.7595
| 329 | 3.8835 | 3.1957 | 4.653 | 4.6078 | 1.8456 | 18.1857
| 330 | 4.5183 | 3.31 | 5.1277 | 4.049 | 1.0953 | 18.1003
| 331 | 3.4345 | 2.7988 | 6.9395 | 3.2087 | 1.5871 | 17.9688
| 332 | 4.2529 | 3.4471 | 7.541 | 4.7016 | 1.7597 | 21.7023
| 333 | 4.114 | 3.0683 | 5.2614 | 5.0775 | 1.4482 | 18.9693
| 334 | 3.9224 | 2.9657 | 4.9481 | 3.518 | 1.4981 | 16.8524
| 335 | 3.4464 | 3.4023 | 5.0322 | 3.5543 | 1.3623 | 16.7975
| 336 | 3.623 | 2.9706 | 4.4522 | 3.6882 | 1.9022 | 16.6361
| 337 | 3.5963 | 3.1757 | 5.8792 | 3.4075 | 1.4272 | 17.4859
| 338 | 3.4803 | 2.2755 | 4.6639 | 3.8597 | 1.2323 | 15.5116
| 339 | 4.4071 | 2.9581 | 5.7076 | 4.4153 | 1.1841 | 18.6722
| 340 | 3.9821 | 2.9487 | 6.4589 | 4.2091 | 1.4206 | 19.0195
| 341 | 3.5695 | 3.625 | 6.5825 | 4.8148 | 1.8629 | 20.4547
| 342 | 4.0203 | 2.8093 | 6.9916 | 4.5184 | 1.4639 | 19.8035
| 343 | 3.1234 | 3.5183 | 6.4984 | 3.3915 | 1.6919 | 18.2236
| 344 | 4.7118 | 2.732 | 6.1794 | 3.9908 | 1.3609 | 18.9748
| 345 | 3.4277 | 2.9781 | 5.5403 | 3.8685 | 1.706 | 17.5207
| 346 | 3.7128 | 2.4044 | 4.2893 | 3.6447 | 1.6107 | 15.6619
| 347 | 4.4978 | 2.257 | 6.0576 | 3.4907 | 1.8021 | 18.1052
| 348 | 4.1324 | 3.3857 | 6.0486 | 3.3058 | 1.3929 | 18.2654
| 349 | 4.3625 | 2.9148 | 4.7135 | 3.3752 | 1.7707 | 17.1366
| 350 | 3.3652 | 3.0662 | 5.0389 | 5.2367 | 1.2859 | 17.9928
| 351 | 3.8262 | 2.3388 | 5.168 | 3.4981 | 1.5256 | 16.3568
| 352 | 4.6307 | 3.3782 | 5.6578 | 3.3363 | 1.7942 | 18.7972
| 353 | 3.8209 | 3.0224 | 4.5383 | 4.9096 | 1.6253 | 17.9165
| 354 | 4.0042 | 2.5493 | 6.2055 | 3.8939 | 1.5301 | 18.1829
| 355 | 4.1086 | 3.5184 | 4.8623 | 3.4874 | 1.8236 | 17.8004
| 356 | 4.638 | 2.9064 | 5.613 | 5.6095 | 1.4947 | 20.2616
| 357 | 4.2642 | 3.097 | 4.995 | 4.1062 | 1.8829 | 18.3453
| 358 | 4.4467 | 3.5488 | 5.2 | 4.8952 | 1.2794 | 19.3701
| 359 | 4.2559 | 3.2508 | 5.9927 | 3.2425 | 1.3486 | 18.0905
| 360 | 3.4718 | 3.364 | 5.0065 | 3.9092 | 1.5404 | 17.2918
| 361 | 4.3982 | 2.7909 | 6.4428 | 4.1837 | 1.7419 | 19.5575
| 362 | 4.0963 | 3.3974 | 4.865 | 4.0371 | 1.0914 | 17.4871
| 363 | 4.206 | 2.8832 | 4.3873 | 5.2532 | 1.3806 | 18.1103
| 364 | 3.5767 | 2.8586 | 5.6988 | 4.5171 | 1.4972 | 18.1485
| 365 | 3.5268 | 2.6533 | 5.529 | 5.0305 | 1.472 | 18.2116
| 366 | 4.2432 | 3.559 | 6.1536 | 5.1245 | 1.1786 | 20.2591
| 367 | 4.1456 | 2.8849 | 6.2666 | 4.2595 | 1.5922 | 19.1487
| 368 | 3.9417 | 3.0204 | 4.848 | 4.51 | 1.7449 | 18.065
| 369 | 3.9549 | 2.4841 | 5.2361 | 4.208 | 1.5259 | 17.409
| 370 | 4.1823 | 2.3028 | 6.3514 | 3.6536 | 1.3958 | 17.8859
| 371 | 3.9168 | 3.5974 | 5.0551 | 4.2975 | 1.3901 | 18.2569
| 372 | 3.771 | 3.4629 | 4.4088 | 4.6867 | 1.3566 | 17.6861
| 373 | 3.8568 | 3.7408 | 6.8836 | 5.007 | 1.4796 | 20.9678
| 374 | 3.9958 | 2.7473 | 4.3348 | 3.6643 | 1.32 | 16.0623
| 375 | 4.5008 | 2.5859 | 6.8357 | 3.2736 | 1.6047 | 18.8008
| 376 | 4.3159 | 2.9037 | 5.853 | 4.6707 | 1.2065 | 18.9497
| 377 | 3.6294 | 2.6887 | 4.5585 | 5.3391 | 1.5263 | 17.7419
| 378 | 4.0512 | 2.6356 | 5.5211 | 4.579 | 1.582 | 18.369
| 379 | 4.5378 | 2.9737 | 6.4902 | 4.5427 | 1.5294 | 20.0737
| 380 | 4.2489 | 3.4325 | 4.3663 | 4.536 | 1.6298 | 18.2136
| 381 | 3.8453 | 3.413 | 5.5598 | 4.6652 | 1.4167 | 18.9
| 382 | 3.9888 | 3.208 | 5.6107 | 4.8774 | 1.3145 | 18.9994
| 383 | 4.5777 | 2.6238 | 5.7807 | 4.035 | 1.4788 | 18.496
| 384 | 4.541 | 3.7156 | 5.1075 | 4.4552 | 1.584 | 19.4034
| 385 | 4.0576 | 2.9753 | 5.6081 | 4.5987 | 1.5383 | 18.778
| 386 | 4.1076 | 2.9017 | 6.6373 | 3.7786 | 1.4239 | 18.8491
| 387 | 4.2232 | 2.8619 | 7.0994 | 3.9179 | 1.7178 | 19.82
| 388 | 3.7106 | 3.4286 | 5.4856 | 5.3241 | 1.3496 | 19.2984
| 389 | 3.9913 | 2.7784 | 4.7467 | 3.2516 | 1.6823 | 16.4504
| 390 | 3.3224 | 3.041 | 5.3232 | 3.4704 | 1.3474 | 16.5044
| 391 | 4.1483 | 2.5128 | 5.5001 | 4.2761 | 1.2755 | 17.7128
| 392 | 3.9512 | 2.3867 | 5.527 | 3.6499 | 1.4585 | 16.9734
| 393 | 3.896 | 2.8521 | 5.8937 | 3.6699 | 1.1386 | 17.4504
| 394 | 4.2628 | 2.2372 | 4.5872 | 4.4582 | 1.7188 | 17.2642
| 395 | 4.2203 | 3.0168 | 6.7338 | 3.718 | 1.2388 | 18.9277
| 396 | 3.7852 | 3.0298 | 7.3708 | 3.4928 | 1.6084 | 19.2869
| 397 | 4.5787 | 2.0807 | 5.2981 | 3.426 | 1.6746 | 17.0581
| 398 | 4.2506 | 2.6027 | 6.5911 | 4.3168 | 1.3048 | 19.066
| 399 | 3.9096 | 2.3268 | 6.3152 | 3.459 | 1.0624 | 17.073
| 400 | 4.0666 | 3.2404 | 4.2822 | 5.1205 | 1.3534 | 18.0631
| 401 | 3.8316 | 2.3464 | 5.9789 | 4.2622 | 1.4905 | 17.9096
| 402 | 3.6852 | 3.3032 | 6.4787 | 4.9987 | 1.5308 | 19.9965
| 403 | 4.3449 | 2.2812 | 6.0027 | 3.605 | 1.4652 | 17.6989
| 404 | 4.7472 | 2.3924 | 6.3366 | 4.1031 | 1.715 | 19.2944
| 405 | 4.1758 | 2.9421 | 7.8058 | 3.6066 | 1.1178 | 19.6481
| 406 | 3.7819 | 3.2088 | 4.8936 | 3.6653 | 1.6869 | 17.2365
| 407 | 3.9983 | 3.1389 | 6.1763 | 3.9797 | 1.4338 | 18.727
| 408 | 3.4904 | 2.8707 | 4.9645 | 4.2529 | 1.5029 | 17.0815
| 409 | 4.4179 | 3.5786 | 4.8364 | 4.6272 | 1.6089 | 19.069
| 410 | 3.7337 | 2.8069 | 5.2938 | 3.3187 | 1.4034 | 16.5565
| 411 | 4.3465 | 3.2628 | 5.4122 | 3.5786 | 1.2051 | 17.8053
| 412 | 4.0743 | 3.0237 | 7.0529 | 4.0324 | 1.4392 | 19.6226
| 413 | 3.3884 | 3.0339 | 4.7556 | 5.441 | 1.7583 | 18.3771
| 414 | 4.2476 | 3.0664 | 5.015 | 4.1274 | 1.9969 | 18.4534
| 415 | 4.0782 | 2.5704 | 5.0013 | 4.8658 | 1.421 | 17.9367
| 416 | 3.8718 | 2.8511 | 5.1091 | 3.2981 | 1.14 | 16.2701
| 417 | 4.6682 | 2.3976 | 4.6668 | 5.7739 | 1.673 | 19.1793
| 418 | 3.7175 | 3.3187 | 6.4884 | 5.2013 | 1.5557 | 20.2816
| 419 | 3.5811 | 3.6376 | 6.4765 | 4.072 | 1.3964 | 19.1636
| 420 | 4.2248 | 2.4016 | 6.8266 | 4.6942 | 1.5769 | 19.7242
| 421 | 3.6434 | 2.8433 | 6.8018 | 4.1017 | 1.7839 | 19.174
| 422 | 4.2368 | 2.8311 | 6.5484 | 4.8367 | 1.8593 | 20.3124
| 423 | 4.0755 | 3.0252 | 6.2452 | 5.0637 | 1.3813 | 19.7909
| 424 | 3.6129 | 2.553 | 4.8314 | 5.1938 | 1.5149 | 17.7059
| 425 | 4.5594 | 3.0422 | 4.569 | 3.3884 | 1.2291 | 16.7881
| 426 | 4.3382 | 3.0254 | 4.1682 | 4.7322 | 1.58 | 17.844
| 427 | 4.8606 | 2.6286 | 4.6868 | 5.3621 | 1.6059 | 19.144
| 428 | 4.2804 | 3.1322 | 5.3894 | 5.6549 | 1.3212 | 19.778
| 429 | 4.2119 | 3.6103 | 5.2814 | 4.6693 | 1.1697 | 18.9426
| 430 | 4.8805 | 3.2421 | 5.141 | 4.7085 | 1.2461 | 19.2182
| 431 | 3.8859 | 2.8503 | 5.0897 | 5.3844 | 1.5412 | 18.7514
| 432 | 4.1582 | 2.4447 | 6.2855 | 4.2207 | 1.8009 | 18.9101
| 433 | 3.5391 | 3.4212 | 4.8055 | 3.7125 | 1.6013 | 17.0797
| 434 | 4.4104 | 2.391 | 5.2184 | 3.7716 | 1.3387 | 17.1302
| 435 | 4.0325 | 2.6682 | 6.457 | 4.0069 | 1.1534 | 18.3181
| 436 | 4.8345 | 3.1239 | 4.8152 | 5.1142 | 1.5862 | 19.4739
| 437 | 4.1407 | 3.1737 | 4.7977 | 3.501 | 1.8501 | 17.4632
| 438 | 4.0107 | 3.1344 | 7.6861 | 5.2921 | 1.5824 | 21.7056
| 439 | 4.5823 | 2.5816 | 6.2145 | 4.9639 | 1.2607 | 19.6029
| 440 | 3.9232 | 2.999 | 5.4328 | 4.2592 | 1.5607 | 18.1749
| 441 | 4.41 | 2.882 | 4.515 | 5.4746 | 1.1008 | 18.3823
| 442 | 4.7938 | 3.0374 | 5.2028 | 3.9375 | 1.3303 | 18.3019
| 443 | 3.6435 | 2.8673 | 5.0791 | 3.8149 | 1.7087 | 17.1136
| 444 | 4.0269 | 3.5026 | 6.6361 | 4.9917 | 1.558 | 20.7153
| 445 | 3.8442 | 2.5747 | 5.0359 | 4.4761 | 1.5223 | 17.4533
| 446 | 4.1935 | 2.5444 | 5.335 | 3.4716 | 1.2716 | 16.816
| 447 | 3.8972 | 3.084 | 4.6904 | 4.5206 | 1.8092 | 18.0015
| 448 | 3.8782 | 3.0803 | 4.924 | 5.7454 | 1.6499 | 19.2779
| 449 | 4.2411 | 2.7984 | 4.9193 | 3.6135 | 1.1758 | 16.7481
| 450 | 4.1441 | 3.006 | 4.4208 | 4.5759 | 1.8517 | 17.9984
| 451 | 4.2914 | 2.8425 | 6.5613 | 3.1932 | 1.7142 | 18.6026
| 452 | 3.7223 | 3.5012 | 5.9533 | 4.252 | 1.6466 | 19.0756
| 453 | 3.4186 | 3.1676 | 5.3834 | 3.8309 | 1.1912 | 16.9917
| 454 | 3.7669 | 3.3551 | 7.2679 | 3.7744 | 1.5665 | 19.7309
| 455 | 3.7148 | 2.369 | 4.9581 | 3.5163 | 1.6019 | 16.1601
| 456 | 3.6322 | 2.9283 | 4.3316 | 3.8252 | 1.8554 | 16.5727
| 457 | 4.2893 | 3.2792 | 6.9723 | 3.551 | 1.4705 | 19.5623
| 458 | 3.8018 | 2.9441 | 5.3273 | 4.3264 | 1.7205 | 18.1201
| 459 | 4.3542 | 3.133 | 6.1458 | 4.1242 | 1.7272 | 19.4845
| 460 | 3.5494 | 2.4153 | 5.8889 | 4.4486 | 1.9033 | 18.2056
| 461 | 4.4022 | 2.9942 | 5.1004 | 3.852 | 1.8496 | 18.1984
| 462 | 4.6448 | 3.2377 | 4.3834 | 4.4441 | 1.2806 | 17.9906
| 463 | 3.9072 | 3.0851 | 5.6803 | 3.6229 | 1.817 | 18.1125
| 464 | 3.6079 | 3.0498 | 7.2601 | 3.9539 | 1.7758 | 19.6475
| 465 | 3.8635 | 3.1602 | 6.2558 | 4.746 | 1.7655 | 19.791
| 466 | 4.324 | 2.6164 | 7.6942 | 4.8035 | 1.5935 | 21.0317
| 467 | 3.4374 | 2.6931 | 6.4139 | 3.7853 | 1.5971 | 17.9268
| 468 | 3.5278 | 2.8687 | 4.7181 | 3.2704 | 1.836 | 16.221
| 469 | 4.2402 | 2.4232 | 6.369 | 3.2923 | 1.7167 | 18.0414
| 470 | 4.0539 | 3.103 | 4.9936 | 4.0505 | 1.4955 | 17.6966
| 471 | 4.4282 | 2.823 | 6.0313 | 5.6509 | 1.6983 | 20.6317
| 472 | 3.7837 | 2.2486 | 6.7777 | 3.7444 | 1.4656 | 18.0201
| 473 | 4.368 | 3.5449 | 6.3305 | 5.0964 | 1.4379 | 20.7776
| 474 | 4.04 | 2.7382 | 7.1953 | 3.7309 | 1.55 | 19.2544
| 475 | 3.9878 | 3.0288 | 5.1612 | 4.0975 | 1.1288 | 17.4041
| 476 | 4.6245 | 3.3511 | 5.2209 | 4.2768 | 1.7029 | 19.1762
| 477 | 3.3605 | 2.0895 | 5.7692 | 3.2855 | 1.8805 | 16.3853
| 478 | 3.8277 | 2.8012 | 4.8912 | 4.0086 | 1.5651 | 17.0938
| 479 | 3.7433 | 3.0585 | 6.4522 | 3.5949 | 1.8949 | 18.7438
| 480 | 4.6526 | 3.5521 | 5.2256 | 3.5747 | 1.2112 | 18.2163
| 481 | 4.575 | 2.5719 | 5.4129 | 4.855 | 1.7492 | 19.164
| 482 | 4.1924 | 3.4269 | 4.6441 | 3.6249 | 1.3795 | 17.2677
| 483 | 3.8904 | 3.027 | 5.7716 | 3.5487 | 1.7363 | 17.974
| 484 | 3.78 | 3.7208 | 4.2642 | 3.2305 | 1.0744 | 16.0699
| 485 | 3.2677 | 2.841 | 5.5558 | 3.9924 | 1.4345 | 17.0915
| 486 | 3.8992 | 3.2835 | 6.8684 | 3.4665 | 1.6841 | 19.2018
| 487 | 3.8095 | 3.3566 | 6.7834 | 5.1308 | 1.9075 | 20.9878
| 488 | 4.4573 | 3.0439 | 7.9057 | 4.7239 | 1.9105 | 22.0412
| 489 | 3.9479 | 3.2267 | 5.348 | 4.2937 | 1.3877 | 18.204
| 490 | 4.5914 | 2.4121 | 5.2837 | 4.2221 | 1.5797 | 18.089
| 491 | 3.9462 | 2.6462 | 5.1807 | 3.5054 | 1.4849 | 16.7634
| 492 | 3.6944 | 3.5746 | 4.6889 | 3.581 | 1.6228 | 17.1616
| 493 | 3.4544 | 3.2168 | 6.3471 | 4.04 | 1.839 | 18.8973
| 494 | 3.1847 | 3.6592 | 6.012 | 4.7978 | 1.7286 | 19.3822
| 495 | 3.9504 | 3.7953 | 6.7584 | 3.6905 | 1.4766 | 19.6713
| 496 | 3.8735 | 3.6551 | 6.8189 | 3.6868 | 1.3026 | 19.3369
| 497 | 4.1671 | 2.8344 | 5.5874 | 4.4426 | 1.5196 | 18.5511
| 498 | 3.6974 | 3.1937 | 5.8781 | 3.59 | 1.2008 | 17.5599
| 499 | 4.7404 | 3.4716 | 4.9345 | 3.5981 | 1.3208 | 18.0654
| 500 | 3.7562 | 3.8448 | 4.7686 | 4.0002 | 1.782 | 18.1518
| 501 | 3.8108 | 3.2982 | 5.5831 | 4.975 | 1.6268 | 19.2937
| 502 | 3.887 | 2.6397 | 6.278 | 3.5848 | 1.842 | 18.2314
| 503 | 3.8027 | 2.507 | 5.9581 | 3.2762 | 1.4683 | 17.0123
| 504 | 4.4245 | 3.3108 | 7.4831 | 3.1732 | 1.6455 | 20.0371
| 505 | 3.9749 | 3.1519 | 6.187 | 3.3976 | 1.7373 | 18.4487
| 506 | 3.9383 | 3.1891 | 6.4347 | 5.0845 | 1.3951 | 20.0417
| 507 | 3.9898 | 2.4935 | 6.5305 | 3.0741 | 1.7998 | 17.8878
| 508 | 3.0578 | 3.6302 | 5.998 | 3.4657 | 1.6424 | 17.7939
| 509 | 3.7349 | 2.8215 | 5.8977 | 4.8457 | 1.3383 | 18.6381
| 510 | 3.9452 | 3.2335 | 5.8921 | 3.3647 | 1.532 | 17.9674
| 511 | 3.3114 | 2.997 | 6.0985 | 4.7301 | 1.4351 | 18.5721
| 512 | 3.4787 | 3.2226 | 6.0905 | 4.1554 | 1.1849 | 18.1322
| 513 | 4.2777 | 2.9053 | 5.2322 | 3.6515 | 1.6001 | 17.6668
| 514 | 4.0649 | 3.0078 | 5.841 | 3.2821 | 1.6616 | 17.8574
| 515 | 3.8953 | 2.9548 | 5.0443 | 4.5004 | 1.3418 | 17.7367
| 516 | 3.6154 | 2.6302 | 6.4118 | 5.352 | 1.6074 | 19.6169
| 517 | 3.7004 | 3.0095 | 6.5395 | 3.4242 | 1.5525 | 18.2262
| 518 | 4.7967 | 2.9178 | 4.6824 | 4.8429 | 1.2346 | 18.4745
| 519 | 3.9651 | 3.046 | 6.3837 | 4.0192 | 1.6871 | 19.101
| 520 | 3.806 | 2.8754 | 5.0922 | 4.989 | 1.7194 | 18.482
| 521 | 3.7887 | 3.3153 | 4.9996 | 4.493 | 1.5535 | 18.1501
| 522 | 4.2177 | 3.3691 | 5.2339 | 4.8911 | 1.2165 | 18.9282
| 523 | 3.5071 | 2.6495 | 4.8492 | 4.2057 | 1.3826 | 16.5941
| 524 | 4.5174 | 2.6976 | 5.6386 | 4.8317 | 1.6152 | 19.3005
| 525 | 3.3836 | 2.7923 | 4.3126 | 4.238 | 1.452 | 16.1784
| 526 | 3.9676 | 2.9093 | 4.2945 | 4.3403 | 1.5155 | 17.0272
| 527 | 4.204 | 3.5891 | 5.5047 | 4.2489 | 1.1942 | 18.7409
| 528 | 4.1868 | 3.7574 | 5.6538 | 4.9067 | 1.7081 | 20.2128
| 529 | 4.3364 | 3.0115 | 5.2034 | 3.5683 | 1.578 | 17.6977
| 530 | 4.1563 | 2.8873 | 5.0087 | 3.8812 | 1.9318 | 17.8653
| 531 | 3.9717 | 2.3882 | 5.0576 | 3.7107 | 1.1205 | 16.2487
| 532 | 4.5158 | 3.078 | 6.5858 | 4.6831 | 1.4781 | 20.3407
| 533 | 3.8622 | 2.8978 | 6.3723 | 3.4775 | 1.4141 | 18.0239
| 534 | 3.7602 | 3.3014 | 4.7743 | 3.6461 | 1.3689 | 16.8509
| 535 | 3.1506 | 3.5366 | 5.4022 | 3.9727 | 1.5488 | 17.6109
| 536 | 3.9921 | 2.9935 | 7.3675 | 3.9986 | 1.8126 | 20.1643
| 537 | 3.8081 | 2.3153 | 5.868 | 4.37 | 1.5092 | 17.8705
| 538 | 4.1526 | 2.5915 | 5.0218 | 5.0938 | 1.3591 | 18.2189
| 539 | 4.2019 | 3.5065 | 7.5985 | 4.2348 | 1.3376 | 20.8792
| 540 | 4.1801 | 3.6332 | 7.5008 | 5.2657 | 1.5829 | 22.1628
| 541 | 4.6463 | 3.1176 | 5.1144 | 3.2215 | 1.2905 | 17.3905
| 542 | 4.0332 | 2.4283 | 5.5175 | 3.8771 | 1.1646 | 17.0207
| 543 | 3.222 | 3.4116 | 5.305 | 5.4331 | 1.3235 | 18.6952
| 544 | 4.0877 | 2.6581 | 7.6475 | 5.3102 | 1.4182 | 21.1217
| 545 | 4.1709 | 2.9341 | 5.5541 | 4.9032 | 1.2477 | 18.81
| 546 | 3.4829 | 2.8289 | 4.8442 | 4.1079 | 1.4791 | 16.743
| 547 | 4.4695 | 2.7061 | 7.5652 | 3.8286 | 1.3835 | 19.9528
| 548 | 4.3068 | 2.7307 | 4.4012 | 5.1293 | 1.1642 | 17.7322
| 549 | 3.9014 | 3.1689 | 5.5344 | 3.3082 | 1.5213 | 17.4343
| 550 | 3.4079 | 2.6711 | 4.3448 | 3.5432 | 1.5034 | 15.4704
| 551 | 3.9569 | 3.1207 | 5.7938 | 4.5652 | 1.4413 | 18.8779
| 552 | 4.4358 | 2.8372 | 6.3903 | 4.6387 | 1.5422 | 19.8442
| 553 | 4.0309 | 3.0513 | 6.6252 | 5.1607 | 1.1054 | 19.9735
| 554 | 3.3138 | 2.7674 | 6.5452 | 4.2149 | 1.7984 | 18.6397
| 555 | 3.544 | 2.0468 | 4.4619 | 3.5107 | 1.7514 | 15.3148
| 556 | 4.6619 | 3.3486 | 5.3791 | 3.964 | 1.4019 | 18.7555
| 557 | 3.8481 | 3.7305 | 7.4329 | 3.6037 | 1.4249 | 20.04
| 558 | 3.5834 | 3.2394 | 5.7112 | 4.5503 | 1.2044 | 18.2887
| 559 | 4.6503 | 2.9353 | 6.2796 | 5.8693 | 1.7069 | 21.4414
| 560 | 4.4817 | 2.8939 | 4.9379 | 5.0904 | 1.6929 | 19.0968
| 561 | 3.8248 | 3.734 | 4.751 | 3.7328 | 1.4834 | 17.526
| 562 | 3.4441 | 2.2061 | 4.7611 | 3.6754 | 1.6234 | 15.7101
| 563 | 3.4647 | 3.0834 | 4.6093 | 5.221 | 1.6968 | 18.0752
| 564 | 4.7224 | 3.4863 | 6.3985 | 3.2051 | 1.2835 | 19.0959
| 565 | 3.5598 | 3.3374 | 5.4651 | 4.6055 | 1.3891 | 18.3568
| 566 | 3.7778 | 3.9351 | 5.9288 | 3.3816 | 1.6158 | 18.6391
| 567 | 4.2992 | 2.9627 | 6.1735 | 3.3271 | 1.1889 | 17.9514
| 568 | 4.2455 | 3.1781 | 4.5031 | 4.3071 | 1.3278 | 17.5616
| 569 | 4.0022 | 2.947 | 6.8128 | 4.629 | 1.7307 | 20.1216
| 570 | 3.5715 | 2.9523 | 4.8829 | 3.5382 | 1.2151 | 16.16
| 571 | 3.1935 | 2.4557 | 5.2451 | 5.1029 | 1.3831 | 17.3802
| 572 | 4.1228 | 2.2234 | 7.5871 | 3.4473 | 1.4434 | 18.824
| 573 | 4.0032 | 3.0174 | 5.6377 | 3.8588 | 1.4317 | 17.9488
| 574 | 3.545 | 2.7718 | 7.3125 | 3.7099 | 1.5122 | 18.8514
| 575 | 4.4042 | 2.6125 | 5.9662 | 5.6832 | 1.4462 | 20.1124
| 576 | 4.4997 | 2.2612 | 5.5643 | 4.7711 | 1.4426 | 18.539
| 577 | 4.3564 | 2.2887 | 5.2703 | 4.5067 | 1.4191 | 17.8412
| 578 | 3.6041 | 2.8322 | 4.7781 | 3.6168 | 1.3224 | 16.1536
| 579 | 4.1133 | 3.4792 | 6.9154 | 3.1464 | 1.4527 | 19.107
| 580 | 4.4273 | 3.3621 | 5.7454 | 3.3204 | 1.5599 | 18.4151
| 581 | 4.5365 | 2.5054 | 6.4947 | 3.2649 | 1.688 | 18.4895
| 582 | 3.9163 | 2.8542 | 6.2974 | 4.592 | 1.4486 | 19.1085
| 583 | 3.2776 | 2.4376 | 5.263 | 4.6729 | 1.3349 | 16.986
| 584 | 4.6223 | 2.6141 | 4.565 | 4.241 | 1.5548 | 17.5972
| 585 | 4.4394 | 3.0907 | 7.1321 | 3.5223 | 1.3859 | 19.5704
| 586 | 4.6092 | 3.0142 | 7.2465 | 3.3857 | 1.6111 | 19.8667
| 587 | 4.1665 | 2.4738 | 7.0417 | 3.1589 | 1.6551 | 18.4959
| 588 | 4.3134 | 2.8269 | 4.8837 | 5.2554 | 1.1279 | 18.4073
| 589 | 3.2934 | 3.272 | 5.6671 | 5.0242 | 1.5508 | 18.8075
| 590 | 3.765 | 3.0213 | 6.4084 | 5.5512 | 1.3257 | 20.0716
| 591 | 4.553 | 2.6818 | 6.484 | 5.0534 | 1.614 | 20.3861
| 592 | 4.6808 | 3.3672 | 4.9746 | 4.7574 | 1.2949 | 19.0749
| 593 | 3.7618 | 3.255 | 4.9859 | 3.8338 | 1.5492 | 17.3857
| 594 | 3.3445 | 3.2873 | 6.8915 | 3.1341 | 1.8188 | 18.4762
| 595 | 4.049 | 3.4065 | 6.5722 | 4.0337 | 1.5671 | 19.6285
| 596 | 3.5818 | 2.8301 | 5.804 | 3.7293 | 1.6753 | 17.6205
| 597 | 4.5687 | 3.3135 | 4.6476 | 4.0546 | 1.3515 | 17.9358
| 598 | 4.2306 | 2.7701 | 6.1584 | 3.5491 | 1.5455 | 18.2537
| 599 | 4.1186 | 3.2848 | 4.8586 | 3.8764 | 1.4304 | 17.569
| 600 | 4.1899 | 3.1746 | 5.4636 | 4.4148 | 1.4471 | 18.69
| 601 | 3.8601 | 3.2956 | 7.8557 | 4.1963 | 1.7114 | 20.9191
| 602 | 3.7996 | 3.6748 | 5.2651 | 4.1651 | 1.6123 | 18.5169
| 603 | 4.3775 | 2.1915 | 4.3512 | 3.7802 | 1.0509 | 15.7513
| 604 | 4.4796 | 2.1966 | 4.5528 | 4.4879 | 1.4297 | 17.1465
| 605 | 3.7929 | 3.7734 | 6.3625 | 3.5711 | 1.6484 | 19.1482
| 606 | 4.487 | 3.5264 | 5.5518 | 4.9349 | 1.4615 | 19.9615
| 607 | 3.8689 | 2.5991 | 5.3628 | 4.2434 | 1.4806 | 17.5547
| 608 | 4.5072 | 2.1572 | 5.9064 | 5.1569 | 1.2555 | 18.9831
| 609 | 4.2387 | 2.6276 | 7.003 | 4.3336 | 1.685 | 19.8879
| 610 | 3.5415 | 3.361 | 6.6696 | 4.0796 | 1.1722 | 18.824
| 611 | 3.9631 | 3.5421 | 5.4563 | 4.0429 | 1.5639 | 18.5683
| 612 | 4.3748 | 2.619 | 5.541 | 5.1081 | 1.3464 | 18.9893
| 613 | 3.5522 | 2.8815 | 5.1167 | 3.8141 | 1.374 | 16.7385
| 614 | 4.441 | 2.2674 | 4.7623 | 3.8632 | 1.2738 | 16.6077
| 615 | 3.4892 | 2.8645 | 5.3517 | 3.8245 | 1.2593 | 16.7893
| 616 | 3.7326 | 2.8913 | 6.7157 | 3.9161 | 1.3279 | 18.5836
| 617 | 4.2328 | 3.0741 | 6.6901 | 3.6118 | 1.2893 | 18.8981
| 618 | 3.1155 | 2.993 | 4.5828 | 4.6148 | 1.4568 | 16.7628
| 619 | 3.9581 | 3.0866 | 5.9004 | 4.1198 | 1.6761 | 18.7411
| 620 | 3.6672 | 3.2061 | 5.4177 | 3.5357 | 1.8672 | 17.6938
| 621 | 4.3963 | 2.7207 | 5.5222 | 3.3593 | 1.5423 | 17.5409
| 622 | 3.9206 | 2.6776 | 6.6745 | 3.6568 | 1.7634 | 18.693
| 623 | 4.3632 | 3.4904 | 6.192 | 3.8573 | 1.7389 | 19.6417
| 624 | 4.2334 | 2.6547 | 5.3547 | 5.1364 | 1.5449 | 18.9242
| 625 | 4.7783 | 2.306 | 6.5587 | 5.0454 | 1.5185 | 20.2069
| 626 | 4.284 | 2.6566 | 6.2321 | 3.902 | 1.2935 | 18.3683
| 627 | 4.6131 | 3.7699 | 6.1999 | 3.6216 | 1.1481 | 19.3526
| 628 | 4.4753 | 3.0873 | 6.9736 | 4.7614 | 1.7674 | 21.0651
| 629 | 3.7267 | 2.7763 | 5.2793 | 3.5273 | 1.8378 | 17.1473
| 630 | 3.3736 | 2.9772 | 7.2203 | 4.0908 | 1.8073 | 19.4692
| 631 | 4.4332 | 3.02 | 5.4534 | 5.837 | 1.5076 | 20.2512
| 632 | 4.6169 | 3.1493 | 5.1328 | 3.396 | 1.5035 | 17.7986
| 633 | 3.9024 | 3.0999 | 6.2829 | 4.596 | 1.5368 | 19.4181
| 634 | 4.2741 | 2.7181 | 4.8796 | 3.2805 | 1.5271 | 16.6794
| 635 | 3.7208 | 3.4507 | 5.0183 | 4.2172 | 1.3981 | 17.8051
| 636 | 4.029 | 2.865 | 4.8084 | 3.7491 | 1.3023 | 16.7538
| 637 | 3.8716 | 3.0391 | 4.8719 | 3.7954 | 1.2141 | 16.7921
| 638 | 3.4864 | 3.1625 | 4.9817 | 5.4245 | 1.243 | 18.2982
| 639 | 4.3853 | 2.3361 | 4.5213 | 5.5186 | 1.7452 | 18.5066
| 640 | 4.1213 | 3.8597 | 4.4828 | 3.7727 | 1.262 | 17.4985
| 641 | 3.5736 | 2.5979 | 4.4566 | 5.209 | 1.3909 | 17.2279
| 642 | 3.9488 | 3.2147 | 5.4822 | 3.7897 | 1.2984 | 17.7337
| 643 | 3.747 | 3.0754 | 5.1871 | 3.4731 | 1.7317 | 17.2143
| 644 | 3.8363 | 3.3492 | 5.4936 | 3.7683 | 1.3094 | 17.7569
| 645 | 4.3913 | 3.0636 | 6.0361 | 3.3401 | 1.3573 | 18.1885
| 646 | 4.0002 | 2.6202 | 5.1894 | 3.7191 | 1.309 | 16.8378
| 647 | 4.0245 | 3.0609 | 5.4292 | 4.1933 | 1.6051 | 18.3129
| 648 | 4.1843 | 3.3916 | 5.1707 | 3.5396 | 1.3598 | 17.646
| 649 | 3.9033 | 3.102 | 6.6195 | 4.3017 | 1.4675 | 19.394
| 650 | 3.9007 | 2.7016 | 5.5249 | 3.8445 | 1.4511 | 17.4227
| 651 | 4.5848 | 2.5377 | 4.9325 | 5.0177 | 1.0876 | 18.1602
| 652 | 4.1425 | 2.6071 | 4.6189 | 5.4609 | 1.4118 | 18.2412
| 653 | 3.2808 | 2.9821 | 7.1717 | 3.648 | 1.1148 | 18.1974
| 654 | 3.3271 | 3.1186 | 6.5651 | 3.4518 | 1.0453 | 17.5078
| 655 | 3.7696 | 3.054 | 6.6289 | 3.4275 | 1.218 | 18.098
| 656 | 3.3074 | 3.5407 | 5.7986 | 3.7622 | 1.1093 | 17.5183
| 657 | 3.9835 | 2.6005 | 5.6414 | 3.6341 | 1.6914 | 17.5509
| 658 | 4.2677 | 2.8467 | 5.6498 | 4.0762 | 1.5415 | 18.382
| 659 | 4.2217 | 3.27 | 5.6772 | 3.4755 | 1.726 | 18.3704
| 660 | 4.5119 | 3.2825 | 6.5765 | 3.5235 | 1.2407 | 19.1351
| 661 | 3.9434 | 3.1453 | 5.4911 | 3.7658 | 1.4081 | 17.7538
| 662 | 4.9779 | 2.911 | 5.9112 | 3.7224 | 1.066 | 18.5885
| 663 | 3.8295 | 2.7408 | 4.3944 | 4.7114 | 1.6478 | 17.3239
| 664 | 3.5018 | 3.4541 | 4.0721 | 5.8992 | 1.5013 | 18.4286
| 665 | 4.245 | 3.0527 | 4.4927 | 4.8403 | 1.6505 | 18.2812
| 666 | 3.9598 | 3.6166 | 4.9669 | 3.4201 | 1.3357 | 17.2991
| 667 | 3.658 | 2.6646 | 4.4131 | 4.6896 | 1.6668 | 17.0922
| 668 | 4.4911 | 3.3875 | 4.321 | 4.0746 | 1.8927 | 18.1669
| 669 | 4.2261 | 3.0896 | 6.1033 | 4.0609 | 1.814 | 19.2939
| 670 | 3.6062 | 2.35 | 5.9026 | 3.9323 | 1.6171 | 17.4081
| 671 | 3.284 | 2.4766 | 4.8381 | 5.2047 | 1.4276 | 17.231
| 672 | 4.008 | 2.5346 | 6.3535 | 3.3491 | 1.4673 | 17.7125
| 673 | 4.0955 | 2.9372 | 5.9262 | 4.3361 | 1.7233 | 19.0182
| 674 | 3.7525 | 2.7484 | 6.165 | 4.5386 | 1.614 | 18.8185
| 675 | 4.0223 | 2.4797 | 5.2681 | 3.808 | 1.7615 | 17.3396
| 676 | 4.3378 | 3.635 | 7.1284 | 4.4666 | 1.4735 | 21.0413
| 677 | 3.679 | 2.4519 | 5.3609 | 4.7128 | 1.5702 | 17.775
| 678 | 3.9729 | 3.3899 | 5.3015 | 4.2869 | 1.879 | 18.8302
| 679 | 3.8329 | 2.7419 | 6.5703 | 4.0144 | 1.4978 | 18.6573
| 680 | 3.794 | 3.2204 | 4.3771 | 4.1634 | 1.668 | 17.2228
| 681 | 3.5094 | 3.1104 | 6.6787 | 4.3883 | 1.9334 | 19.6202
| 682 | 3.6414 | 2.9912 | 4.7715 | 3.8009 | 1.4759 | 16.681
| 683 | 3.3671 | 3.2014 | 5.8263 | 4.0473 | 1.6659 | 18.108
| 684 | 4.1858 | 3.0765 | 5.7306 | 4.4749 | 1.392 | 18.8598
| 685 | 3.6519 | 2.6214 | 4.9141 | 4.2915 | 1.4441 | 16.9229
| 686 | 4.6202 | 3.3047 | 6.0099 | 5.6238 | 1.5543 | 21.1127
| 687 | 3.5309 | 3.6661 | 4.3241 | 3.9085 | 1.3673 | 16.797
| 688 | 4.4888 | 2.5674 | 7.7504 | 5.5466 | 1.4356 | 21.7887
| 689 | 4.0443 | 2.5941 | 4.8332 | 3.061 | 1.3125 | 15.845
| 690 | 4.2926 | 3.1298 | 5.4259 | 4.0209 | 1.8352 | 18.7044
| 691 | 4.6763 | 2.5578 | 4.5844 | 5.7319 | 1.5744 | 19.1249
| 692 | 3.4959 | 3.0799 | 6.7733 | 4.0884 | 1.4449 | 18.8823
| 693 | 4.4217 | 2.3618 | 4.5238 | 4.3809 | 1.8285 | 17.5166
| 694 | 4.56 | 2.9804 | 5.1196 | 3.3621 | 1.1103 | 17.1325
| 695 | 4.1015 | 2.1776 | 4.6207 | 3.1284 | 1.6291 | 15.6573
| 696 | 4.3198 | 3.4387 | 6.1117 | 3.746 | 1.9124 | 19.5286
| 697 | 4.2005 | 2.8809 | 4.7278 | 3.4034 | 1.6212 | 16.8338
| 698 | 4.3279 | 3.4653 | 5.57 | 3.8384 | 1.4188 | 18.6204
| 699 | 4.8063 | 3.0022 | 6.1833 | 4.5706 | 1.5477 | 20.1102
| 700 | 4.5207 | 3.0519 | 5.5085 | 4.2829 | 1.7885 | 19.1525
| 701 | 4.2352 | 2.5771 | 5.1484 | 3.6786 | 1.4864 | 17.1257
| 702 | 3.754 | 3.0404 | 6.1082 | 4.1122 | 1.1979 | 18.2127
| 703 | 3.3475 | 2.1226 | 4.1326 | 5.1427 | 1.397 | 16.1424
| 704 | 4.0927 | 2.4309 | 7.4194 | 3.2461 | 1.4144 | 18.6034
| 705 | 4.0825 | 2.488 | 5.5768 | 3.741 | 1.3894 | 17.2777
| 706 | 3.4054 | 2.9486 | 4.6164 | 3.4829 | 1.5459 | 15.9991
| 707 | 4.3428 | 2.6523 | 4.7378 | 5.6421 | 1.166 | 18.541
| 708 | 3.7764 | 3.885 | 6.6833 | 3.3232 | 1.5999 | 19.2679
| 709 | 3.3623 | 2.9908 | 6.4452 | 3.3331 | 1.577 | 17.7083
| 710 | 4.1043 | 3.7806 | 5.839 | 4.1307 | 1.9239 | 19.7785
| 711 | 4.1397 | 3.2483 | 4.4413 | 4.1998 | 1.4604 | 17.4895
| 712 | 3.8697 | 3.4602 | 5.1451 | 3.5881 | 1.6438 | 17.7069
| 713 | 3.9686 | 2.8858 | 5.154 | 3.6724 | 1.889 | 17.5697
| 714 | 4.0424 | 3.1652 | 7.0452 | 4.8802 | 1.0572 | 20.1903
| 715 | 4.2105 | 2.5869 | 4.8538 | 3.4603 | 1.2675 | 16.3791
| 716 | 3.7089 | 2.6796 | 6.237 | 4.2667 | 1.7936 | 18.6858
| 717 | 4.1194 | 2.6178 | 6.9235 | 3.2939 | 1.3726 | 18.3272
| 718 | 3.7576 | 3.4812 | 6.0404 | 3.9757 | 1.517 | 18.772
| 719 | 3.4698 | 2.7514 | 5.2561 | 5.057 | 1.5111 | 18.0454
| 720 | 3.7059 | 3.1477 | 4.7523 | 3.6913 | 1.4049 | 16.7021
| 721 | 3.9187 | 3.0307 | 5.4427 | 3.6997 | 1.5228 | 17.6147
| 722 | 4.3807 | 3.359 | 5.974 | 4.17 | 1.8146 | 19.6983
| 723 | 3.1639 | 3.0557 | 5.5376 | 3.8907 | 1.2587 | 16.9065
| 724 | 3.8342 | 2.3231 | 5.0726 | 5.2472 | 1.2218 | 17.6988
| 725 | 4.6696 | 2.376 | 4.9975 | 3.259 | 1.4917 | 16.7938
| 726 | 4.3721 | 3.3737 | 5.0665 | 3.9948 | 1.358 | 18.1652
| 727 | 4.8891 | 3.2673 | 5.7847 | 4.1821 | 1.4538 | 19.5769
| 728 | 4.8477 | 3.4444 | 4.8127 | 3.3708 | 1.7823 | 18.2579
| 729 | 4.2312 | 3.1164 | 6.202 | 3.705 | 1.6769 | 18.9315
| 730 | 3.8847 | 3.3319 | 5.0956 | 3.8434 | 1.4617 | 17.6172
| 731 | 3.3353 | 2.903 | 5.4587 | 3.7553 | 1.5805 | 17.0328
| 732 | 3.962 | 2.408 | 5.1336 | 3.739 | 1.4295 | 16.6721
| 733 | 4.1538 | 2.4668 | 5.8183 | 4.558 | 1.1554 | 18.1522
| 734 | 4.0894 | 2.1536 | 4.1629 | 3.5755 | 1.6301 | 15.6115
| 735 | 3.3981 | 3.2887 | 4.7301 | 4.4997 | 1.7351 | 17.6518
| 736 | 3.99 | 3.5572 | 6.1441 | 3.738 | 1.7576 | 19.187
| 737 | 4.2093 | 2.8949 | 5.2278 | 3.515 | 1.2544 | 17.1013
| 738 | 3.8642 | 2.9832 | 5.2121 | 4.9795 | 1.488 | 18.527
| 739 | 4.1154 | 2.6035 | 7.7304 | 3.9829 | 1.4565 | 19.8886
| 740 | 4.393 | 2.3218 | 5.0742 | 3.9041 | 1.9428 | 17.6359
| 741 | 4.0731 | 3.0277 | 4.1109 | 3.822 | 1.249 | 16.2828
| 742 | 4.3486 | 3.5535 | 5.8654 | 4.3953 | 1.8261 | 19.989
| 743 | 3.8894 | 3.7601 | 7.2771 | 4.4054 | 1.6377 | 20.9697
| 744 | 3.9373 | 3.5776 | 5.1363 | 4.4359 | 1.2953 | 18.3824
| 745 | 4.4126 | 3.9448 | 5.0322 | 3.481 | 1.2374 | 18.1079
| 746 | 4.0336 | 2.277 | 5.3718 | 3.9203 | 1.5857 | 17.1885
| 747 | 3.3428 | 3.2063 | 5.7529 | 4.0538 | 1.3647 | 17.7205
| 748 | 3.29 | 2.3406 | 6.6067 | 4.1573 | 1.1346 | 17.5292
| 749 | 3.2368 | 3.4683 | 4.7371 | 5.5072 | 1.6458 | 18.5952
| 750 | 4.3871 | 2.3166 | 5.4487 | 4.5597 | 1.3454 | 18.0575
| 751 | 4.1902 | 2.9696 | 5.9212 | 4.4404 | 1.3005 | 18.8219
| 752 | 3.8496 | 2.446 | 5.5741 | 3.567 | 1.5193 | 16.9561
| 753 | 4.2659 | 2.8084 | 4.3981 | 3.9271 | 1.5787 | 16.9783
| 754 | 3.6486 | 3.4401 | 5.3988 | 3.6378 | 1.2667 | 17.392
| 755 | 3.6778 | 2.96 | 5.9469 | 3.833 | 1.5517 | 17.9693
| 756 | 3.5928 | 2.6663 | 4.9771 | 5.5622 | 1.6695 | 18.4678
| 757 | 3.6569 | 2.5362 | 4.3615 | 4.6798 | 1.2267 | 16.4611
| 758 | 4.0606 | 3.1133 | 4.8962 | 4.3654 | 1.5099 | 17.9454
| 759 | 3.2718 | 2.4953 | 6.123 | 3.6849 | 1.4421 | 17.017
| 760 | 3.9118 | 3.1659 | 5.0864 | 4.4973 | 1.285 | 17.9465
| 761 | 3.9789 | 2.7692 | 5.3008 | 3.1939 | 1.2014 | 16.4441
| 762 | 4.1941 | 3.8034 | 7.1586 | 3.7928 | 1.6889 | 20.6379
| 763 | 4.4502 | 3.5286 | 4.8434 | 4.7659 | 1.3398 | 18.9279
| 764 | 3.6115 | 2.7648 | 5.2429 | 3.2509 | 1.5906 | 16.4607
| 765 | 3.45 | 3.1434 | 4.7189 | 4.6124 | 1.6563 | 17.581
| 766 | 4.0121 | 3.5815 | 5.1789 | 3.3777 | 1.4105 | 17.5606
| 767 | 4.0527 | 3.1597 | 6.3973 | 3.5841 | 1.5386 | 18.7324
| 768 | 4.0513 | 3.3422 | 4.9389 | 3.6422 | 1.3099 | 17.2846
| 769 | 3.2881 | 2.874 | 6.8225 | 3.5571 | 1.6624 | 18.2042
| 770 | 3.6892 | 2.931 | 4.8046 | 3.4845 | 1.5513 | 16.4607
| 771 | 4.0555 | 3.2989 | 5.514 | 4.3785 | 1.9532 | 19.2002
| 772 | 3.5196 | 2.2338 | 6.9511 | 3.9877 | 1.2928 | 17.9849
| 773 | 4.059 | 3.3756 | 6.6501 | 4.2728 | 1.4622 | 19.8198
| 774 | 4.022 | 3.9899 | 6.2921 | 3.3999 | 1.5928 | 19.2968
| 775 | 4.5033 | 2.796 | 5.308 | 4.1334 | 1.7683 | 18.5091
| 776 | 3.421 | 2.6997 | 5.6521 | 4.1132 | 1.8409 | 17.7269
| 777 | 4.6324 | 3.6933 | 4.8704 | 4.8248 | 1.4605 | 19.4814
| 778 | 4.2154 | 2.5966 | 5.1127 | 3.6843 | 1.4402 | 17.0492
| 779 | 4.4531 | 3.3328 | 5.8601 | 3.6429 | 1.514 | 18.8029
| 780 | 3.3187 | 2.8364 | 5.5777 | 4.6581 | 1.5047 | 17.8955
| 781 | 3.5643 | 2.8209 | 6.5931 | 3.753 | 1.2878 | 18.0191
| 782 | 3.5571 | 3.23 | 5.1733 | 3.8652 | 1.6807 | 17.5063
| 783 | 3.2081 | 3.3655 | 6.0714 | 5.5136 | 1.1044 | 19.263
| 784 | 4.5429 | 3.6194 | 4.1855 | 3.5283 | 1.3436 | 17.2197
| 785 | 4.1255 | 3.3755 | 5.4897 | 3.7991 | 1.6358 | 18.4255
| 786 | 4.5317 | 3.1842 | 5.5164 | 4.2562 | 1.2687 | 18.7572
| 787 | 4.3798 | 3.5949 | 6.9608 | 3.9562 | 1.368 | 20.2596
| 788 | 3.7983 | 3.1769 | 6.8442 | 4.0265 | 1.4995 | 19.3453
| 789 | 4.7469 | 3.538 | 5.8835 | 3.5429 | 1.8698 | 19.5811
| 790 | 3.9046 | 2.211 | 5.3747 | 5.4666 | 1.5497 | 18.5067
| 791 | 3.3707 | 2.9992 | 7.0871 | 4.7804 | 1.501 | 19.7383
| 792 | 3.4021 | 3.0009 | 4.7954 | 4.6183 | 1.2228 | 17.0396
| 793 | 4.156 | 3.278 | 6.2186 | 4.7488 | 1.3226 | 19.724
| 794 | 4.4372 | 2.1643 | 5.3956 | 4.1791 | 1.3851 | 17.5613
| 795 | 4.4831 | 2.8577 | 5.3209 | 4.0128 | 1.5207 | 18.1952
| 796 | 4.0092 | 3.2911 | 4.4192 | 3.6318 | 1.3636 | 16.7149
| 797 | 3.9316 | 3.6398 | 6.7465 | 4.3986 | 1.3543 | 20.0709
| 798 | 3.6207 | 3.4745 | 7.6119 | 3.3119 | 1.2662 | 19.2851
| 799 | 4.4013 | 3.1268 | 4.8116 | 3.05 | 1.3652 | 16.7549
| 800 | 3.8555 | 2.7034 | 7.32 | 4.4815 | 1.2124 | 19.5727
| 801 | 3.212 | 3.1004 | 6.7269 | 3.8804 | 1.6347 | 18.5545
| 802 | 3.6258 | 3.3838 | 4.9798 | 3.9419 | 1.699 | 17.6303
| 803 | 4.0253 | 2.8669 | 4.6288 | 4.3839 | 1.7847 | 17.6897
| 804 | 4.0382 | 2.8965 | 5.7654 | 4.3669 | 1.2246 | 18.2915
| 805 | 3.6803 | 2.3311 | 5.1578 | 3.7773 | 1.6342 | 16.5807
| 806 | 4.1544 | 2.8169 | 5.8302 | 3.6801 | 1.2785 | 17.7601
| 807 | 3.1042 | 3.4776 | 7.5594 | 4.6113 | 1.559 | 20.3115
| 808 | 4.5441 | 2.5181 | 6.4273 | 4.233 | 1.4715 | 19.194
| 809 | 4.3889 | 3.2557 | 4.819 | 4.5328 | 1.3481 | 18.3446
| 810 | 3.0656 | 2.9328 | 6.308 | 3.41 | 1.1814 | 16.8978
| 811 | 3.84 | 3.6024 | 5.6294 | 3.7881 | 1.5621 | 18.422
| 812 | 3.7459 | 3.1418 | 7.8201 | 3.4386 | 1.1908 | 19.3372
| 813 | 4.0673 | 2.2833 | 4.7411 | 3.9008 | 1.9281 | 16.9207
| 814 | 4.4673 | 3.1483 | 6.1346 | 5.1738 | 1.4383 | 20.3624
| 815 | 3.4753 | 2.7615 | 7.7578 | 3.5608 | 1.6966 | 19.252
| 816 | 4.6407 | 3.1543 | 6.2482 | 3.7038 | 1.2724 | 19.0194
| 817 | 4.2494 | 3.4925 | 5.1304 | 3.1872 | 1.3688 | 17.4284
| 818 | 4.6635 | 3.14 | 7.5326 | 3.6963 | 1.797 | 20.8294
| 819 | 4.3294 | 2.359 | 5.2154 | 4.8014 | 1.4196 | 18.1248
| 820 | 4.3529 | 2.3075 | 5.663 | 3.7158 | 1.4549 | 17.4941
| 821 | 3.9086 | 2.9205 | 7.0327 | 3.5553 | 1.1583 | 18.5755
| 822 | 4.551 | 3.2037 | 5.7029 | 4.2836 | 1.7208 | 19.462
| 823 | 4.2546 | 3.4298 | 6.1204 | 4.9774 | 1.8324 | 20.6147
| 824 | 4.1953 | 2.9289 | 5.1427 | 3.6016 | 1.5397 | 17.4083
| 825 | 4.4192 | 2.5567 | 6.9816 | 3.5922 | 1.6699 | 19.2195
| 826 | 3.257 | 3.4696 | 6.3785 | 4.0408 | 1.4633 | 18.6092
| 827 | 4.3082 | 3.5706 | 5.96 | 4.5285 | 1.5057 | 19.873
| 828 | 4.9457 | 2.4645 | 6.9463 | 4.4467 | 1.3847 | 20.1879
| 829 | 3.8664 | 3.4992 | 7.0757 | 3.1502 | 1.6212 | 19.2127
| 830 | 4.5882 | 2.38 | 5.2489 | 3.1066 | 1.6567 | 16.9804
| 831 | 3.3856 | 2.7503 | 5.8479 | 4.4263 | 1.372 | 17.7822
| 832 | 3.7666 | 3.6789 | 5.9239 | 3.3795 | 1.3243 | 18.0732
| 833 | 4.0858 | 3.4761 | 5.6939 | 4.6546 | 1.5004 | 19.4108
| 834 | 3.2242 | 3.6632 | 6.8333 | 5.5827 | 1.8579 | 21.1612
| 835 | 4.1099 | 3.0698 | 5.531 | 4.3144 | 1.7478 | 18.7729
| 836 | 3.9466 | 3.1921 | 6.3444 | 4.9313 | 1.8082 | 20.2227
| 837 | 4.2 | 3.2283 | 4.8648 | 4.635 | 1.1867 | 18.1147
| 838 | 3.1698 | 3.3963 | 7.3571 | 3.7282 | 1.3735 | 19.0249
| 839 | 3.2004 | 3.1379 | 5.954 | 3.6284 | 1.3619 | 17.2825
| 840 | 3.8403 | 2.9692 | 4.1093 | 3.4126 | 1.6783 | 16.0096
| 841 | 3.9126 | 2.939 | 7.1908 | 4.2017 | 1.5718 | 19.8158
| 842 | 4.1605 | 2.3572 | 4.7801 | 3.5403 | 1.6198 | 16.458
| 843 | 4.2619 | 2.6438 | 5.7878 | 4.9212 | 1.2913 | 18.9059
| 844 | 4.4417 | 2.8336 | 6.1621 | 4.6014 | 1.9604 | 19.9993
| 845 | 4.5625 | 3.418 | 6.7951 | 3.4626 | 1.3347 | 19.5729
| 846 | 4.5135 | 2.727 | 6.6408 | 5.1818 | 1.4552 | 20.5183
| 847 | 4.2204 | 3.1838 | 5.2065 | 4.3412 | 1.5967 | 18.5487
| 848 | 3.8982 | 3.2929 | 4.5901 | 4.3623 | 1.3708 | 17.5144
| 849 | 3.3959 | 2.2033 | 5.3413 | 3.592 | 1.8545 | 16.3871
| 850 | 3.726 | 2.7348 | 5.7671 | 4.9553 | 1.7694 | 18.9526
| 851 | 3.9148 | 3.0468 | 5.4075 | 4.8994 | 1.525 | 18.7935
| 852 | 4.8281 | 3.7675 | 5.4366 | 4.2462 | 1.4215 | 19.6999
| 853 | 3.8112 | 2.5677 | 6.1123 | 4.4788 | 1.2971 | 18.2672
| 854 | 4.5304 | 3.2045 | 4.7452 | 3.3662 | 1.701 | 17.5472
| 855 | 3.1814 | 3.5727 | 5.1104 | 3.9057 | 1.585 | 17.3552
| 856 | 3.5466 | 3.5976 | 5.736 | 3.2271 | 1.6627 | 17.77
| 857 | 4.5226 | 3.2866 | 5.8635 | 4.5262 | 1.4659 | 19.6649
| 858 | 3.6929 | 3.2813 | 7.4688 | 3.8857 | 1.7461 | 20.0749
| 859 | 4.3255 | 3.2008 | 5.259 | 4.6429 | 1.5575 | 18.9859
| 860 | 4.0777 | 2.7096 | 5.7222 | 3.4459 | 1.4222 | 17.3776
| 861 | 3.5934 | 3.0781 | 4.2967 | 3.1406 | 1.4543 | 15.5631
| 862 | 3.7789 | 2.9621 | 6.5546 | 4.3725 | 1.4112 | 19.0792
| 863 | 3.2454 | 2.1047 | 7.0298 | 3.8164 | 1.628 | 17.8243
| 864 | 4.3018 | 3.853 | 5.1508 | 3.4797 | 1.5273 | 18.3126
| 865 | 4.3515 | 2.0713 | 5.0876 | 3.8873 | 1.9493 | 17.347
| 866 | 3.8162 | 2.9954 | 5.238 | 4.1732 | 1.3271 | 17.5499
| 867 | 3.1745 | 3.0067 | 7.3385 | 4.6217 | 1.6632 | 19.8046
| 868 | 4.1597 | 2.7189 | 5.992 | 3.3443 | 1.6174 | 17.8324
| 869 | 4.0584 | 3.5097 | 5.5476 | 4.2306 | 1.7909 | 19.1372
| 870 | 3.9816 | 2.9366 | 4.5332 | 3.2414 | 1.0349 | 15.7277
| 871 | 4.1031 | 3.2541 | 5.0701 | 5.3006 | 1.5956 | 19.3235
| 872 | 3.4972 | 2.7667 | 5.3486 | 3.1145 | 1.4432 | 16.1701
| 873 | 3.5332 | 2.8768 | 5.9479 | 5.5017 | 1.7767 | 19.6363
| 874 | 4.3609 | 3.3924 | 4.5423 | 4.9713 | 1.0679 | 18.3348
| 875 | 4.527 | 2.7833 | 4.9898 | 4.4379 | 1.5082 | 18.2461
| 876 | 4.0136 | 3.1113 | 5.8475 | 4.3442 | 1.3752 | 18.6918
| 877 | 3.2506 | 2.8905 | 4.2383 | 4.6634 | 1.8652 | 16.908
| 878 | 3.6651 | 2.3786 | 5.439 | 4.471 | 1.2026 | 17.1562
| 879 | 4.098 | 2.9884 | 5.6163 | 3.8188 | 1.7264 | 18.2479
| 880 | 3.647 | 3.4339 | 5.0298 | 3.9698 | 1.5608 | 17.6413
| 881 | 4.6976 | 3.2107 | 6.7927 | 3.4224 | 1.4477 | 19.5711
| 882 | 4.7258 | 3.0125 | 5.75 | 5.7103 | 1.6816 | 20.8802
| 883 | 3.741 | 2.819 | 5.6047 | 4.4619 | 1.5074 | 18.1341
| 884 | 3.4677 | 3.3288 | 4.7343 | 3.468 | 1.6395 | 16.6383
| 885 | 4.7711 | 3.2642 | 5.0173 | 3.812 | 1.8988 | 18.7634
| 886 | 4.0913 | 2.9722 | 5.3105 | 5.2775 | 1.49 | 19.1416
| 887 | 3.4232 | 2.6912 | 7.6322 | 4.2807 | 1.7319 | 19.7592
| 888 | 4.0628 | 2.2711 | 6.0282 | 3.6609 | 1.5678 | 17.5909
| 889 | 4.3694 | 3.1313 | 5.0221 | 4.1872 | 1.3556 | 18.0656
| 890 | 3.6713 | 3.2326 | 4.9256 | 4.2881 | 1.4259 | 17.5435
| 891 | 3.3037 | 2.8597 | 6.0865 | 4.6996 | 1.7753 | 18.7248
| 892 | 3.6509 | 3.2134 | 4.6759 | 4.82 | 1.7433 | 18.1034
| 893 | 3.5048 | 3.0477 | 4.9106 | 3.6396 | 1.0776 | 16.1802
| 894 | 3.7684 | 2.9648 | 6.0643 | 3.4512 | 1.3702 | 17.619
| 895 | 4.4441 | 2.6621 | 4.5122 | 4.0817 | 1.7236 | 17.4237
| 896 | 3.9411 | 2.7758 | 6.2946 | 3.4441 | 1.331 | 17.7867
| 897 | 3.9574 | 2.9007 | 6.9007 | 3.432 | 1.3762 | 18.5671
| 898 | 3.2315 | 3.5122 | 5.2099 | 3.3427 | 1.6404 | 16.9367
| 899 | 4.0706 | 2.5213 | 6.2417 | 3.7758 | 1.4927 | 18.1021
| 900 | 3.6871 | 2.7584 | 5.3657 | 3.7543 | 1.4938 | 17.0592
| 901 | 3.4576 | 3.1066 | 4.4451 | 3.5337 | 1.3327 | 15.8756
| 902 | 4.0636 | 3.0329 | 5.5882 | 3.5349 | 1.7096 | 17.9291
| 903 | 4.0297 | 2.923 | 5.6848 | 3.7697 | 1.3252 | 17.7324
| 904 | 3.6029 | 2.7879 | 4.6567 | 3.8711 | 1.1376 | 16.0562
| 905 | 4.2589 | 2.8125 | 5.4505 | 3.1744 | 1.2533 | 16.9496
| 906 | 3.5121 | 2.6114 | 5.695 | 5.4536 | 1.6272 | 18.8993
| 907 | 4.1347 | 3.1806 | 5.9815 | 5.32 | 1.4873 | 20.1041
| 908 | 3.9426 | 3.4955 | 5.1239 | 3.6583 | 1.1604 | 17.3806
| 909 | 4.0181 | 3.12 | 6.4222 | 3.3301 | 1.3659 | 18.2562
| 910 | 3.6617 | 3.1278 | 5.7916 | 4.1219 | 1.7875 | 18.4904
| 911 | 3.7289 | 3.6937 | 6.38 | 5.0728 | 1.624 | 20.4994
| 912 | 4.3014 | 3.3119 | 4.9036 | 4.3901 | 1.3538 | 18.2607
| 913 | 4.9325 | 2.8023 | 4.269 | 4.1603 | 1.6785 | 17.8427
| 914 | 3.712 | 3.1087 | 6.4388 | 4.3855 | 1.6245 | 19.2696
| 915 | 3.9534 | 2.6964 | 4.0357 | 5.791 | 1.6583 | 18.1348
| 916 | 4.1106 | 2.5538 | 6.0464 | 3.7959 | 1.329 | 17.8356
| 917 | 4.6572 | 3.0954 | 4.8265 | 3.996 | 1.1959 | 17.771
| 918 | 4.1633 | 3.0727 | 4.191 | 4.8504 | 1.5946 | 17.8719
| 919 | 4.1751 | 2.4683 | 5.7786 | 3.7057 | 1.5843 | 17.712
| 920 | 4.1121 | 2.8057 | 5.2179 | 3.4863 | 1.1879 | 16.8099
| 921 | 4.0468 | 2.8563 | 6.1301 | 4.2641 | 1.5373 | 18.8344
| 922 | 4.1331 | 2.5807 | 4.5312 | 4.1264 | 1.52 | 16.8915
| 923 | 3.9303 | 2.7446 | 4.7904 | 3.2664 | 1.5919 | 16.3237
| 924 | 3.9286 | 3.4502 | 7.0225 | 4.3608 | 1.919 | 20.6812
| 925 | 4.0654 | 2.878 | 5.2233 | 3.6772 | 1.3775 | 17.2213
| 926 | 4.394 | 3.0913 | 5.1469 | 3.2784 | 1.4231 | 17.3338
| 927 | 3.8752 | 2.9867 | 5.5966 | 5.3713 | 1.6097 | 19.4395
| 928 | 4.1358 | 3.1532 | 6.5988 | 3.4006 | 1.8106 | 19.099
| 929 | 3.792 | 3.7015 | 4.7656 | 4.8687 | 1.126 | 18.2538
| 930 | 4.1413 | 3.2231 | 5.6822 | 4.9596 | 1.652 | 19.6582
| 931 | 4.1243 | 2.8037 | 5.0244 | 5.3055 | 1.6432 | 18.9011
| 932 | 3.333 | 2.6316 | 4.9719 | 3.5001 | 1.4729 | 15.9095
| 933 | 4.0436 | 2.5461 | 4.9829 | 5.2119 | 1.738 | 18.5225
| 934 | 3.9139 | 3.3272 | 5.6344 | 4.4186 | 1.6512 | 18.9455
| 935 | 3.7723 | 3.7251 | 5.4269 | 4.0115 | 1.6367 | 18.5726
| 936 | 3.3517 | 3.9134 | 5.8346 | 4.0283 | 1.5757 | 18.7037
| 937 | 3.6922 | 2.1696 | 6.0282 | 4.022 | 1.622 | 17.5341
| 938 | 3.5994 | 3.6083 | 6.1014 | 4.7752 | 1.445 | 19.5293
| 939 | 3.7189 | 2.8254 | 5.2539 | 3.8996 | 1.5287 | 17.2265
| 940 | 4.0065 | 3.0315 | 7.1118 | 3.5089 | 1.483 | 19.1418
| 941 | 4.3034 | 3.3944 | 5.4222 | 3.631 | 1.5642 | 18.3152
| 942 | 3.8803 | 3.1821 | 5.0453 | 4.6457 | 1.7507 | 18.504
| 943 | 3.7041 | 3.6135 | 4.3553 | 3.4416 | 1.4061 | 16.5206
| 944 | 4.197 | 2.8454 | 5.7012 | 5.4841 | 1.0926 | 19.3203
| 945 | 4.4225 | 2.9237 | 5.8334 | 4.2695 | 1.8032 | 19.2523
| 946 | 3.6174 | 3.1152 | 5.079 | 4.0055 | 1.298 | 17.1151
| 947 | 3.5217 | 2.7072 | 7.3311 | 4.2114 | 1.0445 | 18.8159
| 948 | 3.9331 | 2.9763 | 5.5504 | 5.112 | 1.1965 | 18.7683
| 949 | 3.7044 | 3.4013 | 4.6124 | 4.1533 | 1.4874 | 17.3587
| 950 | 4.0884 | 3.1356 | 5.0995 | 3.1389 | 1.3433 | 16.8057
| 951 | 3.9402 | 3.2246 | 4.659 | 3.431 | 1.2178 | 16.4726
| 952 | 4.2151 | 2.5501 | 4.9901 | 4.491 | 1.8202 | 18.0665
| 953 | 3.1958 | 3.161 | 4.9701 | 4.8096 | 1.7006 | 17.8372
| 954 | 3.725 | 2.4913 | 7.2133 | 4.0019 | 1.319 | 18.7506
| 955 | 3.6867 | 2.8922 | 6.9379 | 4.2942 | 1.6796 | 19.4906
| 956 | 3.7905 | 2.3657 | 5.4681 | 3.3553 | 1.4742 | 16.4538
| 957 | 4.5722 | 2.7622 | 4.5698 | 4.0776 | 1.3137 | 17.2955
| 958 | 3.659 | 2.9507 | 4.7866 | 3.6949 | 1.4069 | 16.4982
| 959 | 3.2623 | 3.818 | 5.2479 | 3.7355 | 1.4063 | 17.4701
| 960 | 4.4593 | 3.1097 | 5.0022 | 3.5068 | 1.8225 | 17.9005
| 961 | 3.6764 | 3.0605 | 5.4852 | 4.4323 | 1.2386 | 17.8929
| 962 | 3.3293 | 3.6427 | 7.3001 | 4.004 | 1.4557 | 19.7317
| 963 | 3.6217 | 2.5219 | 4.5784 | 4.0163 | 1.3601 | 16.0983
| 964 | 3.4486 | 2.7929 | 5.1588 | 3.4361 | 1.2202 | 16.0566
| 965 | 3.8587 | 3.1507 | 6.2734 | 3.9628 | 1.6576 | 18.9032
| 966 | 3.6841 | 3.3453 | 5.6241 | 3.8554 | 1.4309 | 17.9398
| 967 | 3.9605 | 2.7899 | 6.2516 | 4.3566 | 1.5066 | 18.8653
| 968 | 3.6277 | 2.8995 | 6.3338 | 3.7478 | 1.4098 | 18.0186
| 969 | 3.8428 | 2.4623 | 5.4734 | 3.4974 | 1.4727 | 16.7485
| 970 | 4.7558 | 2.8448 | 5.3875 | 4.3491 | 1.2278 | 18.5649
| 971 | 4.2848 | 2.6382 | 5.8203 | 5.1904 | 1.4366 | 19.3702
| 972 | 4.2034 | 3.407 | 6.6667 | 5.4093 | 1.231 | 20.9175
| 973 | 3.4102 | 2.7001 | 5.3299 | 5.0385 | 1.1578 | 17.6366
| 974 | 4.7093 | 3.2682 | 6.7648 | 3.6822 | 1.5443 | 19.9689
| 975 | 3.5983 | 3.063 | 7.174 | 4.2989 | 1.6316 | 19.7658
| 976 | 3.8544 | 2.9081 | 4.698 | 4.9275 | 1.7531 | 18.1411
| 977 | 3.1371 | 3.3398 | 7.1523 | 3.553 | 1.245 | 18.4271
| 978 | 4.2185 | 3.1223 | 6.9049 | 3.5194 | 1.3988 | 19.1639
| 979 | 4.8963 | 2.8244 | 4.8786 | 3.3544 | 1.5871 | 17.5408
| 980 | 3.9799 | 2.6667 | 6.1158 | 3.9289 | 1.7043 | 18.3955
| 981 | 3.4613 | 3.216 | 5.8436 | 3.3468 | 1.1243 | 16.992
| 982 | 4.0977 | 2.6872 | 6.5124 | 4.5453 | 1.6799 | 19.5226
| 983 | 4.5949 | 3.0822 | 6.9963 | 4.7834 | 1.3294 | 20.7862
| 984 | 3.7736 | 2.7745 | 4.626 | 3.3516 | 1.4409 | 15.9666
| 985 | 3.235 | 2.726 | 6.4692 | 3.5595 | 1.4162 | 17.406
| 986 | 4.293 | 3.2367 | 7.2402 | 4.6517 | 1.4999 | 20.9215
| 987 | 3.9703 | 3.2583 | 5.441 | 4.938 | 1.4818 | 19.0895
| 988 | 4.3314 | 3.0643 | 6.4737 | 4.4509 | 1.4131 | 19.7335
| 989 | 4.001 | 2.9855 | 6.9577 | 3.9397 | 1.5234 | 19.4074
| 990 | 4.0801 | 3.1258 | 6.0158 | 4.5877 | 1.7738 | 19.5832
| 991 | 3.8944 | 2.3971 | 5.2863 | 3.8393 | 1.6939 | 17.111
| 992 | 4.1046 | 3.8077 | 5.9164 | 3.9235 | 1.1415 | 18.8939
| 993 | 3.3233 | 3.218 | 5.7173 | 4.1105 | 1.78 | 18.1491
| 994 | 4.4925 | 3.2767 | 5.7192 | 3.4415 | 1.7657 | 18.6955
| 995 | 3.8228 | 3.0011 | 5.7598 | 4.1153 | 1.5179 | 18.217
| 996 | 3.852 | 3.8938 | 7.1405 | 4.8069 | 1.7392 | 21.4325
| 997 | 4.4637 | 2.8898 | 4.9145 | 3.4148 | 1.6077 | 17.2905
| 998 | 3.674 | 2.5283 | 7.3869 | 3.4087 | 1.4263 | 18.4241
| 999 | 4.1696 | 2.9675 | 5.1632 | 4.1803 | 1.528 | 18.0086
| 1000 | 3.4158 | 2.5899 | 5.0275 | 5.7177 | 1.9698 | 18.7208
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Risk Results 3
Navigation |  | Inputs |  |  |  |  | Outputs | Simulation Statistics |  | Output Cumulative Distributions | Output Distributions | Risk Tornado Diagram
Risk Outputs |  | Plan!$G$6 | Plan!$G$7 | Plan!$G$8 | Plan!$G$9 | Plan!$G$10 | Plan!$G$11 |  | Plan!$G$11 |  |  |  |  | Correlations - Column 1 sorted
Simulation Statistics | Iterations | RiskTriang(D6,E6,F6) | RiskTriang(D7,E7,F7) | RiskTriang(D8,E8,F8) | RiskTriang(D9,E9,F9) | RiskTriang(D10,E10,F10) | LiveDate |  | LiveDate |  |  | Select Output: | Plan!$G$11 |  | Plan!$G$11
Risk Output Percentiles | 1 | 4.4052 | 2.8564 | 4.2538 | 3.6842 | 1.3031 | 16.5027 | Mean | 18.3333 |  |  | Name: | LiveDate | Risk Inputs | LiveDate
Calculate Percent Rank | 2 | 3.029 | 2.6132 | 4.9943 | 3.7078 | 1.3117 | 15.6561 | Median | 18.2664 |  |  | 1 |  | Plan!$G$10 | 0.15363
Correlations | 3 | 3.9648 | 2.7574 | 5.4778 | 3.6486 | 1.5791 | 17.4277 | Mode | #N/A |  |  | Tornado Diagram for LiveDate (Plan!$G$11) |  | Plan!$G$7 | 0.3374
Output Cumulative Distributions | 4 | 4.5676 | 3.9322 | 6.4295 | 3.6802 | 1.718 | 20.3274 | Std. Deviation | 1.2552 |  |  |  |  | Plan!$G$6 | 0.34537
Output Distributions | 5 | 3.4285 | 3.8293 | 5.85 | 3.1452 | 1.3912 | 17.6442 | Variance | 1.5755 |  |  |  |  | Plan!$G$9 | 0.55219
Risk Tornado Diagram | 6 | 3.7267 | 3.0253 | 5.7985 | 3.6557 | 1.5986 | 17.8047 | Kurtosis | -0.2788 |  |  |  |  | Plan!$G$8 | 0.68501
| 7 | 3.6788 | 2.8212 | 4.321 | 3.8406 | 1.5713 | 16.2327 | Skewness | 0.27358
| 8 | 4.0319 | 2.6351 | 4.6636 | 5.4087 | 1.1596 | 17.8989 | Minimum | 15.0123
| 9 | 4.704 | 3.1601 | 5.3619 | 3.4614 | 1.1651 | 17.8524 | Maximum | 21.8577
| 10 | 4.3024 | 2.7491 | 5.1149 | 4.2886 | 1.7004 | 18.1555 | Range | 6.8454
| 11 | 3.622 | 2.4789 | 5.5263 | 3.4539 | 1.4699 | 16.551 | Count | 1000
| 12 | 3.3331 | 2.603 | 6.0966 | 3.6927 | 1.3248 | 17.0503 | Error Count | 0
| 13 | 4.1257 | 3.8566 | 5.0911 | 3.3028 | 1.5878 | 17.9641 | Std. Error | 0.039692
| 14 | 4.3327 | 3.3249 | 5.3547 | 4.4725 | 1.494 | 18.9787 | Confidence Level (95%) | 0.07789
| 15 | 4.6981 | 3.5743 | 7.344 | 4.6369 | 1.4207 | 21.6739
| 16 | 3.5926 | 2.3515 | 5.0613 | 4.5058 | 1.4163 | 16.9275 | Percentiles
| 17 | 4.0567 | 3.1308 | 6.9403 | 5.9359 | 1.3575 | 21.4211 |  | Plan!$G$11
| 18 | 4.0377 | 3.2998 | 5.4988 | 3.622 | 1.8522 | 18.3104 |  | LiveDate
| 19 | 3.5971 | 2.7904 | 5.0246 | 3.7284 | 1.8794 | 17.02 | 0% | 15.0123
| 20 | 4.1344 | 2.6637 | 4.768 | 3.4144 | 1.3426 | 16.3231 | 2.5% | 16.1257
| 21 | 3.1885 | 3.5461 | 5.1108 | 4.037 | 1.2885 | 17.171 | 5% | 16.3123
| 22 | 3.8619 | 2.9061 | 5.3451 | 3.6327 | 1.4824 | 17.2281 | 7.5% | 16.5527
| 23 | 3.2735 | 2.3235 | 5.1087 | 3.6977 | 1.2779 | 15.6813 | 10% | 16.7349
| 24 | 3.324 | 2.7532 | 5.2599 | 5.0868 | 1.613 | 18.0369 | 12.5% | 16.9264
| 25 | 4.5474 | 2.8797 | 4.9757 | 3.9306 | 1.5889 | 17.9223 | 15% | 17.0388
| 26 | 4.9112 | 3.2667 | 7.1189 | 3.1571 | 1.3128 | 19.7668 | 17.5% | 17.1513
| 27 | 4.2906 | 3.221 | 5.2381 | 4.2683 | 1.2599 | 18.2778 | 20% | 17.2845
| 28 | 3.6256 | 2.6956 | 5.8434 | 4.4933 | 1.5899 | 18.2479 | 22.5% | 17.3436
| 29 | 4.0136 | 3.6896 | 6.9005 | 4.9739 | 1.3235 | 20.9012 | 25% | 17.4243
| 30 | 4.7456 | 3.6399 | 5.2903 | 4.3684 | 1.5719 | 19.6161 | 27.5% | 17.4789
| 31 | 3.5373 | 3.0105 | 5.5468 | 5.3968 | 1.3207 | 18.8121 | 30% | 17.5606
| 32 | 3.931 | 3.7962 | 4.5963 | 3.6703 | 1.799 | 17.7929 | 32.5% | 17.6367
| 33 | 3.7449 | 2.9205 | 5.6613 | 3.1311 | 1.6718 | 17.1295 | 35% | 17.7711
| 34 | 3.3033 | 2.403 | 5.5919 | 4.3058 | 1.6965 | 17.3006 | 37.5% | 17.8578
| 35 | 4.0682 | 3.3269 | 4.3269 | 3.3469 | 1.5114 | 16.5805 | 40% | 17.9369
| 36 | 4.478 | 3.0364 | 5.4166 | 3.6112 | 1.2924 | 17.8347 | 42.5% | 17.9895
| 37 | 4.0803 | 2.1348 | 4.4933 | 4.4885 | 1.3482 | 16.5451 | 45% | 18.0715
| 38 | 3.7354 | 3.1104 | 6.5617 | 4.4866 | 1.7329 | 19.627 | 47.5% | 18.173
| 39 | 3.5024 | 2.852 | 4.6091 | 3.4472 | 1.7151 | 16.1257 | 50% | 18.2664
| 40 | 3.5076 | 3.0025 | 4.4288 | 5.4899 | 1.2307 | 17.6594 | 52.5% | 18.345
| 41 | 3.9917 | 2.8433 | 4.7463 | 3.2471 | 1.1829 | 16.0114 | 55% | 18.4386
| 42 | 3.184 | 3.6752 | 4.9044 | 3.3705 | 1.4564 | 16.5906 | 57.5% | 18.5373
| 43 | 3.5546 | 2.6164 | 4.9405 | 4.0859 | 1.3615 | 16.5588 | 60% | 18.6201
| 44 | 4.0179 | 3.305 | 6.6359 | 3.1957 | 1.3519 | 18.5064 | 62.5% | 18.7139
| 45 | 4.2016 | 2.5013 | 4.8763 | 4.8338 | 1.61 | 18.0231 | 65% | 18.811
| 46 | 4.1831 | 3.4393 | 5.0119 | 3.764 | 1.4532 | 17.8516 | 67.5% | 18.8604
| 47 | 4.3731 | 2.9365 | 5.5705 | 3.687 | 1.4488 | 18.0159 | 70% | 18.9618
| 48 | 4.4244 | 3.1248 | 5.7013 | 4.0884 | 1.6245 | 18.9634 | 72.5% | 19.0744
| 49 | 3.0461 | 3.2589 | 6.578 | 3.8735 | 1.5858 | 18.3422 | 75% | 19.1865
| 50 | 4.2846 | 2.9372 | 5.5929 | 4.4162 | 1.9309 | 19.1619 | 77.5% | 19.2936
| 51 | 3.602 | 2.3883 | 5.6004 | 3.9339 | 1.3535 | 16.8782 | 80% | 19.4082
| 52 | 4.1066 | 3.0135 | 6.8435 | 4.8295 | 1.3877 | 20.1808 | 82.5% | 19.5407
| 53 | 4.0328 | 3.0595 | 4.724 | 4.073 | 1.4571 | 17.3465 | 85% | 19.6349
| 54 | 4.0693 | 2.7945 | 5.714 | 3.7926 | 1.1783 | 17.5488 | 87.5% | 19.7863
| 55 | 3.9282 | 3.408 | 5.327 | 3.8321 | 1.4516 | 17.9469 | 90% | 19.9979
| 56 | 4.4452 | 3.6436 | 5.8329 | 3.7667 | 1.5001 | 19.1885 | 92.5% | 20.1834
| 57 | 4.1635 | 3.1667 | 5.7556 | 4.875 | 1.5249 | 19.4858 | 95% | 20.5337
| 58 | 4.9006 | 2.7126 | 4.9338 | 3.7547 | 1.6195 | 17.9212 | 97.5% | 21.0633
| 59 | 3.3924 | 3.0401 | 6.3471 | 3.356 | 1.1133 | 17.2489 | 100% | 21.8577
| 60 | 3.5098 | 2.8067 | 5.3109 | 4.3087 | 1.4799 | 17.416
| 61 | 3.8661 | 3.4448 | 5.375 | 3.6898 | 1.2361 | 17.6118 | Percent Rank
| 62 | 4.2842 | 2.8854 | 4.907 | 3.8945 | 1.4559 | 17.427 |  | Plan!$G$11
| 63 | 4.3291 | 3.2402 | 6.4949 | 3.9993 | 1.4407 | 19.5041 |  | LiveDate
| 64 | 4.5008 | 3.3467 | 5.3203 | 3.7962 | 1.5207 | 18.4846 | Enter Value: | 16.3123
| 65 | 3.4609 | 3.1454 | 5.9153 | 3.4003 | 1.5941 | 17.516 | % rank: | 5%
| 66 | 3.9662 | 2.493 | 5.8855 | 3.4728 | 1.5036 | 17.321
| 67 | 3.3274 | 3.074 | 4.6922 | 3.5371 | 1.5018 | 16.1324 | Correlations
| 68 | 3.4878 | 2.6068 | 5.9686 | 4.0545 | 1.4953 | 17.6131 |  | Plan!$G$11
| 69 | 3.9787 | 2.969 | 6.4168 | 4.0686 | 1.4733 | 18.9064 | Risk Inputs | LiveDate
| 70 | 4.4617 | 3.5823 | 4.8971 | 5.148 | 1.9264 | 20.0155 | Plan!$G$6 | 0.34537
| 71 | 4.4174 | 3.1358 | 4.9263 | 3.172 | 1.2683 | 16.9199 | Plan!$G$7 | 0.3374
| 72 | 4.3691 | 3.0995 | 5.1277 | 3.1062 | 1.4166 | 17.119 | Plan!$G$8 | 0.68501
| 73 | 4.6076 | 2.4114 | 5.8083 | 3.6789 | 1.1389 | 17.6451 | Plan!$G$9 | 0.55219
| 74 | 3.4004 | 3.25 | 5.4786 | 3.9045 | 1.5736 | 17.6072 | Plan!$G$10 | 0.15363
| 75 | 3.9285 | 2.7342 | 5.2168 | 4.9544 | 1.181 | 18.0149
| 76 | 3.7311 | 2.1719 | 4.9877 | 4.9813 | 1.2236 | 17.0955
| 77 | 3.4685 | 3.3117 | 5.7477 | 3.2363 | 1.399 | 17.1632
| 78 | 3.6266 | 2.9658 | 6.4603 | 3.7492 | 1.827 | 18.6288
| 79 | 4.0615 | 2.9479 | 6.6285 | 4.5002 | 1.858 | 19.9961
| 80 | 4.0662 | 3.3039 | 7.4084 | 5.1273 | 1.3095 | 21.2153
| 81 | 4.1873 | 2.8997 | 4.2295 | 4.7288 | 1.0733 | 17.1186
| 82 | 4.065 | 3.1403 | 5.4449 | 4.6761 | 1.0644 | 18.3908
| 83 | 3.8466 | 3.0599 | 5.9549 | 3.3887 | 1.3199 | 17.57
| 84 | 4.7508 | 2.3688 | 5.8768 | 4.281 | 1.1042 | 18.3816
| 85 | 3.4912 | 3.1996 | 6.4317 | 3.6247 | 1.4238 | 18.171
| 86 | 4.028 | 2.5386 | 7.6814 | 4.2462 | 1.5069 | 20.001
| 87 | 3.836 | 2.6979 | 6.7788 | 4.8188 | 1.4506 | 19.5821
| 88 | 4.1778 | 2.0942 | 4.9501 | 3.5882 | 1.6141 | 16.4244
| 89 | 3.9866 | 2.4711 | 5.0493 | 4.0784 | 1.2219 | 16.8073
| 90 | 4.0502 | 3.559 | 5.3018 | 4.4512 | 1.678 | 19.0401
| 91 | 3.8304 | 2.6584 | 4.1594 | 3.9494 | 1.6052 | 16.2028
| 92 | 3.9544 | 2.1837 | 5.6262 | 4.8663 | 1.4233 | 18.0538
| 93 | 3.7821 | 3.0229 | 6.2186 | 3.4944 | 1.4299 | 17.948
| 94 | 4.0349 | 2.5781 | 5.4498 | 3.2444 | 1.0914 | 16.3985
| 95 | 3.9055 | 3.037 | 5.5514 | 4.8009 | 1.2446 | 18.5395
| 96 | 3.9674 | 3.4205 | 7.2746 | 3.9533 | 1.554 | 20.1699
| 97 | 3.9587 | 2.9814 | 5.7457 | 3.7172 | 1.8636 | 18.2665
| 98 | 4.3188 | 2.6266 | 4.6988 | 4.3923 | 1.4866 | 17.5233
| 99 | 4.0484 | 2.5933 | 5.4581 | 3.545 | 1.7063 | 17.3511
| 100 | 3.4336 | 2.5277 | 4.99 | 3.403 | 1.4372 | 15.7915
| 101 | 3.642 | 2.9565 | 6.5199 | 3.2054 | 1.5134 | 17.8372
| 102 | 3.3315 | 3.2423 | 5.7598 | 3.517 | 1.4887 | 17.3393
| 103 | 4.1395 | 3.348 | 5.6734 | 3.4518 | 1.8758 | 18.4885
| 104 | 3.7793 | 2.4898 | 6.906 | 5.0962 | 1.405 | 19.6763
| 105 | 4.6669 | 3.5155 | 5.5959 | 5.2288 | 1.1688 | 20.1759
| 106 | 3.8445 | 3.447 | 5.0947 | 5.1063 | 1.2179 | 18.7104
| 107 | 4.1135 | 3.5412 | 6.1368 | 3.7298 | 1.7454 | 19.2668
| 108 | 3.5631 | 2.2149 | 5.3087 | 3.9393 | 1.4671 | 16.4931
| 109 | 3.7849 | 2.2651 | 6.8099 | 3.7522 | 1.3769 | 17.989
| 110 | 4.1782 | 3.0408 | 6.6697 | 4.3529 | 1.5346 | 19.7762
| 111 | 3.2511 | 2.8081 | 5.0233 | 3.7154 | 1.344 | 16.1419
| 112 | 4.4802 | 3.1579 | 4.4711 | 3.7129 | 1.6261 | 17.4483
| 113 | 3.9687 | 3.0434 | 5.7635 | 3.8719 | 1.9588 | 18.6062
| 114 | 3.7871 | 3.4343 | 5.2931 | 4.3777 | 1.6306 | 18.5228
| 115 | 3.2907 | 2.4955 | 4.1398 | 4.4133 | 1.5668 | 15.906
| 116 | 3.6041 | 2.2859 | 5.3719 | 5.1908 | 1.8089 | 18.2616
| 117 | 4.3445 | 2.939 | 4.8934 | 5.5363 | 1.2073 | 18.9206
| 118 | 4.7905 | 3.1202 | 5.1027 | 3.3861 | 1.4703 | 17.8698
| 119 | 3.6611 | 2.4584 | 6.2887 | 4.7146 | 1.2163 | 18.3391
| 120 | 4.5177 | 2.4744 | 5.2685 | 3.8695 | 1.5486 | 17.6787
| 121 | 3.8527 | 3.3917 | 4.7106 | 3.7317 | 1.8744 | 17.5611
| 122 | 3.6952 | 2.434 | 5.0346 | 5.0519 | 1.5185 | 17.7342
| 123 | 4.2876 | 2.5686 | 6.865 | 3.6147 | 1.2295 | 18.5653
| 124 | 4.4727 | 2.9191 | 4.6631 | 4.4236 | 1.6639 | 18.1423
| 125 | 3.5709 | 3.4127 | 4.672 | 4.5588 | 1.5675 | 17.7818
| 126 | 4.7621 | 3.2064 | 7.0612 | 4.5082 | 1.2867 | 20.8245
| 127 | 4.8987 | 2.9143 | 6.7744 | 4.1507 | 1.7321 | 20.4701
| 128 | 3.4576 | 2.888 | 7.1858 | 3.5533 | 1.2608 | 18.3455
| 129 | 3.2537 | 3.6685 | 5.8384 | 3.4462 | 1.4265 | 17.6332
| 130 | 4.7675 | 2.9132 | 5.0453 | 5.092 | 1.4368 | 19.2548
| 131 | 4.0597 | 2.7462 | 4.1427 | 3.5421 | 1.3848 | 15.8755
| 132 | 3.4971 | 2.9819 | 4.8189 | 4.6151 | 1.1205 | 17.0335
| 133 | 4.2872 | 3.3607 | 6.1792 | 4.3984 | 1.3214 | 19.5469
| 134 | 3.6782 | 2.2318 | 6.6666 | 4.8949 | 1.4036 | 18.8751
| 135 | 4.0747 | 2.81 | 6.1144 | 4.0822 | 1.4289 | 18.5103
| 136 | 3.8118 | 2.5938 | 4.9543 | 4.1558 | 1.9502 | 17.4659
| 137 | 4.461 | 3.1896 | 5.0579 | 4.7608 | 1.6913 | 19.1606
| 138 | 3.6984 | 3.8084 | 7.0497 | 4.5785 | 1.4606 | 20.5955
| 139 | 3.5107 | 3.7324 | 4.6363 | 4.2061 | 1.0421 | 17.1276
| 140 | 4.0152 | 2.1525 | 4.8016 | 4.4737 | 1.9393 | 17.3823
| 141 | 3.495 | 2.633 | 6.6474 | 4.6227 | 1.4177 | 18.8157
| 142 | 3.9612 | 3.7783 | 5.0664 | 3.787 | 1.2381 | 17.8309
| 143 | 3.8564 | 2.6996 | 4.7329 | 4.1274 | 1.5309 | 16.9471
| 144 | 4.1801 | 3.3974 | 5.5814 | 4.2295 | 1.6853 | 19.0736
| 145 | 4.0993 | 2.7637 | 4.8083 | 3.8438 | 1.3941 | 16.9092
| 146 | 3.7942 | 3.3527 | 5.1529 | 5.3865 | 1.9644 | 19.6507
| 147 | 3.7831 | 2.6039 | 5.0169 | 4.3165 | 1.2341 | 16.9546
| 148 | 4.3266 | 2.6766 | 5.8593 | 4.316 | 1.5632 | 18.7417
| 149 | 4.2608 | 2.5827 | 4.7317 | 4.1146 | 1.7463 | 17.436
| 150 | 3.5246 | 3.2342 | 4.929 | 3.6666 | 1.8048 | 17.1592
| 151 | 3.7322 | 3.0538 | 7.5597 | 4.3138 | 1.4327 | 20.0922
| 152 | 4.3893 | 3.3763 | 5.7099 | 4.2591 | 1.5827 | 19.3173
| 153 | 3.2207 | 2.66 | 6.1202 | 4.3505 | 1.7634 | 18.1148
| 154 | 3.8613 | 3.0788 | 6.4682 | 5.3251 | 1.5906 | 20.324
| 155 | 4.091 | 3.8479 | 5.6144 | 3.4869 | 1.8903 | 18.9306
| 156 | 3.4224 | 3.081 | 5.2667 | 4.017 | 1.699 | 17.4861
| 157 | 4.0711 | 3.1934 | 4.8957 | 3.4629 | 1.866 | 17.4891
| 158 | 3.9382 | 2.9607 | 7.1394 | 4.3426 | 1.1511 | 19.532
| 159 | 4.1074 | 3.5238 | 5.0873 | 3.5849 | 1.0703 | 17.3737
| 160 | 4.5728 | 2.9518 | 5.773 | 4.6729 | 1.7986 | 19.769
| 161 | 4.4095 | 3.7746 | 5.1172 | 3.9887 | 1.266 | 18.5559
| 162 | 3.6381 | 3.6031 | 5.4951 | 4.6428 | 1.5123 | 18.8914
| 163 | 3.2393 | 2.7148 | 6.7853 | 4.5681 | 1.6541 | 18.9616
| 164 | 3.6333 | 2.6014 | 5.1758 | 3.4754 | 1.3292 | 16.215
| 165 | 3.99 | 3.5038 | 5.5581 | 5.6726 | 1.4806 | 20.205
| 166 | 4.2753 | 3.7847 | 6.3726 | 3.4565 | 1.3514 | 19.2405
| 167 | 3.8787 | 2.2939 | 5.0415 | 3.8145 | 1.4159 | 16.4445
| 168 | 3.8777 | 2.7993 | 7.3921 | 5.7558 | 1.4687 | 21.2936
| 169 | 4.1692 | 2.9023 | 6.6086 | 5.3442 | 1.5463 | 20.5706
| 170 | 4.1232 | 2.7879 | 5.509 | 5.2364 | 1.5082 | 19.1648
| 171 | 3.8433 | 2.2904 | 7.4752 | 5.1421 | 1.7088 | 20.4598
| 172 | 3.6116 | 2.4628 | 5.1968 | 3.7508 | 1.2508 | 16.2728
| 173 | 4.6248 | 3.6464 | 7.4411 | 4.3549 | 1.3961 | 21.4633
| 174 | 4.2588 | 3.0731 | 5.3591 | 4.275 | 1.4014 | 18.3674
| 175 | 4.719 | 2.2251 | 4.2098 | 3.4982 | 1.2699 | 15.922
| 176 | 4.1005 | 2.9552 | 6.6834 | 3.312 | 1.2913 | 18.3424
| 177 | 4.6114 | 3.6559 | 4.4416 | 3.8851 | 1.1937 | 17.7877
| 178 | 3.5916 | 3.0096 | 5.1746 | 3.1529 | 1.0533 | 15.9819
| 179 | 3.6688 | 3.7423 | 4.1175 | 4.7125 | 1.6497 | 17.8907
| 180 | 3.7769 | 2.1021 | 6.5817 | 3.4438 | 1.7 | 17.6045
| 181 | 3.8369 | 2.6211 | 5.2357 | 4.5476 | 1.6841 | 17.9254
| 182 | 3.7907 | 3.754 | 4.8773 | 4.7558 | 1.5658 | 18.7436
| 183 | 3.2836 | 3.885 | 5.1348 | 3.433 | 1.5662 | 17.3026
| 184 | 4.0343 | 2.313 | 6.0369 | 4.4346 | 1.8865 | 18.7052
| 185 | 4.6612 | 2.7856 | 5.9977 | 4.5332 | 1.7022 | 19.6799
| 186 | 4.0448 | 2.8663 | 5.5486 | 3.3265 | 1.5368 | 17.323
| 187 | 3.9261 | 2.8958 | 6.7644 | 4.2771 | 1.3393 | 19.2027
| 188 | 4.5263 | 2.7829 | 6.0653 | 3.993 | 1.5165 | 18.884
| 189 | 4.1995 | 3.3678 | 5.6741 | 3.7689 | 1.6344 | 18.6447
| 190 | 4.0068 | 3.5849 | 4.6001 | 4.3212 | 1.8111 | 18.3241
| 191 | 3.5727 | 2.6426 | 4.8628 | 5.0223 | 1.4639 | 17.5643
| 192 | 3.9208 | 3.1285 | 4.7545 | 4.4673 | 1.3833 | 17.6544
| 193 | 3.7667 | 2.7216 | 6.8193 | 3.5121 | 1.6222 | 18.4419
| 194 | 4.1093 | 2.8016 | 6.2286 | 3.9451 | 1.37 | 18.4546
| 195 | 3.9969 | 3.4401 | 5.8978 | 3.5646 | 1.3624 | 18.2618
| 196 | 4.2421 | 3.3133 | 4.9148 | 4.099 | 1.1759 | 17.7451
| 197 | 4.7164 | 2.3728 | 5.9845 | 3.5173 | 1.4041 | 17.995
| 198 | 3.6204 | 3.0629 | 4.6882 | 4.3955 | 1.3718 | 17.1387
| 199 | 3.3805 | 3.501 | 5.0538 | 3.5818 | 1.2821 | 16.7992
| 200 | 4.0207 | 3.2796 | 5.8896 | 4.0114 | 1.3868 | 18.588
| 201 | 4.098 | 2.8041 | 6.0601 | 3.2901 | 1.2519 | 17.5041
| 202 | 3.5468 | 3.0337 | 4.623 | 3.4675 | 1.8485 | 16.5196
| 203 | 4.3214 | 2.5742 | 6.7669 | 5.3146 | 1.2192 | 20.1964
| 204 | 3.8243 | 2.5365 | 4.4207 | 3.0856 | 1.1452 | 15.0123
| 205 | 3.8333 | 2.8591 | 6.8223 | 4.14 | 1.3451 | 18.9997
| 206 | 3.7404 | 3.0076 | 4.561 | 3.3346 | 1.1568 | 15.8004
| 207 | 4.6298 | 3.5088 | 6.0283 | 3.5757 | 1.7975 | 19.5401
| 208 | 4.2625 | 3.4159 | 5.4711 | 4.3747 | 1.5452 | 19.0694
| 209 | 4.1148 | 2.4192 | 5.1355 | 4.4802 | 1.484 | 17.6337
| 210 | 4.5209 | 2.3422 | 6.1683 | 4.0243 | 1.4917 | 18.5475
| 211 | 3.685 | 2.6443 | 5.0678 | 4.3766 | 1.1059 | 16.8797
| 212 | 4.2268 | 3.2039 | 4.2503 | 4.9046 | 1.8713 | 18.4569
| 213 | 4.2314 | 2.4424 | 4.6762 | 4.2997 | 1.1005 | 16.7501
| 214 | 3.5142 | 2.4502 | 6.3928 | 3.5998 | 1.4768 | 17.4338
| 215 | 3.8751 | 3.1076 | 4.9307 | 4.6588 | 1.5994 | 18.1717
| 216 | 3.5299 | 2.9719 | 5.4034 | 3.5463 | 1.71 | 17.1615
| 217 | 4.5747 | 3.4567 | 5.4093 | 3.6368 | 1.582 | 18.6595
| 218 | 4.151 | 2.8088 | 5.9114 | 4.1743 | 1.6547 | 18.7003
| 219 | 4.0962 | 3.277 | 6.3392 | 3.846 | 1.8225 | 19.381
| 220 | 3.9597 | 2.7505 | 6.2645 | 3.9291 | 1.5953 | 18.499
| 221 | 3.8279 | 3.1123 | 7.2858 | 4.5203 | 1.5093 | 20.2557
| 222 | 3.8871 | 3.2553 | 4.545 | 3.6778 | 1.6745 | 17.0398
| 223 | 3.4476 | 3.0216 | 6.9347 | 4.429 | 1.3409 | 19.1738
| 224 | 4.2733 | 3.2909 | 4.5746 | 3.6844 | 1.7212 | 17.5444
| 225 | 3.9326 | 3.4738 | 5.4883 | 5.647 | 1.6121 | 20.1539
| 226 | 4.3235 | 2.9744 | 5.1288 | 4.7176 | 1.087 | 18.2314
| 227 | 4.2288 | 3.0888 | 6.1655 | 3.962 | 1.425 | 18.8701
| 228 | 3.2937 | 3.2025 | 5.3369 | 5.1768 | 1.7621 | 18.772
| 229 | 3.7144 | 3.4226 | 5.1787 | 4.3308 | 1.285 | 17.9315
| 230 | 3.8766 | 3.3692 | 4.308 | 4.1092 | 1.7868 | 17.4498
| 231 | 3.7806 | 2.6257 | 6.4516 | 4.9299 | 1.9171 | 19.7048
| 232 | 3.4699 | 2.861 | 5.0604 | 3.9768 | 1.1162 | 16.4843
| 233 | 3.9035 | 3.722 | 5.0861 | 4.633 | 1.5177 | 18.8622
| 234 | 4.4379 | 3.3447 | 5.8106 | 4.4317 | 1.8259 | 19.8508
| 235 | 3.6926 | 3.0839 | 6.4246 | 4.7737 | 1.4331 | 19.408
| 236 | 3.9747 | 3.0767 | 7.1781 | 3.2926 | 1.6448 | 19.1668
| 237 | 3.705 | 3.4097 | 6.0329 | 4.6786 | 1.1547 | 18.981
| 238 | 4.3133 | 3.0019 | 4.8239 | 3.4053 | 1.2642 | 16.8086
| 239 | 4.1699 | 3.4968 | 5.2873 | 3.7311 | 1.6454 | 18.3304
| 240 | 4.1121 | 3.2177 | 5.1426 | 3.7952 | 1.9143 | 18.1818
| 241 | 4.2467 | 2.9186 | 6.5566 | 5.0575 | 1.2181 | 19.9975
| 242 | 3.9988 | 3.5772 | 6.4766 | 4.2086 | 1.5442 | 19.8053
| 243 | 4.1882 | 2.7183 | 5.464 | 3.4161 | 1.7225 | 17.5091
| 244 | 4.3911 | 3.2451 | 5.3162 | 3.2335 | 1.2418 | 17.4277
| 245 | 4.2426 | 2.7165 | 4.7631 | 3.5909 | 1.1708 | 16.484
| 246 | 4.2547 | 3.3237 | 6.6946 | 3.7441 | 1.8845 | 19.9015
| 247 | 3.7383 | 2.855 | 5.3399 | 5.1313 | 1.862 | 18.9266
| 248 | 4.1563 | 3.6603 | 4.6551 | 3.3642 | 1.7941 | 17.6299
| 249 | 3.9125 | 3.0655 | 4.2425 | 4.6932 | 1.4576 | 17.3714
| 250 | 4.803 | 3.6339 | 4.6804 | 3.4221 | 1.6758 | 18.2152
| 251 | 4.5229 | 3.521 | 4.365 | 4.6835 | 1.5267 | 18.6191
| 252 | 4.2158 | 3.0477 | 5.3135 | 3.5837 | 1.6072 | 17.7679
| 253 | 3.5126 | 3.4882 | 5.7429 | 3.4845 | 1.5405 | 17.7686
| 254 | 4.5545 | 2.5181 | 5.2951 | 4.6012 | 1.7954 | 18.7642
| 255 | 4.6781 | 2.7229 | 5.0288 | 4.8271 | 1.6377 | 18.8947
| 256 | 4.1028 | 2.4756 | 4.7793 | 3.4642 | 1.401 | 16.223
| 257 | 3.9353 | 3.2728 | 6.1251 | 3.5252 | 1.3907 | 18.2492
| 258 | 3.4467 | 2.9175 | 5.1915 | 3.7751 | 1.5973 | 16.9281
| 259 | 4.6082 | 2.8833 | 6.2215 | 5.2093 | 1.2805 | 20.2028
| 260 | 3.8716 | 3.2577 | 4.9817 | 3.7452 | 1.6525 | 17.5086
| 261 | 4.322 | 2.6842 | 5.7739 | 3.1922 | 1.4662 | 17.4385
| 262 | 4.1719 | 2.3847 | 5.6416 | 3.4086 | 1.4834 | 17.0901
| 263 | 3.7601 | 3.2529 | 5.4311 | 4.2557 | 1.6025 | 18.3023
| 264 | 4.1051 | 2.8253 | 4.593 | 5.0404 | 1.6938 | 18.2576
| 265 | 3.228 | 3.3317 | 6.5381 | 3.8304 | 1.6816 | 18.6097
| 266 | 4.9728 | 3.8002 | 5.6242 | 4.8249 | 1.86 | 21.082
| 267 | 4.0041 | 3.2006 | 4.886 | 3.4382 | 1.3641 | 16.893
| 268 | 3.9932 | 2.6571 | 6.5521 | 3.2314 | 1.338 | 17.7718
| 269 | 4.8539 | 2.7973 | 5.4496 | 3.6552 | 1.4719 | 18.2278
| 270 | 4.2772 | 3.8202 | 4.7137 | 4.584 | 1.3629 | 18.758
| 271 | 3.3091 | 3.3661 | 6.0901 | 4.1366 | 1.4748 | 18.3767
| 272 | 3.714 | 2.4657 | 6.4839 | 4.7672 | 1.9211 | 19.3519
| 273 | 4.6501 | 2.9843 | 5.5796 | 4.9468 | 1.2458 | 19.4065
| 274 | 3.1033 | 2.5519 | 6.6403 | 4.0286 | 1.5233 | 17.8473
| 275 | 3.9894 | 2.6516 | 4.9782 | 3.0746 | 1.4314 | 16.1252
| 276 | 4.3764 | 3.5421 | 5.4922 | 3.6262 | 1.319 | 18.3559
| 277 | 4.2062 | 2.5555 | 6.5048 | 5.5419 | 1.3655 | 20.1738
| 278 | 4.0459 | 2.7521 | 5.8465 | 3.3949 | 1.4072 | 17.4466
| 279 | 3.8602 | 3.3494 | 7.2563 | 5.4409 | 1.8984 | 21.8053
| 280 | 3.8071 | 3.4596 | 6.8922 | 3.7147 | 1.7342 | 19.6078
| 281 | 4.582 | 2.2883 | 4.7078 | 3.6073 | 1.5512 | 16.7365
| 282 | 3.8799 | 3.4909 | 4.8 | 5.5743 | 1.5771 | 19.3221
| 283 | 4.5867 | 3.9135 | 5.2705 | 5.1733 | 1.5677 | 20.5117
| 284 | 4.4521 | 3.7875 | 6.9524 | 4.7867 | 1.5502 | 21.5288
| 285 | 4.2946 | 2.8224 | 5.3923 | 5.2218 | 1.57 | 19.3012
| 286 | 4.5311 | 2.9996 | 6.2543 | 3.8885 | 1.1793 | 18.8528
| 287 | 3.9409 | 2.8858 | 6.6577 | 4.366 | 1.6151 | 19.4655
| 288 | 4.633 | 2.9108 | 6.2949 | 4.5041 | 1.6289 | 19.9717
| 289 | 4.4433 | 2.994 | 5.3835 | 5.2505 | 1.6084 | 19.6797
| 290 | 4.3943 | 3.1717 | 7.0552 | 5.1041 | 1.2423 | 20.9675
| 291 | 3.4534 | 3.2858 | 5.7625 | 3.6623 | 1.2048 | 17.3688
| 292 | 4.0698 | 2.9405 | 4.9248 | 3.6611 | 1.7444 | 17.3405
| 293 | 3.4725 | 3.1841 | 6.1075 | 5.1218 | 1.1919 | 19.0778
| 294 | 4.4473 | 3.484 | 5.3282 | 3.9592 | 1.3748 | 18.5935
| 295 | 3.8109 | 3.4555 | 4.8445 | 4.9275 | 1.821 | 18.8595
| 296 | 3.9815 | 3.251 | 5.2035 | 4.7312 | 1.2731 | 18.4404
| 297 | 4.2408 | 2.5169 | 6.7203 | 4.6882 | 1.8642 | 20.0304
| 298 | 4.2481 | 2.5452 | 5.6122 | 4.6624 | 1.4683 | 18.5362
| 299 | 4.5286 | 2.3649 | 4.5885 | 4.8144 | 1.4281 | 17.7245
| 300 | 3.7995 | 3.0422 | 6.2809 | 4.1456 | 1.5291 | 18.7973
| 301 | 3.8697 | 2.6059 | 5.8348 | 4.6534 | 1.1079 | 18.0716
| 302 | 4.2149 | 2.9747 | 5.8195 | 4.2639 | 1.5479 | 18.8208
| 303 | 4.2191 | 2.3789 | 4.4872 | 5.3348 | 1.5227 | 17.9427
| 304 | 4.5095 | 2.363 | 4.4107 | 3.4128 | 1.5959 | 16.292
| 305 | 4.0638 | 3.1782 | 6.5425 | 4.197 | 1.5198 | 19.5014
| 306 | 4.1206 | 2.5962 | 5.159 | 3.5133 | 1.7368 | 17.1259
| 307 | 4.0915 | 3.1122 | 7.0184 | 5.0133 | 1.4505 | 20.6859
| 308 | 3.5875 | 3.216 | 5.6083 | 3.6294 | 1.2678 | 17.309
| 309 | 4.0876 | 3.0009 | 6.8279 | 4.1065 | 1.3101 | 19.3331
| 310 | 4.2987 | 3.5116 | 6.9757 | 3.5232 | 1.5925 | 19.9016
| 311 | 3.3099 | 3.3101 | 4.4546 | 4.6562 | 1.5564 | 17.2871
| 312 | 3.6188 | 3.4772 | 5.6177 | 4.402 | 1.0355 | 18.1511
| 313 | 4.6221 | 3.8651 | 5.5736 | 3.7365 | 1.655 | 19.4524
| 314 | 3.4325 | 3.5669 | 5.1052 | 5.4984 | 1.5087 | 19.1117
| 315 | 4.1893 | 3.1548 | 6.9698 | 3.2415 | 1.3776 | 18.933
| 316 | 4.684 | 3.5248 | 4.3131 | 5.0616 | 1.1664 | 18.7499
| 317 | 3.9843 | 2.8673 | 7.2634 | 5.3376 | 1.7138 | 21.1665
| 318 | 4.6567 | 3.4029 | 5.4346 | 5.8949 | 1.2321 | 20.6213
| 319 | 3.4248 | 3.5654 | 5.6581 | 3.9872 | 1.5264 | 18.162
| 320 | 3.4517 | 3.6906 | 5.6155 | 5.6142 | 1.7574 | 20.1294
| 321 | 4.2783 | 3.1855 | 4.8625 | 3.5811 | 1.9351 | 17.8425
| 322 | 4.0548 | 2.257 | 5.3686 | 3.8551 | 1.5242 | 17.0597
| 323 | 4.4122 | 2.2546 | 5.5338 | 3.8561 | 1.8166 | 17.8734
| 324 | 4.481 | 2.309 | 5.5653 | 4.9759 | 1.3538 | 18.6848
| 325 | 4.1918 | 3.3899 | 5.4598 | 3.6428 | 1.3489 | 18.0332
| 326 | 4.1818 | 2.9734 | 5.2789 | 4.2742 | 1.2792 | 17.9875
| 327 | 3.7252 | 3.1303 | 5.2319 | 3.3386 | 1.8406 | 17.2666
| 328 | 3.9027 | 3.4812 | 7.3889 | 4.0536 | 1.5796 | 20.406
| 329 | 4.6469 | 3.42 | 5.6465 | 4.6177 | 1.4551 | 19.7862
| 330 | 4.4843 | 3.329 | 5.3508 | 4.8453 | 1.6166 | 19.6261
| 331 | 3.8939 | 3.0776 | 7.8301 | 4.9952 | 1.58 | 21.3769
| 332 | 3.113 | 2.298 | 5.4425 | 3.9967 | 1.3857 | 16.2358
| 333 | 4.0015 | 2.8527 | 5.8569 | 5.0056 | 1.6927 | 19.4094
| 334 | 4.7353 | 2.8296 | 4.4504 | 4.8724 | 1.355 | 18.2427
| 335 | 4.7578 | 2.9916 | 6.2672 | 4.2029 | 1.6354 | 19.8548
| 336 | 4.0433 | 3.6167 | 7.7332 | 5.288 | 1.1765 | 21.8577
| 337 | 3.6417 | 3.1972 | 5.0826 | 3.7804 | 1.6384 | 17.3403
| 338 | 3.9972 | 3.0832 | 5.0387 | 3.3331 | 1.212 | 16.6641
| 339 | 3.8311 | 3.4652 | 6.7046 | 3.9666 | 1.5554 | 19.5228
| 340 | 3.9425 | 3.7674 | 4.3512 | 3.7896 | 1.4274 | 17.2781
| 341 | 4.3077 | 2.9467 | 5.2476 | 3.808 | 1.5498 | 17.8599
| 342 | 3.8199 | 2.6096 | 6.37 | 4.3624 | 1.5557 | 18.7176
| 343 | 3.4662 | 3.0896 | 6.7013 | 4.5893 | 1.7069 | 19.5534
| 344 | 3.8848 | 2.3482 | 6.0699 | 3.6089 | 1.6598 | 17.5716
| 345 | 4.3876 | 3.1389 | 7.224 | 3.2181 | 1.5751 | 19.5438
| 346 | 4.251 | 2.7072 | 4.4008 | 3.4974 | 1.1966 | 16.053
| 347 | 4.5994 | 3.0312 | 5.1457 | 3.7776 | 1.6031 | 18.1571
| 348 | 4.0766 | 3.0632 | 5.2588 | 3.6588 | 1.0273 | 17.0847
| 349 | 4.1012 | 3.1278 | 6.0398 | 3.7601 | 1.3894 | 18.4183
| 350 | 4.6651 | 2.7619 | 5.6689 | 3.4705 | 1.4339 | 18.0002
| 351 | 4.3526 | 2.4398 | 4.8894 | 4.3604 | 1.2626 | 17.3048
| 352 | 4.1244 | 3.3417 | 5.9722 | 3.5021 | 1.4429 | 18.3834
| 353 | 3.649 | 2.5197 | 5.396 | 4.8441 | 1.3728 | 17.7816
| 354 | 4.6282 | 3.0496 | 7.3782 | 3.4766 | 1.8437 | 20.3762
| 355 | 3.3147 | 3.7575 | 5.9336 | 3.5154 | 1.7162 | 18.2372
| 356 | 3.8762 | 3.2562 | 5.6052 | 3.3841 | 1.3034 | 17.425
| 357 | 4.5767 | 2.2525 | 5.17 | 3.8167 | 1.1849 | 17.0009
| 358 | 3.7467 | 2.7006 | 6.7498 | 4.4563 | 1.6106 | 19.2639
| 359 | 3.7118 | 2.4456 | 5.0504 | 3.3407 | 1.4544 | 16.003
| 360 | 4.3376 | 2.922 | 4.9437 | 4.7194 | 1.8308 | 18.7536
| 361 | 4.1176 | 2.8913 | 5.343 | 3.3263 | 1.75 | 17.4281
| 362 | 4.4072 | 3.3395 | 4.9728 | 4.3345 | 1.2896 | 18.3435
| 363 | 4.4236 | 2.992 | 6.679 | 3.4918 | 1.6687 | 19.2551
| 364 | 3.8495 | 2.5991 | 6.7414 | 5.659 | 1.3342 | 20.1831
| 365 | 4.8497 | 3.2805 | 6.5662 | 3.4585 | 1.4308 | 19.5857
| 366 | 4.468 | 2.0873 | 4.1095 | 3.6339 | 1.5192 | 15.8177
| 367 | 3.864 | 2.8497 | 4.4832 | 4.4681 | 1.7274 | 17.3924
| 368 | 4.4263 | 2.8269 | 7.0069 | 3.9064 | 1.719 | 19.8855
| 369 | 3.6638 | 2.9902 | 5.0793 | 3.7994 | 1.4195 | 16.9521
| 370 | 4.0027 | 3.5124 | 6.2145 | 4.6664 | 1.498 | 19.894
| 371 | 4.1805 | 2.9343 | 5.1185 | 3.8661 | 1.6656 | 17.7649
| 372 | 4.7997 | 2.7547 | 4.5208 | 3.5192 | 1.5595 | 17.1539
| 373 | 3.8415 | 3.2682 | 7.2333 | 5.0688 | 1.4362 | 20.848
| 374 | 4.6888 | 2.9637 | 5.8144 | 5.1571 | 1.6411 | 20.2652
| 375 | 4.0183 | 3.3586 | 5.7161 | 4.7381 | 1.4618 | 19.2929
| 376 | 3.8458 | 3.1234 | 7.3092 | 3.2588 | 1.4604 | 18.9977
| 377 | 3.8992 | 2.3867 | 6.7277 | 5.0665 | 1.307 | 19.387
| 378 | 4.5629 | 3.3723 | 4.8657 | 4.7338 | 1.6442 | 19.1788
| 379 | 3.6161 | 2.9962 | 6.1119 | 4.5106 | 1.7651 | 18.9998
| 380 | 3.6969 | 2.3058 | 4.9469 | 3.594 | 1.5407 | 16.0843
| 381 | 4.1187 | 2.8472 | 4.85 | 4.4841 | 1.1313 | 17.4313
| 382 | 3.8012 | 3.6791 | 6.7582 | 3.5703 | 1.4651 | 19.2738
| 383 | 3.8739 | 3.8327 | 5.2265 | 4.4461 | 1.6427 | 19.022
| 384 | 4.2889 | 3.3932 | 6.2486 | 4.1893 | 1.5615 | 19.6815
| 385 | 3.7073 | 3.3436 | 5.4229 | 3.5794 | 1.4716 | 17.5249
| 386 | 4.3541 | 3.2362 | 4.8371 | 4.4299 | 1.5393 | 18.3964
| 387 | 3.9565 | 3.223 | 6.3086 | 4.2252 | 1.4735 | 19.1868
| 388 | 3.7365 | 3.6273 | 6.3786 | 3.3718 | 1.6372 | 18.7514
| 389 | 4.0054 | 2.9543 | 7.0977 | 4.1614 | 1.4226 | 19.6414
| 390 | 3.7749 | 3.0382 | 5.8726 | 4.7975 | 1.5457 | 19.0288
| 391 | 4.0929 | 3.2864 | 4.3705 | 3.9733 | 1.6214 | 17.3446
| 392 | 4.1626 | 2.3155 | 5.8405 | 5.3808 | 1.4996 | 19.199
| 393 | 3.7166 | 3.245 | 5.9944 | 3.3162 | 1.2983 | 17.5704
| 394 | 4.3118 | 3.7495 | 4.5636 | 4.9097 | 1.7727 | 19.3073
| 395 | 4.1844 | 2.6704 | 5.1142 | 5.3083 | 1.6335 | 18.9107
| 396 | 3.7568 | 2.5907 | 6.2727 | 4.9627 | 1.8015 | 19.3843
| 397 | 3.8212 | 2.7031 | 4.7033 | 5.1827 | 1.6434 | 18.0537
| 398 | 4.0479 | 2.5326 | 4.5071 | 4.3657 | 1.5722 | 17.0257
| 399 | 4.2921 | 2.1968 | 5.2634 | 5.2816 | 1.5141 | 18.548
| 400 | 3.9446 | 3.6734 | 5.1489 | 3.7977 | 1.4965 | 18.0611
| 401 | 3.2004 | 3.2895 | 4.3915 | 3.8827 | 1.5374 | 16.3015
| 402 | 4.2803 | 3.1674 | 4.9514 | 4.7024 | 1.2237 | 18.3251
| 403 | 4.3388 | 2.8814 | 5.2275 | 4.0048 | 1.1618 | 17.6142
| 404 | 4.3184 | 3.0911 | 4.9361 | 4.0145 | 1.5005 | 17.8606
| 405 | 4.0003 | 2.8684 | 5.6823 | 4.9452 | 1.3464 | 18.8426
| 406 | 4.2977 | 2.8644 | 7.1355 | 3.5211 | 1.4925 | 19.3113
| 407 | 4.1374 | 3.1939 | 6.226 | 4.1873 | 1.7182 | 19.4628
| 408 | 3.93 | 2.0569 | 5.6878 | 4.1777 | 1.188 | 17.0403
| 409 | 4.0837 | 3.7375 | 5.0988 | 4.6056 | 1.4268 | 18.9526
| 410 | 4.14 | 3.142 | 5.9005 | 5.6292 | 1.5687 | 20.3805
| 411 | 4.0404 | 3.947 | 5.7833 | 4.3278 | 1.4723 | 19.5709
| 412 | 4.7256 | 2.8148 | 6.4718 | 4.1605 | 1.633 | 19.8057
| 413 | 3.4147 | 2.6793 | 4.8577 | 4.0423 | 1.4491 | 16.4431
| 414 | 3.2695 | 3.2094 | 4.5563 | 4.0809 | 1.6044 | 16.7205
| 415 | 3.7529 | 2.7334 | 6.2919 | 3.4573 | 1.7076 | 17.9431
| 416 | 4.1551 | 2.9785 | 5.9021 | 3.8357 | 1.623 | 18.4944
| 417 | 3.9457 | 2.8352 | 4.2893 | 3.1189 | 1.7133 | 15.9024
| 418 | 3.6239 | 2.828 | 5.9476 | 3.9089 | 1.8926 | 18.201
| 419 | 3.7783 | 2.7576 | 5.7391 | 5.0501 | 1.4377 | 18.7627
| 420 | 4.0035 | 2.5335 | 5.2639 | 3.3441 | 1.7824 | 16.9274
| 421 | 3.5019 | 3.0294 | 4.7943 | 3.8493 | 1.2435 | 16.4184
| 422 | 3.516 | 3.4364 | 7.0866 | 3.7618 | 1.3334 | 19.1342
| 423 | 3.135 | 3.7314 | 5.6778 | 4.7913 | 1.2946 | 18.6301
| 424 | 4.3821 | 2.9324 | 5.883 | 5.1197 | 1.5301 | 19.8474
| 425 | 4.3096 | 2.8307 | 6.9833 | 3.4381 | 1.3413 | 18.9031
| 426 | 3.5326 | 3.3186 | 5.077 | 3.7467 | 1.642 | 17.3169
| 427 | 4.2169 | 2.9083 | 5.7259 | 3.8391 | 1.768 | 18.4582
| 428 | 3.7631 | 2.8369 | 5.2205 | 4.4764 | 1.2462 | 17.5431
| 429 | 3.3572 | 2.43 | 6.3988 | 3.7189 | 1.6477 | 17.5526
| 430 | 4.0506 | 3.6642 | 5.7688 | 4.9847 | 1.6004 | 20.0687
| 431 | 3.7306 | 2.9883 | 4.2991 | 4.5358 | 1.4913 | 17.0452
| 432 | 4.5491 | 3.2282 | 4.1875 | 3.7119 | 1.3049 | 16.9816
| 433 | 3.5216 | 2.2757 | 6.4876 | 4.2835 | 1.543 | 18.1114
| 434 | 3.2784 | 2.5861 | 7.269 | 3.2559 | 1.2279 | 17.6173
| 435 | 4.3844 | 2.958 | 4.6303 | 5.876 | 1.2148 | 19.0634
| 436 | 3.7926 | 2.801 | 5.301 | 4.1353 | 1.4807 | 17.5106
| 437 | 3.9092 | 2.7669 | 4.5853 | 4.441 | 1.5326 | 17.235
| 438 | 3.6548 | 2.9672 | 5.3076 | 4.1765 | 1.2084 | 17.3144
| 439 | 3.7952 | 2.8623 | 4.7194 | 3.443 | 1.2499 | 16.0699
| 440 | 3.3664 | 2.9259 | 7.5391 | 4.2224 | 1.2722 | 19.326
| 441 | 3.7423 | 3.1144 | 7.4439 | 3.7874 | 1.6191 | 19.7071
| 442 | 4.1746 | 2.9422 | 5.2303 | 4.8077 | 1.79 | 18.9448
| 443 | 3.1993 | 3.284 | 5.4637 | 3.2526 | 1.5536 | 16.7532
| 444 | 3.6141 | 3.1571 | 6.5959 | 3.6573 | 1.6649 | 18.6893
| 445 | 3.375 | 2.5223 | 4.8435 | 3.1887 | 1.4426 | 15.3721
| 446 | 3.7013 | 2.8446 | 5.4076 | 3.1642 | 1.4393 | 16.5569
| 447 | 3.7978 | 3.8389 | 4.9385 | 4.0631 | 1.8465 | 18.4849
| 448 | 4.5705 | 2.877 | 6.4162 | 3.8372 | 1.4135 | 19.1143
| 449 | 4.1219 | 2.8322 | 6.5974 | 3.2715 | 1.128 | 17.951
| 450 | 4.2939 | 3.0275 | 5.074 | 5.781 | 1.657 | 19.8335
| 451 | 3.848 | 3.044 | 4.2812 | 3.5663 | 1.7476 | 16.4872
| 452 | 3.9618 | 2.3798 | 6.3207 | 3.9758 | 1.8502 | 18.4882
| 453 | 4.711 | 3.4262 | 5.1816 | 5.0277 | 1.3729 | 19.7195
| 454 | 3.3512 | 3.3539 | 6.1548 | 3.3795 | 1.314 | 17.5534
| 455 | 3.7498 | 2.4336 | 5.3489 | 3.3919 | 1.3862 | 16.3104
| 456 | 3.583 | 2.9096 | 6.6736 | 4.7643 | 1.2005 | 19.1309
| 457 | 3.3771 | 3.0963 | 6.3425 | 3.2009 | 1.3996 | 17.4165
| 458 | 4.1579 | 2.6729 | 7.4204 | 3.8948 | 1.3546 | 19.5006
| 459 | 3.9683 | 3.0179 | 6.36 | 3.6696 | 1.3153 | 18.3311
| 460 | 4.2491 | 2.6617 | 5.5539 | 4.9412 | 1.1991 | 18.605
| 461 | 4.365 | 3.6195 | 5.1932 | 3.5314 | 1.552 | 18.2611
| 462 | 3.4759 | 3.6483 | 4.6841 | 3.2985 | 1.7882 | 16.895
| 463 | 3.7494 | 3.1057 | 5.2818 | 4.058 | 1.299 | 17.4939
| 464 | 4.0897 | 2.8907 | 6.1866 | 3.3307 | 1.6729 | 18.1706
| 465 | 3.8262 | 3.1378 | 4.684 | 3.3689 | 1.5359 | 16.5528
| 466 | 3.5481 | 3.0822 | 4.2037 | 4.4099 | 1.346 | 16.5898
| 467 | 4.2136 | 3.1269 | 5.7503 | 4.1122 | 1.379 | 18.5821
| 468 | 4.2438 | 3.4757 | 6.5921 | 3.0525 | 1.483 | 18.8471
| 469 | 3.5359 | 2.8169 | 5.0098 | 4.097 | 1.4463 | 16.9058
| 470 | 3.9512 | 2.9006 | 6.6626 | 4.7897 | 1.2543 | 19.5583
| 471 | 3.6702 | 2.5412 | 7.8507 | 5.8174 | 1.8242 | 21.7038
| 472 | 3.5936 | 3.4353 | 5.0342 | 4.2384 | 1.499 | 17.8005
| 473 | 3.9476 | 3.6942 | 4.9929 | 4.0192 | 1.4614 | 18.1153
| 474 | 3.6083 | 3.3404 | 5.6543 | 4.1136 | 1.7667 | 18.4832
| 475 | 3.4405 | 2.4616 | 6.8779 | 3.5083 | 1.2259 | 17.5141
| 476 | 4.2716 | 2.7414 | 5.5013 | 5.079 | 1.4112 | 19.0046
| 477 | 4.0725 | 2.928 | 4.9096 | 3.8264 | 1.6858 | 17.4223
| 478 | 3.9536 | 3.0667 | 6.2083 | 4.6492 | 1.8933 | 19.771
| 479 | 3.415 | 3.3363 | 6.0438 | 3.9615 | 1.6471 | 18.4038
| 480 | 4.2352 | 2.9535 | 6.9928 | 4.9866 | 1.5223 | 20.6903
| 481 | 3.1213 | 3.08 | 5.4195 | 4.5851 | 1.6015 | 17.8074
| 482 | 4.3863 | 2.9447 | 6.1037 | 4.2491 | 1.4122 | 19.096
| 483 | 4.5129 | 3.3789 | 6.0767 | 5.61 | 1.6204 | 21.199
| 484 | 4.1499 | 2.5052 | 4.6399 | 3.5478 | 1.114 | 15.9568
| 485 | 4.8358 | 3.414 | 6.3819 | 4.4175 | 1.81 | 20.8593
| 486 | 4.2112 | 2.902 | 5.1403 | 3.8757 | 1.6407 | 17.7699
| 487 | 4.0397 | 2.1849 | 5.8678 | 4.7065 | 1.5694 | 18.3682
| 488 | 3.3947 | 2.7864 | 7.8056 | 5.0332 | 1.1906 | 20.2105
| 489 | 4.4905 | 3.4945 | 4.7383 | 4.9534 | 1.6872 | 19.3638
| 490 | 3.8347 | 2.4878 | 5.7236 | 4.8797 | 1.653 | 18.5788
| 491 | 4.3797 | 3.0926 | 4.6511 | 4.883 | 1.677 | 18.6833
| 492 | 3.3967 | 2.4968 | 5.6898 | 4.2144 | 1.7513 | 17.549
| 493 | 3.3689 | 2.3027 | 5.5871 | 4.118 | 1.5096 | 16.8863
| 494 | 4.4834 | 3.2479 | 6.8751 | 4.1586 | 1.253 | 20.0179
| 495 | 3.755 | 3.2276 | 7.5987 | 4.001 | 1.5287 | 20.111
| 496 | 3.9371 | 3.3996 | 7.5076 | 3.9209 | 1.3923 | 20.1576
| 497 | 4.198 | 3.3026 | 4.7502 | 4.2671 | 1.4076 | 17.9255
| 498 | 3.6871 | 2.6719 | 5.7319 | 4.6408 | 1.6324 | 18.364
| 499 | 3.9496 | 2.7268 | 6.7955 | 3.941 | 1.33 | 18.7429
| 500 | 3.2468 | 2.3906 | 5.6395 | 4.2532 | 1.7054 | 17.2354
| 501 | 4.1081 | 3.2943 | 4.5793 | 4.747 | 1.6159 | 18.3445
| 502 | 3.54 | 2.9522 | 7.0349 | 4.5269 | 1.5042 | 19.5582
| 503 | 4.1128 | 2.7094 | 5.288 | 3.6511 | 1.6831 | 17.4443
| 504 | 4.082 | 2.8762 | 6.1222 | 3.6876 | 1.1956 | 17.9636
| 505 | 4.708 | 2.0435 | 6.1873 | 5.4617 | 1.2282 | 19.6286
| 506 | 3.1563 | 2.9989 | 6.7351 | 3.5269 | 1.5568 | 17.974
| 507 | 4.6044 | 3.1335 | 4.8129 | 4.3046 | 1.2935 | 18.1489
| 508 | 4.0866 | 3.7702 | 6.0829 | 3.8045 | 1.8294 | 19.5737
| 509 | 4.5969 | 2.275 | 5.1555 | 3.8903 | 1.1643 | 17.082
| 510 | 3.0959 | 3.0971 | 6.4549 | 4.2722 | 1.3711 | 18.2913
| 511 | 3.429 | 3.0129 | 4.9211 | 5.2414 | 1.4221 | 18.0264
| 512 | 3.2614 | 2.5888 | 7.6089 | 3.3216 | 1.4031 | 18.1838
| 513 | 3.8384 | 2.3992 | 6.0515 | 4.2422 | 1.735 | 18.2663
| 514 | 3.6667 | 3.4655 | 4.8156 | 4.9665 | 1.6388 | 18.5531
| 515 | 3.7061 | 3.0937 | 4.8349 | 3.7088 | 1.659 | 17.0025
| 516 | 3.4925 | 3.358 | 5.5121 | 5.7132 | 1.3307 | 19.4065
| 517 | 3.2661 | 2.5583 | 5.8213 | 3.6752 | 1.3887 | 16.7097
| 518 | 3.6941 | 3.5313 | 6.0642 | 4.7083 | 1.3232 | 19.321
| 519 | 3.4206 | 2.2818 | 5.531 | 4.0733 | 1.3 | 16.6067
| 520 | 4.2372 | 3.1908 | 7.5619 | 4.8677 | 1.2053 | 21.0628
| 521 | 4.3779 | 2.5647 | 5.6293 | 3.5037 | 1.3687 | 17.4443
| 522 | 3.7914 | 2.4071 | 4.8908 | 3.3584 | 1.296 | 15.7438
| 523 | 4.8251 | 2.7763 | 5.9814 | 4.2619 | 1.4295 | 19.2743
| 524 | 4.4694 | 3.0171 | 5.5887 | 4.582 | 1.7506 | 19.4078
| 525 | 3.7393 | 3.3192 | 6.0067 | 4.6293 | 1.616 | 19.3105
| 526 | 3.5505 | 2.8027 | 6.3371 | 3.577 | 1.5549 | 17.8222
| 527 | 3.8131 | 2.4473 | 5.3387 | 4.9933 | 1.2831 | 17.8755
| 528 | 4.3048 | 2.874 | 5.2412 | 4.9246 | 1.3741 | 18.7187
| 529 | 3.6588 | 2.8421 | 4.4087 | 3.7241 | 1.4208 | 16.0545
| 530 | 4.1298 | 2.7959 | 6.5853 | 4.3806 | 1.7787 | 19.6703
| 531 | 3.56 | 2.5631 | 6.3557 | 3.9008 | 1.5424 | 17.922
| 532 | 3.6808 | 2.7385 | 4.4787 | 5.0885 | 1.7282 | 17.7148
| 533 | 4.5033 | 2.7648 | 4.5813 | 3.5331 | 1.6743 | 17.0567
| 534 | 4.2453 | 2.3585 | 5.7967 | 4.4378 | 1.4922 | 18.3305
| 535 | 3.7183 | 3.226 | 6.482 | 3.9342 | 1.591 | 18.9516
| 536 | 4.519 | 2.5305 | 4.9613 | 4.2192 | 1.7031 | 17.9331
| 537 | 3.9364 | 3.2885 | 7.028 | 4.233 | 1.6521 | 20.138
| 538 | 4.0242 | 3.5976 | 7.211 | 4.9579 | 1.5968 | 21.3875
| 539 | 3.5454 | 3.4246 | 5.8618 | 3.2259 | 1.316 | 17.3738
| 540 | 4.4646 | 2.7441 | 5.107 | 4.0339 | 1.3904 | 17.7399
| 541 | 4.8071 | 2.7552 | 6.4631 | 4.4542 | 1.6502 | 20.1299
| 542 | 4.0797 | 3.0691 | 6.1572 | 3.6011 | 1.723 | 18.6301
| 543 | 3.9341 | 3.0354 | 4.0299 | 5.3057 | 1.6802 | 17.9853
| 544 | 4.3578 | 3.1363 | 5.7791 | 5.2631 | 1.6511 | 20.1874
| 545 | 3.6353 | 2.2003 | 6.089 | 4.6064 | 1.41 | 17.941
| 546 | 3.8228 | 2.8188 | 7.0762 | 4.1823 | 1.3318 | 19.2319
| 547 | 3.5557 | 2.162 | 5.5401 | 3.183 | 1.5031 | 15.9438
| 548 | 3.6175 | 3.1645 | 5.2525 | 3.8477 | 1.0852 | 16.9674
| 549 | 3.372 | 2.619 | 6.3153 | 5.0296 | 1.4991 | 18.835
| 550 | 4.2215 | 2.931 | 6.0415 | 4.1308 | 1.4972 | 18.8221
| 551 | 3.5836 | 2.567 | 7.1082 | 5.4539 | 1.8424 | 20.5552
| 552 | 3.9216 | 3.1532 | 6.9238 | 3.101 | 1.7398 | 18.8394
| 553 | 4.4496 | 2.3457 | 5.3769 | 3.9276 | 1.7848 | 17.8846
| 554 | 4.0074 | 2.962 | 7.1162 | 4.1511 | 1.5937 | 19.8303
| 555 | 4.6817 | 3.2391 | 4.8072 | 4.9114 | 1.5204 | 19.1599
| 556 | 3.4392 | 2.7682 | 4.9014 | 3.6531 | 1.4357 | 16.1976
| 557 | 4.0298 | 2.8727 | 6.8041 | 3.4292 | 1.6047 | 18.7406
| 558 | 4.3465 | 3.6339 | 6.9984 | 4.8982 | 1.3633 | 21.2402
| 559 | 3.9729 | 3.1698 | 5.9793 | 5.4177 | 1.5889 | 20.1286
| 560 | 4.6347 | 3.4488 | 7.2984 | 4.3439 | 1.5127 | 21.2385
| 561 | 3.6318 | 2.7696 | 6.2455 | 3.6405 | 1.4059 | 17.6933
| 562 | 3.6744 | 3.1812 | 6.027 | 4.5937 | 1.7919 | 19.2683
| 563 | 4.5881 | 2.8484 | 6.0792 | 3.4244 | 1.4414 | 18.3815
| 564 | 4.0095 | 3.3146 | 5.9601 | 4.1835 | 1.8054 | 19.2731
| 565 | 4.1606 | 3.1589 | 5.1944 | 4.7588 | 1.3841 | 18.6569
| 566 | 4.1283 | 2.8239 | 5.7043 | 3.4062 | 1.7268 | 17.7895
| 567 | 4.02 | 3.1885 | 5.9484 | 5.3706 | 1.5076 | 20.035
| 568 | 4.5106 | 2.5751 | 5.9984 | 3.2193 | 1.7254 | 18.0288
| 569 | 3.2415 | 3.657 | 4.7653 | 3.8018 | 1.5374 | 17.0031
| 570 | 3.722 | 2.7479 | 5.4671 | 5.4729 | 1.4152 | 18.8251
| 571 | 4.4361 | 2.7419 | 4.9898 | 5.693 | 1.3389 | 19.1996
| 572 | 4.0252 | 3.622 | 5.9511 | 3.8255 | 1.4245 | 18.8482
| 573 | 3.9521 | 3.0697 | 5.6529 | 5.1627 | 1.3812 | 19.2186
| 574 | 4.2044 | 3.4317 | 6.8475 | 3.638 | 1.4856 | 19.6072
| 575 | 3.4114 | 2.3297 | 6.0528 | 3.8805 | 1.512 | 17.1863
| 576 | 3.8658 | 2.6821 | 5.8038 | 4.1479 | 1.4065 | 17.9061
| 577 | 3.689 | 3.134 | 5.6968 | 3.3898 | 1.4444 | 17.3541
| 578 | 3.9437 | 2.6886 | 4.7873 | 3.968 | 1.3178 | 16.7054
| 579 | 3.9875 | 3.1047 | 7.3424 | 5.3905 | 1.1409 | 20.9659
| 580 | 4.5343 | 2.9068 | 4.5697 | 5.5133 | 1.4898 | 19.0139
| 581 | 4.0784 | 3.6519 | 5.9237 | 4.0254 | 1.4106 | 19.09
| 582 | 3.7696 | 2.7136 | 6.3966 | 4.3467 | 1.4499 | 18.6765
| 583 | 3.9737 | 2.8718 | 6.4425 | 4.1008 | 1.5218 | 18.9106
| 584 | 3.7889 | 3.2116 | 5.6218 | 5.7355 | 1.2325 | 19.5903
| 585 | 4.7514 | 2.3271 | 5.5578 | 4.236 | 1.44 | 18.3122
| 586 | 4.0124 | 3.1866 | 5.0056 | 5.6421 | 1.7609 | 19.6076
| 587 | 4.3165 | 3.2786 | 4.9648 | 3.7256 | 1.4813 | 17.7668
| 588 | 4.3482 | 2.9248 | 6.6126 | 3.383 | 1.5869 | 18.8555
| 589 | 3.5689 | 3.1625 | 6.7135 | 4.1989 | 1.505 | 19.1488
| 590 | 4.3103 | 3.7133 | 5.332 | 4.9356 | 1.3058 | 19.597
| 591 | 3.6307 | 2.4197 | 6.7451 | 3.586 | 1.6978 | 18.0793
| 592 | 4.4945 | 3.746 | 4.9203 | 5.1534 | 1.3075 | 19.6217
| 593 | 3.9927 | 3.5305 | 4.8842 | 3.2601 | 1.2793 | 16.9468
| 594 | 3.8588 | 2.3201 | 6.1743 | 5.2312 | 1.5708 | 19.1552
| 595 | 3.8196 | 3.2701 | 6.0039 | 4.1299 | 1.6258 | 18.8493
| 596 | 4.7895 | 2.9493 | 5.3707 | 4.691 | 1.4958 | 19.2963
| 597 | 3.4195 | 3.714 | 6.3307 | 3.9458 | 1.5511 | 18.9611
| 598 | 3.8159 | 2.7246 | 5.0034 | 3.7427 | 1.3025 | 16.589
| 599 | 3.9575 | 3.2189 | 4.7513 | 4.0128 | 1.6678 | 17.6084
| 600 | 4.3013 | 2.4834 | 5.4275 | 4.294 | 1.426 | 17.9321
| 601 | 4.3806 | 2.6126 | 4.615 | 3.9699 | 1.8686 | 17.4467
| 602 | 3.9146 | 2.4565 | 5.6808 | 3.5719 | 1.771 | 17.3948
| 603 | 3.6008 | 2.1114 | 6.1713 | 3.308 | 1.3983 | 16.5898
| 604 | 3.6818 | 3.4704 | 4.8738 | 4.6094 | 1.7243 | 18.3597
| 605 | 4.2083 | 3.4295 | 4.7457 | 3.5348 | 1.4385 | 17.3568
| 606 | 3.599 | 2.8941 | 4.7367 | 4.0507 | 1.5836 | 16.8642
| 607 | 3.606 | 2.7399 | 4.5679 | 3.8123 | 1.5317 | 16.2578
| 608 | 4.2577 | 2.9646 | 5.1883 | 3.7411 | 1.8381 | 17.9898
| 609 | 4.4009 | 3.1327 | 4.1913 | 3.6811 | 1.5849 | 16.991
| 610 | 3.3612 | 2.8786 | 5.4546 | 3.8534 | 1.7374 | 17.2852
| 611 | 4.3957 | 2.8929 | 6.0472 | 3.5619 | 1.5596 | 18.4573
| 612 | 4.2263 | 2.6861 | 4.342 | 4.0427 | 1.4938 | 16.7908
| 613 | 3.7882 | 2.8542 | 7.2467 | 4.0893 | 1.5416 | 19.52
| 614 | 4.3247 | 3.1155 | 5.6315 | 4.6852 | 1.0579 | 18.8149
| 615 | 3.9808 | 2.3962 | 5.5234 | 5.0435 | 1.4932 | 18.437
| 616 | 3.8289 | 2.3692 | 4.5054 | 3.912 | 1.7438 | 16.3592
| 617 | 4.3062 | 2.7664 | 5.8031 | 5.3183 | 1.4693 | 19.6632
| 618 | 4.2534 | 3.0268 | 4.9134 | 3.4502 | 1.7833 | 17.4272
| 619 | 4.1481 | 3.4052 | 4.0863 | 4.1427 | 1.8559 | 17.6381
| 620 | 4.1737 | 3.3753 | 6.62 | 3.7722 | 1.5733 | 19.5145
| 621 | 3.6437 | 3.6252 | 5.7221 | 4.1721 | 1.1885 | 18.3517
| 622 | 3.8987 | 3.0198 | 4.4611 | 3.9472 | 1.4345 | 16.7612
| 623 | 3.4788 | 3.1724 | 5.568 | 3.6107 | 1.4874 | 17.3172
| 624 | 3.6398 | 3.3872 | 4.1679 | 4.1907 | 1.2096 | 16.5951
| 625 | 3.4739 | 2.2488 | 5.8301 | 4.1933 | 1.4125 | 17.1586
| 626 | 3.8884 | 2.8803 | 4.6691 | 4.4993 | 1.3447 | 17.2818
| 627 | 4.6918 | 3.0721 | 6.5103 | 3.7845 | 1.4779 | 19.5366
| 628 | 3.0734 | 3.4185 | 6.9858 | 3.3953 | 1.3937 | 18.2667
| 629 | 4.2806 | 3.72 | 4.8257 | 4.3907 | 1.5143 | 18.7313
| 630 | 3.7715 | 2.9597 | 4.3616 | 3.8513 | 1.3257 | 16.2698
| 631 | 4.7429 | 3.0485 | 4.8682 | 4.4005 | 1.6316 | 18.6917
| 632 | 4.233 | 2.6306 | 5.4838 | 5.2787 | 1.9006 | 19.5267
| 633 | 4.4993 | 2.7791 | 4.9709 | 3.8215 | 1.3765 | 17.4472
| 634 | 4.0751 | 2.8746 | 5.894 | 4.2357 | 1.4523 | 18.5317
| 635 | 4.1758 | 3.169 | 7.1951 | 3.5367 | 1.7102 | 19.7868
| 636 | 4.2225 | 2.9707 | 4.7922 | 3.4195 | 1.5337 | 16.9385
| 637 | 3.8902 | 3.9005 | 4.3964 | 3.4353 | 1.7165 | 17.339
| 638 | 4.2826 | 3.6096 | 6.8341 | 4.7533 | 1.6175 | 21.0971
| 639 | 4.3157 | 2.1769 | 7.7794 | 3.11 | 1.4626 | 18.8447
| 640 | 4.022 | 3.2083 | 6.0144 | 3.1411 | 1.3247 | 17.7105
| 641 | 4.1677 | 3.488 | 5.0147 | 3.4406 | 1.2573 | 17.3683
| 642 | 4.6772 | 3.0611 | 5.9388 | 4.614 | 1.6632 | 19.9543
| 643 | 4.8147 | 3.0459 | 5.0468 | 3.8782 | 1.4633 | 18.2489
| 644 | 3.8329 | 2.85 | 6.0218 | 3.5079 | 1.7739 | 17.9864
| 645 | 3.8164 | 3.3857 | 6.5242 | 5.4374 | 1.3356 | 20.4993
| 646 | 4.8888 | 3.5394 | 7.6284 | 4.4972 | 1.1417 | 21.6956
| 647 | 3.6282 | 2.9431 | 5.378 | 4.0086 | 1.2257 | 17.1835
| 648 | 4.1938 | 2.6668 | 5.4521 | 3.8792 | 1.5777 | 17.7697
| 649 | 3.8537 | 3.2434 | 5.4257 | 3.0072 | 1.6925 | 17.2225
| 650 | 4.6701 | 2.7025 | 5.0918 | 4.5495 | 1.333 | 18.3469
| 651 | 3.6562 | 3.2329 | 5.8661 | 3.3133 | 1.3782 | 17.4467
| 652 | 3.4446 | 3.2472 | 5.2556 | 5.4843 | 1.8001 | 19.2319
| 653 | 4.1465 | 2.6915 | 5.9889 | 4.3486 | 1.6794 | 18.8549
| 654 | 4.1108 | 3.1917 | 5.2028 | 4.0348 | 1.4305 | 17.9707
| 655 | 3.7975 | 3.183 | 5.6662 | 3.1274 | 1.5281 | 17.3021
| 656 | 4.2666 | 2.2055 | 5.1661 | 5.4304 | 1.704 | 18.7726
| 657 | 4.9392 | 2.4438 | 5.5368 | 5.1954 | 1.2998 | 19.415
| 658 | 3.9241 | 2.7838 | 4.3547 | 3.9245 | 1.7629 | 16.7501
| 659 | 3.7653 | 3.5712 | 4.6594 | 4.241 | 1.0944 | 17.3314
| 660 | 4.4653 | 2.65 | 5.2111 | 5.0097 | 1.676 | 19.0122
| 661 | 3.911 | 2.7303 | 5.4144 | 5.5514 | 1.6244 | 19.2314
| 662 | 4.052 | 3.3811 | 6.9616 | 4.0711 | 1.6135 | 20.0794
| 663 | 3.3356 | 2.5243 | 4.3847 | 5.5762 | 1.4046 | 17.2254
| 664 | 3.7547 | 3.1745 | 7.1916 | 3.5933 | 1.6969 | 19.411
| 665 | 3.2999 | 3.0876 | 5.1682 | 4.6459 | 1.4001 | 17.6017
| 666 | 4.3626 | 2.7069 | 5.1991 | 3.7832 | 1.5573 | 17.6091
| 667 | 3.1922 | 3.5172 | 6.2384 | 3.4863 | 1.3807 | 17.8147
| 668 | 3.9016 | 3.0915 | 6.6052 | 5.2746 | 1.0834 | 19.9563
| 669 | 3.703 | 3.311 | 5.223 | 3.4723 | 1.3951 | 17.1045
| 670 | 3.609 | 3.6302 | 4.5429 | 4.7263 | 1.4421 | 17.9504
| 671 | 4.4309 | 3.024 | 5.1874 | 3.4117 | 1.4981 | 17.5519
| 672 | 3.8511 | 3.0866 | 4.5247 | 3.1391 | 1.5682 | 16.1697
| 673 | 3.405 | 2.6226 | 5.5167 | 5.2459 | 1.3433 | 18.1335
| 674 | 4.296 | 2.9893 | 4.5488 | 4.4123 | 1.2579 | 17.5042
| 675 | 3.2164 | 3.2634 | 6.134 | 4.8903 | 1.3269 | 18.831
| 676 | 4.0288 | 2.3348 | 4.4347 | 3.7337 | 1.7804 | 16.3124
| 677 | 4.0889 | 3.0712 | 7.0955 | 3.7025 | 1.2137 | 19.1718
| 678 | 4.0951 | 2.5152 | 5.5029 | 4.7705 | 1.1553 | 18.0389
| 679 | 3.8041 | 2.636 | 6.3271 | 4.5571 | 1.4581 | 18.7823
| 680 | 3.61 | 2.6478 | 5.9269 | 3.2968 | 1.6396 | 17.1209
| 681 | 4.223 | 3.7277 | 5.3649 | 3.5217 | 1.5976 | 18.4349
| 682 | 4.2692 | 3.3294 | 4.8331 | 4.2526 | 1.3948 | 18.079
| 683 | 4.8629 | 3.5451 | 4.5126 | 4.3399 | 1.7665 | 19.027
| 684 | 4.6953 | 2.9464 | 7.5233 | 4.1192 | 1.6826 | 20.9668
| 685 | 3.2316 | 2.143 | 7.319 | 4.7007 | 1.4901 | 18.8844
| 686 | 4.0562 | 2.7449 | 6.0558 | 4.8062 | 1.8064 | 19.4695
| 687 | 3.6756 | 3.0161 | 5.917 | 3.7756 | 1.1325 | 17.5167
| 688 | 4.3563 | 2.8151 | 4.3892 | 3.5572 | 1.5916 | 16.7093
| 689 | 4.1044 | 3.0299 | 4.8554 | 3.2784 | 1.3179 | 16.586
| 690 | 4.4164 | 2.5601 | 6.5306 | 3.511 | 1.5639 | 18.582
| 691 | 4.4102 | 3.4726 | 4.4671 | 3.951 | 1.7422 | 18.0432
| 692 | 4.3516 | 3.2193 | 6.7818 | 3.306 | 1.7402 | 19.399
| 693 | 4.721 | 2.9399 | 6.3522 | 3.9217 | 1.7751 | 19.71
| 694 | 3.7023 | 2.2691 | 6.1306 | 3.5979 | 1.235 | 16.9348
| 695 | 4.0151 | 2.3397 | 5.7798 | 3.9171 | 1.3501 | 17.4018
| 696 | 4.3296 | 2.897 | 5.2349 | 3.5583 | 1.2536 | 17.2734
| 697 | 3.6733 | 3.005 | 6.3844 | 5.5317 | 1.3703 | 19.9647
| 698 | 3.398 | 2.3318 | 6.0118 | 5.1679 | 1.3286 | 18.238
| 699 | 3.1458 | 2.8118 | 4.9832 | 3.9554 | 1.3758 | 16.2719
| 700 | 4.4421 | 2.9333 | 6.4373 | 3.2667 | 1.6617 | 18.7411
| 701 | 3.8055 | 2.6379 | 6.896 | 3.6227 | 1.5528 | 18.5149
| 702 | 3.7108 | 3.3339 | 5.7524 | 3.7387 | 1.2668 | 17.8026
| 703 | 4.2338 | 2.9867 | 5.8919 | 3.5434 | 1.5065 | 18.1623
| 704 | 3.6659 | 2.6454 | 5.644 | 4.7844 | 1.4787 | 18.2184
| 705 | 3.2136 | 2.4161 | 5.3243 | 4.3234 | 1.6302 | 16.9076
| 706 | 4.3316 | 3.0578 | 6.4038 | 3.4304 | 1.4394 | 18.663
| 707 | 4.8761 | 2.697 | 5.5632 | 4.7508 | 1.6364 | 19.5235
| 708 | 4.0162 | 3.0645 | 6.2007 | 3.7914 | 1.7524 | 18.8253
| 709 | 3.7477 | 3.5636 | 6.4476 | 4.4585 | 1.4775 | 19.6949
| 710 | 4.6194 | 2.2109 | 4.9658 | 4.577 | 1.8965 | 18.2696
| 711 | 4.5426 | 3.176 | 5.7914 | 3.5009 | 1.7588 | 18.7697
| 712 | 4.1527 | 2.705 | 4.2714 | 4.0224 | 1.3472 | 16.4988
| 713 | 3.4799 | 2.5708 | 4.9999 | 4.3708 | 1.5811 | 17.0026
| 714 | 3.8632 | 2.7899 | 4.7608 | 4.076 | 1.1442 | 16.6341
| 715 | 3.5415 | 3.8267 | 4.883 | 3.2797 | 1.9129 | 17.4439
| 716 | 4.5559 | 3.3066 | 5.3986 | 4.216 | 1.4096 | 18.8867
| 717 | 3.7285 | 3.6381 | 6.1424 | 5.7455 | 1.5105 | 20.765
| 718 | 3.1776 | 3.3618 | 5.1617 | 3.5612 | 1.3596 | 16.622
| 719 | 4.0944 | 2.9298 | 5.1445 | 3.209 | 1.6118 | 16.9895
| 720 | 3.663 | 3.3217 | 5.9068 | 3.5629 | 1.5871 | 18.0415
| 721 | 4.1621 | 2.4274 | 4.5369 | 3.6354 | 1.402 | 16.1639
| 722 | 3.9273 | 2.841 | 5.6985 | 4.1216 | 1.3586 | 17.9469
| 723 | 4.4978 | 2.681 | 6.1951 | 4.8856 | 1.4819 | 19.7414
| 724 | 3.3467 | 3.2135 | 4.96 | 3.8974 | 1.8726 | 17.2901
| 725 | 3.4632 | 3.1815 | 4.4468 | 4.3269 | 1.6267 | 17.045
| 726 | 4.0543 | 2.6237 | 5.8172 | 4.0318 | 1.3755 | 17.9025
| 727 | 3.5191 | 3.3231 | 4.2655 | 3.9155 | 1.2708 | 16.294
| 728 | 4.1905 | 3.4591 | 6.6871 | 3.4266 | 1.3085 | 19.0718
| 729 | 4.2115 | 3.6063 | 5.8756 | 4.5432 | 1.695 | 19.9315
| 730 | 3.8977 | 2.6749 | 6.2533 | 3.4189 | 1.4456 | 17.6904
| 731 | 3.5529 | 3.1 | 6.4435 | 3.4804 | 1.5621 | 18.1389
| 732 | 3.9998 | 3.2737 | 6.2757 | 4.572 | 1.8186 | 19.9397
| 733 | 4.0468 | 2.9152 | 5.7309 | 3.8922 | 1.6705 | 18.2557
| 734 | 3.4377 | 2.1549 | 4.2232 | 4.9156 | 1.4435 | 16.1749
| 735 | 4.2031 | 3.6022 | 6.9487 | 3.9024 | 1.2905 | 19.9469
| 736 | 3.4043 | 2.7987 | 4.9559 | 4.4056 | 1.6113 | 17.1759
| 737 | 3.1675 | 3.0979 | 6.5143 | 4.2069 | 1.4785 | 18.4651
| 738 | 4.6522 | 2.9801 | 4.534 | 4.9999 | 1.5448 | 18.7111
| 739 | 4.1439 | 2.9272 | 7.6668 | 3.9827 | 1.5388 | 20.2593
| 740 | 4.1383 | 2.895 | 6.5007 | 3.7583 | 1.832 | 19.1243
| 741 | 4.2306 | 3.6664 | 5.3478 | 4.4779 | 1.663 | 19.3857
| 742 | 4.3991 | 3.3565 | 4.3377 | 4.0076 | 1.5628 | 17.6637
| 743 | 3.454 | 2.9048 | 5.8536 | 3.2046 | 1.2813 | 16.6984
| 744 | 4.4589 | 3.1082 | 4.7173 | 4.5651 | 1.5331 | 18.3826
| 745 | 4.3356 | 2.7772 | 6.4933 | 3.7004 | 1.6951 | 19.0016
| 746 | 4.2657 | 2.4812 | 5.7387 | 4.0848 | 1.5763 | 18.1466
| 747 | 4.3403 | 2.9212 | 6.5432 | 3.5394 | 1.3676 | 18.7116
| 748 | 4.2189 | 3.2817 | 7.1279 | 4.4447 | 1.2632 | 20.3365
| 749 | 4.1159 | 2.618 | 6.2121 | 5.507 | 1.8176 | 20.2706
| 750 | 3.6461 | 2.6905 | 5.9638 | 3.8132 | 1.4869 | 17.6005
| 751 | 3.2602 | 2.9163 | 5.6651 | 4.3882 | 1.2747 | 17.5046
| 752 | 4.4577 | 3.1434 | 6.6234 | 5.0381 | 1.2598 | 20.5224
| 753 | 3.5211 | 3.4794 | 5.9291 | 4.1415 | 1.4678 | 18.5389
| 754 | 4.2561 | 3.1519 | 5.3811 | 4.514 | 1.4646 | 18.7677
| 755 | 3.6717 | 3.2316 | 5.0429 | 3.4993 | 1.2395 | 16.6849
| 756 | 4.7012 | 3.8115 | 6.302 | 3.8584 | 1.1735 | 19.8465
| 757 | 3.4889 | 3.2642 | 4.879 | 5.4769 | 1.5295 | 18.6385
| 758 | 4.0846 | 2.6879 | 6.1618 | 3.3546 | 1.7115 | 18.0004
| 759 | 4.4738 | 2.6937 | 6.1002 | 3.5517 | 1.4889 | 18.3083
| 760 | 4.3606 | 3.1477 | 4.6036 | 3.9097 | 1.5992 | 17.6209
| 761 | 3.652 | 2.9835 | 6.9582 | 5.2684 | 1.7708 | 20.6329
| 762 | 4.455 | 3.0051 | 5.2126 | 4.4488 | 1.689 | 18.8104
| 763 | 3.5585 | 3.3727 | 5.561 | 4.1038 | 1.5782 | 18.1742
| 764 | 3.5666 | 3.4986 | 6.4238 | 3.2238 | 1.1106 | 17.8234
| 765 | 3.3036 | 2.51 | 5.7117 | 4.3026 | 1.8547 | 17.6826
| 766 | 3.6827 | 2.9287 | 6.6449 | 5.1859 | 1.5609 | 20.0031
| 767 | 3.922 | 3.454 | 5.8271 | 5.0179 | 1.5754 | 19.7963
| 768 | 4.2094 | 2.9771 | 6.2307 | 4.622 | 1.335 | 19.3741
| 769 | 3.8096 | 2.9231 | 4.8395 | 4.65 | 1.6673 | 17.8895
| 770 | 4.4403 | 3.2251 | 4.6172 | 4.2863 | 1.5026 | 18.0714
| 771 | 3.8412 | 2.8198 | 4.7272 | 3.7205 | 1.5523 | 16.661
| 772 | 4.3592 | 2.5039 | 6.8104 | 3.7378 | 1.1935 | 18.6047
| 773 | 3.7609 | 3.0066 | 5.1513 | 5.1086 | 1.8227 | 18.85
| 774 | 3.8254 | 2.9974 | 5.8806 | 5.8431 | 1.097 | 19.6435
| 775 | 4.1453 | 2.4527 | 4.8281 | 3.4313 | 1.7043 | 16.5617
| 776 | 4.7851 | 2.2396 | 5.4743 | 3.9796 | 1.6484 | 18.1271
| 777 | 4.237 | 2.3526 | 5.4458 | 5.3507 | 1.7928 | 19.179
| 778 | 3.7846 | 3.1219 | 5.163 | 4.056 | 1.4762 | 17.6017
| 779 | 3.3833 | 2.7922 | 4.5542 | 4.837 | 1.7011 | 17.2678
| 780 | 4.4188 | 3.1422 | 6.5271 | 3.449 | 1.3315 | 18.8686
| 781 | 3.5792 | 2.6662 | 5.1846 | 3.506 | 1.6458 | 16.5819
| 782 | 4.9248 | 3.1013 | 4.8218 | 3.7566 | 1.8128 | 18.4174
| 783 | 3.3883 | 2.9629 | 6.4107 | 3.489 | 1.3602 | 17.6112
| 784 | 4.2009 | 2.8286 | 4.8699 | 4.3853 | 1.2953 | 17.58
| 785 | 3.2807 | 3.2621 | 4.6105 | 4.0665 | 1.7902 | 17.01
| 786 | 3.5777 | 3.2375 | 6.237 | 4.1703 | 1.3224 | 18.5449
| 787 | 3.2365 | 2.7934 | 5.1564 | 3.8597 | 1.6909 | 16.7368
| 788 | 4.7797 | 2.8062 | 5.9404 | 5.5625 | 1.6808 | 20.7696
| 789 | 3.8507 | 3.4509 | 5.4109 | 4.9032 | 1.7598 | 19.3754
| 790 | 3.3849 | 3.557 | 4.5988 | 3.0632 | 1.9236 | 16.5274
| 791 | 4.1587 | 2.9858 | 6.8363 | 4.4925 | 1.3059 | 19.7792
| 792 | 4.253 | 3.506 | 6.1472 | 3.2143 | 1.4668 | 18.5874
| 793 | 4.0272 | 2.4732 | 6.9129 | 4.1805 | 1.7124 | 19.3062
| 794 | 3.5432 | 3.7096 | 5.242 | 3.1799 | 1.7562 | 17.4309
| 795 | 4.4357 | 3.5708 | 5.0761 | 4.297 | 1.4468 | 18.8264
| 796 | 3.7523 | 3.5892 | 4.7741 | 3.6133 | 1.5765 | 17.3054
| 797 | 3.6363 | 3.4468 | 7.3604 | 3.2856 | 1.1369 | 18.866
| 798 | 3.9819 | 2.5376 | 5.6863 | 4.047 | 1.8334 | 18.0862
| 799 | 3.942 | 2.2355 | 6.4066 | 5.3659 | 1.2372 | 19.1872
| 800 | 4.012 | 2.5773 | 6.2696 | 4.5992 | 1.2484 | 18.7066
| 801 | 3.9776 | 2.9703 | 4.8471 | 4.7399 | 1.4445 | 17.9794
| 802 | 3.5758 | 3.5373 | 5.2534 | 4.5698 | 1.7551 | 18.6915
| 803 | 4.7384 | 3.8665 | 6.2982 | 3.346 | 1.1836 | 19.4327
| 804 | 4.5391 | 3.5598 | 4.4941 | 3.8636 | 1.414 | 17.8705
| 805 | 4.5923 | 2.7185 | 5.2182 | 3.3022 | 1.6614 | 17.4927
| 806 | 4.6022 | 2.9875 | 7.026 | 4.2906 | 1.135 | 20.0413
| 807 | 3.9184 | 3.0146 | 5.0707 | 4.4204 | 1.7387 | 18.1628
| 808 | 3.8856 | 2.7729 | 5.3982 | 3.3501 | 1.4214 | 16.8282
| 809 | 3.5734 | 3.5499 | 7.4147 | 4.3328 | 1.6277 | 20.4986
| 810 | 4.3642 | 3.3077 | 5.584 | 4.8554 | 1.6583 | 19.7697
| 811 | 4.1411 | 3.3941 | 5.2142 | 5.6808 | 1.5355 | 19.9658
| 812 | 4.5357 | 2.5509 | 6.1906 | 4.194 | 1.5471 | 19.0183
| 813 | 3.8174 | 2.5844 | 5.2457 | 4.0391 | 1.7308 | 17.4174
| 814 | 4.1717 | 3.4039 | 5.2486 | 3.8061 | 1.099 | 17.7293
| 815 | 3.3397 | 3.0467 | 6.3617 | 3.5677 | 1.6695 | 17.9853
| 816 | 4.1956 | 2.4076 | 4.8305 | 3.9986 | 1.4595 | 16.8917
| 817 | 4.2243 | 3.177 | 5.3178 | 4.0206 | 1.2557 | 17.9954
| 818 | 3.9626 | 2.629 | 7.6954 | 4.5514 | 1.2474 | 20.0858
| 819 | 3.8926 | 3.5193 | 6.1379 | 5.4212 | 1.1242 | 20.0953
| 820 | 3.7338 | 2.5477 | 4.6734 | 3.4828 | 1.6862 | 16.124
| 821 | 4.2698 | 2.6113 | 4.5008 | 3.2638 | 1.5932 | 16.2389
| 822 | 3.8676 | 2.6541 | 4.9737 | 4.2013 | 1.6788 | 17.3754
| 823 | 3.5641 | 2.7293 | 4.9445 | 5.1997 | 1.5025 | 17.9401
| 824 | 4.4924 | 3.2149 | 4.9857 | 5.2561 | 1.5397 | 19.4888
| 825 | 3.8571 | 3.3633 | 5.4705 | 4.0608 | 1.9482 | 18.7
| 826 | 4.197 | 2.4259 | 4.9109 | 5.2933 | 1.4538 | 18.2809
| 827 | 4.3745 | 3.3826 | 5.4398 | 3.4959 | 1.6491 | 18.3419
| 828 | 3.9851 | 3.5287 | 6.1532 | 4.541 | 1.4142 | 19.6222
| 829 | 4.507 | 2.5797 | 7.1693 | 3.6423 | 1.6602 | 19.5585
| 830 | 4.1277 | 3.3657 | 4.6271 | 3.2699 | 1.0617 | 16.4521
| 831 | 3.2053 | 2.6395 | 7.4936 | 4.1542 | 1.5605 | 19.0532
| 832 | 3.7186 | 2.9438 | 5.2743 | 3.6911 | 1.0073 | 16.6352
| 833 | 4.5927 | 2.4548 | 4.6325 | 3.5552 | 1.5169 | 16.7522
| 834 | 4.3497 | 3.4017 | 5.5212 | 3.7009 | 1.8802 | 18.8536
| 835 | 3.1285 | 3.2719 | 5.4368 | 3.8196 | 1.586 | 17.2429
| 836 | 4.3413 | 3.7908 | 6.7549 | 4.3575 | 1.5475 | 20.792
| 837 | 4.6155 | 2.9591 | 5.8233 | 3.4816 | 1.5948 | 18.4743
| 838 | 4.2384 | 3.6107 | 7.7187 | 3.3515 | 1.2205 | 20.1397
| 839 | 3.7585 | 2.264 | 6.6511 | 3.5724 | 1.2765 | 17.5225
| 840 | 3.8951 | 2.509 | 4.8101 | 3.3741 | 1.5179 | 16.1062
| 841 | 3.9717 | 3.18 | 4.7234 | 5.2028 | 1.4323 | 18.5102
| 842 | 4.3926 | 2.5723 | 6.2054 | 4.5543 | 1.5324 | 19.257
| 843 | 4.143 | 2.6839 | 4.7847 | 3.54 | 1.3374 | 16.489
| 844 | 3.5271 | 3.384 | 6.3898 | 4.0303 | 1.4546 | 18.7858
| 845 | 3.6541 | 3.4857 | 4.6514 | 4.7769 | 1.1612 | 17.7292
| 846 | 3.9338 | 2.4135 | 5.4808 | 4.6337 | 1.4946 | 17.9563
| 847 | 4.4761 | 3.1553 | 5.5451 | 3.574 | 1.5381 | 18.2887
| 848 | 3.5862 | 2.5487 | 5.0646 | 5.1153 | 1.4755 | 17.7903
| 849 | 4.3675 | 2.7208 | 5.4926 | 3.1732 | 1.3523 | 17.1064
| 850 | 4.4532 | 2.8825 | 5.0186 | 3.6502 | 1.9064 | 17.9108
| 851 | 3.6469 | 3.1657 | 5.5109 | 4.0911 | 1.5051 | 17.9197
| 852 | 4.1473 | 2.8655 | 6.019 | 3.3661 | 1.6279 | 18.0259
| 853 | 4.4878 | 3.2925 | 6.3214 | 4.5167 | 1.6236 | 20.242
| 854 | 3.995 | 2.7748 | 5.2763 | 3.9569 | 1.4707 | 17.4738
| 855 | 4.1357 | 2.8382 | 5.2059 | 4.4415 | 1.388 | 18.0093
| 856 | 4.5455 | 2.424 | 6.7253 | 4.2797 | 1.6089 | 19.5834
| 857 | 4.414 | 2.7602 | 5.6344 | 3.9135 | 1.5257 | 18.2478
| 858 | 4.4032 | 2.8184 | 5.014 | 4.6269 | 1.736 | 18.5984
| 859 | 4.3717 | 3.0517 | 4.4738 | 4.227 | 1.2653 | 17.3895
| 860 | 3.8028 | 3.3506 | 4.7882 | 4.5294 | 1.7866 | 18.2575
| 861 | 4.0581 | 2.3556 | 4.5317 | 3.943 | 1.9084 | 16.7969
| 862 | 4.6143 | 3.5336 | 6.3348 | 5.3616 | 1.4082 | 21.2524
| 863 | 3.3184 | 2.8872 | 5.5763 | 4.5404 | 1.3107 | 17.633
| 864 | 4.3029 | 3.3959 | 5.9088 | 4.5638 | 1.3609 | 19.5322
| 865 | 4.0223 | 2.8131 | 5.4172 | 3.5504 | 1.565 | 17.3681
| 866 | 4.0358 | 3.4626 | 6.5678 | 4.919 | 1.2406 | 20.2259
| 867 | 4.5047 | 2.8355 | 7.1587 | 3.4238 | 1.8357 | 19.7585
| 868 | 3.8725 | 3.1459 | 5.5145 | 3.7046 | 1.6723 | 17.9099
| 869 | 3.7264 | 2.3178 | 5.1261 | 4.1236 | 1.202 | 16.4959
| 870 | 4.0381 | 3.551 | 7.3677 | 4.3835 | 1.4453 | 20.7855
| 871 | 3.8079 | 2.7312 | 4.8594 | 4.2186 | 1.5581 | 17.1752
| 872 | 3.9164 | 3.1503 | 7.4556 | 5.6003 | 1.1199 | 21.2424
| 873 | 3.762 | 2.6768 | 6.0855 | 3.4693 | 1.0761 | 17.0697
| 874 | 3.9943 | 2.5062 | 5.6037 | 4.5184 | 1.4519 | 18.0745
| 875 | 4.0255 | 2.6686 | 4.7968 | 4.4052 | 1.3168 | 17.2129
| 876 | 3.9636 | 3.5782 | 7.1447 | 4.7223 | 1.4859 | 20.8946
| 877 | 4.009 | 3.0547 | 5.5064 | 3.555 | 1.6896 | 17.8146
| 878 | 3.5041 | 2.562 | 5.3898 | 3.3777 | 1.3825 | 16.2161
| 879 | 3.5286 | 3.2653 | 5.1375 | 3.8107 | 1.1865 | 16.9288
| 880 | 4.4332 | 3.8782 | 6.9284 | 4.8942 | 1.5807 | 21.7147
| 881 | 4.0772 | 3.5955 | 6.5074 | 3.8345 | 1.6036 | 19.6182
| 882 | 3.907 | 2.5136 | 4.9007 | 5.0728 | 1.9451 | 18.3392
| 883 | 4.3702 | 3.0317 | 7.3055 | 4.698 | 1.5645 | 20.9698
| 884 | 4.4282 | 2.2225 | 5.4022 | 4.6708 | 1.5253 | 18.2489
| 885 | 3.9832 | 3.5853 | 7.5134 | 3.8036 | 1.7416 | 20.6271
| 886 | 3.5609 | 3.0758 | 5.5286 | 4.592 | 1.7815 | 18.5388
| 887 | 3.9698 | 3.2959 | 5.7341 | 3.99 | 1.148 | 18.1379
| 888 | 4.1937 | 2.7715 | 6.1168 | 3.3191 | 1.3972 | 17.7982
| 889 | 4.0102 | 2.9116 | 5.9904 | 4.5965 | 1.488 | 18.9967
| 890 | 4.2616 | 2.5427 | 4.5175 | 5.1451 | 1.4844 | 17.9514
| 891 | 3.3593 | 2.9934 | 6.0241 | 4.8593 | 1.3966 | 18.6328
| 892 | 3.5803 | 2.0743 | 6.3131 | 3.6309 | 1.0465 | 16.6451
| 893 | 3.9759 | 2.4998 | 5.7942 | 4.1685 | 1.4656 | 17.904
| 894 | 3.8833 | 2.8397 | 6.7914 | 4.1078 | 1.5057 | 19.128
| 895 | 4.1863 | 3.0676 | 5.8524 | 3.6187 | 1.8472 | 18.5722
| 896 | 3.7436 | 3.2306 | 6.8608 | 5.2135 | 1.4849 | 20.5334
| 897 | 3.4835 | 3.0212 | 7.2027 | 3.8287 | 1.5073 | 19.0434
| 898 | 3.8911 | 3.2058 | 4.4298 | 4.1662 | 1.5436 | 17.2366
| 899 | 4.7293 | 2.8695 | 5.599 | 4.8405 | 1.6063 | 19.6446
| 900 | 4.5845 | 2.7375 | 6.1985 | 3.6731 | 1.7689 | 18.9624
| 901 | 4.0832 | 3.0087 | 5.3041 | 3.6968 | 1.2767 | 17.3695
| 902 | 4.1657 | 3.5938 | 6.3662 | 3.2757 | 1.3583 | 18.7596
| 903 | 4.1539 | 2.8589 | 5.7204 | 3.6172 | 1.4623 | 17.8127
| 904 | 3.9191 | 2.904 | 5.5411 | 5.1352 | 1.2029 | 18.7024
| 905 | 4.3351 | 2.4374 | 6.1828 | 4.848 | 1.4473 | 19.2506
| 906 | 4.5514 | 2.8457 | 5.0206 | 3.398 | 1.17 | 16.9857
| 907 | 4.4296 | 2.6323 | 5.0012 | 4.8633 | 1.5587 | 18.4852
| 908 | 3.5347 | 2.4003 | 5.9316 | 4.4616 | 1.6573 | 17.9855
| 909 | 3.6586 | 3.0118 | 6.2405 | 3.8425 | 1.6181 | 18.3715
| 910 | 4.6415 | 3.103 | 4.9172 | 3.8874 | 1.4791 | 18.0282
| 911 | 3.9173 | 3.3327 | 7.0394 | 4.9695 | 1.905 | 21.1639
| 912 | 4.7748 | 3.4671 | 6.5476 | 5.4047 | 1.5237 | 21.7179
| 913 | 4.6716 | 3.6987 | 4.8043 | 3.6037 | 1.4589 | 18.2373
| 914 | 3.906 | 3.4111 | 5.6925 | 5.3529 | 1.2713 | 19.6338
| 915 | 3.353 | 2.5537 | 4.5281 | 4.1328 | 1.4478 | 16.0154
| 916 | 3.8554 | 3.2541 | 6.8561 | 4.0936 | 1.3498 | 19.409
| 917 | 3.9082 | 3.3014 | 6.3045 | 4.4643 | 1.5162 | 19.4946
| 918 | 4.5306 | 2.6627 | 5.6358 | 5.7914 | 1.7755 | 20.396
| 919 | 4.1333 | 3.0576 | 5.1 | 3.2834 | 1.3689 | 16.9431
| 920 | 3.8023 | 3.3771 | 7.0778 | 4.9372 | 1.6347 | 20.8292
| 921 | 4.0625 | 3.0328 | 5.5257 | 3.3594 | 1.3136 | 17.294
| 922 | 4.0734 | 2.2444 | 4.4193 | 5.5886 | 1.8836 | 18.2092
| 923 | 4.5605 | 2.5878 | 5.3869 | 4.3098 | 1.5154 | 18.3605
| 924 | 4.6434 | 3.0512 | 5.707 | 3.7058 | 1.7299 | 18.8373
| 925 | 4.1306 | 2.467 | 5.789 | 4.2118 | 1.6707 | 18.269
| 926 | 3.8824 | 2.6548 | 5.171 | 3.7585 | 1.6292 | 17.0959
| 927 | 3.589 | 3.2108 | 5.3343 | 3.5292 | 1.8135 | 17.4768
| 928 | 4.0306 | 2.8573 | 5.3613 | 3.8243 | 1.2563 | 17.3298
| 929 | 4.2741 | 3.4924 | 4.781 | 3.6195 | 1.15 | 17.317
| 930 | 4.0969 | 3.4282 | 5.1228 | 3.4015 | 1.4189 | 17.4684
| 931 | 3.4583 | 2.8634 | 5.9656 | 3.9725 | 1.3278 | 17.5876
| 932 | 3.9244 | 3.5546 | 5.9445 | 4.5227 | 1.7484 | 19.6947
| 933 | 4.6537 | 3.2753 | 4.4591 | 3.6656 | 1.42 | 17.4737
| 934 | 4.4045 | 2.1899 | 5.389 | 3.7679 | 1.6564 | 17.4078
| 935 | 3.9141 | 2.7606 | 4.7715 | 3.6643 | 1.2101 | 16.3206
| 936 | 3.8687 | 3.118 | 5.9187 | 3.2887 | 1.3651 | 17.5593
| 937 | 4.8442 | 3.0032 | 6.1497 | 3.6955 | 1.5214 | 19.214
| 938 | 3.9402 | 2.9951 | 5.2792 | 4.2291 | 1.2855 | 17.7291
| 939 | 3.7674 | 3.1036 | 5.0842 | 3.8713 | 1.5832 | 17.4098
| 940 | 3.979 | 3.8934 | 7.6472 | 3.6021 | 1.4181 | 20.5398
| 941 | 3.3638 | 2.7102 | 4.29 | 3.9643 | 1.8037 | 16.132
| 942 | 3.2866 | 3.0945 | 7.4696 | 3.5906 | 1.3837 | 18.825
| 943 | 3.3417 | 3.2935 | 5.9753 | 3.3219 | 1.382 | 17.3144
| 944 | 3.948 | 2.7736 | 6.2585 | 3.4784 | 1.5276 | 17.9861
| 945 | 4.8194 | 3.1244 | 6.695 | 5.2994 | 1.2969 | 21.2352
| 946 | 3.8819 | 2.7807 | 6.7105 | 4.0955 | 1.0795 | 18.5482
| 947 | 3.7736 | 3.962 | 5.6501 | 3.9254 | 1.7292 | 19.0403
| 948 | 4.0417 | 3.0391 | 6.8691 | 3.6724 | 1.6209 | 19.2433
| 949 | 4.3976 | 3.0261 | 4.6981 | 4.744 | 1.8147 | 18.6806
| 950 | 4.1525 | 2.6481 | 5.4856 | 3.6462 | 1.3927 | 17.325
| 951 | 3.7226 | 3.1204 | 6.2821 | 4.2482 | 1.5844 | 18.9578
| 952 | 4.4209 | 2.3753 | 5.2086 | 4.7942 | 1.5419 | 18.3408
| 953 | 3.8899 | 3.4424 | 5.6602 | 4.5325 | 1.4968 | 19.0218
| 954 | 4.0531 | 3.0563 | 5.9585 | 3.5954 | 1.2923 | 17.9556
| 955 | 3.69 | 2.1248 | 4.3757 | 4.261 | 1.7546 | 16.2062
| 956 | 4.7683 | 3.0182 | 4.7769 | 3.2496 | 1.515 | 17.328
| 957 | 4.4898 | 3.2218 | 4.6204 | 3.9842 | 1.6078 | 17.924
| 958 | 3.4848 | 3.0853 | 7.2267 | 3.628 | 1.3401 | 18.765
| 959 | 3.9507 | 3.2602 | 4.8522 | 4.7813 | 1.777 | 18.6215
| 960 | 4.1197 | 2.4843 | 5.1328 | 4.3199 | 1.5493 | 17.606
| 961 | 4.8273 | 3.1611 | 5.7674 | 3.6049 | 1.8347 | 19.1954
| 962 | 3.9009 | 3.7049 | 5.0261 | 3.7228 | 1.125 | 17.4797
| 963 | 3.4996 | 3.3369 | 4.3293 | 4.1636 | 1.4739 | 16.8032
| 964 | 4.5151 | 3.0533 | 6.8832 | 4.6669 | 1.6008 | 20.7192
| 965 | 3.9113 | 2.9357 | 5.097 | 4.0035 | 1.1718 | 17.1193
| 966 | 4.3434 | 3.2354 | 6.9207 | 3.0894 | 1.3663 | 18.9551
| 967 | 4.1657 | 3.6824 | 4.7578 | 5.2185 | 1.2757 | 19.1001
| 968 | 3.7088 | 3.1731 | 5.3222 | 5.4497 | 1.198 | 18.8519
| 969 | 4.0422 | 3.2985 | 5.037 | 4.8096 | 1.3565 | 18.5436
| 970 | 3.6509 | 2.5254 | 5.356 | 5.709 | 1.5011 | 18.7425
| 971 | 3.8399 | 3.686 | 4.7068 | 5.5188 | 1.4349 | 19.1864
| 972 | 3.3452 | 3.5923 | 4.9572 | 3.9807 | 1.2125 | 17.0879
| 973 | 4.5406 | 2.9504 | 5.0062 | 3.8193 | 1.7205 | 18.037
| 974 | 4.2646 | 2.5979 | 7.9368 | 4.8205 | 1.9829 | 21.6026
| 975 | 3.322 | 3.1162 | 7.0699 | 3.1672 | 1.3975 | 18.0729
| 976 | 3.5953 | 2.9681 | 6.0728 | 4.4256 | 1.288 | 18.3497
| 977 | 4.6394 | 3.3161 | 6.0932 | 3.3626 | 1.6666 | 19.0779
| 978 | 4.0605 | 3.763 | 5.7855 | 3.8995 | 1.574 | 19.0825
| 979 | 3.6992 | 2.8336 | 6.0084 | 3.5289 | 1.3009 | 17.371
| 980 | 4.5791 | 2.6414 | 4.6956 | 3.4653 | 1.1519 | 16.5334
| 981 | 4.1259 | 2.3943 | 4.6472 | 4.2954 | 1.511 | 16.9739
| 982 | 3.1509 | 3.1958 | 5.0315 | 3.3766 | 1.6063 | 16.3612
| 983 | 3.8957 | 3.6143 | 5.285 | 3.9196 | 1.6884 | 18.4031
| 984 | 3.7727 | 2.7259 | 4.6445 | 3.9362 | 1.9704 | 17.0497
| 985 | 3.8148 | 3.1092 | 7.5792 | 3.6446 | 1.38 | 19.5279
| 986 | 4.5587 | 2.898 | 5.4297 | 4.0457 | 1.1286 | 18.0607
| 987 | 4.8704 | 2.9788 | 5.1219 | 4.0649 | 1.4909 | 18.5269
| 988 | 3.9553 | 3.1979 | 4.9356 | 4.1262 | 1.7246 | 17.9395
| 989 | 3.4081 | 3.2035 | 4.742 | 3.4905 | 1.475 | 16.3192
| 990 | 3.72 | 3.1176 | 6.6182 | 4.3369 | 1.2839 | 19.0766
| 991 | 4.2073 | 3.15 | 5.0562 | 3.8666 | 1.7783 | 18.0583
| 992 | 3.9712 | 2.7822 | 6.5727 | 3.7792 | 1.4585 | 18.5638
| 993 | 4.5653 | 2.1279 | 7.0097 | 4.8523 | 1.3367 | 19.8919
| 994 | 3.166 | 3.1479 | 5.1814 | 3.3376 | 1.4092 | 16.242
| 995 | 4.1317 | 2.49 | 5.2989 | 5.0796 | 1.5351 | 18.5352
| 996 | 3.7685 | 3.7015 | 4.9686 | 4.0491 | 1.3669 | 17.8545
| 997 | 4.0663 | 2.7352 | 5.0721 | 5.0049 | 1.5314 | 18.4098
| 998 | 3.6856 | 2.9759 | 4.9968 | 3.7711 | 1.7536 | 17.183
| 999 | 3.9889 | 2.8897 | 7.153 | 3.9944 | 1.3558 | 19.3817
| 1000 | 3.0849 | 3.5071 | 7.3266 | 3.8612 | 1.839 | 19.6188
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Risk Results 4
Navigation |  | Inputs |  |  |  |  | Outputs | Simulation Statistics |  | Output Cumulative Distributions | Output Distributions | Risk Tornado Diagram
Risk Outputs |  | Plan!$G$6 | Plan!$G$7 | Plan!$G$8 | Plan!$G$9 | Plan!$G$10 | Plan!$G$11 |  | Plan!$G$11 |  |  |  |  | Correlations - Column 1 sorted
Simulation Statistics | Iterations | RiskTriang(D6,E6,F6) | RiskTriang(D7,E7,F7) | RiskTriang(D8,E8,F8) | RiskTriang(D9,E9,F9) | RiskTriang(D10,E10,F10) | LiveDate |  | LiveDate |  |  | Select Output: | Plan!$G$11 |  | Plan!$G$11
Risk Output Percentiles | 1 | 4.1407 | 2.9286 | 5.892 | 4.8626 | 1.1054 | 18.9292 | Mean | 18.3333 |  |  | Name: | LiveDate | Risk Inputs | LiveDate
Calculate Percent Rank | 2 | 3.7247 | 3.268 | 4.7435 | 5.0631 | 1.3405 | 18.1398 | Median | 18.264 |  |  | 1 |  | Plan!$G$10 | 0.18508
Correlations | 3 | 4.1018 | 3.0447 | 6.1276 | 5.2517 | 1.3859 | 19.9116 | Mode | #N/A |  |  | Tornado Diagram for LiveDate (Plan!$G$11) |  | Plan!$G$7 | 0.3204
Output Cumulative Distributions | 4 | 3.9109 | 3.1359 | 5.7657 | 5.7114 | 1.5394 | 20.0634 | Std. Deviation | 1.2593 |  |  |  |  | Plan!$G$6 | 0.35107
Output Distributions | 5 | 4.0125 | 3.4802 | 4.8749 | 4.5851 | 1.6976 | 18.6503 | Variance | 1.5858 |  |  |  |  | Plan!$G$9 | 0.5405
Risk Tornado Diagram | 6 | 3.9694 | 3.4135 | 5.1549 | 5.6786 | 1.3312 | 19.5476 | Kurtosis | -0.13332 |  |  |  |  | Plan!$G$8 | 0.69674
| 7 | 3.7479 | 2.8425 | 6.7282 | 3.6789 | 1.7837 | 18.7811 | Skewness | 0.32923
| 8 | 4.3366 | 2.9645 | 6.5881 | 4.7482 | 1.3925 | 20.0299 | Minimum | 15.4615
| 9 | 4.1229 | 3.4388 | 4.6509 | 4.9605 | 1.6681 | 18.8412 | Maximum | 22.6694
| 10 | 3.4075 | 3.7444 | 5.0369 | 3.4489 | 1.1899 | 16.8275 | Range | 7.208
| 11 | 3.6727 | 2.8147 | 4.8433 | 3.586 | 1.6408 | 16.5576 | Count | 1000
| 12 | 4.2102 | 3.0329 | 6.8864 | 4.0671 | 1.6552 | 19.8517 | Error Count | 0
| 13 | 4.0448 | 3.4353 | 6.1374 | 3.8007 | 1.4931 | 18.9113 | Std. Error | 0.039822
| 14 | 3.7783 | 2.975 | 5.3597 | 3.4955 | 1.769 | 17.3775 | Confidence Level (95%) | 0.078144
| 15 | 3.4474 | 2.0962 | 6.0595 | 3.2112 | 1.3746 | 16.1888
| 16 | 3.983 | 2.4521 | 4.9689 | 4.2255 | 1.318 | 16.9475 | Percentiles
| 17 | 4.7884 | 2.725 | 6.1956 | 3.3133 | 1.7347 | 18.757 |  | Plan!$G$11
| 18 | 3.545 | 3.5035 | 5.2609 | 3.9222 | 1.4845 | 17.7161 |  | LiveDate
| 19 | 3.9257 | 3.2967 | 6.2051 | 4.9297 | 1.4857 | 19.843 | 0% | 15.4615
| 20 | 4.6753 | 3.1326 | 4.9815 | 3.6379 | 1.6844 | 18.1117 | 2.5% | 16.1198
| 21 | 3.6581 | 3.2258 | 4.6459 | 4.3089 | 1.6304 | 17.469 | 5% | 16.3888
| 22 | 4.1273 | 3.4902 | 5.4619 | 4.7187 | 1.2002 | 18.9983 | 7.5% | 16.5711
| 23 | 3.3763 | 2.9087 | 5.0611 | 3.7589 | 1.3241 | 16.4292 | 10% | 16.7452
| 24 | 4.4941 | 2.9514 | 6.3866 | 3.7993 | 1.4639 | 19.0953 | 12.5% | 16.8981
| 25 | 4.1899 | 2.459 | 5.682 | 4.1651 | 1.3511 | 17.8472 | 15% | 17.0029
| 26 | 3.9307 | 2.5669 | 4.7283 | 4.8239 | 1.5336 | 17.5834 | 17.5% | 17.084
| 27 | 3.8286 | 2.5821 | 5.8932 | 4.8812 | 1.3163 | 18.5014 | 20% | 17.2103
| 28 | 4.5271 | 2.7715 | 4.5443 | 3.4275 | 1.6617 | 16.9321 | 22.5% | 17.3107
| 29 | 3.9374 | 2.7552 | 4.0552 | 3.7568 | 1.4221 | 15.9266 | 25% | 17.408
| 30 | 4.7379 | 3.7922 | 5.4593 | 3.288 | 1.2883 | 18.5657 | 27.5% | 17.5248
| 31 | 3.6651 | 3.5791 | 5.2181 | 4.819 | 1.5457 | 18.827 | 30% | 17.617
| 32 | 3.9445 | 2.4413 | 5.7295 | 3.9965 | 1.7581 | 17.8698 | 32.5% | 17.7095
| 33 | 4.2747 | 3.4208 | 5.0695 | 4.7382 | 1.4266 | 18.9299 | 35% | 17.7829
| 34 | 3.8722 | 3.0768 | 4.0907 | 5.5635 | 1.3526 | 17.9558 | 37.5% | 17.8691
| 35 | 3.8477 | 2.1629 | 5.421 | 5.4422 | 1.4098 | 18.2836 | 40% | 17.9431
| 36 | 4.7286 | 2.7142 | 6.0037 | 5.0565 | 1.541 | 20.0439 | 42.5% | 18.0169
| 37 | 4.7581 | 3.8694 | 6.2464 | 3.9402 | 1.3804 | 20.1944 | 45% | 18.1165
| 38 | 4.1491 | 3.6727 | 6.1748 | 3.0518 | 1.385 | 18.4334 | 47.5% | 18.1865
| 39 | 4.4965 | 3.6536 | 5.7802 | 4.1674 | 1.5435 | 19.6412 | 50% | 18.264
| 40 | 3.3323 | 2.1772 | 6.3344 | 3.6236 | 1.9003 | 17.3678 | 52.5% | 18.3642
| 41 | 3.7368 | 2.8548 | 5.9539 | 4.4306 | 1.7502 | 18.7264 | 55% | 18.4459
| 42 | 3.9405 | 2.7845 | 5.6668 | 3.3495 | 1.3967 | 17.1381 | 57.5% | 18.5123
| 43 | 3.6466 | 2.5713 | 5.2715 | 4.7422 | 1.4124 | 17.6441 | 60% | 18.6005
| 44 | 3.491 | 3.0101 | 5.1389 | 5.3652 | 1.4777 | 18.4829 | 62.5% | 18.6795
| 45 | 3.9814 | 3.2458 | 6.0643 | 3.202 | 1.322 | 17.8154 | 65% | 18.779
| 46 | 4.5651 | 3.8399 | 5.1259 | 3.7644 | 1.1918 | 18.487 | 67.5% | 18.8639
| 47 | 3.7857 | 3.0413 | 6.3981 | 4.8064 | 1.6533 | 19.6848 | 70% | 18.9707
| 48 | 3.9077 | 2.7027 | 5.2623 | 4.4703 | 1.7723 | 18.1153 | 72.5% | 19.0494
| 49 | 4.5079 | 2.5228 | 4.8173 | 5.0262 | 1.9356 | 18.8098 | 75% | 19.1483
| 50 | 4.0414 | 3.4421 | 6.5736 | 4.9056 | 1.4416 | 20.4043 | 77.5% | 19.2699
| 51 | 4.4838 | 3.7775 | 5.8555 | 5.0748 | 1.6255 | 20.8171 | 80% | 19.3652
| 52 | 3.9045 | 2.9106 | 7.5432 | 3.4927 | 1.4798 | 19.3307 | 82.5% | 19.5495
| 53 | 3.3233 | 3.0253 | 4.6111 | 5.0013 | 1.0815 | 17.0426 | 85% | 19.6859
| 54 | 4.1263 | 3.0637 | 7.5633 | 3.9279 | 1.7296 | 20.4108 | 87.5% | 19.8229
| 55 | 4.1977 | 2.938 | 4.5858 | 5.2169 | 1.2764 | 18.2149 | 90% | 19.9718
| 56 | 4.0592 | 2.7591 | 6.1029 | 4.9434 | 1.7996 | 19.6642 | 92.5% | 20.1834
| 57 | 3.5471 | 3.4613 | 5.9454 | 3.7256 | 1.6906 | 18.37 | 95% | 20.4786
| 58 | 4.3777 | 3.122 | 7.1156 | 4.3111 | 1.8736 | 20.8 | 97.5% | 21.0147
| 59 | 3.8703 | 2.4353 | 5.2523 | 3.8211 | 1.3261 | 16.705 | 100% | 22.6694
| 60 | 4.0558 | 2.8479 | 7.0294 | 4.0735 | 1.4015 | 19.4082
| 61 | 4.5178 | 3.2985 | 6.4421 | 5.378 | 1.4775 | 21.114 | Percent Rank
| 62 | 3.8992 | 2.6636 | 4.5935 | 4.2552 | 1.4119 | 16.8233 |  | Plan!$G$11
| 63 | 4.4195 | 3.6908 | 4.2564 | 4.9718 | 1.2822 | 18.6206 |  | LiveDate
| 64 | 3.8879 | 3.2774 | 5.6981 | 4.4424 | 1.5091 | 18.8148 | Enter Value: | 16.3888
| 65 | 4.2298 | 2.8079 | 4.738 | 4.0924 | 1.6372 | 17.5053 | % rank: | 5%
| 66 | 4.3812 | 3.2325 | 4.4609 | 3.775 | 1.1404 | 16.99
| 67 | 3.3035 | 2.574 | 5.2801 | 4.2038 | 1.5544 | 16.9159 | Correlations
| 68 | 4.2876 | 2.4691 | 6.1113 | 3.8573 | 1.5277 | 18.253 |  | Plan!$G$11
| 69 | 3.2215 | 2.7702 | 6.807 | 3.3396 | 1.7594 | 17.8977 | Risk Inputs | LiveDate
| 70 | 3.4444 | 2.5621 | 4.2635 | 4.6339 | 1.5781 | 16.482 | Plan!$G$6 | 0.35107
| 71 | 4.3792 | 3.129 | 4.6085 | 4.4774 | 1.4062 | 18.0002 | Plan!$G$7 | 0.3204
| 72 | 3.1192 | 3.0361 | 4.7762 | 3.3511 | 1.3337 | 15.6162 | Plan!$G$8 | 0.69674
| 73 | 4.0169 | 3.0529 | 5.4869 | 5.0874 | 1.3599 | 19.004 | Plan!$G$9 | 0.5405
| 74 | 4.3975 | 2.8381 | 5.8843 | 5.4991 | 1.5284 | 20.1473 | Plan!$G$10 | 0.18508
| 75 | 3.5319 | 2.3533 | 5.8052 | 4.5931 | 1.6107 | 17.8942
| 76 | 3.8031 | 3.2172 | 4.5613 | 4.6078 | 1.7761 | 17.9654
| 77 | 4.2852 | 2.9585 | 5.3364 | 5.2095 | 1.5464 | 19.3359
| 78 | 3.9162 | 3.167 | 4.6375 | 3.8694 | 1.4806 | 17.0707
| 79 | 3.8221 | 3.4724 | 6.2822 | 3.4352 | 1.3971 | 18.4091
| 80 | 3.4411 | 2.6468 | 5.8442 | 5.2893 | 1.4548 | 18.6761
| 81 | 3.989 | 2.9592 | 5.4802 | 3.7403 | 1.3023 | 17.471
| 82 | 3.4761 | 2.9634 | 5.1229 | 3.6558 | 1.5179 | 16.7361
| 83 | 3.9989 | 3.205 | 4.4547 | 4.7712 | 1.1231 | 17.5529
| 84 | 3.3185 | 3.3021 | 5.318 | 4.5919 | 1.7419 | 18.2724
| 85 | 3.965 | 3.4864 | 5.0149 | 5.59 | 1.2129 | 19.2693
| 86 | 4.2537 | 2.8536 | 5.3721 | 4.5426 | 1.4902 | 18.5123
| 87 | 4.2621 | 3.3976 | 5.3253 | 4.8542 | 1.5259 | 19.3651
| 88 | 4.2254 | 3.0967 | 4.5892 | 4.1553 | 1.2921 | 17.3587
| 89 | 4.568 | 2.6556 | 4.5822 | 3.4399 | 1.4989 | 16.7446
| 90 | 4.6227 | 3.0501 | 5.609 | 3.5169 | 1.4027 | 18.2014
| 91 | 3.6082 | 2.9433 | 5.0602 | 3.8092 | 1.4833 | 16.9042
| 92 | 4.1104 | 2.5755 | 5.9587 | 4.0505 | 1.522 | 18.217
| 93 | 3.5415 | 3.1393 | 7.5975 | 4.837 | 1.1385 | 20.2537
| 94 | 4.5084 | 2.2781 | 4.8649 | 3.2325 | 1.4675 | 16.3514
| 95 | 4.0398 | 2.6827 | 7.7501 | 4.0225 | 1.6179 | 20.113
| 96 | 4.2732 | 3.1208 | 6.2856 | 3.3017 | 1.3749 | 18.3562
| 97 | 4.2332 | 2.7404 | 6.2739 | 3.7708 | 1.6632 | 18.6815
| 98 | 4.4469 | 3.4987 | 6.4331 | 3.7467 | 1.7195 | 19.8448
| 99 | 3.7391 | 3.2562 | 6.0008 | 3.5308 | 1.6335 | 18.1605
| 100 | 4.1099 | 2.8103 | 5.8521 | 3.7165 | 1.6466 | 18.1354
| 101 | 3.294 | 3.1751 | 4.5756 | 4.3252 | 1.7302 | 17.1001
| 102 | 4.4451 | 3.5695 | 4.4165 | 3.5139 | 1.6719 | 17.6169
| 103 | 3.5631 | 2.9369 | 5.1951 | 4.4377 | 1.4626 | 17.5953
| 104 | 3.8265 | 3.8753 | 5.38 | 4.7222 | 1.2722 | 19.0763
| 105 | 3.7805 | 3.008 | 6.6543 | 5.5084 | 1.7736 | 20.7247
| 106 | 3.5206 | 2.4689 | 5.3439 | 3.5435 | 1.3437 | 16.2207
| 107 | 4.1789 | 2.2989 | 5.348 | 3.5387 | 1.4942 | 16.8587
| 108 | 4.3329 | 3.1302 | 5.1455 | 3.2198 | 1.669 | 17.4974
| 109 | 4.0722 | 3.489 | 6.3178 | 4.0458 | 1.7053 | 19.6301
| 110 | 4.2507 | 2.3904 | 7.0029 | 4.9992 | 1.5913 | 20.2345
| 111 | 4.6196 | 2.6113 | 5.507 | 4.1281 | 1.1863 | 18.0522
| 112 | 3.7121 | 3.2011 | 6.4247 | 4.0431 | 1.4822 | 18.8634
| 113 | 4.2162 | 3.3542 | 4.8903 | 4.6938 | 1.1447 | 18.2992
| 114 | 3.5823 | 3.3887 | 5.5735 | 4.5482 | 1.5425 | 18.6351
| 115 | 3.9179 | 2.95 | 6.1584 | 4.4573 | 1.4998 | 18.9834
| 116 | 3.3657 | 2.8524 | 7.0817 | 4.1425 | 1.505 | 18.9474
| 117 | 4.3374 | 3.0081 | 6.1428 | 3.6721 | 1.6267 | 18.7871
| 118 | 3.237 | 2.8962 | 5.0194 | 4.3593 | 1.6054 | 17.1173
| 119 | 4.4205 | 3.0505 | 7.0014 | 3.5353 | 1.7149 | 19.7226
| 120 | 3.9503 | 2.4943 | 6.4387 | 4.1878 | 1.3475 | 18.4186
| 121 | 4.4271 | 2.7358 | 5.4845 | 4.0262 | 1.5306 | 18.2043
| 122 | 3.2245 | 2.6302 | 5.0427 | 3.5471 | 1.0929 | 15.5374
| 123 | 3.7576 | 3.2524 | 6.6439 | 5.184 | 1.3454 | 20.1832
| 124 | 3.7757 | 2.6858 | 5.5434 | 3.7152 | 1.917 | 17.637
| 125 | 4.1332 | 2.8932 | 4.1671 | 4.4079 | 1.6087 | 17.2101
| 126 | 3.6756 | 2.8046 | 5.47 | 3.9478 | 1.4172 | 17.3152
| 127 | 4.1942 | 3.0544 | 5.4971 | 3.5067 | 1.5315 | 17.784
| 128 | 3.7863 | 3.2219 | 6.1499 | 3.6147 | 1.2719 | 18.0447
| 129 | 3.6032 | 2.6787 | 5.2842 | 4.2223 | 1.248 | 17.0364
| 130 | 4.2783 | 3.1648 | 6.3496 | 4.4006 | 1.1348 | 19.3281
| 131 | 4.415 | 2.9556 | 6.0726 | 4.5326 | 1.84 | 19.8158
| 132 | 4.6457 | 3.2863 | 6.0852 | 3.5012 | 1.6666 | 19.185
| 133 | 4.0998 | 3.4963 | 6.1169 | 3.1582 | 1.7603 | 18.6315
| 134 | 3.5536 | 3.1726 | 6.8747 | 3.6325 | 1.4492 | 18.6826
| 135 | 4.6272 | 2.5007 | 4.7901 | 4.6782 | 1.6675 | 18.2636
| 136 | 3.7834 | 2.3362 | 5.4076 | 3.9858 | 1.9323 | 17.4453
| 137 | 4.4545 | 2.8192 | 6.2299 | 4.9091 | 1.6205 | 20.0331
| 138 | 4.817 | 3.1073 | 4.893 | 3.4966 | 1.516 | 17.83
| 139 | 4.1579 | 3.0463 | 5.5001 | 3.7355 | 1.325 | 17.7649
| 140 | 4.4433 | 2.7772 | 5.5149 | 3.9138 | 1.3873 | 18.0366
| 141 | 3.5349 | 3.6805 | 5.3305 | 3.2122 | 1.4842 | 17.2424
| 142 | 3.6861 | 3.5363 | 5.1425 | 4.9881 | 1.2893 | 18.6424
| 143 | 4.9086 | 2.0053 | 4.3133 | 5.3412 | 1.1844 | 17.7528
| 144 | 3.8902 | 3.2022 | 6.7372 | 3.2714 | 1.4946 | 18.5957
| 145 | 4.5878 | 2.7615 | 6.8578 | 3.4427 | 1.5477 | 19.1974
| 146 | 4.2213 | 2.7042 | 6.3025 | 3.9056 | 1.3266 | 18.4602
| 147 | 3.9943 | 2.6497 | 6.4971 | 3.6936 | 1.5184 | 18.3531
| 148 | 4.2184 | 3.2636 | 7.6177 | 5.113 | 1.7275 | 21.9402
| 149 | 3.8914 | 3.0851 | 4.4074 | 3.919 | 1.5009 | 16.8038
| 150 | 3.1364 | 2.5267 | 5.7626 | 3.541 | 1.5793 | 16.546
| 151 | 3.8758 | 3.007 | 4.3802 | 4.0785 | 1.8247 | 17.1661
| 152 | 3.7297 | 3.2998 | 4.9594 | 3.4063 | 1.7217 | 17.1169
| 153 | 3.9323 | 3.3332 | 6.2591 | 4.8383 | 1.3416 | 19.7044
| 154 | 4.2471 | 3.8857 | 6.7614 | 4.6986 | 1.7479 | 21.3407
| 155 | 3.7938 | 3.6655 | 5.4193 | 4.3731 | 1.1995 | 18.4512
| 156 | 4.1695 | 3.3719 | 4.8845 | 3.0968 | 1.382 | 16.9046
| 157 | 3.9667 | 3.1407 | 6.6478 | 4.4931 | 1.4764 | 19.7247
| 158 | 3.1563 | 2.6447 | 5.4337 | 4.2894 | 1.4205 | 16.9446
| 159 | 3.8573 | 2.2502 | 6.0124 | 5.3192 | 1.426 | 18.8651
| 160 | 3.6253 | 3.2595 | 4.6009 | 4.2436 | 1.5812 | 17.3104
| 161 | 3.7413 | 2.8162 | 5.1655 | 4.4821 | 1.5859 | 17.7909
| 162 | 3.4374 | 2.7924 | 5.2464 | 3.5763 | 1.6081 | 16.6605
| 163 | 4.7347 | 2.8001 | 6.5946 | 3.2173 | 1.7343 | 19.081
| 164 | 4.3732 | 2.2754 | 4.6777 | 5.2666 | 1.1729 | 17.7657
| 165 | 4.2324 | 2.6781 | 7.852 | 3.6039 | 1.564 | 19.9304
| 166 | 4.0645 | 2.7789 | 6.1903 | 3.8041 | 1.1423 | 17.9802
| 167 | 4.792 | 2.4647 | 5.3413 | 3.5629 | 1.7205 | 17.8813
| 168 | 3.9018 | 2.5565 | 6.241 | 4.6891 | 1.5517 | 18.9402
| 169 | 4.0848 | 3.524 | 5.2956 | 3.7432 | 1.4086 | 18.0563
| 170 | 4.5457 | 2.8227 | 4.9714 | 4.1832 | 1.2864 | 17.8094
| 171 | 3.5753 | 2.6803 | 5.3866 | 3.5555 | 1.4832 | 16.681
| 172 | 3.6163 | 2.5353 | 4.7598 | 3.7781 | 1.5672 | 16.2568
| 173 | 3.9469 | 2.3737 | 5.0862 | 5.142 | 1.371 | 17.9199
| 174 | 3.8776 | 3.0787 | 5.3822 | 4.2116 | 1.538 | 18.0881
| 175 | 4.2314 | 2.6386 | 6.0185 | 5.6149 | 1.7363 | 20.2396
| 176 | 3.5878 | 2.9607 | 6.1646 | 3.8803 | 1.5125 | 18.106
| 177 | 4.5871 | 2.8412 | 4.8587 | 3.7492 | 1.5789 | 17.6152
| 178 | 3.8898 | 2.9098 | 5.55 | 3.9897 | 1.4723 | 17.8114
| 179 | 4.1662 | 3.1152 | 5.8736 | 4.2065 | 1.7859 | 19.1475
| 180 | 4.1202 | 2.8678 | 5.913 | 3.2926 | 1.5234 | 17.717
| 181 | 3.9663 | 2.6515 | 5.6134 | 4.7929 | 1.5873 | 18.6114
| 182 | 3.3116 | 3.3704 | 5.0818 | 3.6944 | 1.7285 | 17.1867
| 183 | 3.986 | 3.0561 | 4.8119 | 3.25 | 1.3695 | 16.4734
| 184 | 4.9528 | 2.753 | 7.313 | 4.3187 | 1.5 | 20.8375
| 185 | 3.8929 | 3.4554 | 4.3936 | 3.5505 | 1.1185 | 16.4109
| 186 | 4.6313 | 3.5402 | 7.3532 | 3.3475 | 1.6129 | 20.4851
| 187 | 4.0809 | 3.4199 | 6.6806 | 5.5455 | 1.7073 | 21.4342
| 188 | 3.9732 | 3.1079 | 4.6517 | 3.8465 | 1.3728 | 16.952
| 189 | 4.0745 | 3.1778 | 6.5531 | 4.5116 | 1.6341 | 19.9511
| 190 | 4.076 | 2.4072 | 5.9622 | 4.6699 | 1.3535 | 18.4688
| 191 | 4.3504 | 2.8969 | 5.5479 | 5.2015 | 1.9634 | 19.9601
| 192 | 4.32 | 2.5405 | 5.8397 | 4.6208 | 1.1784 | 18.4994
| 193 | 3.7624 | 3.6418 | 5.4658 | 3.4999 | 1.1295 | 17.4994
| 194 | 3.5587 | 3.3056 | 7.2041 | 3.627 | 1.1306 | 18.826
| 195 | 3.3879 | 3.343 | 6.3643 | 3.6301 | 1.7567 | 18.4821
| 196 | 4.3399 | 2.8151 | 5.2344 | 4.1951 | 1.2819 | 17.8664
| 197 | 3.3276 | 3.4742 | 5.1193 | 3.865 | 1.2959 | 17.082
| 198 | 4.2814 | 3.1258 | 4.5636 | 4.4555 | 1.6331 | 18.0593
| 199 | 4.0576 | 3.0806 | 5.1399 | 4.357 | 1.5469 | 18.182
| 200 | 4.2053 | 2.8705 | 6.9955 | 4.1124 | 1.9455 | 20.1292
| 201 | 3.7272 | 3.7589 | 6.6043 | 4.5894 | 1.1608 | 19.8406
| 202 | 3.7744 | 2.8234 | 6.2377 | 4.1427 | 1.4699 | 18.4482
| 203 | 3.9923 | 2.6416 | 4.9869 | 5.2839 | 1.3632 | 18.2679
| 204 | 3.4296 | 2.8338 | 6.0471 | 3.6591 | 1.2968 | 17.2664
| 205 | 3.1872 | 2.8864 | 5.7144 | 4.4404 | 1.4993 | 17.7277
| 206 | 3.1511 | 2.2126 | 6.1079 | 4.8914 | 1.4927 | 17.8556
| 207 | 4.4811 | 3.1271 | 6.4658 | 5.1224 | 1.2807 | 20.4772
| 208 | 4.5146 | 2.5849 | 5.006 | 3.3989 | 1.5807 | 17.0851
| 209 | 4.4581 | 3.2156 | 4.3191 | 3.8504 | 1.5655 | 17.4087
| 210 | 4.2753 | 3.0866 | 5.0794 | 3.5878 | 1.6322 | 17.6613
| 211 | 4.3276 | 3.7634 | 5.9281 | 3.6167 | 1.9239 | 19.5596
| 212 | 3.8145 | 3.6264 | 4.6206 | 3.4863 | 1.5366 | 17.0844
| 213 | 4.235 | 2.2857 | 6.2482 | 3.551 | 1.3427 | 17.6625
| 214 | 3.3735 | 3.2472 | 5.677 | 3.7631 | 1.1496 | 17.2104
| 215 | 4.1391 | 2.3219 | 6.038 | 4.0642 | 1.2026 | 17.7657
| 216 | 3.9853 | 2.914 | 5.3159 | 5.1099 | 1.6658 | 18.9908
| 217 | 4.1544 | 2.7321 | 6.1996 | 4.1034 | 1.614 | 18.8034
| 218 | 3.108 | 3.152 | 5.7154 | 3.2913 | 1.3136 | 16.5802
| 219 | 4.0092 | 2.9663 | 5.9043 | 4.2842 | 1.7447 | 18.9088
| 220 | 3.6926 | 2.5433 | 4.6925 | 3.5056 | 1.5447 | 15.9787
| 221 | 3.5273 | 2.8936 | 5.1698 | 3.2514 | 1.4635 | 16.3057
| 222 | 3.9028 | 2.6916 | 5.1177 | 4.6957 | 1.4426 | 17.8504
| 223 | 3.2811 | 2.8826 | 5.4731 | 3.608 | 1.6476 | 16.8924
| 224 | 4.5737 | 3.3742 | 4.4879 | 4.6251 | 1.8702 | 18.9312
| 225 | 4.5634 | 3.6976 | 5.8369 | 4.0538 | 1.5824 | 19.7341
| 226 | 3.2031 | 3.4471 | 4.2244 | 3.7889 | 1.472 | 16.1355
| 227 | 3.7998 | 3.0703 | 4.8686 | 3.8138 | 1.4481 | 17.0007
| 228 | 4.063 | 2.7483 | 6.2247 | 3.8257 | 1.5943 | 18.4559
| 229 | 4.0948 | 2.481 | 4.7517 | 4.94 | 1.2421 | 17.5096
| 230 | 4.0533 | 3.8095 | 5.0473 | 3.7375 | 1.2362 | 17.8838
| 231 | 4.1145 | 2.6482 | 5.3228 | 3.6202 | 1.6516 | 17.3573
| 232 | 4.7178 | 3.159 | 5.9624 | 5.2995 | 1.1614 | 20.3001
| 233 | 4.2444 | 2.783 | 6.8111 | 3.7291 | 1.4542 | 19.0218
| 234 | 3.8065 | 3.0706 | 4.9985 | 5.485 | 1.6595 | 19.0201
| 235 | 4.1222 | 3.3881 | 5.1209 | 3.229 | 1.4429 | 17.3032
| 236 | 3.2973 | 2.8304 | 5.4374 | 3.1616 | 1.6241 | 16.3508
| 237 | 4.0799 | 3.0584 | 7.1179 | 5.6037 | 1.7487 | 21.6086
| 238 | 3.1764 | 3.4308 | 5.0938 | 3.5662 | 1.2531 | 16.5203
| 239 | 4.4255 | 3.6436 | 5.9192 | 4.1858 | 1.4865 | 19.6605
| 240 | 4.2956 | 3.4943 | 4.8986 | 4.9804 | 1.6874 | 19.3563
| 241 | 3.3615 | 3.2241 | 5.9706 | 5.4267 | 1.4519 | 19.4348
| 242 | 4.083 | 2.1079 | 5.1671 | 4.4359 | 1.5169 | 17.3108
| 243 | 4.8415 | 3.1581 | 5.0458 | 4.0399 | 1.4499 | 18.5352
| 244 | 4.0318 | 2.3315 | 4.9855 | 5.3835 | 1.7683 | 18.5008
| 245 | 4.4411 | 3.1844 | 4.9007 | 4.4285 | 1.2076 | 18.1624
| 246 | 4.1415 | 3.2366 | 5.2043 | 4.0622 | 1.9053 | 18.5499
| 247 | 3.4596 | 3.3129 | 4.1363 | 3.97 | 1.771 | 16.6497
| 248 | 4.2269 | 3.2748 | 6.9135 | 4.3792 | 1.4071 | 20.2014
| 249 | 3.9227 | 3.0628 | 5.058 | 4.3648 | 1.8589 | 18.2671
| 250 | 4.2774 | 3.3009 | 6.2977 | 4.1227 | 1.59 | 19.5887
| 251 | 3.9601 | 3.4079 | 5.9492 | 3.6916 | 1.7822 | 18.7911
| 252 | 4.1162 | 3.7702 | 4.2016 | 3.1978 | 1.3092 | 16.595
| 253 | 3.9604 | 3.8578 | 5.3425 | 4.3666 | 1.6416 | 19.1689
| 254 | 3.9125 | 3.3531 | 7.3912 | 4.6122 | 1.9223 | 21.1913
| 255 | 4.036 | 3.2894 | 5.8583 | 4.3774 | 1.5262 | 19.0874
| 256 | 3.1442 | 3.0345 | 4.7846 | 4.618 | 1.3122 | 16.8936
| 257 | 4.1999 | 2.7993 | 4.8543 | 3.5427 | 1.6501 | 17.0464
| 258 | 3.7431 | 3.2921 | 5.6803 | 4.1064 | 1.0789 | 17.9008
| 259 | 3.8411 | 3.0135 | 5.5296 | 4.7759 | 1.275 | 18.435
| 260 | 3.7101 | 2.8372 | 4.9937 | 5.0406 | 1.233 | 17.8147
| 261 | 4.2573 | 3.0392 | 7.3045 | 5.1528 | 1.3566 | 21.1103
| 262 | 4.3603 | 2.6259 | 6.5462 | 4.121 | 1.7085 | 19.362
| 263 | 3.9682 | 3.5124 | 6.7187 | 3.9008 | 1.7643 | 19.8644
| 264 | 4.1906 | 3.3575 | 6.6816 | 5.0239 | 1.685 | 20.9386
| 265 | 3.3564 | 3.1503 | 5.4918 | 4.397 | 1.6457 | 18.0412
| 266 | 3.2148 | 2.3561 | 6.9681 | 3.8508 | 1.5956 | 17.9854
| 267 | 4.2365 | 3.6102 | 5.1021 | 3.6287 | 1.198 | 17.7755
| 268 | 3.8982 | 3.336 | 4.9505 | 4.4249 | 1.6563 | 18.2659
| 269 | 3.7031 | 3.6137 | 5.1759 | 3.9806 | 1.7365 | 18.2098
| 270 | 4.8947 | 2.2669 | 4.9033 | 4.6395 | 1.599 | 18.3033
| 271 | 4.0109 | 3.5652 | 5.4256 | 5.2208 | 1.5505 | 19.773
| 272 | 4.8103 | 2.7193 | 4.5558 | 5.2418 | 1.4716 | 18.7989
| 273 | 4.0495 | 3.3221 | 4.7588 | 4.8478 | 1.4168 | 18.3951
| 274 | 4.0149 | 3.7168 | 5.8477 | 3.4315 | 1.5207 | 18.5315
| 275 | 4.3833 | 2.8953 | 6.4603 | 5.1907 | 1.3278 | 20.2574
| 276 | 4.4566 | 3.0615 | 5.9327 | 4.1487 | 1.3949 | 18.9945
| 277 | 3.8594 | 2.8357 | 5.4522 | 3.3644 | 1.5098 | 17.0215
| 278 | 4.3626 | 3.2846 | 4.4932 | 5.8109 | 1.8074 | 19.7587
| 279 | 3.2911 | 3.1871 | 4.8526 | 4.9679 | 1.2635 | 17.5623
| 280 | 4.4516 | 3.0292 | 5.3761 | 4.0462 | 1.5246 | 18.4277
| 281 | 3.7731 | 2.6423 | 4.7676 | 5.0446 | 1.2396 | 17.4671
| 282 | 4.0003 | 3.069 | 6.1021 | 3.7306 | 1.5618 | 18.4638
| 283 | 3.6087 | 2.4665 | 5.9004 | 3.9396 | 1.6446 | 17.5597
| 284 | 3.5692 | 3.1697 | 7.7876 | 5.2332 | 1.2092 | 20.9689
| 285 | 3.7762 | 3.3258 | 5.6413 | 3.5711 | 1.832 | 18.1464
| 286 | 3.8963 | 3.1541 | 4.8442 | 4.5584 | 1.2925 | 17.7456
| 287 | 3.268 | 2.7058 | 6.0871 | 3.2587 | 1.4588 | 16.7784
| 288 | 4.7045 | 3.1509 | 5.2376 | 4.7299 | 1.2504 | 19.0734
| 289 | 4.3962 | 3.85 | 5.3015 | 4.5272 | 1.5679 | 19.6428
| 290 | 4.4854 | 3.135 | 6.687 | 3.9119 | 1.6224 | 19.8417
| 291 | 3.597 | 2.4274 | 5.7438 | 3.657 | 1.2342 | 16.6594
| 292 | 4.6127 | 3.2279 | 6.1857 | 4.3351 | 1.4326 | 19.794
| 293 | 3.8557 | 2.8175 | 7.255 | 4.8258 | 1.2348 | 19.9888
| 294 | 3.6908 | 3.5773 | 4.8858 | 4.2533 | 1.5417 | 17.9489
| 295 | 3.634 | 2.9468 | 4.5426 | 3.917 | 1.4876 | 16.528
| 296 | 4.2528 | 2.595 | 5.367 | 5.5562 | 1.3381 | 19.1091
| 297 | 3.2872 | 3.3933 | 5.8073 | 4.239 | 1.6573 | 18.3841
| 298 | 3.8311 | 2.7103 | 4.8338 | 3.3446 | 1.2511 | 15.9709
| 299 | 4.2688 | 3.3098 | 5.0935 | 3.8192 | 1.9413 | 18.4325
| 300 | 3.6323 | 2.1434 | 5.0971 | 3.2424 | 1.7389 | 15.854
| 301 | 4.2842 | 2.6001 | 5.0722 | 4.7093 | 1.0188 | 17.6847
| 302 | 4.2549 | 2.6 | 5.6588 | 3.6409 | 1.7424 | 17.897
| 303 | 3.9456 | 3.3289 | 5.0175 | 5.0804 | 1.6432 | 19.0156
| 304 | 3.9268 | 2.242 | 6.7138 | 3.4157 | 1.8211 | 18.1194
| 305 | 3.8192 | 3.1883 | 4.9326 | 4.2631 | 1.7124 | 17.9156
| 306 | 4.0434 | 3.2044 | 5.9861 | 3.1863 | 1.3176 | 17.7378
| 307 | 4.7252 | 2.5923 | 6.4022 | 4.1993 | 1.5189 | 19.4378
| 308 | 4.0515 | 3.738 | 5.1793 | 3.4229 | 1.611 | 18.0026
| 309 | 4.2798 | 3.303 | 5.1869 | 3.5241 | 1.542 | 17.8358
| 310 | 4.1346 | 2.6875 | 6.6759 | 4.8737 | 1.3077 | 19.6795
| 311 | 4.4183 | 3.5754 | 6.3971 | 3.2626 | 1.651 | 19.3044
| 312 | 3.9362 | 2.3695 | 4.9531 | 4.1515 | 1.4745 | 16.8847
| 313 | 4.0354 | 3.8937 | 5.0028 | 4.6624 | 1.3801 | 18.9744
| 314 | 3.5813 | 3.6873 | 7.4177 | 3.5935 | 1.5022 | 19.7819
| 315 | 4.6003 | 3.0732 | 5.1743 | 3.8597 | 1.3158 | 18.0233
| 316 | 4.2974 | 2.246 | 4.7539 | 3.6773 | 1.4154 | 16.39
| 317 | 4.0172 | 3.9183 | 5.5682 | 3.6468 | 1.5136 | 18.6641
| 318 | 3.706 | 2.5088 | 4.9563 | 4.7644 | 1.7107 | 17.6463
| 319 | 4.5725 | 2.4998 | 4.3605 | 3.452 | 1.7242 | 16.609
| 320 | 3.6524 | 3.0371 | 6.3048 | 5.8852 | 1.8281 | 20.7076
| 321 | 4.6666 | 3.695 | 6.6338 | 3.0665 | 1.3037 | 19.3656
| 322 | 3.7892 | 3.0965 | 5.5255 | 4.2486 | 1.4577 | 18.1174
| 323 | 4.3045 | 3.5204 | 5.5533 | 3.6099 | 1.7553 | 18.7434
| 324 | 4.1251 | 3.4495 | 6.2085 | 4.4974 | 1.3537 | 19.6343
| 325 | 3.9915 | 3.9235 | 7.0613 | 3.3721 | 1.759 | 20.1074
| 326 | 4.202 | 2.6856 | 6.8156 | 3.8768 | 1.8261 | 19.406
| 327 | 4.5026 | 3.3342 | 5.4444 | 3.5275 | 1.5401 | 18.3487
| 328 | 4.1594 | 2.5105 | 4.5108 | 3.6116 | 1.3995 | 16.1918
| 329 | 4.0944 | 3.1934 | 4.8202 | 4.129 | 1.5886 | 17.8255
| 330 | 4.2116 | 3.7256 | 5.3071 | 5.3886 | 1.4566 | 20.0894
| 331 | 3.9287 | 2.9062 | 5.1593 | 3.5377 | 1.3899 | 16.9217
| 332 | 3.7523 | 2.9264 | 5.8683 | 3.9492 | 1.3773 | 17.8736
| 333 | 3.9741 | 2.7674 | 5.8714 | 4.5131 | 1.7806 | 18.9066
| 334 | 3.9279 | 2.9725 | 6.9508 | 4.1313 | 1.8562 | 19.8388
| 335 | 4.5702 | 3.8182 | 5.7041 | 3.9566 | 1.2148 | 19.2639
| 336 | 4.2257 | 2.9944 | 7.6667 | 3.3233 | 1.868 | 20.0782
| 337 | 3.7154 | 3.3247 | 4.1752 | 4.453 | 1.7244 | 17.3927
| 338 | 3.4002 | 3.09 | 6.3637 | 4.2321 | 1.6346 | 18.7207
| 339 | 3.6186 | 2.8214 | 5.5612 | 3.5602 | 1.1561 | 16.7176
| 340 | 4.0459 | 2.6187 | 5.9376 | 3.5247 | 1.4181 | 17.545
| 341 | 4.631 | 2.3962 | 5.3191 | 4.597 | 1.767 | 18.7102
| 342 | 3.5667 | 2.8054 | 5.5037 | 4.0493 | 1.5212 | 17.4463
| 343 | 3.548 | 2.7229 | 4.8658 | 3.8395 | 1.5959 | 16.5722
| 344 | 4.0871 | 2.668 | 4.4823 | 3.2565 | 1.5295 | 16.0234
| 345 | 4.2826 | 2.9251 | 6.6639 | 3.5349 | 1.2305 | 18.6369
| 346 | 4.3313 | 3.6832 | 4.8268 | 4.3325 | 1.5628 | 18.7365
| 347 | 4.5463 | 2.7852 | 6.6209 | 4.992 | 1.4465 | 20.3909
| 348 | 4.4074 | 2.2632 | 6.6291 | 4.1572 | 1.6538 | 19.1106
| 349 | 3.8864 | 2.8095 | 6.1325 | 3.1772 | 1.5618 | 17.5675
| 350 | 4.0504 | 2.6391 | 4.6553 | 3.8233 | 1.125 | 16.2931
| 351 | 3.9617 | 2.8317 | 5.1042 | 5.5813 | 1.5763 | 19.0552
| 352 | 3.5855 | 3.0798 | 5.8215 | 3.6541 | 1.5737 | 17.7146
| 353 | 3.3677 | 3.3864 | 5.15 | 4.7663 | 1.4642 | 18.1347
| 354 | 4.0074 | 3.6253 | 5.2444 | 4.3835 | 1.6743 | 18.935
| 355 | 3.8829 | 2.7139 | 4.5067 | 3.7687 | 1.4912 | 16.3634
| 356 | 4.9719 | 3.2739 | 5.9077 | 3.8427 | 1.7747 | 19.7709
| 357 | 4.1832 | 2.7331 | 5.0018 | 4.6311 | 1.2568 | 17.8059
| 358 | 3.915 | 3.4669 | 5.2878 | 5.3272 | 1.2478 | 19.2447
| 359 | 4.3933 | 2.9963 | 4.3875 | 3.5748 | 1.5742 | 16.9262
| 360 | 3.4205 | 2.7274 | 5.9041 | 3.7506 | 1.2775 | 17.0801
| 361 | 4.1672 | 3.314 | 5.068 | 4.3445 | 1.6919 | 18.5856
| 362 | 3.6786 | 2.7291 | 5.6069 | 4.9039 | 1.4288 | 18.3472
| 363 | 3.6748 | 3.0224 | 4.6296 | 4.2305 | 1.446 | 17.0033
| 364 | 4.7796 | 3.4403 | 4.6868 | 4.7521 | 1.1542 | 18.813
| 365 | 4.5202 | 3.2716 | 5.0112 | 3.362 | 1.83 | 17.9949
| 366 | 3.4345 | 2.6959 | 6.3786 | 4.6861 | 1.7878 | 18.9831
| 367 | 3.077 | 3.1328 | 4.9736 | 3.4889 | 1.4609 | 16.1332
| 368 | 4.1882 | 3.5864 | 4.371 | 3.9587 | 1.4267 | 17.5309
| 369 | 3.5738 | 2.3492 | 6.0559 | 3.9325 | 1.5354 | 17.4469
| 370 | 3.4515 | 2.9951 | 5.5589 | 3.6677 | 1.6144 | 17.2877
| 371 | 3.9239 | 2.9687 | 5.6866 | 5.0543 | 1.7322 | 19.3658
| 372 | 3.9218 | 2.9449 | 5.3259 | 3.6638 | 1.5039 | 17.3604
| 373 | 4.7411 | 3.3069 | 4.7422 | 3.7759 | 1.8492 | 18.4152
| 374 | 4.5123 | 2.8261 | 4.9403 | 4.4073 | 1.6011 | 18.287
| 375 | 3.9086 | 2.6578 | 5.7259 | 3.511 | 1.6286 | 17.4319
| 376 | 3.8355 | 2.708 | 6.7784 | 5.2462 | 1.6868 | 20.2549
| 377 | 3.7986 | 3.0265 | 6.275 | 5.4886 | 1.4731 | 20.0618
| 378 | 3.6273 | 3.0673 | 5.5418 | 4.8683 | 1.3953 | 18.5
| 379 | 4.9195 | 2.4482 | 5.0082 | 5.168 | 1.5591 | 19.103
| 380 | 3.9568 | 3.2332 | 6.7552 | 5.7919 | 1.4212 | 21.1583
| 381 | 4.363 | 3.3955 | 5.7495 | 3.3081 | 1.6963 | 18.5125
| 382 | 3.5699 | 2.9357 | 6.1704 | 4.815 | 1.6315 | 19.1226
| 383 | 3.3426 | 3.5267 | 5.7996 | 4.1024 | 1.8037 | 18.5751
| 384 | 4.2228 | 3.0254 | 4.4707 | 4.1537 | 1.8906 | 17.7632
| 385 | 3.9718 | 2.8601 | 5.1081 | 4.4198 | 1.2286 | 17.5883
| 386 | 4.2077 | 3.2496 | 6.5927 | 4.5536 | 1.8108 | 20.4142
| 387 | 4.4003 | 2.85 | 6.6961 | 3.8884 | 1.675 | 19.5098
| 388 | 4.7759 | 2.7982 | 5.639 | 3.3946 | 1.348 | 17.9557
| 389 | 4.1188 | 2.4729 | 4.7643 | 3.455 | 1.5072 | 16.3183
| 390 | 3.9966 | 2.9614 | 6.3457 | 3.5081 | 1.8087 | 18.6204
| 391 | 3.8498 | 2.878 | 7.1936 | 4.0102 | 1.2166 | 19.1481
| 392 | 3.7676 | 3.2946 | 4.9263 | 5.1298 | 1.2584 | 18.3767
| 393 | 4.0607 | 3.0772 | 4.7925 | 4.6417 | 1.0867 | 17.6588
| 394 | 4.6525 | 2.738 | 5.2175 | 4.7315 | 1.9126 | 19.2521
| 395 | 3.9517 | 2.8809 | 4.8175 | 4.8743 | 1.527 | 18.0513
| 396 | 3.412 | 3.5898 | 5.8279 | 3.7274 | 1.6933 | 18.2504
| 397 | 4.1495 | 3.0995 | 5.066 | 4.0188 | 1.1933 | 17.5272
| 398 | 4.5346 | 2.9048 | 5.2232 | 3.3202 | 1.0262 | 17.009
| 399 | 3.4811 | 3.1023 | 6.929 | 5.2767 | 1.5879 | 20.3769
| 400 | 4.3476 | 3.8234 | 7.6356 | 4.1162 | 1.4092 | 21.3319
| 401 | 4.0219 | 2.9008 | 5.9757 | 3.4029 | 1.1575 | 17.4588
| 402 | 4.6253 | 3.4528 | 5.9418 | 4.3134 | 1.6384 | 19.9716
| 403 | 4.101 | 3.1247 | 5.1463 | 4.5719 | 1.6782 | 18.6222
| 404 | 4.7497 | 2.6593 | 7.1563 | 3.7552 | 1.5892 | 19.9096
| 405 | 4.299 | 3.0208 | 5.0767 | 4.2685 | 1.9583 | 18.6232
| 406 | 4.5981 | 3.0387 | 4.5341 | 4.8017 | 1.8903 | 18.863
| 407 | 3.8039 | 3.1036 | 4.9622 | 3.7869 | 1.3029 | 16.9595
| 408 | 3.4948 | 3.7428 | 6.09 | 4.2918 | 1.5867 | 19.2062
| 409 | 3.1668 | 3.4856 | 7.2717 | 4.2996 | 1.121 | 19.3446
| 410 | 3.8638 | 2.8692 | 6.2101 | 4.8883 | 1.4788 | 19.3101
| 411 | 3.7559 | 3.1474 | 4.8894 | 5.0481 | 1.6114 | 18.4522
| 412 | 4.6495 | 3.0117 | 6.0764 | 3.1808 | 1.2016 | 18.12
| 413 | 3.7176 | 3.1062 | 6.2306 | 4.2135 | 1.1474 | 18.4154
| 414 | 4.3677 | 2.5521 | 6.5486 | 4.3906 | 1.6096 | 19.4685
| 415 | 3.7975 | 3.2432 | 5.5212 | 4.6371 | 1.4965 | 18.6954
| 416 | 3.9434 | 3.6705 | 5.2777 | 3.437 | 1.5829 | 17.9115
| 417 | 3.1116 | 2.8709 | 4.4773 | 3.6477 | 1.5602 | 15.6678
| 418 | 3.4688 | 2.7511 | 5.3374 | 3.3308 | 1.4504 | 16.3386
| 419 | 3.8441 | 2.8127 | 6.1528 | 3.5151 | 1.751 | 18.0757
| 420 | 4.3943 | 2.5488 | 5.5054 | 4.5845 | 1.6395 | 18.6724
| 421 | 4.4048 | 2.8913 | 7.0094 | 3.5684 | 1.2219 | 19.0959
| 422 | 3.8733 | 3.4702 | 5.8659 | 3.4112 | 1.658 | 18.2787
| 423 | 3.8131 | 3.2145 | 5.6951 | 3.2818 | 1.6491 | 17.6537
| 424 | 3.5923 | 2.584 | 7.1423 | 5.3077 | 1.5341 | 20.1604
| 425 | 4.0295 | 2.9031 | 5.0994 | 3.7808 | 1.5933 | 17.406
| 426 | 4.1645 | 2.6224 | 6.3155 | 4.6909 | 1.1758 | 18.9691
| 427 | 3.8209 | 3.4172 | 4.2755 | 4.9952 | 1.8654 | 18.3742
| 428 | 3.8398 | 3.501 | 4.5222 | 5.7666 | 1.2698 | 18.8995
| 429 | 3.7487 | 2.9886 | 5.026 | 3.6183 | 1.7788 | 17.1603
| 430 | 3.6693 | 3.1017 | 5.4155 | 3.4753 | 1.3304 | 16.9921
| 431 | 3.4068 | 2.6136 | 6.2898 | 4.146 | 1.4509 | 17.9071
| 432 | 4.6882 | 2.9682 | 5.2828 | 3.275 | 1.4918 | 17.7059
| 433 | 4.1288 | 3.4278 | 4.3316 | 4.4474 | 1.5646 | 17.9002
| 434 | 4.1454 | 3.2614 | 6.1886 | 3.4186 | 1.1763 | 18.1904
| 435 | 4.3224 | 3.0717 | 5.8628 | 3.6514 | 1.4808 | 18.389
| 436 | 3.8679 | 2.4516 | 5.5669 | 3.6615 | 1.6498 | 17.1977
| 437 | 3.6723 | 2.7004 | 6.6059 | 3.5036 | 1.5844 | 18.0665
| 438 | 4.246 | 2.974 | 4.7862 | 4.2162 | 1.5578 | 17.7802
| 439 | 3.7324 | 2.6984 | 6.5172 | 4.0955 | 1.7062 | 18.7498
| 440 | 4.0691 | 2.856 | 5.2079 | 3.1235 | 1.7779 | 17.0343
| 441 | 4.1518 | 2.7426 | 6.0309 | 3.8986 | 1.3729 | 18.197
| 442 | 3.6818 | 2.9222 | 4.5492 | 3.8224 | 1.4973 | 16.4728
| 443 | 3.4242 | 2.5579 | 4.9915 | 3.7829 | 1.6412 | 16.3977
| 444 | 4.1179 | 3.0947 | 4.4338 | 3.9629 | 1.7165 | 17.3258
| 445 | 3.6929 | 3.1911 | 5.2317 | 3.859 | 1.6836 | 17.6584
| 446 | 4.6388 | 2.769 | 4.6056 | 3.9975 | 1.2667 | 17.2776
| 447 | 3.9634 | 3.1466 | 5.5094 | 4.5791 | 1.388 | 18.5865
| 448 | 4.2565 | 3.7484 | 6.5821 | 3.3763 | 1.5376 | 19.5009
| 449 | 3.6494 | 2.2266 | 4.7361 | 3.643 | 1.2576 | 15.5127
| 450 | 3.9973 | 3.2776 | 4.2348 | 3.382 | 1.5647 | 16.4564
| 451 | 3.8541 | 2.6704 | 6.0694 | 5.8578 | 1.5239 | 19.9756
| 452 | 3.2522 | 2.5691 | 6.0066 | 3.8444 | 1.4046 | 17.0768
| 453 | 3.7019 | 2.4266 | 4.628 | 4.1902 | 1.4067 | 16.3535
| 454 | 4.3098 | 2.9914 | 6.161 | 3.1817 | 1.5055 | 18.1494
| 455 | 4.091 | 2.2598 | 4.9185 | 5.6234 | 1.697 | 18.5898
| 456 | 3.9296 | 2.9157 | 5.4974 | 4.8587 | 1.315 | 18.5164
| 457 | 4.2929 | 3.0648 | 4.2523 | 3.2859 | 1.8986 | 16.7946
| 458 | 3.3396 | 2.5767 | 5.1344 | 3.698 | 1.3606 | 16.1094
| 459 | 3.6561 | 2.8571 | 5.6251 | 4.6688 | 1.3295 | 18.1365
| 460 | 4.1824 | 2.9991 | 5.3883 | 3.2825 | 1.7917 | 17.6439
| 461 | 3.4614 | 2.137 | 6.978 | 3.9946 | 1.6155 | 18.1864
| 462 | 4.6029 | 2.4789 | 6.4745 | 5.4748 | 1.7911 | 20.8222
| 463 | 4.4303 | 3.087 | 6.3312 | 3.4794 | 1.2993 | 18.6272
| 464 | 3.7002 | 3.2125 | 4.935 | 4.0557 | 1.6755 | 17.5789
| 465 | 3.6135 | 3.091 | 4.7052 | 4.1791 | 1.8546 | 17.4434
| 466 | 3.7355 | 2.4241 | 7.0357 | 3.3883 | 1.5293 | 18.1129
| 467 | 3.1968 | 3.075 | 4.4252 | 4.1744 | 1.5663 | 16.4378
| 468 | 3.9535 | 3.031 | 5.2972 | 5.7302 | 1.3502 | 19.3622
| 469 | 3.8079 | 2.1974 | 5.7672 | 4.8856 | 1.3434 | 18.0015
| 470 | 4.3235 | 2.9178 | 5.3033 | 3.8869 | 1.0634 | 17.4951
| 471 | 4.0751 | 2.3838 | 7.0166 | 4.3541 | 1.5116 | 19.3412
| 472 | 3.984 | 2.4037 | 4.1105 | 3.8917 | 1.7112 | 16.1012
| 473 | 4.7228 | 3.1921 | 4.9461 | 3.5222 | 1.4976 | 17.8808
| 474 | 4.4803 | 2.8836 | 7.0437 | 3.565 | 1.486 | 19.4585
| 475 | 4.6064 | 3.0434 | 4.9575 | 4.7599 | 1.4321 | 18.7993
| 476 | 3.6808 | 2.7494 | 4.8089 | 3.4843 | 1.8796 | 16.603
| 477 | 3.9827 | 2.7217 | 5.4892 | 5.1944 | 1.3586 | 18.7465
| 478 | 3.6847 | 2.5787 | 6.4989 | 3.4044 | 1.3582 | 17.5249
| 479 | 3.9583 | 3.2345 | 5.1113 | 4.0908 | 1.9897 | 18.3846
| 480 | 4.1778 | 2.8899 | 5.5392 | 5.0104 | 1.4009 | 19.0181
| 481 | 4.4716 | 3.0568 | 5.9962 | 3.5585 | 1.5068 | 18.5899
| 482 | 4.0918 | 3.1631 | 4.9214 | 3.7789 | 1.2602 | 17.2154
| 483 | 4.4932 | 2.5207 | 5.6486 | 3.2463 | 1.1666 | 17.0754
| 484 | 3.7602 | 3.0015 | 5.7089 | 4.038 | 1.0981 | 17.6067
| 485 | 4.5042 | 3.3599 | 6.8505 | 5.6504 | 1.8626 | 22.2276
| 486 | 3.5295 | 3.1983 | 5.6693 | 5.1647 | 1.5141 | 19.076
| 487 | 3.4642 | 3.3646 | 6.4059 | 4.0753 | 1.1501 | 18.4601
| 488 | 3.2787 | 3.609 | 4.9251 | 4.956 | 1.1157 | 17.8845
| 489 | 3.7499 | 3.2207 | 6.4302 | 4.7793 | 1.7662 | 19.9464
| 490 | 3.1273 | 3.6363 | 6.0335 | 4.389 | 1.4228 | 18.6089
| 491 | 3.0927 | 3.6847 | 7.0736 | 5.4559 | 1.6526 | 20.9595
| 492 | 4.7991 | 3.1002 | 6.9093 | 4.0278 | 1.4672 | 20.3037
| 493 | 3.2611 | 2.3787 | 5.6547 | 5.8342 | 1.648 | 18.7768
| 494 | 4.3001 | 2.9665 | 5.273 | 5.0154 | 1.8574 | 19.4124
| 495 | 3.4787 | 3.0932 | 5.2011 | 4.2657 | 1.7853 | 17.8241
| 496 | 4.3252 | 3.481 | 5.3099 | 3.5114 | 1.5748 | 18.2025
| 497 | 4.3645 | 3.3153 | 5.6464 | 4.2527 | 1.2844 | 18.8633
| 498 | 4.1462 | 2.9901 | 5.4049 | 3.5539 | 1.5218 | 17.6169
| 499 | 4.2497 | 3.7954 | 5.3566 | 3.3419 | 1.733 | 18.4767
| 500 | 4.0961 | 2.9982 | 4.948 | 3.8736 | 1.6193 | 17.5351
| 501 | 4.8295 | 2.5622 | 5.6711 | 3.8485 | 1.3658 | 18.2771
| 502 | 3.7656 | 2.6349 | 5.5883 | 4.0698 | 1.3962 | 17.4548
| 503 | 4.7541 | 3.1236 | 5.712 | 3.6836 | 1.3113 | 18.5846
| 504 | 4.642 | 3.1966 | 5.3595 | 4.4858 | 1.3789 | 19.0629
| 505 | 3.6643 | 3.2934 | 5.4024 | 3.6503 | 1.5146 | 17.525
| 506 | 4.6735 | 2.926 | 5.185 | 3.689 | 1.7377 | 18.2112
| 507 | 4.4766 | 2.1265 | 6.0452 | 3.773 | 1.553 | 17.9743
| 508 | 3.3518 | 3.0832 | 5.3832 | 3.193 | 1.6294 | 16.6405
| 509 | 4.2008 | 3.3815 | 7.8326 | 5.3042 | 1.0344 | 21.7535
| 510 | 3.5955 | 3.2392 | 5.2999 | 3.8327 | 1.3346 | 17.302
| 511 | 4.2387 | 2.5397 | 5.2581 | 3.6451 | 1.5242 | 17.2057
| 512 | 3.683 | 3.5996 | 5.446 | 4.5612 | 1.557 | 18.8468
| 513 | 4.1682 | 2.9013 | 6.3101 | 4.0946 | 1.3198 | 18.794
| 514 | 4.429 | 3.1123 | 6.0098 | 4.5174 | 1.2644 | 19.3329
| 515 | 4.1553 | 3.6063 | 5.4583 | 3.4675 | 1.7769 | 18.4643
| 516 | 3.6245 | 2.365 | 7.7583 | 4.1172 | 1.4603 | 19.3253
| 517 | 4.1745 | 2.6174 | 7.3479 | 4.246 | 1.2856 | 19.6714
| 518 | 4.7647 | 2.3686 | 5.4475 | 3.9739 | 1.4143 | 17.969
| 519 | 4.4612 | 2.4402 | 7.1278 | 3.6825 | 1.4315 | 19.1432
| 520 | 3.7339 | 2.9068 | 4.7983 | 4.2979 | 1.0572 | 16.794
| 521 | 3.8524 | 3.5336 | 6.651 | 5.1284 | 1.8468 | 21.0122
| 522 | 4.4495 | 3.0194 | 6.5617 | 4.4643 | 1.6901 | 20.1851
| 523 | 4.9332 | 3.1602 | 5.1533 | 5.204 | 1.487 | 19.9376
| 524 | 4.2144 | 2.7117 | 5.0911 | 3.8807 | 1.3923 | 17.2901
| 525 | 3.895 | 3.4832 | 5.7909 | 4 | 1.511 | 18.6801
| 526 | 4.2711 | 3.5276 | 7.3727 | 3.5819 | 1.2779 | 20.0312
| 527 | 4.22 | 2.2321 | 6.2224 | 4.7831 | 1.7316 | 19.1892
| 528 | 4.8683 | 3.0472 | 5.4232 | 3.5568 | 1.5849 | 18.4804
| 529 | 4.4663 | 2.8257 | 5.0508 | 3.4143 | 1.1519 | 16.9089
| 530 | 4.5912 | 3.1947 | 6.1197 | 3.6006 | 1.5167 | 19.0229
| 531 | 3.5786 | 2.418 | 5.8341 | 3.5697 | 1.7017 | 17.1022
| 532 | 3.9425 | 2.5246 | 4.8031 | 3.9754 | 1.073 | 16.3186
| 533 | 4.3297 | 2.9563 | 6.9834 | 3.7323 | 1.5635 | 19.5651
| 534 | 4.4765 | 2.9796 | 5.1714 | 5.1512 | 1.2685 | 19.0472
| 535 | 3.8815 | 3.2652 | 7.4269 | 4.3146 | 1.8117 | 20.6999
| 536 | 3.3473 | 3.0605 | 4.7145 | 3.5958 | 1.2738 | 15.9919
| 537 | 3.7315 | 2.6042 | 5.6609 | 4.5009 | 1.2179 | 17.7154
| 538 | 4.2176 | 2.6357 | 5.6337 | 4.1852 | 1.3055 | 17.9777
| 539 | 4.1566 | 3.4039 | 4.7782 | 4.0829 | 1.5538 | 17.9754
| 540 | 4.1373 | 2.503 | 4.4307 | 4.217 | 1.5719 | 16.8599
| 541 | 4.3177 | 2.8797 | 4.6436 | 4.3472 | 1.5326 | 17.7209
| 542 | 3.8942 | 3.3517 | 6.8633 | 4.6611 | 1.7537 | 20.5241
| 543 | 3.274 | 3.3764 | 7.529 | 3.4981 | 1.55 | 19.2275
| 544 | 4.0616 | 2.9816 | 5.2254 | 4.8046 | 1.6058 | 18.6791
| 545 | 3.3847 | 2.5983 | 4.5681 | 4.3857 | 1.2411 | 16.1778
| 546 | 3.5567 | 2.4822 | 4.703 | 4.6809 | 1.3464 | 16.7692
| 547 | 4.5428 | 3.0143 | 6.1671 | 3.8356 | 1.7974 | 19.3571
| 548 | 3.8296 | 3.5821 | 6.8808 | 4.2018 | 1.8672 | 20.3615
| 549 | 4.5829 | 3.4676 | 5.8609 | 4.0974 | 1.7045 | 19.7133
| 550 | 3.9908 | 2.7891 | 4.6153 | 5.098 | 1.4737 | 17.9669
| 551 | 4.0056 | 2.9381 | 6.7262 | 3.2419 | 1.503 | 18.4148
| 552 | 4.0477 | 2.6097 | 4.7333 | 4.1329 | 1.6161 | 17.1396
| 553 | 3.4993 | 2.646 | 5.9782 | 4.3391 | 1.2797 | 17.7423
| 554 | 4.4096 | 3.0914 | 6.037 | 3.3983 | 1.194 | 18.1303
| 555 | 4.0653 | 3.0402 | 4.2839 | 3.3603 | 1.6711 | 16.4209
| 556 | 4.3707 | 3.138 | 4.8786 | 3.5177 | 1.3823 | 17.2872
| 557 | 4.0046 | 3.7282 | 6.0207 | 4.5813 | 1.2912 | 19.626
| 558 | 4.312 | 3.5457 | 4.684 | 4.5525 | 1.3877 | 18.4819
| 559 | 3.9885 | 2.9411 | 5.0203 | 3.3156 | 1.2322 | 16.4976
| 560 | 4.2238 | 3.0748 | 5.1494 | 5.6382 | 1.4953 | 19.5815
| 561 | 4.3573 | 2.4906 | 4.7622 | 3.9423 | 1.8329 | 17.3853
| 562 | 4.4633 | 3.21 | 4.7819 | 4.9353 | 1.595 | 18.9855
| 563 | 3.7786 | 2.9712 | 5.0308 | 5.0658 | 1.6854 | 18.5318
| 564 | 3.19 | 3.3106 | 5.5285 | 3.1026 | 1.895 | 17.0267
| 565 | 3.9628 | 2.3947 | 4.9117 | 4.6031 | 1.1794 | 17.0517
| 566 | 4.3156 | 2.5172 | 4.9038 | 3.7941 | 1.5106 | 17.0412
| 567 | 4.7854 | 2.1869 | 7.3381 | 4.0294 | 1.5695 | 19.9093
| 568 | 3.526 | 2.6131 | 4.6665 | 4.785 | 1.21 | 16.8006
| 569 | 4.6971 | 3.3308 | 5.9259 | 5.2396 | 1.2847 | 20.4782
| 570 | 4.2902 | 2.9274 | 5.2565 | 3.9375 | 1.3363 | 17.748
| 571 | 3.7689 | 3.3628 | 6.1808 | 3.5992 | 1.4306 | 18.3423
| 572 | 3.7445 | 3.3398 | 5.1069 | 4.0569 | 1.6722 | 17.9203
| 573 | 3.9573 | 3.1833 | 5.5718 | 3.6055 | 1.631 | 17.949
| 574 | 3.3853 | 3.4129 | 6.5984 | 3.7974 | 1.6147 | 18.8088
| 575 | 4.6812 | 3.3294 | 5.832 | 5.3478 | 1.5564 | 20.7469
| 576 | 3.4724 | 3.0429 | 6.8203 | 4.8315 | 1.4196 | 19.5866
| 577 | 4.8815 | 3.0355 | 6.7718 | 3.7602 | 1.8097 | 20.2587
| 578 | 3.4262 | 3.9369 | 7.3306 | 4.0251 | 1.2745 | 19.9933
| 579 | 3.7934 | 2.5448 | 5.1319 | 3.9551 | 1.0615 | 16.4867
| 580 | 3.815 | 3.0127 | 6.4579 | 3.8636 | 1.4392 | 18.5885
| 581 | 4.3206 | 2.7938 | 6.4106 | 4.459 | 1.6002 | 19.5843
| 582 | 3.6177 | 3.6335 | 4.8126 | 4.4785 | 1.3646 | 17.9069
| 583 | 3.6373 | 3.105 | 7.6786 | 4.2863 | 1.1072 | 19.8144
| 584 | 3.4968 | 2.2909 | 4.7104 | 4.5226 | 1.4885 | 16.5091
| 585 | 3.543 | 3.157 | 7.0909 | 3.5622 | 1.8236 | 19.1766
| 586 | 3.7193 | 2.6322 | 5.1162 | 5.3952 | 1.3049 | 18.1679
| 587 | 3.4922 | 3.1489 | 5.5981 | 3.0734 | 1.3605 | 16.673
| 588 | 4.0486 | 2.6719 | 4.4027 | 3.6871 | 1.7101 | 16.5204
| 589 | 3.3299 | 3.3595 | 5.6431 | 5.3386 | 1.1097 | 18.7808
| 590 | 4.3858 | 3.1899 | 4.5775 | 4.5096 | 1.3398 | 18.0025
| 591 | 4.5823 | 2.0868 | 5.3956 | 3.637 | 1.1699 | 16.8716
| 592 | 4.2646 | 2.8488 | 5.972 | 4.3927 | 1.2298 | 18.7079
| 593 | 4.241 | 2.6332 | 7.1961 | 3.7071 | 1.2543 | 19.0317
| 594 | 3.8661 | 2.1273 | 4.3457 | 5.1032 | 1.7133 | 17.1556
| 595 | 4.1954 | 3.173 | 5.1631 | 4.5388 | 1.1282 | 18.1986
| 596 | 3.1819 | 2.7739 | 6.6931 | 4.3549 | 1.4556 | 18.4594
| 597 | 4.2429 | 3.1276 | 4.6804 | 4.7102 | 1.5033 | 18.2644
| 598 | 3.474 | 3.5922 | 5.9517 | 5.2704 | 1.4037 | 19.692
| 599 | 3.9771 | 2.6999 | 5.6282 | 3.6525 | 1.6393 | 17.5971
| 600 | 4.4344 | 3.5292 | 5.3301 | 3.6621 | 1.3547 | 18.3104
| 601 | 3.8322 | 2.667 | 5.4423 | 4.6643 | 1.0763 | 17.6821
| 602 | 4.7076 | 2.629 | 5.612 | 3.0948 | 1.3129 | 17.3563
| 603 | 4.0376 | 3.0514 | 6.0508 | 4.8429 | 1.4684 | 19.4511
| 604 | 3.8874 | 2.4209 | 5.2924 | 3.8729 | 1.6185 | 17.0921
| 605 | 4.1538 | 3.113 | 6.9244 | 3.9876 | 1.3916 | 19.5703
| 606 | 4.1051 | 3.0452 | 5.7352 | 3.4081 | 1.7214 | 18.0152
| 607 | 4.1916 | 3.2548 | 4.8372 | 3.6418 | 1.8863 | 17.8116
| 608 | 3.4895 | 2.4078 | 5.8478 | 4.0125 | 1.1745 | 16.9321
| 609 | 4.0674 | 3.8133 | 5.035 | 3.4476 | 1.3231 | 17.6864
| 610 | 3.9332 | 3.1823 | 6.7026 | 4.5368 | 1.6234 | 19.9784
| 611 | 3.9058 | 2.7971 | 5.211 | 4.2722 | 1.4311 | 17.617
| 612 | 3.7221 | 2.3761 | 7.222 | 4.565 | 1.7941 | 19.6794
| 613 | 3.8183 | 2.9927 | 5.4138 | 3.4682 | 1.5927 | 17.2857
| 614 | 3.7609 | 3.8651 | 5.7544 | 3.8959 | 1.4129 | 18.6892
| 615 | 3.8765 | 3.7048 | 4.6396 | 4.2932 | 1.3616 | 17.8758
| 616 | 4.2669 | 2.3505 | 7.2451 | 3.5194 | 1.1806 | 18.5624
| 617 | 4.6095 | 2.6275 | 4.6229 | 4.0022 | 1.3496 | 17.2117
| 618 | 4.8598 | 2.4161 | 4.5024 | 3.8159 | 1.1828 | 16.777
| 619 | 4.147 | 3.2383 | 5.9222 | 4.4104 | 1.4338 | 19.1517
| 620 | 3.6051 | 2.8606 | 4.7 | 3.3178 | 1.5689 | 16.0524
| 621 | 4.0707 | 2.3236 | 5.6031 | 4.8647 | 1.6032 | 18.4652
| 622 | 4.1029 | 3.4749 | 4.6623 | 4.0098 | 1.8719 | 18.1218
| 623 | 4.0428 | 3.4242 | 4.9821 | 3.9669 | 1.266 | 17.682
| 624 | 4.3499 | 2.7167 | 5.8157 | 3.5279 | 1.2201 | 17.6302
| 625 | 4.0883 | 3.5687 | 6.3377 | 3.855 | 1.4922 | 19.3419
| 626 | 4.7149 | 2.2532 | 7.0648 | 3.7447 | 1.0706 | 18.8482
| 627 | 4.0538 | 2.7264 | 6.7996 | 4.3503 | 1.5342 | 19.4644
| 628 | 3.2311 | 3.2036 | 6.382 | 4.6526 | 1.4524 | 18.9218
| 629 | 4.2656 | 2.9875 | 7.4421 | 3.4651 | 1.0463 | 19.2067
| 630 | 4.131 | 3.0024 | 4.5264 | 4.1813 | 1.1876 | 17.0288
| 631 | 3.8436 | 2.191 | 6.5043 | 3.8715 | 1.2704 | 17.6808
| 632 | 3.8333 | 2.4469 | 5.3335 | 3.8671 | 1.7521 | 17.2329
| 633 | 3.9931 | 2.6724 | 5.5176 | 3.5893 | 1.559 | 17.3313
| 634 | 4.5524 | 3.4519 | 7.2806 | 3.3808 | 1.6378 | 20.3035
| 635 | 3.9199 | 3.5831 | 5.4769 | 4.7952 | 1.3738 | 19.1489
| 636 | 3.9871 | 3.0166 | 5.7403 | 4.4161 | 1.8196 | 18.9796
| 637 | 3.8715 | 2.5341 | 5.4269 | 4.006 | 1.628 | 17.4665
| 638 | 4.0035 | 2.5129 | 7.1037 | 5.1575 | 1.2938 | 20.0715
| 639 | 3.7695 | 2.7394 | 5.1986 | 3.9507 | 1.3236 | 16.9818
| 640 | 4.2701 | 2.8518 | 5.6565 | 5.6973 | 1.3449 | 19.8207
| 641 | 4.4155 | 3.2815 | 6.3481 | 4.162 | 1.6015 | 19.8086
| 642 | 4.098 | 2.8393 | 5.2701 | 3.9765 | 1.9549 | 18.1387
| 643 | 4.4994 | 3.1188 | 4.7301 | 4.798 | 1.369 | 18.5153
| 644 | 4.4674 | 2.6956 | 4.1876 | 3.6755 | 1.5985 | 16.6247
| 645 | 4.5771 | 3.3367 | 5.0325 | 5.0387 | 1.6094 | 19.5943
| 646 | 4.3594 | 3.4237 | 6.5792 | 3.4253 | 1.1629 | 18.9505
| 647 | 4.3903 | 3.7893 | 5.7878 | 3.5778 | 1.3688 | 18.914
| 648 | 4.0018 | 3.645 | 4.6172 | 4.5348 | 1.7654 | 18.5642
| 649 | 4.5289 | 2.9786 | 5.7382 | 4.1485 | 1.2385 | 18.6327
| 650 | 4.3533 | 2.4371 | 6.0941 | 4.0723 | 1.5725 | 18.5293
| 651 | 4.2889 | 2.6528 | 6.0782 | 4.6575 | 1.5204 | 19.1979
| 652 | 4.4233 | 2.3869 | 4.7256 | 4.9689 | 1.5768 | 18.0815
| 653 | 4.3985 | 3.0036 | 7.2369 | 3.8534 | 1.2443 | 19.7367
| 654 | 4.4317 | 2.9541 | 6.2632 | 4.7748 | 1.5085 | 19.9322
| 655 | 3.9789 | 2.9628 | 5.1825 | 5.4173 | 1.6122 | 19.1538
| 656 | 3.6888 | 3.1642 | 5.2498 | 3.1222 | 1.0908 | 16.3158
| 657 | 3.6015 | 3.213 | 4.3258 | 5.5305 | 1.1973 | 17.868
| 658 | 4.5606 | 2.1157 | 7.1684 | 4.1714 | 1.2114 | 19.2276
| 659 | 3.9525 | 3.0051 | 4.7506 | 3.703 | 1.5483 | 16.9595
| 660 | 3.6226 | 3.6369 | 5.2132 | 3.8168 | 1.7078 | 17.9974
| 661 | 3.6291 | 2.3159 | 4.8728 | 4.2497 | 1.4742 | 16.5418
| 662 | 3.5236 | 2.9698 | 7.2617 | 5.0764 | 1.441 | 20.2726
| 663 | 4.1317 | 2.8978 | 5.8234 | 3.6217 | 1.3065 | 17.7812
| 664 | 4.5247 | 2.9417 | 4.4403 | 3.9831 | 1.5802 | 17.4701
| 665 | 3.5393 | 3.1434 | 4.3469 | 3.4782 | 1.4896 | 15.9973
| 666 | 3.7909 | 3.5732 | 5.7321 | 4.1078 | 1.4769 | 18.6809
| 667 | 4.826 | 2.946 | 4.8504 | 3.8277 | 1.4591 | 17.9092
| 668 | 4.3383 | 2.3163 | 6.8699 | 3.4596 | 1.8834 | 18.8674
| 669 | 3.5644 | 3.4313 | 7.3815 | 3.2369 | 1.4244 | 19.0385
| 670 | 4.3077 | 3.1617 | 6.5655 | 5.5111 | 1.2066 | 20.7526
| 671 | 3.2133 | 3.4331 | 4.9275 | 3.6358 | 1.3837 | 16.5933
| 672 | 4.4533 | 2.6628 | 4.5308 | 5.1463 | 1.68 | 18.4732
| 673 | 4.0967 | 3.0548 | 4.8298 | 5.7402 | 1.7176 | 19.4391
| 674 | 4.6587 | 3.2103 | 5.5955 | 4.7414 | 1.5966 | 19.8025
| 675 | 4.0897 | 3.0191 | 7.5104 | 4.653 | 1.8406 | 21.1128
| 676 | 3.9955 | 3.2694 | 5.8094 | 4.4023 | 1.5611 | 19.0379
| 677 | 3.8547 | 3.3416 | 6.8886 | 5.1344 | 1.3937 | 20.6129
| 678 | 4.0246 | 2.6896 | 5.6182 | 3.5808 | 1.7979 | 17.7112
| 679 | 3.3541 | 2.3266 | 6.3562 | 3.4772 | 1.3517 | 16.8658
| 680 | 3.8691 | 3.4364 | 4.3357 | 3.788 | 1.6041 | 17.0334
| 681 | 4.2963 | 3.01 | 6.7101 | 4.1648 | 1.7897 | 19.971
| 682 | 4.0703 | 3.7854 | 5.3964 | 4.0878 | 1.6073 | 18.9472
| 683 | 3.8252 | 3.8289 | 7.5552 | 4.9388 | 1.8158 | 21.9638
| 684 | 4.1358 | 2.845 | 5.2676 | 4.4662 | 1.7004 | 18.4149
| 685 | 4.084 | 2.8884 | 7.5892 | 3.4816 | 1.5149 | 19.5582
| 686 | 3.8229 | 2.0758 | 5.0786 | 3.9041 | 1.7408 | 16.6222
| 687 | 4.1794 | 3.9067 | 4.7694 | 5.0076 | 1.4292 | 19.2923
| 688 | 3.4818 | 2.7885 | 5.5383 | 5.9668 | 1.8138 | 19.5892
| 689 | 3.2477 | 2.9851 | 7.1309 | 4.2791 | 1.5401 | 19.1829
| 690 | 3.6508 | 2.5646 | 4.9641 | 4.4451 | 1.4334 | 17.0579
| 691 | 3.7209 | 3.4566 | 6.027 | 3.2777 | 1.556 | 18.0382
| 692 | 3.0457 | 2.3389 | 5.4099 | 3.8625 | 1.367 | 16.0241
| 693 | 3.5188 | 3.5639 | 4.8228 | 4.1961 | 1.5915 | 17.6932
| 694 | 3.6543 | 3.0843 | 4.9945 | 3.7114 | 1.586 | 17.0304
| 695 | 4.0387 | 3.5487 | 5.7506 | 3.9599 | 1.3983 | 18.6962
| 696 | 4.3042 | 2.9898 | 6.2929 | 4.4849 | 1.6918 | 19.7635
| 697 | 4.2064 | 2.4143 | 5.9427 | 3.3329 | 1.5596 | 17.4559
| 698 | 4.0223 | 3.2801 | 4.4231 | 3.7912 | 1.1332 | 16.6499
| 699 | 4.0669 | 3.7349 | 5.7236 | 4.5193 | 1.227 | 19.2716
| 700 | 4.0029 | 2.8622 | 5.5637 | 4.8975 | 1.6066 | 18.933
| 701 | 3.8384 | 2.5317 | 6.9862 | 3.7173 | 1.226 | 18.2995
| 702 | 3.3351 | 3.478 | 7.4654 | 3.8061 | 1.4109 | 19.4955
| 703 | 3.7422 | 2.5497 | 6.4725 | 3.7549 | 1.2188 | 17.7381
| 704 | 3.7288 | 2.8439 | 5.9128 | 4.4042 | 1.6209 | 18.5107
| 705 | 3.8606 | 2.7344 | 6.5295 | 4.5049 | 1.4907 | 19.1201
| 706 | 3.5102 | 3.3468 | 5.7934 | 3.9651 | 1.6251 | 18.2406
| 707 | 3.9399 | 2.5182 | 6.3398 | 3.4387 | 1.7815 | 18.0182
| 708 | 4.3766 | 3.6536 | 5.3523 | 4.5686 | 1.458 | 19.4091
| 709 | 4.4111 | 3.1534 | 5.276 | 3.8854 | 1.4534 | 18.1792
| 710 | 4.531 | 2.8628 | 5.0538 | 3.4295 | 1.749 | 17.6261
| 711 | 4.2933 | 2.5281 | 5.6863 | 3.9534 | 1.689 | 18.1501
| 712 | 4.2044 | 3.4066 | 6.2151 | 4.2275 | 1.8464 | 19.9
| 713 | 3.5837 | 2.6754 | 6.2009 | 4.9861 | 1.6938 | 19.1399
| 714 | 3.9167 | 2.4872 | 6.9197 | 4.9197 | 1.5484 | 19.7918
| 715 | 4.4056 | 3.5066 | 5.2144 | 4.7617 | 1.5451 | 19.4333
| 716 | 3.9344 | 2.7771 | 5.5822 | 3.3912 | 1.6572 | 17.3421
| 717 | 3.457 | 3.2179 | 5.6376 | 3.5533 | 1.2466 | 17.1123
| 718 | 3.796 | 2.8722 | 4.4491 | 5.1704 | 1.6819 | 17.9695
| 719 | 3.772 | 3.3993 | 5.3529 | 3.3532 | 1.3808 | 17.2583
| 720 | 3.971 | 3.1421 | 5.0849 | 3.3743 | 1.3408 | 16.913
| 721 | 4.7699 | 3.0221 | 5.756 | 4.7881 | 1.7707 | 20.1068
| 722 | 3.7516 | 2.2952 | 5.7752 | 3.8412 | 1.5078 | 17.1711
| 723 | 4.5971 | 2.9803 | 5.8033 | 4.5233 | 1.8349 | 19.739
| 724 | 3.7462 | 2.8587 | 5.7463 | 4.5748 | 1.8047 | 18.7308
| 725 | 4.4027 | 3.2289 | 4.8792 | 4.0991 | 1.6049 | 18.2148
| 726 | 4.055 | 3.6299 | 4.789 | 4.2244 | 1.2371 | 17.9353
| 727 | 4.172 | 2.873 | 5.785 | 3.7043 | 1.1886 | 17.7229
| 728 | 4.1717 | 2.72 | 4.716 | 4.3713 | 1.5057 | 17.4847
| 729 | 3.5034 | 3.1162 | 6.9551 | 3.4716 | 1.1121 | 18.1585
| 730 | 4.2383 | 2.7936 | 5.5786 | 4.3815 | 1.6767 | 18.6687
| 731 | 4.1383 | 2.432 | 7.0845 | 5.6688 | 1.5552 | 20.8788
| 732 | 4.2593 | 3.0651 | 6.2182 | 3.1541 | 1.5665 | 18.2632
| 733 | 4.2488 | 3.0048 | 7.2121 | 5.3608 | 1.4705 | 21.297
| 734 | 4.7459 | 2.587 | 4.9515 | 3.3961 | 1.8784 | 17.5588
| 735 | 3.754 | 3.0935 | 5.8179 | 4.4337 | 1.5302 | 18.6294
| 736 | 3.5727 | 2.5477 | 4.8007 | 3.3697 | 1.1708 | 15.4615
| 737 | 4.0467 | 3.1364 | 5.0137 | 4.4698 | 1.2787 | 17.9452
| 738 | 4.3446 | 3.028 | 7.1465 | 3.3342 | 1.4342 | 19.2875
| 739 | 3.6412 | 2.8035 | 5.4567 | 4.0342 | 1.4849 | 17.4207
| 740 | 3.6708 | 2.6157 | 5.3754 | 3.9682 | 1.5387 | 17.1689
| 741 | 3.4124 | 2.949 | 5.5227 | 4.6774 | 1.8516 | 18.4132
| 742 | 3.9037 | 2.515 | 6.6706 | 4.2961 | 1.5975 | 18.9828
| 743 | 3.3143 | 2.9218 | 4.4804 | 3.8299 | 1.8205 | 16.3669
| 744 | 4.0266 | 3.2576 | 6.758 | 3.6807 | 1.4668 | 19.1896
| 745 | 4.3349 | 3.561 | 4.3985 | 3.5969 | 1.4378 | 17.329
| 746 | 4.079 | 3.155 | 5.2055 | 4.9283 | 1.5313 | 18.8991
| 747 | 4.4422 | 3.0821 | 5.1274 | 4.6306 | 1.3217 | 18.604
| 748 | 3.8805 | 2.775 | 4.6975 | 4.6731 | 1.4282 | 17.4542
| 749 | 4.5353 | 2.79 | 6.0237 | 3.8031 | 1.416 | 18.5682
| 750 | 3.8375 | 2.4299 | 5.601 | 4.4186 | 1.4968 | 17.7838
| 751 | 4.2096 | 2.6024 | 6.4239 | 4.6059 | 1.5836 | 19.4254
| 752 | 3.9001 | 2.7434 | 5.4117 | 4.9628 | 1.265 | 18.2829
| 753 | 3.6113 | 2.4562 | 6.0133 | 4.6477 | 1.6611 | 18.3896
| 754 | 4.3743 | 3.5422 | 5.2883 | 5.1177 | 1.2049 | 19.5273
| 755 | 4.0818 | 2.9936 | 6.9367 | 4.0315 | 1.2559 | 19.2996
| 756 | 3.9991 | 2.9042 | 5.2365 | 5.5341 | 1.6592 | 19.3331
| 757 | 3.4841 | 2.8741 | 4.7728 | 3.6028 | 1.5278 | 16.2617
| 758 | 3.2427 | 3.4015 | 5.9357 | 3.1303 | 1.2611 | 16.9714
| 759 | 4.5936 | 2.675 | 6.1792 | 4.0417 | 1.4568 | 18.9464
| 760 | 3.8422 | 3.049 | 5.8134 | 4.14 | 1.6954 | 18.54
| 761 | 4.1841 | 2.3105 | 6.0414 | 4.193 | 1.5492 | 18.2783
| 762 | 3.4049 | 2.444 | 6.2799 | 4.7013 | 1.4407 | 18.2709
| 763 | 4.0292 | 2.7953 | 4.9755 | 3.4908 | 1.9384 | 17.2292
| 764 | 3.3695 | 2.7724 | 5.7017 | 3.3903 | 1.6649 | 16.8987
| 765 | 4.7008 | 3.364 | 5.5352 | 3.5456 | 1.0544 | 18.1999
| 766 | 4.0772 | 2.8068 | 6.3863 | 3.1646 | 1.679 | 18.1139
| 767 | 4.1741 | 3.5522 | 5.7074 | 4.1349 | 1.5013 | 19.0699
| 768 | 3.7051 | 2.8851 | 6.7657 | 4.5696 | 1.6625 | 19.588
| 769 | 3.9758 | 2.5595 | 5.4686 | 4.2056 | 1.4817 | 17.6911
| 770 | 4.026 | 2.5891 | 5.3643 | 3.67 | 1.1687 | 16.8181
| 771 | 4.6796 | 3.0588 | 5.43 | 4.0175 | 1.5511 | 18.737
| 772 | 4.6538 | 2.9325 | 6.9019 | 5.4254 | 1.6734 | 21.5871
| 773 | 4.3283 | 2.9576 | 6.8343 | 3.7675 | 1.5094 | 19.3972
| 774 | 3.6668 | 2.4893 | 7.186 | 3.6968 | 1.5781 | 18.617
| 775 | 3.594 | 3.2439 | 6.5407 | 5.2299 | 1.3648 | 19.9733
| 776 | 3.8973 | 3.3848 | 4.4671 | 3.9157 | 1.2254 | 16.8903
| 777 | 3.5171 | 2.1561 | 7.7024 | 3.5727 | 1.7627 | 18.711
| 778 | 3.7376 | 3.9771 | 6.5307 | 5.7787 | 1.4939 | 21.518
| 779 | 3.5089 | 3.5326 | 7.0519 | 5.4667 | 1.801 | 21.3611
| 780 | 4.1873 | 2.3059 | 6.5363 | 3.971 | 1.3099 | 18.3104
| 781 | 4.6965 | 3.6044 | 7.1648 | 5.408 | 1.7957 | 22.6694
| 782 | 3.2592 | 2.9869 | 4.2165 | 4.1252 | 1.4396 | 16.0273
| 783 | 3.7096 | 2.7449 | 5.6225 | 5.5196 | 1.333 | 18.9296
| 784 | 3.919 | 3.506 | 4.8604 | 3.3671 | 1.5773 | 17.2298
| 785 | 4.2028 | 3.3453 | 6.1388 | 4.0615 | 1.2901 | 19.0385
| 786 | 4.3466 | 3.2508 | 5.5863 | 3.4731 | 1.2834 | 17.9402
| 787 | 3.5015 | 2.6822 | 4.6735 | 3.894 | 1.2621 | 16.0134
| 788 | 4.4737 | 3.1145 | 7.6403 | 4.5448 | 1.3667 | 21.14
| 789 | 3.8023 | 2.3027 | 6.5703 | 4.7469 | 1.4006 | 18.8228
| 790 | 4.4374 | 3.6001 | 6.9397 | 5.2117 | 1.6693 | 21.8582
| 791 | 3.8346 | 3.2478 | 5.0408 | 3.6263 | 1.2494 | 16.9988
| 792 | 4.6428 | 3.2301 | 5.7711 | 5.035 | 1.3721 | 20.0511
| 793 | 3.5526 | 3.4436 | 5.6168 | 4.616 | 1.5324 | 18.7615
| 794 | 3.4392 | 2.3627 | 6.7467 | 3.3048 | 1.7464 | 17.5999
| 795 | 4.3894 | 2.2344 | 5.2286 | 5.1824 | 1.1585 | 18.1932
| 796 | 3.6043 | 3.3781 | 5.7583 | 4.423 | 1.4656 | 18.6293
| 797 | 4.3109 | 2.0532 | 5.7826 | 5.354 | 1.4237 | 18.9244
| 798 | 3.6619 | 2.8428 | 5.5521 | 3.5479 | 1.2946 | 16.8992
| 799 | 4.0233 | 3.3169 | 5.3908 | 4.3286 | 1.2598 | 18.3195
| 800 | 3.8008 | 2.9111 | 6.7341 | 4.2758 | 1.2456 | 18.9673
| 801 | 4.5387 | 2.8024 | 6.5209 | 4.0857 | 1.7033 | 19.6511
| 802 | 4.0583 | 2.5703 | 5.5333 | 3.08 | 1.8051 | 17.047
| 803 | 4.5118 | 2.6616 | 4.5919 | 3.9259 | 1.3758 | 17.0669
| 804 | 4.4381 | 3.2193 | 6.8372 | 4.015 | 1.9155 | 20.425
| 805 | 3.1727 | 3.6573 | 4.8717 | 3.7662 | 1.5902 | 17.058
| 806 | 3.9414 | 2.6912 | 5.5567 | 4.6103 | 1.1016 | 17.9012
| 807 | 3.6952 | 3.3387 | 6.1299 | 4.0065 | 1.7139 | 18.8842
| 808 | 3.4176 | 2.9733 | 5.189 | 4.11 | 1.6794 | 17.3693
| 809 | 3.7262 | 3.5952 | 6.2669 | 4.9146 | 1.0959 | 19.5989
| 810 | 4.7621 | 2.7589 | 5.0564 | 3.7216 | 1.6461 | 17.9451
| 811 | 3.5511 | 3.5542 | 6.0674 | 5.4348 | 1.3636 | 19.9711
| 812 | 4.2131 | 3.3667 | 5.8964 | 4.1186 | 1.6882 | 19.2831
| 813 | 3.8851 | 2.7616 | 5.432 | 3.4436 | 1.223 | 16.7453
| 814 | 4.5244 | 3.2413 | 5.8286 | 3.7006 | 1.5443 | 18.8392
| 815 | 3.8746 | 3.3498 | 5.5131 | 3.4307 | 1.6826 | 17.8508
| 816 | 3.7818 | 3.6599 | 5.0223 | 3.4501 | 1.4241 | 17.3381
| 817 | 3.697 | 2.215 | 4.7968 | 5.4485 | 1.3988 | 17.5561
| 818 | 4.1511 | 3.8019 | 5.2537 | 3.8973 | 1.4351 | 18.539
| 819 | 4.1761 | 3.7724 | 5.9655 | 5.3173 | 1.4691 | 20.7004
| 820 | 4.1427 | 3.1658 | 4.9884 | 3.592 | 1.3461 | 17.2349
| 821 | 4.0197 | 2.3983 | 4.72 | 3.8287 | 1.1658 | 16.1324
| 822 | 4.314 | 2.7565 | 5.0643 | 3.7249 | 1.7548 | 17.6146
| 823 | 4.4705 | 3.6218 | 4.4945 | 3.7393 | 1.7889 | 18.1149
| 824 | 3.9752 | 3.3477 | 7.0469 | 3.9096 | 1.4252 | 19.7047
| 825 | 3.5897 | 3.3178 | 5.1939 | 3.1417 | 1.4139 | 16.657
| 826 | 4.3875 | 3.0236 | 7.5043 | 3.2704 | 1.5514 | 19.7372
| 827 | 3.3458 | 3.494 | 6.493 | 4.4891 | 1.3553 | 19.1772
| 828 | 4.0207 | 3.5383 | 6.7944 | 4.8336 | 1.5923 | 20.7794
| 829 | 4.0326 | 3.4258 | 4.9434 | 5.3294 | 1.1036 | 18.8348
| 830 | 3.9554 | 2.4842 | 6.0816 | 5.5694 | 1.3207 | 19.4113
| 831 | 4.0133 | 3.3738 | 6.7894 | 3.4221 | 1.5157 | 19.1143
| 832 | 3.5373 | 2.7364 | 6.3253 | 4.5992 | 1.5524 | 18.7506
| 833 | 4.1301 | 2.8344 | 4.94 | 4.5071 | 1.383 | 17.7947
| 834 | 3.5339 | 3.8377 | 5.2651 | 4.1144 | 1.8606 | 18.6117
| 835 | 3.3005 | 2.7096 | 5.9924 | 4.5637 | 1.2977 | 17.8639
| 836 | 3.6204 | 3.1453 | 6.4898 | 3.3054 | 1.4613 | 18.0222
| 837 | 3.3601 | 2.6929 | 5.1357 | 3.7522 | 1.463 | 16.404
| 838 | 4.193 | 2.8658 | 4.882 | 3.9929 | 1.4374 | 17.371
| 839 | 3.4519 | 2.8472 | 5.4945 | 5.0313 | 1.8436 | 18.6686
| 840 | 3.5764 | 2.6656 | 5.4827 | 3.2296 | 1.3909 | 16.3452
| 841 | 4.1211 | 2.9842 | 7.1778 | 4.3034 | 1.378 | 19.9646
| 842 | 3.9785 | 3.231 | 4.8558 | 3.4873 | 1.2213 | 16.774
| 843 | 4.2419 | 2.607 | 5.4497 | 3.1115 | 1.8431 | 17.2532
| 844 | 4.1087 | 3.1688 | 7.4331 | 5.7142 | 1.4364 | 21.8612
| 845 | 3.8107 | 3.6752 | 5.8779 | 3.3366 | 1.8151 | 18.5155
| 846 | 4.1063 | 3.1202 | 5.5919 | 3.195 | 1.3563 | 17.3697
| 847 | 3.59 | 3.1961 | 5.4748 | 3.746 | 1.362 | 17.3691
| 848 | 4.1598 | 2.5075 | 6.0541 | 4.9532 | 1.7456 | 19.4202
| 849 | 4.0274 | 2.8667 | 4.5692 | 4.0799 | 1.7395 | 17.2827
| 850 | 4.2606 | 3.5156 | 4.6709 | 4.0679 | 1.9292 | 18.4441
| 851 | 3.307 | 3.7538 | 6.3711 | 4.4748 | 1.2134 | 19.1201
| 852 | 3.2691 | 2.5943 | 5.1296 | 3.6903 | 1.3323 | 16.0157
| 853 | 3.8519 | 2.3883 | 6.2569 | 3.8368 | 1.6026 | 17.9365
| 854 | 3.9094 | 2.5801 | 5.6512 | 4.2822 | 1.6276 | 18.0505
| 855 | 3.7128 | 2.93 | 4.915 | 4.5294 | 1.2986 | 17.3858
| 856 | 3.9801 | 2.1711 | 5.3994 | 3.4709 | 1.5351 | 16.5566
| 857 | 4.5501 | 2.9339 | 5.3698 | 3.4937 | 1.4598 | 17.8073
| 858 | 4.6113 | 3.5108 | 6.5233 | 3.3439 | 1.4791 | 19.4683
| 859 | 3.7234 | 3.7231 | 5.3623 | 3.1709 | 1.1951 | 17.1749
| 860 | 3.9351 | 2.8909 | 4.458 | 4.9771 | 1.8844 | 18.1454
| 861 | 4.8473 | 2.6233 | 4.4981 | 3.812 | 1.6216 | 17.4023
| 862 | 3.2848 | 3.7028 | 4.3535 | 3.3678 | 1.5173 | 16.2262
| 863 | 4.0084 | 2.976 | 4.8962 | 4.3492 | 1.4215 | 17.6512
| 864 | 3.7877 | 2.2068 | 6.6161 | 4.2597 | 1.513 | 18.3833
| 865 | 3.5609 | 2.6199 | 7.2289 | 4.0584 | 1.664 | 19.1322
| 866 | 3.3777 | 3.3802 | 4.9773 | 4.55 | 1.307 | 17.5923
| 867 | 4.1444 | 2.2221 | 4.9057 | 3.3553 | 1.2955 | 15.923
| 868 | 3.6371 | 3.2603 | 6.0989 | 4.2403 | 1.9754 | 19.212
| 869 | 4.4867 | 3.383 | 6.3235 | 5.0949 | 1.6227 | 20.9108
| 870 | 3.9543 | 2.8875 | 4.6893 | 3.7338 | 1.2053 | 16.4701
| 871 | 3.9706 | 2.1839 | 4.919 | 3.5328 | 1.3375 | 15.9438
| 872 | 4.6699 | 3.4585 | 5.3101 | 3.2955 | 1.4617 | 18.1958
| 873 | 4.6645 | 3.5578 | 5.2434 | 4.219 | 1.6261 | 19.3108
| 874 | 3.5066 | 3.3944 | 4.1929 | 3.7094 | 1.5429 | 16.3462
| 875 | 3.9249 | 2.9328 | 4.2419 | 4.2786 | 1.6441 | 17.0223
| 876 | 4.0863 | 2.2027 | 4.7232 | 5.2641 | 1.9103 | 18.1866
| 877 | 4.8578 | 2.5045 | 5.6654 | 3.2083 | 1.4689 | 17.7049
| 878 | 4.1646 | 2.1511 | 5.0735 | 4.4498 | 1.3002 | 17.1392
| 879 | 3.8117 | 2.9979 | 5.7185 | 3.6997 | 1.5196 | 17.7473
| 880 | 3.8653 | 3.2647 | 5.7723 | 3.3786 | 1.8366 | 18.1175
| 881 | 4.4131 | 2.4742 | 6.6274 | 4.2583 | 1.4078 | 19.1808
| 882 | 3.7838 | 2.7873 | 6.4484 | 3.264 | 1.3934 | 17.6769
| 883 | 3.661 | 2.7467 | 4.5376 | 3.4637 | 1.5756 | 15.9845
| 884 | 4.5785 | 3.0298 | 7.2877 | 4.879 | 1.7229 | 21.4978
| 885 | 3.817 | 2.9442 | 6.3583 | 3.035 | 1.5701 | 17.7246
| 886 | 4.1624 | 2.7545 | 5.5835 | 3.6141 | 1.6358 | 17.7502
| 887 | 4.0152 | 3.4105 | 6.6132 | 4.1603 | 1.3887 | 19.5878
| 888 | 3.4648 | 2.5373 | 4.9794 | 3.4343 | 1.3288 | 15.7447
| 889 | 4.1614 | 2.9198 | 4.9298 | 4.2743 | 1.488 | 17.7734
| 890 | 3.4873 | 3.3913 | 4.3684 | 4.4617 | 1.4435 | 17.1521
| 891 | 4.1244 | 2.3437 | 5.5758 | 3.312 | 1.3388 | 16.6947
| 892 | 3.3941 | 2.9771 | 5.0878 | 5.0178 | 1.5979 | 18.0746
| 893 | 3.824 | 3.3083 | 6.8408 | 3.6068 | 1.7253 | 19.3053
| 894 | 4.6351 | 3.4152 | 6.639 | 4.8567 | 1.368 | 20.914
| 895 | 3.8627 | 2.8805 | 5.0403 | 5.2586 | 1.6428 | 18.6849
| 896 | 4.1126 | 3.1424 | 5.1911 | 5.4016 | 1.1169 | 18.9645
| 897 | 4.0931 | 3.225 | 4.5153 | 3.2675 | 1.905 | 17.0059
| 898 | 3.8457 | 2.8205 | 5.0497 | 3.5212 | 1.3764 | 16.6134
| 899 | 3.2074 | 3.1097 | 4.3055 | 4.3073 | 1.268 | 16.1979
| 900 | 3.4548 | 3.1307 | 4.9973 | 3.5794 | 1.8973 | 17.0594
| 901 | 4.8052 | 3.1786 | 5.6311 | 3.5028 | 1.6603 | 18.778
| 902 | 3.5571 | 2.53 | 4.4461 | 3.8834 | 1.7035 | 16.12
| 903 | 4.6621 | 2.9124 | 6.8971 | 3.2236 | 1.4708 | 19.1661
| 904 | 4.197 | 3.2914 | 4.5197 | 3.2994 | 1.5118 | 16.8193
| 905 | 4.1074 | 3.1989 | 4.967 | 3.1471 | 1.1842 | 16.6047
| 906 | 4.5562 | 3.5461 | 6.6587 | 3.878 | 1.1458 | 19.7848
| 907 | 3.9119 | 3.3558 | 6.3726 | 3.936 | 1.7016 | 19.2779
| 908 | 4.4333 | 2.763 | 7.4011 | 3.8342 | 1.4104 | 19.842
| 909 | 4.4914 | 3.4025 | 4.4113 | 4.362 | 1.5706 | 18.2379
| 910 | 4.6933 | 3.6486 | 5.6927 | 4.3312 | 1.43 | 19.7958
| 911 | 4.2868 | 3.5556 | 6.7826 | 5.1051 | 1.7933 | 21.5234
| 912 | 4.6856 | 3.7187 | 6.4143 | 4.3242 | 1.4356 | 20.5784
| 913 | 3.7915 | 2.3072 | 4.6662 | 3.3839 | 1.4149 | 15.5637
| 914 | 3.6459 | 2.2885 | 6.9648 | 3.9443 | 1.7161 | 18.5597
| 915 | 4.1812 | 3.2072 | 7.7242 | 4.1755 | 1.3282 | 20.6164
| 916 | 3.4468 | 3.7116 | 7.4543 | 4.9474 | 1.2241 | 20.7841
| 917 | 3.3914 | 3.2836 | 7.0261 | 4.7065 | 1.6949 | 20.1024
| 918 | 3.5218 | 3.0174 | 7.3204 | 3.4579 | 1.4659 | 18.7833
| 919 | 3.644 | 2.3592 | 5.0057 | 4.3954 | 1.0416 | 16.446
| 920 | 4.5544 | 2.9481 | 4.937 | 4.4921 | 1.4273 | 18.359
| 921 | 3.8793 | 3.2728 | 4.1495 | 5.6021 | 1.2528 | 18.1565
| 922 | 3.809 | 3.6178 | 6.4439 | 4.338 | 1.7187 | 19.9274
| 923 | 4.0339 | 2.6052 | 6.308 | 3.9214 | 1.5548 | 18.4233
| 924 | 4.0389 | 3.5178 | 6.828 | 4.0025 | 1.8177 | 20.2049
| 925 | 4.0734 | 2.4551 | 6.5067 | 3.5295 | 1.4758 | 18.0406
| 926 | 4.0314 | 3.1708 | 5.0289 | 3.9302 | 1.3486 | 17.51
| 927 | 4.4891 | 2.7798 | 5.798 | 4.0364 | 1.3355 | 18.4387
| 928 | 4.3442 | 3.7619 | 7.3636 | 4.3427 | 1.3083 | 21.1206
| 929 | 3.6986 | 2.342 | 6.1446 | 3.9852 | 1.3707 | 17.5412
| 930 | 3.398 | 3.1178 | 6.1233 | 3.7228 | 1.319 | 17.6809
| 931 | 3.7162 | 2.9167 | 6.1147 | 3.3864 | 1.7436 | 17.8777
| 932 | 3.4158 | 3.4632 | 6.4181 | 4.21 | 1.5358 | 19.0429
| 933 | 4.3018 | 2.5545 | 5.1581 | 3.9084 | 1.5819 | 17.5046
| 934 | 3.6426 | 2.8645 | 5.9813 | 4.9004 | 1.8292 | 19.218
| 935 | 4.0069 | 2.9399 | 6.704 | 5.3706 | 1.4441 | 20.4656
| 936 | 4.1147 | 3.4463 | 5.2305 | 3.8082 | 1.6812 | 18.2808
| 937 | 3.8469 | 2.8276 | 5.0268 | 3.1346 | 1.5732 | 16.409
| 938 | 3.3961 | 2.8117 | 4.9134 | 3.3242 | 1.5997 | 16.0451
| 939 | 3.4267 | 3.0319 | 5.8852 | 4.7174 | 1.5372 | 18.5983
| 940 | 4.1858 | 2.7048 | 4.3022 | 5.2957 | 1.3577 | 17.8462
| 941 | 4.3057 | 3.0001 | 7.4892 | 5.464 | 1.4055 | 21.6645
| 942 | 4.0118 | 2.7296 | 4.8351 | 4.8484 | 1.6987 | 18.1235
| 943 | 3.8487 | 3.2824 | 5.7208 | 3.6664 | 1.4956 | 18.014
| 944 | 3.9143 | 3.4084 | 5.2214 | 4.6273 | 1.8755 | 19.0469
| 945 | 4.5009 | 2.591 | 6.8014 | 3.4019 | 1.4894 | 18.7846
| 946 | 3.9386 | 3.241 | 5.7782 | 3.9463 | 1.4984 | 18.4024
| 947 | 4.3554 | 3.5089 | 6.8545 | 4.2355 | 1.4781 | 20.4324
| 948 | 3.8057 | 3.179 | 6.4852 | 3.4612 | 1.4532 | 18.3844
| 949 | 4.801 | 2.953 | 4.6347 | 4.4136 | 1.4477 | 18.25
| 950 | 3.6126 | 3.2677 | 5.1017 | 3.924 | 1.6187 | 17.5245
| 951 | 3.381 | 3.1107 | 5.1135 | 3.3587 | 1.8521 | 16.8161
| 952 | 4.3846 | 2.4113 | 5.2416 | 3.784 | 1.4039 | 17.2253
| 953 | 3.5989 | 2.9237 | 4.6934 | 3.9795 | 1.727 | 16.9225
| 954 | 3.7589 | 3.2087 | 5.8894 | 3.9029 | 1.445 | 18.205
| 955 | 3.7655 | 3.2535 | 6.4519 | 4.3171 | 1.2432 | 19.0311
| 956 | 3.6393 | 2.7812 | 5.3125 | 4.8182 | 1.6169 | 18.1682
| 957 | 4.834 | 2.9525 | 5.6751 | 5.1757 | 1.5061 | 20.1435
| 958 | 4.0188 | 3.016 | 6.2365 | 4.7143 | 1.475 | 19.4607
| 959 | 3.084 | 3.5942 | 5.1814 | 4.3228 | 1.838 | 18.0204
| 960 | 4.0629 | 2.8762 | 4.7476 | 4.1371 | 1.4115 | 17.2353
| 961 | 3.4331 | 2.272 | 6.2681 | 3.4127 | 1.4021 | 16.788
| 962 | 3.4711 | 2.4921 | 6.5586 | 4.7338 | 1.4369 | 18.6925
| 963 | 4.3663 | 3.0667 | 4.2906 | 4.7548 | 1.419 | 17.8973
| 964 | 3.8624 | 2.462 | 7.9464 | 4.3014 | 1.4467 | 20.0189
| 965 | 4.4633 | 3.181 | 4.0863 | 4.1695 | 1.4651 | 17.3652
| 966 | 3.5144 | 2.2391 | 6.3905 | 4.7248 | 1.8016 | 18.6705
| 967 | 4.3415 | 3.2878 | 4.6587 | 4.0839 | 1.4383 | 17.8103
| 968 | 4.5406 | 2.7652 | 5.1971 | 3.7963 | 1.5043 | 17.8036
| 969 | 4.2286 | 2.7509 | 6.4797 | 4.924 | 1.3348 | 19.7181
| 970 | 3.8581 | 2.833 | 4.5516 | 4.8116 | 1.2873 | 17.3417
| 971 | 4.2632 | 3.3205 | 4.376 | 3.584 | 1.6702 | 17.2141
| 972 | 3.6879 | 2.931 | 5.6895 | 3.7128 | 1.6364 | 17.6575
| 973 | 4.3723 | 2.9836 | 6.7415 | 3.4463 | 1.5228 | 19.0665
| 974 | 3.6972 | 3.6197 | 6.2526 | 3.8907 | 1.5254 | 18.9856
| 975 | 4.521 | 3.1759 | 5.9173 | 5.6614 | 1.677 | 20.9526
| 976 | 3.6774 | 2.9153 | 4.8062 | 4.6471 | 1.084 | 17.13
| 977 | 4.3172 | 2.982 | 6.1554 | 5.0885 | 1.4189 | 19.962
| 978 | 3.2341 | 3.368 | 7.4802 | 4.2369 | 1.5685 | 19.8878
| 979 | 4.5591 | 2.382 | 6.4695 | 4.3706 | 1.3901 | 19.1712
| 980 | 3.0394 | 3.0881 | 5.1607 | 3.9323 | 1.5711 | 16.7915
| 981 | 3.5135 | 3.707 | 4.2768 | 3.6697 | 1.4489 | 16.6158
| 982 | 3.8277 | 3.3196 | 5.626 | 3.6226 | 1.5584 | 17.9543
| 983 | 4.7108 | 2.829 | 4.8404 | 4.4997 | 1.3783 | 18.2582
| 984 | 3.949 | 2.3328 | 5.9914 | 3.7063 | 1.3844 | 17.3639
| 985 | 3.5059 | 2.8765 | 7.1016 | 3.5844 | 1.4401 | 18.5086
| 986 | 4.616 | 2.9187 | 5.8796 | 4.2669 | 1.455 | 19.1363
| 987 | 3.6591 | 3.6648 | 4.9096 | 3.4194 | 1.5017 | 17.1545
| 988 | 3.6305 | 2.6566 | 4.8273 | 4.9171 | 1.1376 | 17.169
| 989 | 4.3539 | 2.8992 | 6.9442 | 3.5939 | 1.301 | 19.0921
| 990 | 4.1037 | 2.718 | 4.7083 | 3.3282 | 1.7616 | 16.6199
| 991 | 4.8857 | 2.2808 | 5.5931 | 5.0702 | 1.4513 | 19.2811
| 992 | 4.1115 | 3.0983 | 5.3925 | 4.0207 | 1.6021 | 18.2251
| 993 | 3.7074 | 3.1852 | 5.4386 | 3.4627 | 1.4445 | 17.2384
| 994 | 3.9481 | 2.497 | 6.5115 | 3.6334 | 1.3978 | 17.9878
| 995 | 3.2543 | 2.7659 | 5.3501 | 3.7192 | 1.3861 | 16.4757
| 996 | 3.6536 | 3.4649 | 4.8475 | 3.4835 | 1.4818 | 16.9314
| 997 | 3.6354 | 3.3272 | 5.2903 | 3.6858 | 1.3142 | 17.253
| 998 | 3.8835 | 3.5225 | 4.6 | 3.6733 | 1.2406 | 16.9199
| 999 | 3.3224 | 2.4005 | 5.9838 | 3.454 | 1.6549 | 16.8157
| 1000 | 3.7632 | 2.4756 | 7.2953 | 3.7933 | 1.6995 | 19.0268
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.