## Sheet1
[8 empty] | positive correlation | Correlation Matrix
matrix
|  | Minimum | Most Likely | Maximum | Duration | Risk Note | New Duration
| Analyze | 3 | 4 | 5 | 4 |  | 100 |  | 1
| Design | 2 | 3 | 4 | 3 |  | 40 |  | 0.9 | 1
| Build | 4 | 5 | 8 | 5.6667 | NF Requirements (IM, IS, HR, …) | 5.6667
| Test | 3 | 3.5 | 6 | 4.1667 | UAT iteration risk | 4.1667
| Deploy | 1 | 1.5 | 2 | 1.5 |  | 1.5
| Go Live Date |  |  |  | 18.3333 |  | 151.3333
Corrmat
R | https://www.rdocumentation.org/packages/pgirmess/versions/1.7.0/topics/cormat
Palisade | https://kb.palisade.com/index.php?pg=kb.page&id=1537

## XLRisk
Simulation Settings |  | Simulation Inputs |  | Simulation Outputs
Seed | 0
Update Screen | FALSE | Range | Formula | Range | Name
Iterations | 100 | Sheet1!$F$7 | RiskTriang(C7,D7,E7) | Sheet1!$F$12 | LiveDate
Latin Hypercube | TRUE | Sheet1!$F$8 | RiskTriang(C8,D8,E8) | Sheet1!$H$12 | CorrelatedDate
Calculate data dables during simulation | TRUE | Sheet1!$F$9 | RiskTriang(C9,D9,E9)
|  | Sheet1!$F$10 | RiskTriang(C10,D10,E10)
|  | Sheet1!$F$11 | RiskTriang(C11,D11,E11)
|  | Sheet1!$H$7 | RiskNormal(100,20,RiskCorrmat($L$7:$M$8,1))
Macro to run before each iteration |  | Sheet1!$H$8 | RiskNormal(40,20,RiskCorrmat($L$7:$M$8,2))
Macro to run after each iteration |  | Sheet1!$H$9 | RiskTriang(C9,D9,E9)
|  | Sheet1!$H$10 | RiskTriang(C10,D10,E10)
|  | Sheet1!$H$11 | RiskTriang(C11,D11,E11)

## Risk Results 1
Navigation |  | Inputs |  |  |  |  | Outputs | Simulation Statistics |  | Output Cumulative Distributions | Output Distributions | Risk Tornado Diagram
Risk Outputs |  | Sheet1!$F$7 | Sheet1!$F$8 | Sheet1!$F$9 | Sheet1!$F$10 | Sheet1!$F$11 | Sheet1!$F$12 |  | Sheet1!$F$12 |  |  |  |  | Correlations - Column 1 sorted
Simulation Statistics | Iterations | RiskTriang(C7,D7,E7) | RiskTriang(C8,D8,E8) | RiskTriang(C9,D9,E9) | RiskTriang(C10,D10,E10) | RiskTriang(C11,D11,E11) | LiveDate |  | LiveDate |  |  | Select Output: | Sheet1!$F$12 |  | Sheet1!$F$12
Risk Output Percentiles | 1 | 3.9836 | 3.6772 | 6.9473 | 3.6558 | 1.8662 | 20.1301 | Mean | 18.3332 |  |  | Name: | LiveDate | Risk Inputs | LiveDate
Calculate Percent Rank | 2 | 3.8211 | 2.8978 | 5.6908 | 3.74 | 1.5572 | 17.7069 | Median | 18.2115 |  |  | 1 |  | Sheet1!$F$11 | -0.030052
Correlations | 3 | 4.7098 | 2.7836 | 4.6761 | 3.8909 | 1.1524 | 17.2127 | Mode | #N/A |  |  | Tornado Diagram for LiveDate (Sheet1!$F$12) |  | Sheet1!$F$7 | 0.17147
Output Cumulative Distributions | 4 | 4.7664 | 3.1827 | 4.8884 | 3.9243 | 1.4185 | 18.1804 | Std. Deviation | 1.1528 |  |  |  |  | Sheet1!$F$8 | 0.29147
Output Distributions | 5 | 4.2115 | 3.5259 | 5.3884 | 4.5668 | 1.2549 | 18.9474 | Variance | 1.3289 |  |  |  |  | Sheet1!$F$10 | 0.51726
Risk Tornado Diagram | 6 | 3.9769 | 3.2087 | 6.1732 | 4.018 | 1.695 | 19.0718 | Kurtosis | -0.1774 |  |  |  |  | Sheet1!$F$9 | 0.73589
| 7 | 4.5427 | 3.8398 | 5.9937 | 4.3177 | 1.4626 | 20.1566 | Skewness | 0.31786
| 8 | 3.7764 | 2.7205 | 6.4295 | 3.6233 | 1.7174 | 18.2671 | Minimum | 15.7138
| 9 | 3.6732 | 2.8884 | 4.1044 | 4.1335 | 1.8066 | 16.6062 | Maximum | 21.5037
| 10 | 4.5698 | 2.3276 | 6.0564 | 4.2884 | 1.3733 | 18.6156 | Range | 5.7899
| 11 | 3.7741 | 3.464 | 5.9669 | 4.148 | 1.0117 | 18.3646 | Count | 100
| 12 | 4.177 | 3.6407 | 5.1131 | 4.5396 | 1.3971 | 18.8674 | Error Count | 0
| 13 | 3.3797 | 3.6929 | 7.2559 | 3.9758 | 1.452 | 19.7563 | Std. Error | 0.11528
| 14 | 3.4017 | 3.1275 | 4.7683 | 5.7775 | 1.6035 | 18.6785 | Confidence Level (95%) | 0.22873
| 15 | 3.74 | 2.9722 | 6.0851 | 4.9909 | 1.7449 | 19.533
| 16 | 3.8277 | 3.1515 | 5.8984 | 4.6491 | 1.7059 | 19.2325 | Percentiles
| 17 | 3.3366 | 2.8036 | 4.4459 | 3.3518 | 1.7758 | 15.7138 |  | Sheet1!$F$12
| 18 | 3.8551 | 3.4202 | 5.6206 | 3.4532 | 1.5649 | 17.9141 |  | LiveDate
| 19 | 4.8702 | 2.9944 | 5.7677 | 3.4089 | 1.2081 | 18.2492 | 0% | 15.7138
| 20 | 3.8843 | 2.9502 | 4.897 | 4.8893 | 1.3402 | 17.9611 | 2.5% | 16.4503
| 21 | 4.3397 | 2.2491 | 6.0314 | 4.832 | 1.7107 | 19.1629 | 5% | 16.5245
| 22 | 3.9142 | 2.1094 | 5.1609 | 3.9945 | 1.4942 | 16.6731 | 7.5% | 16.6322
| 23 | 4.5242 | 2.8383 | 6.1237 | 3.8361 | 1.7302 | 19.0526 | 10% | 16.8205
| 24 | 3.5393 | 3.6174 | 7.095 | 5.6583 | 1.5936 | 21.5037 | 12.5% | 17.1336
| 25 | 4.0568 | 3.3849 | 4.5815 | 3.9326 | 1.4357 | 17.3915 | 15% | 17.2792
| 26 | 4.0971 | 3.075 | 6.6269 | 4.6711 | 1.548 | 20.0181 | 17.5% | 17.3218
| 27 | 3.1396 | 3.0925 | 6.4899 | 4.7778 | 1.5399 | 19.0397 | 20% | 17.3845
| 28 | 4.0408 | 3.3676 | 5.8752 | 3.4264 | 1.3375 | 18.0475 | 22.5% | 17.5084
| 29 | 4.0137 | 2.3087 | 6.2564 | 5.3181 | 1.5997 | 19.4965 | 25% | 17.5257
| 30 | 3.5566 | 3.0556 | 5.3173 | 3.1505 | 1.4028 | 16.4828 | 27.5% | 17.5653
| 31 | 4.2707 | 2.5365 | 5.6298 | 3.6875 | 1.524 | 17.6486 | 30% | 17.6724
| 32 | 3.9471 | 2.5505 | 4.8115 | 4.4299 | 1.6176 | 17.3566 | 32.5% | 17.7131
| 33 | 3.5984 | 2.3789 | 4.8361 | 4.2344 | 1.4788 | 16.5267 | 35% | 17.8198
| 34 | 4.4073 | 3.3395 | 7.0813 | 3.6322 | 1.4382 | 19.8985 | 37.5% | 17.8765
| 35 | 4.0507 | 3.7747 | 6.2813 | 4.1802 | 1.3835 | 19.6705 | 40% | 18.0129
| 36 | 4.2471 | 2.9689 | 5.3738 | 3.5875 | 1.3567 | 17.5341 | 42.5% | 18.0808
| 37 | 4.3316 | 2.3509 | 6.157 | 3.4856 | 1.7878 | 18.1129 | 45% | 18.1113
| 38 | 4.1199 | 2.8257 | 4.708 | 4.5934 | 1.3045 | 17.5515 | 47.5% | 18.1422
| 39 | 4.1128 | 3.2649 | 4.9864 | 3.8976 | 1.5419 | 17.8036 | 50% | 18.2115
| 40 | 4.4387 | 2.7368 | 4.7212 | 4.0769 | 1.3479 | 17.3215 | 52.5% | 18.2667
| 41 | 3.615 | 3.5539 | 6.6758 | 5.2693 | 1.8857 | 20.9997 | 55% | 18.3839
| 42 | 4.4869 | 2.7915 | 6.2051 | 4.7146 | 1.4467 | 19.6447 | 57.5% | 18.4149
| 43 | 3.7503 | 3.0684 | 5.547 | 4.4876 | 1.5618 | 18.4152 | 60% | 18.5221
| 44 | 3.3671 | 3.2386 | 7.3374 | 4.841 | 1.1395 | 19.9237 | 62.5% | 18.6103
| 45 | 3.8697 | 2.707 | 4.663 | 4.395 | 1.6238 | 17.2586 | 65% | 18.6675
| 46 | 4.4315 | 3.0261 | 5.4626 | 5.3435 | 1.6318 | 19.8955 | 67.5% | 18.7158
| 47 | 4.2622 | 3.2788 | 4.9556 | 4.0322 | 1.5267 | 18.0555 | 70% | 18.8289
| 48 | 3.878 | 3.5041 | 5.0541 | 5.0351 | 1.1025 | 18.5737 | 72.5% | 18.9294
| 49 | 3.7314 | 3.5988 | 5.5866 | 3.3144 | 1.0912 | 17.3225 | 75% | 19.051
| 50 | 3.5766 | 3.7217 | 4.2601 | 3.7146 | 1.6861 | 16.9591 | 77.5% | 19.1378
| 51 | 3.288 | 3.1066 | 6.3557 | 4.2925 | 1.6791 | 18.7219 | 80% | 19.5038
| 52 | 4.0209 | 3.0312 | 4.4643 | 3.8446 | 1.9219 | 17.2828 | 82.5% | 19.6191
| 53 | 3.9047 | 3.0979 | 5.8377 | 3.7496 | 1.7484 | 18.3383 | 85% | 19.6718
| 54 | 4.0912 | 3.0505 | 5.8094 | 3.5048 | 1.26 | 17.7158 | 87.5% | 19.7479
| 55 | 3.7037 | 3.1287 | 5.4086 | 3.6928 | 1.5744 | 17.5083 | 90% | 19.901
| 56 | 4.4974 | 2.8488 | 6.3792 | 4.0605 | 1.2648 | 19.0505 | 92.5% | 19.9818
| 57 | 3.933 | 2.6443 | 5.245 | 4.924 | 1.3656 | 18.1119 | 95% | 20.1314
| 58 | 3.627 | 2.8192 | 5.0722 | 4.752 | 1.4123 | 17.6827 | 97.5% | 20.763
| 59 | 3.6398 | 2.9446 | 6.7096 | 3.0262 | 1.7905 | 18.1107 | 100% | 21.5037
| 60 | 3.5172 | 2.9225 | 5.0056 | 4.225 | 1.4159 | 17.0862
| 61 | 4.6368 | 2.5935 | 6.9629 | 5.1939 | 1.3119 | 20.699 | Percent Rank
| 62 | 3.4467 | 2.4554 | 5.1315 | 3.5633 | 1.8478 | 16.4447 |  | Sheet1!$F$12
| 63 | 4.1939 | 2.763 | 7.8172 | 3.53 | 1.6402 | 19.9442 |  | LiveDate
| 64 | 4.3156 | 3.1962 | 7.1702 | 4.6071 | 1.5318 | 20.8209 | Enter Value: | 16.5245
| 65 | 3.6897 | 3.3234 | 5.3166 | 3.2901 | 1.8172 | 17.437 | % rank: | 4.9%
| 66 | 4.0648 | 3.1623 | 4.797 | 5.1634 | 1.474 | 18.6615
| 67 | 3.6568 | 3.166 | 4.969 | 4.9468 | 1.4835 | 18.2221 | Correlations
| 68 | 3.9638 | 2.6786 | 5.8078 | 5.5489 | 1.635 | 19.6341 |  | Sheet1!$F$12
| 69 | 3.8028 | 2.8825 | 5.2695 | 3.21 | 1.6719 | 16.8368 | Risk Inputs | LiveDate
| 70 | 3.2259 | 3.0147 | 6.8847 | 4.1068 | 1.279 | 18.5111 | Sheet1!$F$7 | 0.17147
| 71 | 3.4719 | 2.6701 | 7.6338 | 3.5661 | 1.5165 | 18.8585 | Sheet1!$F$8 | 0.29147
| 72 | 3.9542 | 2.4206 | 5.9459 | 3.8741 | 1.3312 | 17.5259 | Sheet1!$F$9 | 0.73589
| 73 | 3.5052 | 3.2963 | 4.3241 | 4.7336 | 1.6658 | 17.525 | Sheet1!$F$10 | 0.51726
| 74 | 3.7886 | 2.1964 | 6.3313 | 5.5161 | 1.7557 | 19.588 | Sheet1!$F$11 | -0.030052
| 75 | 4.8118 | 3.5427 | 4.6167 | 3.3435 | 1.1939 | 17.5088
| 76 | 4.2919 | 3.4062 | 6.493 | 4.2603 | 1.2279 | 19.6793
| 77 | 4.2343 | 3.2829 | 4.5256 | 3.7853 | 1.464 | 17.2921
| 78 | 4.2994 | 2.7294 | 5.7397 | 3.6724 | 1.3876 | 17.8285
| 79 | 3.9212 | 2.6619 | 5.1956 | 5.4188 | 1.4895 | 18.6871
| 80 | 3.8466 | 3.9053 | 5.6629 | 3.7939 | 1.6075 | 18.8162
| 81 | 3.7177 | 3.2184 | 6.6024 | 3.6096 | 1.5118 | 18.66
| 82 | 4.2245 | 2.9891 | 5.3482 | 3.2208 | 1.8304 | 17.6131
| 83 | 4.3867 | 3.2377 | 5.4838 | 4.3748 | 1.2885 | 18.7715
| 84 | 3.4584 | 2.484 | 4.3507 | 4.199 | 1.9517 | 16.4439
| 85 | 4.1719 | 2.5186 | 6.5355 | 3.4725 | 1.1585 | 17.8571
| 86 | 4.4654 | 3.4864 | 4.9169 | 3.7693 | 1.4552 | 18.0932
| 87 | 3.2739 | 3.0067 | 6.7588 | 3.5143 | 1.6472 | 18.201
| 88 | 4.6768 | 2.576 | 5.1763 | 4.4742 | 1.5786 | 18.4819
| 89 | 4.0057 | 3.3649 | 5.0285 | 4.0965 | 1.3755 | 17.8712
| 90 | 4.1437 | 3.4503 | 7.4093 | 3.8202 | 1.1861 | 20.0095
| 91 | 4.3829 | 2.9153 | 5.0974 | 4.5249 | 1.2207 | 18.1412
| 92 | 4.1624 | 2.7538 | 6.8206 | 4.339 | 1.6581 | 19.7339
| 93 | 3.1495 | 2.9347 | 5.5524 | 3.3955 | 1.5027 | 16.5349
| 94 | 4.0775 | 2.6103 | 5.2081 | 3.2628 | 1.5088 | 16.6674
| 95 | 4.1299 | 2.6267 | 5.2942 | 5.0614 | 1.4265 | 18.5387
| 96 | 4.7485 | 2.4378 | 4.8561 | 5.1253 | 1.2436 | 18.4113
| 97 | 4.5842 | 2.8685 | 5.7038 | 3.9513 | 1.2995 | 18.4074
| 98 | 4.355 | 2.5067 | 4.5561 | 3.5429 | 1.4958 | 16.4565
| 99 | 4.6238 | 3.3178 | 5.443 | 3.3712 | 1.3239 | 18.0798
| 100 | 3.9931 | 2.2134 | 5.5199 | 4.4043 | 1.5818 | 17.7125
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Risk Results 2
Navigation |  | Inputs | [9 empty] | Outputs | Simulation Statistics |  | Output Cumulative Distributions | Output Distributions | Risk Tornado Diagram
Risk Outputs |  | Sheet1!$F$7 | Sheet1!$F$8 | Sheet1!$F$9 | Sheet1!$F$10 | Sheet1!$F$11 | Sheet1!$H$7 | Sheet1!$H$8 | Sheet1!$H$9 | Sheet1!$H$10 | Sheet1!$H$11 | Sheet1!$F$12 |  | Sheet1!$F$12 |  |  |  |  | Correlations - Column 1 sorted
Simulation Statistics | Iterations | RiskTriang(C7,D7,E7) | RiskTriang(C8,D8,E8) | RiskTriang(C9,D9,E9) | RiskTriang(C10,D10,E10) | RiskTriang(C11,D11,E11) | RiskNormal(100,20,RiskCorrmat($L$7:$M$8,1)) | RiskNormal(40,20,RiskCorrmat($L$7:$M$8,2)) | RiskTriang(C9,D9,E9) | RiskTriang(C10,D10,E10) | RiskTriang(C11,D11,E11) | LiveDate |  | LiveDate |  |  | Select Output: | Sheet1!$F$12 |  | Sheet1!$F$12
Risk Output Percentiles | 1 | 3.3246 | 2.9195 | 6.8661 | 3.7972 | 1.3416 | 92.9999 | 22.2027 | 4.9975 | 4.0048 | 1.3945 | 18.2491 | Mean | 18.3375 |  |  | Name: | LiveDate | Risk Inputs | LiveDate
Calculate Percent Rank | 2 | 3.8322 | 3.4056 | 5.8053 | 4.8856 | 1.5121 | 98.6843 | 27.5814 | 6.4016 | 3.8794 | 1.0711 | 19.4408 | Median | 18.175 |  |  | 1 |  | Sheet1!$H$8
Correlations | 3 | 4.0566 | 2.8661 | 5.2908 | 3.3894 | 1.7977 | 101.7216 | 36.5306 | 5.2478 | 4.9 | 1.1531 | 17.4007 | Mode | #N/A |  |  | Tornado Diagram for LiveDate (Sheet1!$F$12) |  | Sheet1!$H$7
Output Cumulative Distributions | 4 | 3.6194 | 3.0386 | 4.8603 | 3.1562 | 1.5481 | 95.6108 | 33.5105 | 4.4365 | 3.7659 | 1.2985 | 16.2226 | Std. Deviation | 1.4772 |  |  |  |  | Sheet1!$H$9
Output Distributions | 5 | 4.2358 | 3.0462 | 6.7447 | 5.1762 | 1.3859 | 89.3292 | 33.1408 | 5.4006 | 4.2698 | 1.2698 | 20.5889 | Variance | 2.1822 |  |  |  |  | Sheet1!$H$11
Risk Tornado Diagram | 6 | 3.2976 | 2.6521 | 5.1577 | 3.3078 | 1.8095 | 77.6754 | 21.6813 | 6.0014 | 3.4059 | 1.5817 | 16.2248 | Kurtosis | -0.67334 |  |  |  |  | Sheet1!$H$10
| 7 | 4.4089 | 3.2522 | 5.5273 | 5.2566 | 1.7539 | 141.6924 | 73.3699 | 5.3067 | 5.0563 | 1.2153 | 20.1989 | Skewness | 0.19735 |  |  |  |  | Sheet1!$F$11 | 0.39303
| 8 | 4.6994 | 3.505 | 7.8638 | 4.3505 | 1.7769 | 111.3144 | 55.9825 | 4.5567 | 4.4647 | 1.5211 | 22.1956 | Minimum | 15.3849 |  |  |  |  | Sheet1!$F$8 | 0.48403
| 9 | 4.1477 | 2.6219 | 6.5767 | 3.0704 | 1.2418 | 79.1664 | 15.5782 | 4.8393 | 3.7522 | 1.7093 | 17.6585 | Maximum | 22.1956 |  |  |  |  | Sheet1!$F$7 | 0.51488
| 10 | 3.1533 | 3.0984 | 5.4985 | 3.8512 | 1.5735 | 94.5828 | 29.1003 | 6.5655 | 4.3162 | 1.6231 | 17.1748 | Range | 6.8107 |  |  |  |  | Sheet1!$F$10 | 0.55364
| 11 | 4.3723 | 3.6432 | 6.9916 | 4.2214 | 1.631 | 116.3708 | 56.2627 | 4.34 | 3.2968 | 1.6114 | 20.8595 | Count | 100 |  |  |  |  | Sheet1!$F$9 | 0.72461
| 12 | 3.9515 | 3.065 | 6.1819 | 4.2271 | 1.178 | 126.5155 | 65.1139 | 4.2524 | 4.5423 | 1.23 | 18.6035 | Error Count | 0
| 13 | 3.4636 | 2.7004 | 5.2244 | 3.7658 | 1.5391 | 122.8434 | 44.0666 | 7.8908 | 3.9076 | 1.449 | 16.6933 | Std. Error | 0.14772
| 14 | 4.7282 | 3.5416 | 5.8739 | 5.0483 | 1.8645 | 96.2378 | 30.289 | 5.8174 | 5.5705 | 1.6568 | 21.0564 | Confidence Level (95%) | 0.29311
| 15 | 3.8441 | 3.0021 | 5.4138 | 3.7198 | 1.3076 | 104.4314 | 54.1739 | 6.0173 | 3.2459 | 1.1648 | 17.2873
| 16 | 4.0473 | 3.7562 | 6.0977 | 4.392 | 1.4244 | 103.6164 | 50.73 | 4.5851 | 4.7075 | 1.5391 | 19.7176 | Percentiles
| 17 | 4.5258 | 2.8444 | 4.151 | 4.3099 | 1.2532 | 79.3233 | 12.4482 | 6.172 | 5.3911 | 1.3645 | 17.0843 |  | Sheet1!$F$12
| 18 | 3.8781 | 2.8184 | 6.3379 | 4.9606 | 1.4666 | 86.2992 | 36.4584 | 5.8647 | 3.5789 | 1.7726 | 19.4615 |  | LiveDate
| 19 | 3.9353 | 2.6756 | 5.7417 | 3.5361 | 1.855 | 105.8643 | 43.5894 | 6.9043 | 3.9789 | 1.5153 | 17.7438 | 0% | 15.3849
| 20 | 4.0905 | 3.3055 | 4.9985 | 3.7811 | 1.2694 | 50.2939 | -0.55693 | 7.5 | 4.4878 | 1.4243 | 17.445 | 2.5% | 15.8593
| 21 | 4.4483 | 2.3733 | 4.9493 | 3.3346 | 1.5095 | 107.2306 | 48.7177 | 6.0935 | 3.4839 | 1.2106 | 16.615 | 5% | 16.1907
| 22 | 4.5013 | 2.2759 | 4.6447 | 3.9955 | 1.6367 | 92.3127 | 38.0867 | 6.6592 | 3.9165 | 1.3678 | 17.0541 | 7.5% | 16.3279
| 23 | 3.9099 | 3.1838 | 5.9055 | 4.4606 | 1.4634 | 118.7113 | 51.1155 | 4.9354 | 3.6443 | 1.305 | 18.9232 | 10% | 16.5263
| 24 | 3.4768 | 3.3636 | 5.5899 | 5.3007 | 1.3335 | 55.5608 | 7.173 | 5.4795 | 3.9666 | 1.7631 | 19.0644 | 12.5% | 16.6217
| 25 | 4.1319 | 3.4224 | 6.4101 | 5.4046 | 1.6558 | 68.8613 | 9.6228 | 4.9612 | 3.6232 | 1.2591 | 21.0248 | 15% | 16.6908
| 26 | 3.9761 | 3.7109 | 7.3184 | 3.2765 | 1.5039 | 88.3496 | 24.0541 | 5.2644 | 4.0772 | 1.2796 | 19.7858 | 17.5% | 17.003
| 27 | 4.6128 | 3.2459 | 6.5333 | 3.6292 | 1.8858 | 95.1016 | 31.5753 | 4.9102 | 5.3573 | 1.4402 | 19.907 | 20% | 17.0491
| 28 | 3.7585 | 3.1656 | 4.7106 | 3.4723 | 1.3723 | 106.1416 | 44.9044 | 4.6846 | 3.2375 | 1.6829 | 16.4793 | 22.5% | 17.1035
| 29 | 3.4003 | 2.6119 | 5.4076 | 3.6689 | 1.0909 | 80.3126 | 5.3037 | 5.5429 | 3.6111 | 1.4873 | 16.1795 | 25% | 17.1522
| 30 | 3.6569 | 2.5273 | 4.8244 | 4.6538 | 1.4755 | 100.6703 | 60.4851 | 5.6787 | 4.0227 | 1.5981 | 17.1379 | 27.5% | 17.1752
| 31 | 3.7374 | 2.1395 | 5.4442 | 4.6117 | 1.5922 | 123.6569 | 58.9087 | 4.9392 | 4.3688 | 1.3365 | 17.5248 | 30% | 17.3025
| 32 | 4.5505 | 3.4605 | 6.1399 | 4.3144 | 1.6418 | 69.8459 | -25.7479 | 5.4204 | 4.1258 | 1.0401 | 20.1071 | 32.5% | 17.4085
| 33 | 4.2124 | 2.912 | 5.8513 | 4.5621 | 1.3465 | 83.9027 | 34.8957 | 6.128 | 4.6193 | 1.319 | 18.8844 | 35% | 17.5603
| 34 | 3.7148 | 2.7904 | 5.5689 | 3.9059 | 1.1963 | 129.732 | 67.7579 | 5.6525 | 4.2317 | 1.705 | 17.1763 | 37.5% | 17.7572
| 35 | 3.9013 | 3.4871 | 5.7687 | 5.6318 | 1.45 | 108.4055 | 48.9157 | 4.5197 | 4.3934 | 1.7281 | 20.239 | 40% | 17.938
| 36 | 4.3669 | 3.3369 | 5.3053 | 5.3475 | 1.3604 | 109.3938 | 53.8121 | 7.2978 | 5.0383 | 1.6944 | 19.7171 | 42.5% | 18.0044
| 37 | 4.1102 | 3.1218 | 4.9284 | 3.2469 | 1.6126 | 74.8831 | 20.9076 | 5.1934 | 3.6325 | 1.7541 | 17.0198 | 45% | 18.0424
| 38 | 3.2639 | 3.2696 | 5.6038 | 4.7376 | 1.1296 | 90.5918 | 34.3848 | 6.7744 | 4.2597 | 1.5083 | 18.0044 | 47.5% | 18.1113
| 39 | 4.273 | 3.614 | 7.2298 | 4.1395 | 1.5234 | 99.4731 | 49.728 | 5.0587 | 4.8626 | 1.1382 | 20.7796 | 50% | 18.175
| 40 | 4.0321 | 2.9742 | 5.6958 | 4.2005 | 1.7412 | 117.6942 | 66.0713 | 5.061 | 5.1963 | 1.499 | 18.6438 | 52.5% | 18.2387
| 41 | 4.1592 | 2.8063 | 5.8293 | 5.0001 | 1.6628 | 84.945 | 28.1277 | 6.3128 | 3.6709 | 1.6399 | 19.4577 | 55% | 18.3522
| 42 | 4.1259 | 3.1063 | 6.4649 | 4.3621 | 1.2749 | 85.6003 | 18.7246 | 5.9727 | 5.6531 | 1.1883 | 19.334 | 57.5% | 18.5227
| 43 | 4.1964 | 2.6367 | 5.025 | 3.1768 | 1.5978 | 119.9479 | 72.0051 | 7.3738 | 3.535 | 1.5743 | 16.6328 | 60% | 18.6196
| 44 | 3.9976 | 3.1595 | 5.9466 | 3.6003 | 1.4059 | 87.2031 | 16.5234 | 6.0677 | 3.5907 | 1.5596 | 18.11 | 62.5% | 18.7147
| 45 | 3.86 | 2.9863 | 5.3759 | 3.5954 | 1.2116 | 112.5021 | 48.0789 | 5.3371 | 3.4319 | 1.6855 | 17.0292 | 65% | 18.8979
| 46 | 4.84 | 2.9428 | 6.9524 | 4.7515 | 1.6845 | 102.1459 | 39.5126 | 6.7505 | 4.1706 | 1.5672 | 21.1712 | 67.5% | 19.1201
| 47 | 3.7711 | 2.7436 | 4.5872 | 4.4507 | 1.6043 | 102.9413 | 52.519 | 5.5828 | 3.3495 | 1.4811 | 17.1569 | 70% | 19.3998
| 48 | 4.3988 | 2.3922 | 4.6692 | 4.4123 | 1.1224 | 89.9078 | 37.1436 | 6.4867 | 3.4603 | 1.6176 | 16.9949 | 72.5% | 19.4539
| 49 | 4.3414 | 2.4983 | 4.3262 | 5.6006 | 1.3141 | 136.8528 | 77.5204 | 5.7197 | 3.5608 | 1.7174 | 18.0806 | 75% | 19.6757
| 50 | 4.5961 | 2.8838 | 5.2596 | 3.9202 | 1.3207 | 94.135 | 30.76 | 6.4964 | 4.9504 | 1.2527 | 17.9805 | 77.5% | 19.7158
| 51 | 4.7874 | 3.3087 | 6.6203 | 3.6785 | 1.7605 | 87.9097 | 23.6856 | 5.0996 | 4.6555 | 1.7415 | 20.1555 | 80% | 19.753
| 52 | 4.2439 | 3.0801 | 5.5173 | 3.8707 | 1.6192 | 92.1974 | 23.1097 | 7.2169 | 4.3468 | 1.4563 | 18.3312 | 82.5% | 19.8816
| 53 | 4.4651 | 3.2892 | 4.4721 | 4.2789 | 1.7335 | 109.3522 | 42.5045 | 4.7673 | 3.5174 | 1.8718 | 18.2388 | 85% | 19.9353
| 54 | 4.0723 | 2.9339 | 4.7773 | 3.7324 | 1.5775 | 110.5044 | 42.7462 | 6.9484 | 3.8311 | 1.9203 | 17.0934 | 87.5% | 20.0785
| 55 | 3.4284 | 3.322 | 6.2653 | 3.4902 | 1.6764 | 101.1688 | 40.8321 | 5.1603 | 4.7171 | 1.3266 | 18.1823 | 90% | 20.2013
| 56 | 3.7019 | 3.0177 | 5.6298 | 3.4844 | 1.2963 | 127.597 | 57.2497 | 5.1019 | 3.1315 | 1.46 | 17.1302 | 92.5% | 20.4402
| 57 | 3.8174 | 3.933 | 6.1187 | 3.5599 | 1.703 | 96.4738 | 39.0489 | 5.2907 | 4.8089 | 1.8567 | 19.132 | 95% | 20.7836
| 58 | 4.9304 | 3.3776 | 5.9741 | 3.8859 | 1.768 | 111.9791 | 41.0484 | 6.9982 | 3.6945 | 1.3524 | 19.936 | 97.5% | 21.0414
| 59 | 3.5048 | 2.8353 | 4.3548 | 3.7566 | 1.0406 | 98.1972 | 37.5212 | 6.445 | 3.7125 | 1.3892 | 15.4922 | 100% | 22.1956
| 60 | 4.4232 | 2.8548 | 6.0111 | 3.5069 | 1.4377 | 65.7679 | 13.6661 | 5.564 | 3.3847 | 1.2421 | 18.2336
| 61 | 4.6657 | 3.1351 | 5.072 | 4.7963 | 1.7253 | 60.8145 | 14.8517 | 5.015 | 4.0987 | 1.6489 | 19.3945 | Percent Rank
| 62 | 4.0099 | 2.5532 | 7.0828 | 5.4751 | 1.4872 | 151.7674 | 91.0581 | 4.352 | 4.0282 | 1.4048 | 20.6083 |  | Sheet1!$F$12
| 63 | 3.6146 | 2.479 | 6.2065 | 4.6017 | 1.2588 | 131.5995 | 70.5415 | 4.8216 | 5.2509 | 1.589 | 18.1607 |  | LiveDate
| 64 | 3.9638 | 3.5804 | 5.4721 | 5.1277 | 1.5685 | 114.2708 | 45.9101 | 6.2699 | 4.1525 | 1.2854 | 19.7125 | Enter Value: | 16.1907
| 65 | 3.5298 | 2.7665 | 4.2164 | 4.2609 | 1.3978 | 125.3899 | 63.447 | 5.9188 | 3.3407 | 1.4448 | 16.1714 | % rank: | 4.9%
| 66 | 3.8057 | 3.3891 | 5.6546 | 3.4573 | 1.6977 | 63.4562 | -4.5895 | 4.7915 | 3.5439 | 1.4679 | 18.0044
| 67 | 3.5924 | 2.447 | 7.45 | 4.9294 | 1.5163 | 103.2427 | 32.4447 | 6.8181 | 4.7739 | 1.3456 | 19.9351 | Correlations
| 68 | 3.5133 | 2.7513 | 6.5279 | 4.0213 | 1.7104 | 110.0914 | 43.3839 | 5.5128 | 3.7803 | 1.7772 | 18.5243 |  | Sheet1!$F$12
| 69 | 3.3794 | 2.5351 | 5.2464 | 3.5352 | 1.4952 | 119.3192 | 50.0852 | 7.1334 | 4.6763 | 1.5326 | 16.1913 | Risk Inputs | LiveDate
| 70 | 3.7271 | 3.2299 | 4.4217 | 4.8154 | 1.8337 | 108.1679 | 63.541 | 6.3663 | 5.3022 | 1.4351 | 18.0279 | Sheet1!$F$7 | 0.51488
| 71 | 3.684 | 3.2035 | 4.73 | 3.4168 | 1.433 | 105.1551 | 57.7905 | 5.4389 | 4.5826 | 1.503 | 16.4674 | Sheet1!$F$8 | 0.48403
| 72 | 3.235 | 2.3179 | 5.1793 | 3.7024 | 1.1423 | 77.3231 | 24.8244 | 4.1639 | 3.4446 | 1.6311 | 15.5769 | Sheet1!$F$9 | 0.72461
| 73 | 3.8703 | 3.5691 | 6.0484 | 3.9686 | 1.9556 | 70.9526 | 11.2115 | 5.3637 | 4.4075 | 1.3834 | 19.412 | Sheet1!$F$10 | 0.55364
| 74 | 3.7979 | 2.9679 | 5.1055 | 3.8427 | 1.6507 | 83.0325 | 32.1366 | 5.6315 | 4.5577 | 1.977 | 17.3646 | Sheet1!$F$11 | 0.39303
| 75 | 3.5814 | 3.8069 | 5.3436 | 4.0436 | 1.3921 | 133.7108 | 85.2191 | 7.6469 | 3.2031 | 1.5462 | 18.1678 | Sheet1!$H$7
| 76 | 4.2608 | 3.5245 | 7.1919 | 3.6601 | 1.5853 | 82.0971 | 29.8047 | 5.2282 | 5.1756 | 1.4108 | 20.2227 | Sheet1!$H$8
| 77 | 4.0949 | 2.599 | 6.4193 | 3.3755 | 1.3623 | 128.5155 | 68.8068 | 5.0226 | 5.8523 | 1.4242 | 17.8509 | Sheet1!$H$9
| 78 | 4.0207 | 2.1964 | 4.7651 | 3.2411 | 1.1615 | 81.1457 | 26.2367 | 4.8772 | 5.0013 | 1.5521 | 15.3849 | Sheet1!$H$10
| 79 | 4.0181 | 3.2138 | 4.5435 | 3.3497 | 1.4064 | 137.7937 | 79.42 | 6.6045 | 4.2239 | 1.4167 | 16.5315 | Sheet1!$H$11
| 80 | 3.7834 | 2.9957 | 6.8426 | 4.6787 | 1.5284 | 113.3821 | 53.4208 | 5.6068 | 3.6922 | 1.1841 | 19.8287
| 81 | 4.6484 | 2.4571 | 5.9846 | 3.6154 | 1.6723 | 122.3082 | 38.7016 | 4.4881 | 4.1213 | 1.4937 | 18.3779
| 82 | 3.6446 | 3.6563 | 4.8866 | 3.4243 | 1.5573 | 86.5377 | 19.8383 | 5.129 | 4.5076 | 1.1059 | 17.169
| 83 | 3.1194 | 3.0223 | 4.4998 | 4.5079 | 1.4237 | 97.2893 | 55.1745 | 5.784 | 3.802 | 1.5771 | 16.573
| 84 | 3.9244 | 3.151 | 4.6254 | 4.5482 | 1.3304 | 115.9066 | 61.2598 | 6.1585 | 5.1101 | 1.3787 | 17.5795
| 85 | 3.6722 | 2.8995 | 5.7111 | 4.0665 | 1.5434 | 97.7533 | 59.1592 | 4.7296 | 3.8481 | 1.6022 | 17.8927
| 86 | 3.9836 | 2.4127 | 6.7863 | 4.1181 | 1.4154 | 115.093 | 40.0668 | 5.1852 | 4.4323 | 1.5136 | 18.7161
| 87 | 3.5526 | 2.958 | 5.0058 | 3.9429 | 1.3778 | 93.6815 | 46.2744 | 4.6369 | 3.4064 | 1.314 | 16.8371
| 88 | 4.0807 | 2.7842 | 6.2808 | 5.0605 | 1.8246 | 100.1981 | 45.489 | 5.7553 | 3.504 | 1.6361 | 20.0308
| 89 | 3.8925 | 3.4482 | 4.8999 | 5.9418 | 1.5625 | 73.0974 | 26.6734 | 4.8517 | 4.045 | 1.4722 | 19.7448
| 90 | 4.5595 | 2.2331 | 6.6763 | 4.0553 | 1.2264 | 73.8837 | 3.5514 | 5.3514 | 3.0312 | 1.3598 | 18.7506
| 91 | 4.2939 | 3.0584 | 5.2043 | 4.4767 | 1.4702 | 104.7818 | 47.219 | 5.9454 | 3.3131 | 1.8047 | 18.5035
| 92 | 4.4727 | 2.7074 | 5.3279 | 4.1609 | 1.918 | 114.0573 | 35.0361 | 6.2054 | 4.1883 | 1.5557 | 18.5869
| 93 | 4.1705 | 2.8757 | 7.5778 | 3.8237 | 1.4805 | 83.5221 | 25.4375 | 6.2649 | 3.9422 | 1.8944 | 19.9282
| 94 | 4.3264 | 2.689 | 4.8423 | 4.7021 | 1.4945 | 117.2153 | 47.1527 | 4.713 | 4.2986 | 1.6686 | 18.0543
| 95 | 4.2811 | 2.2973 | 5.0913 | 4.8404 | 1.4581 | 76.4846 | 18.0526 | 5.7464 | 3.82 | 1.8202 | 17.9682
| 96 | 3.3675 | 3.1956 | 5.131 | 4.1719 | 1.4431 | 99.6382 | 51.9731 | 4.6102 | 3.875 | 1.5264 | 17.3091
| 97 | 4.2181 | 3.0937 | 7.0924 | 3.9802 | 1.2866 | 90.9267 | 41.8765 | 5.4726 | 4.923 | 1.8387 | 19.671
| 98 | 4.3075 | 2.7319 | 6.3526 | 4.0951 | 1.2184 | 91.5788 | 28.4581 | 7.0498 | 4.7974 | 1.7902 | 18.7055
| 99 | 4.187 | 3.735 | 4.9667 | 5.1814 | 1.6195 | 107.0438 | 35.9363 | 5.8541 | 3.7398 | 1.6613 | 19.6897
| 100 | 3.9451 | 2.5707 | 5.056 | 3.5715 | 1.5332 | 120.7417 | 61.7515 | 6.6461 | 5.5057 | 1.4795 | 16.6764
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Risk Results 3
Navigation |  | Inputs | [9 empty] | Outputs |  | Simulation Statistics |  |  | Output Cumulative Distributions | Output Distributions | Risk Tornado Diagram
Risk Outputs |  | Sheet1!$F$7 | Sheet1!$F$8 | Sheet1!$F$9 | Sheet1!$F$10 | Sheet1!$F$11 | Sheet1!$H$7 | Sheet1!$H$8 | Sheet1!$H$9 | Sheet1!$H$10 | Sheet1!$H$11 | Sheet1!$F$12 | Sheet1!$H$12 |  | Sheet1!$F$12 | Sheet1!$H$12 |  |  |  |  | Correlations - Column 1 sorted
Simulation Statistics | Iterations | RiskTriang(C7,D7,E7) | RiskTriang(C8,D8,E8) | RiskTriang(C9,D9,E9) | RiskTriang(C10,D10,E10) | RiskTriang(C11,D11,E11) | RiskNormal(100,20,RiskCorrmat($L$7:$M$8,1)) | RiskNormal(40,20,RiskCorrmat($L$7:$M$8,2)) | RiskTriang(C9,D9,E9) | RiskTriang(C10,D10,E10) | RiskTriang(C11,D11,E11) | LiveDate | CorrelatedDate |  | LiveDate | CorrelatedDate |  |  | Select Output: | Sheet1!$F$12 |  | Sheet1!$F$12 | Sheet1!$H$12
Risk Output Percentiles | 1 | 4.0131 | 3.7245 | 5.7668 | 3.8302 | 1.5043 | 110.7198 | 39.9843 | 5.3908 | 3.0418 | 1.5 | 18.8389 | 160.6367 | Mean | 18.3356 | 151.2161 |  |  | Name: | LiveDate | Risk Inputs | LiveDate | CorrelatedDate
Calculate Percent Rank | 2 | 3.1276 | 3.3718 | 6.9531 | 4.9862 | 1.2977 | 119.4771 | 65.5806 | 5.4895 | 3.1771 | 1.538 | 19.7365 | 195.2622 | Median | 18.2959 | 152.4016 |  |  | 1 |  | Sheet1!$H$8 |  | 0.9729
Correlations | 3 | 3.86 | 3.4818 | 6.963 | 4.8133 | 1.4365 | 70.5237 | -6.086 | 7.8829 | 4.7089 | 1.1333 | 20.5547 | 78.1629 | Mode | #N/A | #N/A |  |  | Tornado Diagram for LiveDate (Sheet1!$F$12) |  | Sheet1!$H$7 |  | 0.97457
Output Cumulative Distributions | 4 | 3.8135 | 3.0883 | 6.4574 | 3.5501 | 1.5524 | 113.938 | 46.6072 | 6.1613 | 3.9096 | 1.4677 | 18.4617 | 172.0837 | Std. Deviation | 1.2019 | 39.0704 |  |  |  |  | Sheet1!$H$9 |  | -0.06889
Output Distributions | 5 | 4.2509 | 3.2205 | 6.4175 | 3.3207 | 1.5145 | 110.1757 | 57.0138 | 7.6121 | 4.3868 | 1.57 | 18.7241 | 180.7584 | Variance | 1.4446 | 1526.4933 |  |  |  |  | Sheet1!$H$11 |  | 0.038478
Risk Tornado Diagram | 6 | 4.3825 | 3.6286 | 6.7503 | 3.5023 | 1.6756 | 78.2536 | 26.0871 | 5.2503 | 4.3362 | 1.4488 | 19.9393 | 115.376 | Kurtosis | -0.63121 | 0.080345 |  |  |  |  | Sheet1!$H$10 |  | -0.13884
| 7 | 4.1207 | 3.1807 | 5.6181 | 4.0202 | 1.1956 | 92.7191 | 45.917 | 6.6664 | 4.0322 | 1.7125 | 18.1352 | 151.0472 | Skewness | -0.12161 | -0.073296 |  |  |  |  | Sheet1!$F$11 | 0.0062136
| 8 | 3.8719 | 2.1027 | 5.7441 | 3.573 | 1.3727 | 109.2662 | 32.8593 | 5.2756 | 3.6115 | 1.55 | 16.6645 | 152.5626 | Minimum | 15.5553 | 35.8256 |  |  |  |  | Sheet1!$F$8 | 0.32612
| 9 | 3.7009 | 2.7669 | 4.8547 | 3.3854 | 1.3601 | 94.5966 | 44.4278 | 5.3805 | 3.6504 | 1.4194 | 16.068 | 149.4746 | Maximum | 20.7445 | 251.0885 |  |  |  |  | Sheet1!$F$7 | 0.34536
| 10 | 4.3455 | 2.6535 | 4.8091 | 3.6829 | 1.8791 | 75.8027 | 14.3174 | 5.9073 | 5.1502 | 1.8522 | 17.3701 | 103.0299 | Range | 5.1892 | 215.2628 |  |  |  |  | Sheet1!$F$10 | 0.5069
| 11 | 3.6771 | 2.5931 | 5.0937 | 3.6742 | 1.6784 | 102.6366 | 39.0675 | 5.569 | 3.9962 | 1.5323 | 16.7164 | 152.8016 | Count | 100 | 100 |  |  |  |  | Sheet1!$F$9 | 0.69215
| 12 | 3.6787 | 3.6571 | 7.2589 | 3.2023 | 1.7469 | 104.4356 | 37.6003 | 4.5648 | 3.2617 | 1.6088 | 19.5439 | 151.4711 | Error Count | 0 | 0
| 13 | 4.1585 | 2.9586 | 6.1012 | 4.7642 | 1.6066 | 87.5613 | 26.8543 | 4.8613 | 3.5159 | 1.4532 | 19.5892 | 124.2461 | Std. Error | 0.12019 | 3.907
| 14 | 3.5616 | 3.0418 | 5.515 | 5.6005 | 1.2644 | 105.2545 | 34.8634 | 4.8315 | 3.2375 | 1.3485 | 18.9833 | 149.5353 | Confidence Level (95%) | 0.23849 | 7.7524
| 15 | 4.2295 | 2.6651 | 6.1969 | 4.4173 | 1.6397 | 91.9727 | 33.446 | 4.5042 | 3.7715 | 1.4163 | 19.1485 | 135.1108
| 16 | 3.8098 | 3.3096 | 6.5691 | 3.5551 | 1.5298 | 130.5247 | 67.2873 | 6.298 | 3.3295 | 1.4275 | 18.7734 | 208.867 | Percentiles
| 17 | 4.8349 | 3.0744 | 7.2151 | 3.3988 | 1.0665 | 97.8733 | 30.4915 | 5.6719 | 4.3052 | 1.3118 | 19.5897 | 139.6537 |  | Sheet1!$F$12 | Sheet1!$H$12
| 18 | 3.7137 | 2.8186 | 5.0295 | 4.0059 | 1.5344 | 100.8119 | 51.7535 | 5.0857 | 4.2705 | 1.3756 | 17.1021 | 163.2973 |  | LiveDate | CorrelatedDate
| 19 | 3.5714 | 2.8972 | 5.1091 | 4.4904 | 1.6586 | 107.5197 | 50.8043 | 6.4259 | 3.7463 | 1.324 | 17.7266 | 169.8203 | 0% | 15.5553 | 35.8256
| 20 | 4.0084 | 2.9245 | 5.1262 | 3.9039 | 1.5411 | 139.0409 | 82.5111 | 5.5825 | 3.1484 | 1.7396 | 17.5042 | 232.0225 | 2.5% | 16.1295 | 80.5351
| 21 | 4.414 | 2.5595 | 5.6599 | 3.9623 | 1.5633 | 40.0813 | -14.2075 | 4.7025 | 3.4465 | 1.8029 | 18.159 | 35.8256 | 5% | 16.3071 | 87.6997
| 22 | 3.7231 | 3.5756 | 5.1887 | 3.6404 | 1.9124 | 65.7937 | 11.1097 | 5.645 | 3.6919 | 1.4704 | 18.0401 | 87.7107 | 7.5% | 16.4993 | 91.3445
| 23 | 3.6518 | 3.3962 | 4.6709 | 4.8411 | 1.5947 | 114.2269 | 28.4917 | 7.4755 | 4.2364 | 1.2514 | 18.1548 | 155.6819 | 10% | 16.7112 | 97.6013
| 24 | 3.1862 | 3.4959 | 5.4783 | 4.1281 | 1.5682 | 134.7569 | 69.8342 | 4.9921 | 4.7743 | 1.5011 | 17.8566 | 215.8585 | 12.5% | 16.8707 | 105.3888
| 25 | 3.7571 | 2.629 | 5.3255 | 4.5097 | 1.4834 | 109.7742 | 53.7189 | 6.767 | 3.427 | 1.7786 | 17.7048 | 175.4657 | 15% | 17.0416 | 115.5508
| 26 | 4.3076 | 2.9742 | 5.2108 | 3.2688 | 1.3947 | 125.7983 | 75.1321 | 6.3925 | 5.0987 | 1.1566 | 17.156 | 213.5782 | 17.5% | 17.15 | 116.5851
| 27 | 4.2753 | 3.3404 | 6.8043 | 3.4077 | 1.4976 | 69.5292 | 15.9543 | 6.0774 | 4.8836 | 1.2804 | 19.3254 | 97.7249 | 20% | 17.2623 | 118.9839
| 28 | 3.2765 | 3.0029 | 4.2489 | 3.6003 | 1.4267 | 90.7716 | 21.8883 | 5.8715 | 3.5691 | 1.6878 | 15.5553 | 123.7883 | 22.5% | 17.3263 | 122.154
| 29 | 4.2587 | 3.8785 | 5.2649 | 4.9477 | 1.422 | 115.6849 | 49.2013 | 5.7149 | 5.5031 | 1.5089 | 19.7717 | 177.6131 | 25% | 17.439 | 122.947
| 30 | 3.6322 | 3.4196 | 6.7019 | 3.7103 | 1.1836 | 129.4189 | 69.3316 | 4.7967 | 3.6367 | 1.6621 | 18.6477 | 208.8459 | 27.5% | 17.709 | 124.7813
| 31 | 3.3324 | 2.6879 | 6.7859 | 4.2412 | 1.2541 | 91.5943 | 29.9431 | 7.0517 | 3.3699 | 1.3435 | 18.3016 | 133.3024 | 30% | 17.7577 | 128.2532
| 32 | 4.3622 | 2.7117 | 4.708 | 4.9334 | 1.3462 | 115.3413 | 55.3267 | 4.4286 | 5.3858 | 1.516 | 18.0614 | 181.9983 | 32.5% | 17.8325 | 133.6189
| 33 | 4.1069 | 3.3033 | 5.0409 | 4.468 | 1.3615 | 81.2298 | 2.6528 | 7.2161 | 4.0566 | 1.3341 | 18.2807 | 96.4894 | 35% | 17.8874 | 138.8114
| 34 | 4.0717 | 2.6022 | 4.8751 | 4.1505 | 1.3338 | 98.345 | 43.0832 | 5.1695 | 4.1568 | 1.486 | 17.0333 | 152.2405 | 37.5% | 18.0428 | 141.8193
| 35 | 3.9365 | 3.237 | 7.1288 | 3.7015 | 1.5434 | 103.8026 | 41.6687 | 7.37 | 4.1973 | 1.7945 | 19.5472 | 158.8331 | 40% | 18.1178 | 145.7174
| 36 | 3.9583 | 2.2062 | 4.6411 | 4.2584 | 1.3079 | 102.4744 | 61.8988 | 6.6211 | 4.6167 | 1.2692 | 16.3719 | 176.8802 | 42.5% | 18.1626 | 148.4269
| 37 | 4.1933 | 3.1253 | 5.5796 | 4.1631 | 1.7699 | 90.4356 | 19.5858 | 6.5602 | 4.9112 | 1.4842 | 18.8314 | 122.977 | 45% | 18.2173 | 149.7074
| 38 | 3.5894 | 3.0402 | 6.8832 | 5.0492 | 1.7244 | 106.416 | 47.5276 | 5.6026 | 5.6981 | 1.8909 | 20.2865 | 167.1353 | 47.5% | 18.2792 | 151.0578
| 39 | 4.3956 | 3.0268 | 4.5161 | 4.6432 | 1.5097 | 106.992 | 52.8286 | 6.352 | 3.7221 | 1.7177 | 18.0915 | 171.6124 | 50% | 18.2959 | 152.4016
| 40 | 3.8973 | 2.9447 | 5.9021 | 5.7257 | 1.8445 | 124.0613 | 55.8272 | 5.203 | 3.5286 | 1.5253 | 20.3143 | 190.1454 | 52.5% | 18.3817 | 153.2483
| 41 | 3.5365 | 3.715 | 4.9423 | 4.7122 | 1.4929 | 56.961 | 12.2485 | 4.3454 | 3.8538 | 1.7522 | 18.3989 | 79.161 | 55% | 18.4543 | 155.8984
| 42 | 4.0349 | 2.803 | 5.6919 | 3.6587 | 1.6287 | 119.0312 | 50.2441 | 6.9059 | 3.7416 | 1.0664 | 17.8172 | 180.9891 | 57.5% | 18.5354 | 156.9785
| 43 | 4.4697 | 2.3746 | 4.8451 | 3.775 | 1.6889 | 94.1251 | 36.9911 | 7.1431 | 4.506 | 1.2935 | 17.1533 | 144.0588 | 60% | 18.6718 | 160.4096
| 44 | 4.142 | 2.1688 | 4.533 | 3.7894 | 1.1515 | 85.8456 | 23.2338 | 4.611 | 3.9233 | 1.6592 | 15.7847 | 119.2728 | 62.5% | 18.7532 | 161.629
| 45 | 4.5119 | 2.8309 | 5.9563 | 3.8489 | 1.3876 | 84.1595 | 32.3457 | 6.3311 | 4.0207 | 1.595 | 18.5355 | 128.4521 | 65% | 18.8202 | 165.589
| 46 | 4.0528 | 2.3729 | 5.4031 | 3.3269 | 1.8121 | 86.0399 | 22.7855 | 6.254 | 4.9828 | 1.9053 | 16.9678 | 121.9675 | 67.5% | 18.8449 | 166.9826
| 47 | 4.4809 | 3.6226 | 6.508 | 4.355 | 1.0945 | 81.8777 | 24.3291 | 4.2365 | 4.3239 | 1.4598 | 20.0612 | 116.227 | 70% | 18.9777 | 171.5965
| 48 | 3.8851 | 2.8924 | 5.923 | 5.4448 | 1.3256 | 108.2083 | 47.038 | 5.8484 | 3.9862 | 1.1817 | 19.4708 | 166.2626 | 72.5% | 19.082 | 174.7048
| 49 | 3.7625 | 3.1043 | 6.6486 | 3.2434 | 1.4533 | 74.2125 | 0.4045 | 5.6798 | 5.7644 | 1.4301 | 18.2121 | 87.4913 | 75% | 19.199 | 176.4934
| 50 | 4.0493 | 2.7002 | 5.8413 | 3.9257 | 1.7627 | 84.6869 | 25.6943 | 5.271 | 5.5276 | 1.6771 | 18.2791 | 122.8569 | 77.5% | 19.4308 | 179.8935
| 51 | 3.9217 | 3.2862 | 6.148 | 3.4391 | 1.4705 | 136.6962 | 78.6283 | 5.7781 | 4.1029 | 1.5571 | 18.2654 | 226.7628 | 80% | 19.507 | 182.1008
| 52 | 3.9451 | 2.9278 | 5.3007 | 5.0948 | 1.7069 | 89.1802 | 21.2573 | 5.7294 | 4.8605 | 1.6181 | 18.9754 | 122.6456 | 82.5% | 19.5755 | 187.2356
| 53 | 4.7893 | 2.272 | 5.7971 | 5.8302 | 1.3511 | 113.2756 | 59.516 | 4.0955 | 4.1831 | 1.4403 | 20.0396 | 182.5105 | 85% | 19.7407 | 190.1885
| 54 | 4.1782 | 2.7912 | 6.2785 | 4.378 | 1.4748 | 153.0854 | 88.48 | 4.4875 | 3.412 | 1.6236 | 19.1007 | 251.0885 | 87.5% | 19.7879 | 194.6605
| 55 | 4.5527 | 3.1883 | 4.3003 | 5.2383 | 1.104 | 99.5213 | 30.9322 | 5.1494 | 4.2499 | 1.6696 | 18.3836 | 141.5224 | 90% | 19.9493 | 198.6329
| 56 | 4.2049 | 3.44 | 5.0703 | 3.4896 | 1.6993 | 62.9492 | 17.6039 | 4.5942 | 3.5953 | 1.7328 | 17.904 | 90.4754 | 92.5% | 20.074 | 208.858
| 57 | 4.224 | 3.5314 | 5.449 | 4.8044 | 1.4889 | 79.9799 | 27.8804 | 5.1096 | 3.6999 | 1.1583 | 19.4978 | 117.828 | 95% | 20.2484 | 213.6922
| 58 | 4.4392 | 3.1312 | 5.5426 | 4.5434 | 1.8337 | 93.3955 | 49.8353 | 4.6574 | 3.8962 | 1.4753 | 19.4901 | 153.2597 | 97.5% | 20.3987 | 226.8432
| 59 | 4.3024 | 2.4768 | 6.3377 | 4.5788 | 1.575 | 95.8984 | 36.8251 | 4.7677 | 3.3603 | 1.3894 | 19.2706 | 142.2408 | 100% | 20.7445 | 251.0885
| 60 | 3.6397 | 3.2021 | 7.0429 | 3.1627 | 1.5935 | 104.8206 | 40.2874 | 4.9307 | 5.2741 | 1.2034 | 18.6409 | 156.5162
| 61 | 4.5016 | 3.2467 | 4.9246 | 4.3291 | 1.2053 | 68.5068 | 10.2615 | 6.8958 | 5.2832 | 1.3988 | 18.2073 | 92.3461 | Percent Rank
| 62 | 4.61 | 2.4573 | 4.897 | 5.3343 | 1.8766 | 86.8194 | 16.8081 | 5.8095 | 5.0216 | 1.445 | 19.1752 | 115.9037 |  | Sheet1!$F$12 | Sheet1!$H$12
| 63 | 3.393 | 2.9878 | 5.1571 | 3.2995 | 1.5841 | 112.2668 | 42.3462 | 4.952 | 4.5917 | 1.5833 | 16.4214 | 165.74 |  | LiveDate | CorrelatedDate
| 64 | 3.8424 | 2.7376 | 5.3435 | 5.4606 | 1.4301 | 96.328 | 58.8433 | 5.128 | 3.3913 | 1.817 | 18.8142 | 165.5077 | Enter Value: | 16.3071 | 87.6997
| 65 | 4.5689 | 2.3299 | 7.6809 | 4.222 | 1.2818 | 120.9587 | 45.4704 | 5.01 | 3.4863 | 1.2886 | 20.0835 | 176.2141 | % rank: | 4.9% | 5%
| 66 | 4.0788 | 3.7857 | 4.5773 | 3.9451 | 1.4494 | 100.1119 | 38.4405 | 4.6911 | 3.4678 | 1.373 | 17.8362 | 148.0844
| 67 | 3.7968 | 3.0563 | 4.9809 | 4.0263 | 1.2881 | 111.7775 | 38.9386 | 4.7477 | 3.9682 | 1.4026 | 17.1484 | 160.8346 | Correlations
| 68 | 3.9108 | 2.3116 | 5.9942 | 3.8167 | 1.2702 | 111.4586 | 48.4298 | 5.7929 | 4.5516 | 1.3567 | 17.3035 | 171.5897 |  | Sheet1!$F$12 | Sheet1!$H$12
| 69 | 3.4201 | 2.6401 | 6.3679 | 3.4531 | 1.5808 | 125.4501 | 65.807 | 5.4595 | 4.95 | 1.6335 | 17.462 | 203.3001 | Risk Inputs | LiveDate | CorrelatedDate
| 70 | 3.982 | 2.847 | 7.4464 | 3.7267 | 1.7957 | 122.2138 | 60.9991 | 6.1863 | 4.1356 | 1.5591 | 19.7977 | 195.0939 | Sheet1!$F$7 | 0.34536
| 71 | 4.3269 | 2.7862 | 6.0156 | 3.8931 | 1.8244 | 120.7276 | 51.263 | 5.4319 | 4.4401 | 1.1057 | 18.8462 | 182.9684 | Sheet1!$F$8 | 0.32612
| 72 | 4.2895 | 2.9096 | 4.796 | 3.5832 | 1.7107 | 97.1173 | 40.9429 | 5.4119 | 4.8305 | 1.5456 | 17.2889 | 149.8482 | Sheet1!$F$9 | 0.69215
| 73 | 4.5894 | 2.5394 | 5.1835 | 4.1906 | 1.4051 | 95.3653 | 41.4663 | 5.3352 | 4.2198 | 1.9553 | 17.9081 | 148.3419 | Sheet1!$F$10 | 0.5069
| 74 | 4.4335 | 3.8495 | 5.572 | 4.2932 | 1.6163 | 76.5677 | 27.4312 | 6.4577 | 3.8643 | 1.2607 | 19.7645 | 115.5817 | Sheet1!$F$11 | 0.0062136
| 75 | 3.8326 | 2.5019 | 7.3905 | 3.5123 | 1.5202 | 117.4286 | 59.8976 | 6.0356 | 4.4153 | 1.5131 | 18.7574 | 189.2902 | Sheet1!$H$7 |  | 0.97457
| 76 | 4.6517 | 3.1569 | 6.0618 | 5.1446 | 1.2314 | 93.3592 | 53.0147 | 4.3772 | 3.8312 | 1.5807 | 20.2464 | 156.163 | Sheet1!$H$8 |  | 0.9729
| 77 | 4.7254 | 2.4251 | 5.8282 | 3.5289 | 1.7826 | 142.8477 | 73.4007 | 4.8133 | 4.0983 | 1.7559 | 18.2902 | 226.9159 | Sheet1!$H$9 |  | -0.06889
| 78 | 3.9599 | 3.5897 | 4.3525 | 3.0814 | 1.6211 | 90.0465 | 35.2265 | 6.7402 | 3.5411 | 1.693 | 16.6047 | 137.2472 | Sheet1!$H$10 |  | -0.13884
| 79 | 3.2412 | 3.4163 | 4.1671 | 4.5518 | 1.6666 | 75.4089 | 14.7928 | 6.5096 | 4.6365 | 1.627 | 17.0431 | 102.9749 | Sheet1!$H$11 |  | 0.038478
| 80 | 3.3616 | 3.0198 | 5.2746 | 4.4328 | 1.6348 | 103.218 | 43.5963 | 5.0493 | 3.821 | 1.3313 | 17.7236 | 157.0159
| 81 | 4.6653 | 3.1705 | 5.8754 | 3.7926 | 1.4081 | 80.4401 | 33.9068 | 6.2136 | 4.5338 | 1.5308 | 18.9119 | 126.625
| 82 | 3.7475 | 2.8663 | 4.4614 | 3.7477 | 1.3747 | 88.6971 | 20.6227 | 5.3558 | 3.628 | 1.6472 | 16.1975 | 119.9508
| 83 | 3.4767 | 3.253 | 5.3737 | 4.8848 | 1.4601 | 96.6004 | 44.948 | 6.8065 | 3.793 | 1.5651 | 18.4483 | 153.7131
| 84 | 3.8665 | 2.7267 | 4.62 | 3.4603 | 1.5554 | 118.2189 | 64.3551 | 5.5134 | 4.3601 | 1.4906 | 16.229 | 193.9381
| 85 | 3.5256 | 2.8737 | 4.9685 | 3.6195 | 1.324 | 132.5218 | 54.5649 | 4.9636 | 4.4634 | 1.6005 | 16.3113 | 198.1143
| 86 | 3.9989 | 2.5122 | 5.0106 | 3.3515 | 1.9393 | 116.8255 | 62.978 | 5.9605 | 3.2857 | 1.383 | 16.8125 | 190.4328
| 87 | 4.9328 | 3.0631 | 4.4233 | 4.0735 | 1.7288 | 78.8377 | 19.1603 | 4.9126 | 5.1929 | 1.2169 | 18.2215 | 109.3203
| 88 | 4.0836 | 3.1064 | 6.1343 | 5.3237 | 1.4454 | 62.2366 | 7.9341 | 5.9918 | 4.4833 | 1.4081 | 20.0935 | 82.0539
| 89 | 3.4924 | 2.4221 | 5.4199 | 5.1963 | 1.2403 | 101.4247 | 35.9936 | 6.6017 | 4.0688 | 1.8613 | 17.771 | 149.95
| 90 | 3.6112 | 3.5146 | 4.7585 | 4.0497 | 1.3838 | 99.4389 | 31.5329 | 5.9246 | 3.6635 | 1.1992 | 17.3179 | 141.7591
| 91 | 4.1726 | 3.3562 | 6.3917 | 5.087 | 1.7371 | 88.2596 | 29.0465 | 5.2086 | 3.5029 | 1.7715 | 20.7445 | 127.7891
| 92 | 4.03 | 2.7588 | 6.2245 | 4.2792 | 1.4154 | 108.5073 | 42.9014 | 5.0665 | 3.5588 | 1.7083 | 18.708 | 161.7424
| 93 | 3.9752 | 2.58 | 7.5435 | 4.6115 | 1.1351 | 72.3942 | 6.877 | 5.3004 | 4.6712 | 1.3613 | 19.8453 | 90.6042
| 94 | 3.2966 | 2.8574 | 5.2474 | 3.876 | 1.5214 | 83.8209 | 35.5217 | 6.1251 | 5.0538 | 1.5937 | 16.7988 | 132.1153
| 95 | 3.4368 | 3.4623 | 6.2412 | 4.6601 | 1.2171 | 105.7931 | 58.2507 | 7.2265 | 3.7913 | 1.3028 | 19.0175 | 176.3645
| 96 | 3.7795 | 3.2749 | 4.7401 | 4.0854 | 1.4685 | 98.9417 | 48.2172 | 6.0453 | 5.4123 | 1.6418 | 17.3484 | 160.2582
| 97 | 4.0955 | 2.9917 | 5.4707 | 4.1075 | 1.1664 | 127.878 | 71.7995 | 4.8753 | 4.7167 | 1.8402 | 17.8317 | 211.1098
| 98 | 4.7157 | 3.1411 | 6.579 | 4.7295 | 1.3097 | 82.6823 | 25.2082 | 5.0294 | 3.3155 | 1.0933 | 20.475 | 117.3288
| 99 | 3.4476 | 3.3336 | 5.7112 | 4.3882 | 1.6524 | 101.6211 | 32.1681 | 6.9979 | 4.7934 | 1.2426 | 18.5331 | 146.8231
| 100 | 4.1337 | 2.9606 | 5.6299 | 3.9823 | 1.6021 | 123.15 | 56.2973 | 5.5323 | 3.9353 | 1.2251 | 18.3086 | 190.1401
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Risk Results 4
Navigation |  | Inputs | [9 empty] | Outputs |  | Simulation Statistics |  |  | Output Cumulative Distributions | Output Distributions | Risk Tornado Diagram
Risk Outputs |  | Sheet1!$F$7 | Sheet1!$F$8 | Sheet1!$F$9 | Sheet1!$F$10 | Sheet1!$F$11 | Sheet1!$H$7 | Sheet1!$H$8 | Sheet1!$H$9 | Sheet1!$H$10 | Sheet1!$H$11 | Sheet1!$F$12 | Sheet1!$H$12 |  | Sheet1!$F$12 | Sheet1!$H$12 |  |  |  |  | Correlations - Column 1 sorted
Simulation Statistics | Iterations | RiskTriang(C7,D7,E7) | RiskTriang(C8,D8,E8) | RiskTriang(C9,D9,E9) | RiskTriang(C10,D10,E10) | RiskTriang(C11,D11,E11) | RiskNormal(100,20,RiskCorrmat($L$7:$M$8,1)) | RiskNormal(40,20,RiskCorrmat($L$7:$M$8,2)) | RiskTriang(C9,D9,E9) | RiskTriang(C10,D10,E10) | RiskTriang(C11,D11,E11) | LiveDate | CorrelatedDate |  | LiveDate | CorrelatedDate |  |  | Select Output: | Sheet1!$F$12 |  | Sheet1!$F$12 | Sheet1!$H$12
Risk Output Percentiles | 1 | 3.5785 | 2.9391 | 4.4884 | 3.5361 | 1.643 | 124.5613 | 62.7365 | 6.3352 | 4.1857 | 1.6191 | 16.185 | 199.4378 | Mean | 18.3329 | 151.2067 |  |  | Name: | LiveDate | Risk Inputs | LiveDate | CorrelatedDate
Calculate Percent Rank | 2 | 3.1004 | 2.0605 | 7.0142 | 3.6656 | 1.0711 | 121.5377 | 67.3243 | 5.1024 | 3.2312 | 1.1912 | 16.9118 | 198.3868 | Median | 18.3728 | 151.8237 |  |  | 1 |  | Sheet1!$H$8 |  | 0.9745
Correlations | 3 | 4.1277 | 2.5837 | 4.1991 | 5.2562 | 1.6863 | 90.5257 | 48.851 | 6.1632 | 3.6087 | 1.2675 | 17.853 | 150.4162 | Mode | #N/A | #N/A |  |  | Tornado Diagram for LiveDate (Sheet1!$F$12) |  | Sheet1!$H$7 |  | 0.97544
Output Cumulative Distributions | 4 | 4.4658 | 3.7816 | 5.6281 | 3.129 | 1.4667 | 118.2524 | 59.9836 | 5.3321 | 3.7139 | 1.3652 | 18.4712 | 188.6472 | Std. Deviation | 1.1582 | 39.2614 |  |  |  |  | Sheet1!$H$9 |  | -0.18711
Output Distributions | 5 | 3.8746 | 2.8317 | 5.8995 | 4.2266 | 1.5683 | 114.9452 | 59.4099 | 5.436 | 4.5747 | 1.7794 | 18.4006 | 186.1453 | Variance | 1.3415 | 1541.4596 |  |  |  |  | Sheet1!$H$11 |  | 0.091186
Risk Tornado Diagram | 6 | 4.2973 | 2.7279 | 6.6163 | 4.8079 | 1.3194 | 73.5063 | 31.8042 | 5.0642 | 4.0785 | 1.232 | 19.7689 | 115.6851 | Kurtosis | -0.095224 | 0.18735 |  |  |  |  | Sheet1!$H$10 |  | 0.082339
| 7 | 4.2758 | 2.8191 | 6.1965 | 4.5966 | 1.7361 | 95.1986 | 45.4192 | 4.6417 | 3.6725 | 1.9145 | 19.6241 | 150.8465 | Skewness | 0.32789 | -0.054968 |  |  |  |  | Sheet1!$F$11 | 0.13342
| 8 | 3.7354 | 3.4442 | 6.8428 | 3.6081 | 1.1333 | 93.3749 | 29.1989 | 5.2387 | 3.0658 | 1.588 | 18.7637 | 132.4663 | Minimum | 16.185 | 31.825 |  |  |  |  | Sheet1!$F$8 | 0.1741
| 9 | 4.5523 | 2.7755 | 6.3988 | 3.4155 | 1.4962 | 33.6425 | -12.8081 | 4.7289 | 4.413 | 1.8487 | 18.6382 | 31.825 | Maximum | 21.7527 | 253.2539 |  |  |  |  | Sheet1!$F$7 | 0.38839
| 10 | 4.4971 | 3.8058 | 6.2159 | 4.8722 | 1.4596 | 87.5695 | 10.9212 | 5.4889 | 4.4791 | 1.1189 | 20.8505 | 109.5776 | Range | 5.5677 | 221.4289 |  |  |  |  | Sheet1!$F$10 | 0.50315
| 11 | 4.0989 | 3.6662 | 5.3426 | 3.2275 | 1.7594 | 104.9776 | 46.4807 | 5.5406 | 3.5187 | 1.3208 | 18.0946 | 161.8384 | Count | 100 | 100 |  |  |  |  | Sheet1!$F$9 | 0.66401
| 12 | 3.7046 | 3.6051 | 5.0586 | 3.5782 | 1.5915 | 105.1664 | 43.0844 | 4.1305 | 3.5212 | 1.6973 | 17.538 | 157.5998 | Error Count | 0 | 0
| 13 | 3.7538 | 3.4142 | 5.2844 | 4.3478 | 1.9255 | 60.3585 | 2.2717 | 5.7468 | 4.2219 | 1.4374 | 18.7257 | 74.0362 | Std. Error | 0.11582 | 3.9261
| 14 | 3.7785 | 3.5834 | 5.3262 | 4.1957 | 1.265 | 90.0295 | 22.2934 | 6.2962 | 4.0311 | 1.7619 | 18.1488 | 124.4122 | Confidence Level (95%) | 0.22982 | 7.7903
| 15 | 4.0567 | 2.8968 | 7.1241 | 3.8243 | 1.5961 | 75.2874 | 20.1104 | 6.7331 | 3.9872 | 1.3123 | 19.498 | 107.4303
| 16 | 3.3739 | 3.0151 | 4.7898 | 4.4188 | 1.5603 | 111.8194 | 50.6453 | 5.5795 | 4.9939 | 1.6358 | 17.1578 | 174.6739 | Percentiles
| 17 | 3.9929 | 3.3643 | 7.3511 | 3.5347 | 1.5821 | 101.8053 | 42.1147 | 6.4915 | 3.4059 | 1.6758 | 19.825 | 155.4931 |  | Sheet1!$F$12 | Sheet1!$H$12
| 18 | 3.8968 | 3.0714 | 5.1753 | 4.1519 | 1.6982 | 118.7251 | 63.6306 | 4.9428 | 5.0188 | 1.9713 | 17.9935 | 194.2886 |  | LiveDate | CorrelatedDate
| 19 | 4.3079 | 3.294 | 5.2092 | 4.171 | 1.73 | 110.4464 | 61.741 | 4.4207 | 5.2756 | 1.4794 | 18.7122 | 183.3631 | 0% | 16.185 | 31.825
| 20 | 4.0164 | 3.381 | 4.9256 | 3.5961 | 1.4791 | 114.2778 | 55.0022 | 5.0168 | 4.8106 | 1.3024 | 17.3981 | 180.4099 | 2.5% | 16.3812 | 79.6601
| 21 | 4.2172 | 3.5567 | 6.4531 | 3.3367 | 1.5572 | 96.1 | 29.662 | 5.9545 | 3.7862 | 1.3334 | 19.1209 | 136.8362 | 5% | 16.5559 | 89.1189
| 22 | 4.1741 | 2.804 | 5.818 | 5.063 | 1.2089 | 150.5735 | 91.643 | 5.1733 | 4.362 | 1.502 | 19.0679 | 253.2539 | 7.5% | 16.7306 | 99.1541
| 23 | 3.4619 | 2.3819 | 6.6678 | 4.4413 | 1.5452 | 124.5239 | 48.3627 | 7.0896 | 3.9016 | 1.5503 | 18.4981 | 185.4281 | 10% | 16.8209 | 103.2142
| 24 | 4.5568 | 2.6644 | 7.6373 | 3.616 | 1.25 | 97.0115 | 38.8105 | 6.9115 | 3.4419 | 1.5213 | 19.7245 | 147.6968 | 12.5% | 16.9067 | 108.0682
| 25 | 3.9799 | 2.2955 | 5.2607 | 3.853 | 1.49 | 102.5506 | 31.1572 | 5.2166 | 3.5415 | 1.4735 | 16.8791 | 143.9394 | 15% | 17.0879 | 110.0318
| 26 | 4.5765 | 2.8863 | 4.8015 | 4.4908 | 1.4079 | 94.3699 | 32.6673 | 5.3655 | 4.7649 | 1.75 | 18.163 | 138.9176 | 17.5% | 17.1815 | 114.5082
| 27 | 4.631 | 3.1876 | 5.0938 | 3.7757 | 1.8009 | 107.2171 | 54.4369 | 6.6919 | 3.4079 | 1.4047 | 18.489 | 173.1586 | 20% | 17.2724 | 119.2486
| 28 | 3.9307 | 2.9646 | 4.738 | 3.7516 | 1.4395 | 130.5569 | 79.3481 | 4.8391 | 3.7531 | 1.8323 | 16.8244 | 220.3295 | 22.5% | 17.3028 | 121.0178
| 29 | 3.9733 | 3.0269 | 4.9979 | 4.5548 | 1.6705 | 76.0844 | 22.4757 | 6.2055 | 4.176 | 1.1704 | 18.2234 | 110.112 | 25% | 17.3987 | 123.4442
| 30 | 4.1854 | 3.2445 | 5.4902 | 3.8025 | 1.8396 | 68.994 | 20.1237 | 7.6662 | 4.9175 | 1.6002 | 18.5623 | 103.3018 | 27.5% | 17.4715 | 127.4287
| 31 | 3.8112 | 2.2397 | 6.5864 | 5.6785 | 1.4245 | 106.1884 | 35.6571 | 7.292 | 5.1405 | 1.4674 | 19.7402 | 155.7455 | 30% | 17.6806 | 130.8759
| 32 | 4.229 | 3.291 | 5.4049 | 4.358 | 1.8854 | 91.984 | 16.4864 | 6.4348 | 3.1437 | 1.4897 | 19.1682 | 119.5387 | 32.5% | 17.8237 | 132.5069
| 33 | 4.8513 | 3.3397 | 4.7631 | 3.8896 | 1.5013 | 81.3665 | 16.7256 | 5.6779 | 5.5183 | 1.5167 | 18.3449 | 110.8049 | 35% | 17.8886 | 136.457
| 34 | 3.7915 | 3.3983 | 5.7354 | 3.7411 | 1.6143 | 122.9875 | 49.4491 | 4.39 | 3.1744 | 1.2778 | 18.2807 | 181.2789 | 37.5% | 17.9642 | 138.7399
| 35 | 4.0311 | 3.2096 | 5.9244 | 5.793 | 1.7865 | 119.5908 | 58.3689 | 6.0848 | 3.6529 | 1.5276 | 20.7446 | 189.225 | 40% | 18.112 | 139.9244
| 36 | 4.9407 | 2.881 | 5.4168 | 4.3295 | 1.3863 | 108.9807 | 43.8011 | 5.7638 | 5.3699 | 1.3819 | 18.9544 | 165.2976 | 42.5% | 18.1672 | 144.0327
| 37 | 3.4093 | 2.3227 | 6.0827 | 5.5127 | 1.4452 | 71.1651 | 12.7447 | 5.3524 | 3.2619 | 1.6906 | 18.7726 | 94.2147 | 45% | 18.2473 | 147.3977
| 38 | 3.6581 | 3.1896 | 6.5389 | 4.1181 | 1.1735 | 67.0047 | 18.3756 | 6.1278 | 4.4023 | 1.622 | 18.6781 | 97.5324 | 47.5% | 18.3163 | 150.4244
| 39 | 4.0058 | 2.93 | 7.2432 | 4.0856 | 1.7042 | 116.2718 | 70.6368 | 5.7037 | 3.999 | 1.6314 | 19.9688 | 198.2427 | 50% | 18.3728 | 151.8237
| 40 | 3.7237 | 2.7583 | 5.1356 | 4.2977 | 1.5099 | 86.7672 | 26.2869 | 4.5402 | 4.5398 | 1.5744 | 17.4252 | 123.7085 | 52.5% | 18.4886 | 155.4853
| 41 | 3.8309 | 2.9936 | 6.74 | 4.4692 | 1.1505 | 103.1877 | 41.3816 | 5.1341 | 3.6807 | 1.7977 | 19.1842 | 155.1818 | 55% | 18.5353 | 157.482
| 42 | 4.0452 | 2.1909 | 5.1561 | 4.5489 | 1.2208 | 99.9692 | 30.2972 | 6.5926 | 4.4519 | 1.1266 | 17.1618 | 142.4375 | 57.5% | 18.5747 | 159.0959
| 43 | 4.7548 | 2.9864 | 4.5947 | 4.6661 | 1.5227 | 81.7711 | 25.3285 | 6.4678 | 5.1206 | 1.5778 | 18.5247 | 120.2658 | 60% | 18.6255 | 162.1675
| 44 | 4.2627 | 3.4563 | 5.2297 | 3.9961 | 1.3911 | 79.3624 | 26.7689 | 6.2674 | 3.8218 | 1.8679 | 18.3359 | 118.0883 | 62.5% | 18.6731 | 163.5958
| 45 | 3.3771 | 2.4363 | 4.3651 | 5.6091 | 1.4349 | 109.6851 | 36.97 | 7.3205 | 3.856 | 1.2888 | 17.2224 | 159.1205 | 65% | 18.7169 | 165.636
| 46 | 3.6108 | 2.3538 | 6.2468 | 3.2023 | 1.5731 | 108.5187 | 44.593 | 4.7942 | 4.0945 | 1.653 | 16.9868 | 163.6535 | 67.5% | 18.7575 | 167.396
| 47 | 4.4867 | 2.6604 | 4.4277 | 3.4709 | 1.3378 | 82.6508 | 15.2818 | 6.6382 | 3.4834 | 1.0771 | 16.3835 | 109.1312 | 70% | 18.7857 | 169.2311
| 48 | 4.6755 | 3.0549 | 5.1957 | 5.1894 | 1.2568 | 111.5812 | 45.7727 | 5.1887 | 5.0515 | 1.2402 | 19.3723 | 168.8343 | 72.5% | 18.8131 | 172.5732
| 49 | 3.4983 | 3.107 | 6.1283 | 4.5179 | 1.3775 | 102.0181 | 47.5758 | 7.6138 | 3.7352 | 1.7185 | 18.6289 | 162.6613 | 75% | 18.9732 | 178.4033
| 50 | 4.1985 | 3.5027 | 4.3213 | 3.3944 | 1.4867 | 126.2681 | 57.8032 | 4.991 | 3.7642 | 1.5085 | 16.9035 | 194.335 | 77.5% | 19.0474 | 180.6651
| 51 | 3.9532 | 2.851 | 5.112 | 4.6466 | 1.1036 | 115.4742 | 40.8947 | 5.9494 | 3.9579 | 1.4434 | 17.6664 | 167.7196 | 80% | 19.1714 | 183.7761
| 52 | 3.8156 | 2.682 | 4.8727 | 4.7799 | 1.5365 | 84.0796 | 34.116 | 5.6503 | 4.2744 | 1.3414 | 17.6867 | 129.4617 | 82.5% | 19.3541 | 187.8341
| 53 | 3.4392 | 3.6339 | 6.4996 | 3.4431 | 1.6074 | 85.2098 | 24.8258 | 4.2146 | 4.6519 | 1.6673 | 18.6232 | 120.5694 | 85% | 19.5169 | 194.2956
| 54 | 4.0213 | 2.6395 | 6.8926 | 4.0816 | 1.358 | 58.3403 | 2.5482 | 6.3607 | 4.2595 | 1.7729 | 18.9931 | 73.2815 | 87.5% | 19.7344 | 197.4098
| 55 | 4.0742 | 3.0809 | 6.0176 | 3.3169 | 1.4705 | 94.7662 | 28.688 | 4.5885 | 3.3551 | 1.0613 | 17.96 | 132.4592 | 90% | 19.8142 | 198.7212
| 56 | 3.537 | 3.3268 | 5.0028 | 4.8454 | 1.1731 | 136.7557 | 73.7257 | 5.7928 | 3.8676 | 1.6125 | 17.8852 | 221.7543 | 92.5% | 20.0172 | 203.6892
| 57 | 3.2751 | 2.5571 | 5.6185 | 3.7678 | 1.2238 | 112.886 | 55.7718 | 6.0541 | 4.7245 | 1.3255 | 16.4423 | 180.7619 | 95% | 20.384 | 220.2214
| 58 | 4.6962 | 3.0457 | 6.3464 | 5.3554 | 1.3001 | 96.5966 | 35.9906 | 6.9045 | 5.6459 | 1.8945 | 20.7439 | 147.0321 | 97.5% | 20.7443 | 221.3076
| 59 | 4.2121 | 2.2754 | 5.4698 | 3.4936 | 1.8647 | 101.2339 | 40.1958 | 6.1889 | 3.926 | 1.2564 | 17.3156 | 152.801 | 100% | 21.7527 | 253.2539
| 60 | 3.9471 | 3.7431 | 4.544 | 3.8668 | 1.6618 | 85.9785 | 5.8016 | 5.2594 | 4.9435 | 1.7008 | 17.7628 | 103.6839
| 61 | 3.8838 | 3.2614 | 5.9574 | 4.051 | 1.533 | 97.6711 | 51.509 | 4.6887 | 3.4952 | 1.4287 | 18.6867 | 158.7927 | Percent Rank
| 62 | 3.6917 | 2.5394 | 4.7057 | 4.1254 | 1.631 | 98.0697 | 27.3336 | 5.2743 | 3.7054 | 1.3699 | 16.6934 | 135.7528 |  | Sheet1!$F$12 | Sheet1!$H$12
| 63 | 3.8697 | 2.9222 | 5.7132 | 3.9657 | 1.6526 | 88.9794 | 33.6501 | 4.7591 | 3.8891 | 1.4203 | 18.1235 | 132.6981 |  | LiveDate | CorrelatedDate
| 64 | 4.5108 | 3.2758 | 5.6521 | 4.0073 | 1.282 | 127.4933 | 57.378 | 4.7045 | 4.8845 | 1.5614 | 18.7281 | 196.0216 | Enter Value: | 16.5559 | 89.1189
| 65 | 4.4044 | 2.716 | 7.0266 | 4.9508 | 1.2933 | 93.3172 | 34.6751 | 5.8345 | 4.0578 | 1.5668 | 20.3911 | 139.4513 | % rank: | 5% | 5%
| 66 | 4.3685 | 3.1444 | 5.8655 | 4.9861 | 1.9522 | 132.8908 | 61.2682 | 4.3005 | 4.5219 | 1.7166 | 20.3167 | 204.698
| 67 | 4.3581 | 2.8411 | 4.8437 | 3.6293 | 1.579 | 98.6239 | 53.0665 | 5.8715 | 5.1824 | 1.5317 | 17.2511 | 164.276 | Correlations
| 68 | 4.3845 | 2.4914 | 6.2987 | 5.3919 | 1.8171 | 64.6839 | 9.863 | 6.4063 | 3.4592 | 1.4636 | 20.3836 | 85.876 |  | Sheet1!$F$12 | Sheet1!$H$12
| 69 | 3.9064 | 2.5686 | 4.9016 | 3.8413 | 1.344 | 77.3878 | 35.1724 | 4.5036 | 4.2311 | 1.3565 | 16.5619 | 122.6513 | Risk Inputs | LiveDate | CorrelatedDate
| 70 | 3.7743 | 3.533 | 4.6413 | 4.2653 | 1.6036 | 110.7442 | 56.7358 | 4.8234 | 4.3488 | 1.3882 | 17.8174 | 178.0405 | Sheet1!$F$7 | 0.38839
| 71 | 4.1138 | 2.4818 | 5.9872 | 4.6297 | 1.3632 | 72.7128 | 18.8673 | 4.9751 | 3.6181 | 1.1748 | 18.5757 | 101.3481 | Sheet1!$F$8 | 0.1741
| 72 | 4.1298 | 2.6002 | 5.6895 | 3.4795 | 1.3989 | 91.5493 | 24.5214 | 5.9061 | 3.5622 | 1.2995 | 17.2979 | 126.8385 | Sheet1!$F$9 | 0.66401
| 73 | 3.7152 | 3.4818 | 6.7587 | 4.6924 | 1.4048 | 129.2902 | 64.9022 | 5.0877 | 3.3168 | 1.6449 | 20.0529 | 204.2417 | Sheet1!$F$10 | 0.50315
| 74 | 3.6258 | 3.5256 | 5.5749 | 3.4364 | 1.2895 | 104.3746 | 46.9186 | 4.879 | 3.8343 | 1.513 | 17.4522 | 161.5195 | Sheet1!$F$11 | 0.13342
| 75 | 4.1482 | 2.7031 | 4.6714 | 5.0476 | 1.3296 | 121.9215 | 66.7205 | 5.3986 | 3.3854 | 1.2154 | 17.8999 | 198.6415 | Sheet1!$H$7 |  | 0.97544
| 76 | 4.4388 | 3.0943 | 5.534 | 3.6974 | 1.455 | 68.0808 | 8.5074 | 6.5558 | 4.8579 | 1.2548 | 18.2194 | 89.2567 | Sheet1!$H$8 |  | 0.9745
| 77 | 3.6749 | 2.9575 | 6.4433 | 4.2071 | 1.5123 | 112.4119 | 42.5665 | 5.864 | 4.1481 | 1.8262 | 18.795 | 166.8167 | Sheet1!$H$9 |  | -0.18711
| 78 | 3.5214 | 2.8627 | 7.1846 | 4.0353 | 1.3682 | 133.8979 | 75.4372 | 4.615 | 4.5852 | 1.6805 | 18.9722 | 220.2157 | Sheet1!$H$10 |  | 0.082339
| 79 | 3.839 | 2.906 | 5.0695 | 3.0841 | 1.4804 | 117.2567 | 49.9726 | 4.9071 | 5.5433 | 1.8122 | 16.3791 | 179.4919 | Sheet1!$H$11 |  | 0.091186
| 80 | 4.242 | 3.6914 | 5.5168 | 3.9825 | 1.349 | 78.1176 | 13.525 | 5.0298 | 4.0119 | 1.742 | 18.7816 | 102.4264
| 81 | 3.5965 | 2.9701 | 4.9434 | 4.7633 | 1.0045 | 107.1311 | 52.3107 | 6.026 | 3.6384 | 1.4506 | 17.2777 | 170.5569
| 82 | 4.3298 | 2.797 | 5.0397 | 5.0935 | 1.7162 | 100.2537 | 52.0594 | 7.0591 | 5.4083 | 1.484 | 18.9762 | 166.2646
| 83 | 3.1945 | 3.1533 | 6.1641 | 5.2883 | 1.527 | 145.237 | 83.6205 | 5.0489 | 4.7883 | 1.5867 | 19.3273 | 240.2813
| 84 | 3.3331 | 3.2262 | 5.5875 | 3.7161 | 1.2428 | 103.5276 | 47.9564 | 5.6748 | 4.3025 | 1.7301 | 17.1057 | 163.1914
| 85 | 4.0678 | 2.7436 | 5.4361 | 3.3552 | 1.7963 | 80.6592 | 20.9956 | 7.0099 | 4.1346 | 1.1423 | 17.3989 | 113.9416
| 86 | 3.9263 | 3.2179 | 4.217 | 3.3791 | 1.5169 | 95.6308 | 31.5471 | 7.1811 | 4.4488 | 1.4321 | 16.2571 | 140.2399
| 87 | 4.338 | 3.1386 | 5.3158 | 3.9008 | 1.6225 | 113.9914 | 41.9244 | 5.3025 | 4.7034 | 1.5972 | 18.3158 | 167.5189
| 88 | 3.2901 | 2.5202 | 7.4356 | 3.9144 | 1.6364 | 90.8077 | 27.869 | 5.5193 | 4.1125 | 1.5391 | 18.7967 | 129.8477
| 89 | 3.6439 | 2.6294 | 5.7691 | 3.2983 | 1.4486 | 100.5552 | 39.8268 | 4.4833 | 4.3329 | 1.5455 | 16.7893 | 150.7437
| 90 | 4.0923 | 3.4235 | 4.6074 | 4.729 | 1.4146 | 83.3779 | 44.3166 | 6.0091 | 3.7992 | 1.2115 | 18.2667 | 138.7145
| 91 | 4.2914 | 3.3192 | 5.3706 | 3.2553 | 1.654 | 138.9388 | 69.2594 | 5.4696 | 5.734 | 1.4121 | 17.8905 | 220.814
| 92 | 3.5586 | 3.0347 | 4.497 | 4.2681 | 1.4225 | 78.6115 | -1.9817 | 4.9315 | 3.2849 | 1.6555 | 16.7809 | 86.5017
| 93 | 4.4333 | 3.0058 | 5.8483 | 3.5123 | 1.7487 | 88.1245 | 23.4389 | 5.6021 | 3.5772 | 1.4574 | 18.5483 | 122.2
| 94 | 3.9682 | 3.0987 | 7.8425 | 5.1646 | 1.6787 | 88.4535 | 33.2754 | 4.8707 | 3.3422 | 1.3747 | 21.7527 | 131.3166
| 95 | 3.8567 | 2.4099 | 6.9588 | 3.6564 | 1.7213 | 92.5957 | 39.0754 | 7.4312 | 4.6863 | 1.3949 | 18.6033 | 145.1834
| 96 | 3.4813 | 2.7653 | 4.864 | 4.3996 | 1.776 | 120.6947 | 71.6791 | 5.5704 | 3.5842 | 1.4132 | 17.2862 | 202.9417
| 97 | 4.6209 | 3.1691 | 5.7875 | 3.9347 | 1.8549 | 107.9238 | 37.7341 | 6.7908 | 3.4407 | 1.4963 | 19.3671 | 157.3857
| 98 | 4.1522 | 3.8699 | 6.0528 | 3.5516 | 1.1912 | 99.2689 | 37.1784 | 5.4235 | 4.6156 | 1.4949 | 18.8178 | 147.9813
| 99 | 3.2441 | 3.119 | 4.9645 | 3.6879 | 1.5481 | 105.8235 | 53.6775 | 5.1585 | 3.9435 | 1.5541 | 16.5635 | 170.157
| 100 | 4.7897 | 2.4667 | 6.311 | 4.9328 | 1.3128 | 85.4057 | 38.2302 | 6.826 | 5.2481 | 1.3479 | 19.813 | 137.0579
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.